## Sheet1
Unnamed: 0 | Unnamed: 1 | Unnamed: 2 | Unnamed: 3 | Unnamed: 4 | Unnamed: 5 | Unnamed: 6 | Unnamed: 7 | Unnamed: 8 | Unnamed: 9 | Unnamed: 10 | Unnamed: 11 | Unnamed: 12 | Unnamed: 13 | Unnamed: 14 | Unnamed: 15 | Date Print : | Unnamed: 17 | Unnamed: 18 | Unnamed: 19 | Unnamed: 20
LCD_DATE | JOB | PROCESS_CODE | RSC_LOCATION | RSC_CODE | NUMBER_OPERATOR | JOB_QUANTITY | EXPECT_OUTPUT_PER_HOUR | HOURS_NEED | DAY_NEED | SETTING_HOURS | BREAK_HOURS | NO_PROD | START_DATE | PLANNED_START | PLANNED_END | LATEST_COMPLETION_DATE | ACCUMULATED_DAILY_OUTPUT | BALANCE_QUANTITY | BAL_HR | PRIORITY
2025-05-01 | JOAW24090215 | CD11-027-P05-06 | WN | TW01 | 1 | 10000 | 400 | 25 | 1.0417 | 1 | 2 | 8 | 3/15/2025 13:00:00 AM |  |  |  | 9969 | 31 |  | 3
2025-05-01 | JOST24120021 | CM10-009-P04-05 | AL | CHECKING | 1 | 41613 | 1200 | 34.6775 | 4.3347 | 1 | 2 | 8 |  |  |  |  | 17400 | 24213 |  | 3
2025-05-01 | JOAW24120118 | CD11-026-P05-06 | WN | TW01 | 1 | 15000 | 420 | 35.7143 | 4.4643 | 1 | 5 | 8 | [5 empty] | 15000 |  | 3
2025-05-01 | JOAW24120201 | CM03-001-P02-04 | ST | VM04 | 1 | 100806 | 250 | 403.224 | 50.403 | 1 | 2 | 12 |  |  |  |  | 100806 | 0 |  | 3
2025-05-01 | JOAW24120201 | CM03-001-P03-04 | AL | CHECKING | 1 | 100806 | 250 | 403.224 | 50.403 | 1 | 2 | 8 |  |  |  |  | 57547 | 43259 |  | 3
2025-05-05 | JOST24120090 | CP08-544-P01-02 | ST | STICK LABEL | 1 | 1100 | 30 | 36.6667 | 4.5833 | 1 | 2 | 8 |  |  |  |  | 428 | 672 |  | 1
2025-05-05 | JOST24120092 | CP08-545-P01-02 | ST | STICK LABEL | 1 | 500 | 18 | 27.7778 | 3.4722 | 1 | 2 | 8 | [5 empty] | 500 |  | 3
2025-05-05 | JOST24120047 | CP08-046-P03-04 | AL | CHECKING | 1 | 30120 | 1800 | 16.7333 | 2.0917 | 1 | 2 | 8 | [5 empty] | 30120 |  | 3
2025-05-17 | JOTP24110201 | CP08-553-P05-07 | TR | PAINTING | 1 | 252 | 12 | 21 | 2.625 | 1 | 2 | 8 | 2025-04-16 07:00 |  |  |  | 211 | 41 |  | 1
2025-05-17 | JOTP24110201 | CP08-553-P06-07 | TR | PACK & LABEL | 1 | 252 | 12 | 21 | 2.625 | 1 | 2 | 8 | 2025-04-17 09:00 |  |  |  | 182 | 70 |  | 1
2025-05-17 | JOST24120179 | CP08-289-P04-06 | ST-4 | TP08 | 1 | 28632 | 360 | 79.5333 | 9.9417 | 1 | 2 | 8 | 2025-04-18 08:00 |  |  |  | 5990 | 22642 |  | 3
2025-05-17 | JOST24120179 | CP08-289-P05-06 | AL | CHECKING | 1 | 28632 | 360 | 79.5333 | 9.9417 | 1 | 2 | 8 | 2025-04-19 |  |  |  | 5990 | 22642 |  | 3
2025-05-17 | JOST24120433 | CH04-002-P01-07 | ST-3 | PP25 | 1 | 5900 | 300 | 19.6667 | 2.4583 | 1 | 2 | 8 | [5 empty] | 5900 |  | 3
2025-05-17 | JOST24120433 | CH04-002-P02-07 | ST-3 | PP26-110T | 1 | 5900 | 300 | 19.6667 | 2.4583 | 1 | 2 | 8 | [5 empty] | 5900 |  | 3
2025-05-18 | JOST24120433 | CH04-002-P03-07 | ST-3 | PP20 | 1 | 5900 | 300 | 19.6667 | 2.4583 | 1 | 2 | 8 | [5 empty] | 5900 |  | 3
2025-05-19 | JOST24120433 | CH04-002-P04-07 | ST-3 | PP28-110T | 1 | 5900 | 300 | 19.6667 | 2.4583 | 1 | 2 | 8 | [5 empty] | 5900 |  | 3
2025-05-20 | JOST24120433 | CH04-002-P05-07 | ST-3 | SW01 | 1 | 5900 | 300 | 19.6667 | 2.4583 | 1 | 2 | 8 | [5 empty] | 5900 |  | 3
2025-05-21 | JOST24120433 | CH04-002-P06-07 | ST-1 | OPT PAINTING | 1 | 5900 | 120 | 49.1667 | 6.1458 | 1 | 2 | 8 | [5 empty] | 5900 |  | 3
2025-05-22 | JOST24120408 | CT10-001-P01-06 | ST-3 | PP09-160T | 1 | 6080 | 330 | 18.4242 | 2.303 | 1 | 2 | 8 |  |  |  |  | 6042 | 38 |  | 3
2025-05-23 | JOST24120408 | CT10-001-P02-06 | ST-3 | PP18 | 1 | 6080 | 330 | 18.4242 | 2.303 | 1 | 2 | 8 |  |  |  |  | 6042 | 38 |  | 3
2025-05-24 | JOST24120408 | CT10-001-P03-06 | ST-3 | PP17-110T | 1 | 6080 | 330 | 18.4242 | 2.303 | 1 | 2 | 8 |  |  |  |  | 6042 | 38 |  | 3
2025-05-24 | JOST24120408 | CT10-001-P04-06 | ST-3 | PP16-110T | 1 | 6080 | 330 | 18.4242 | 2.303 | 1 | 2 | 8 |  |  |  |  | 6042 | 38 |  | 3
2025-05-24 | JOST24120408 | CT10-001-P05-06 | ST-3 | PP27-110T | 2 | 6080 | 330 | 18.4242 | 2.303 | 1 | 2 | 8 |  |  |  |  | 6042 | 38 |  | 3
2025-05-24 | JOAW24120119 | CD11-026-P05-06 | WN | TW01 | 1 | 15000 | 420 | 35.7143 | 4.4643 | 1 | 2 | 8 | [5 empty] | 15000 |  | 3
2025-05-24 | JOAW24120383 | CP08-557-P08-09 | AL | CHECKING | 1 | 1000 | 15 | 66.6667 | 8.3333 | 1 | 2 | 8 | [5 empty] | 1000 |  | 3
2025-05-24 | JOST24120359 | CP08-504A-P02-04 | ST-4 | PP24-160T | 1 | 216 | 300 | 0.72 | 0.09 | 1 | 2 | 8 | [5 empty] | 216 |  | 3
2025-05-28 | JOST24120359 | CP08-504A-P03-04 | ST-4 | PP24-160T | 1 | 216 | 300 | 0.72 | 0.09 | 1 | 2 | 8 | [5 empty] | 216 |  | 3
2025-05-28 | JOST24120337 | CP08-352-P02-04 | ST-4 | PP26-110T | 1 | 5440 | 360 | 15.1111 | 1.8889 | 1 | 2 | 8 | [5 empty] | 5440 |  | 3
2025-05-28 | JOST24120337 | CP08-352-P03-04 | ST-4 | PP28-110T | 1 | 5440 | 360 | 15.1111 | 1.8889 | 1 | 2 | 8 | [5 empty] | 5440 |  | 3
2025-05-31 | JOST24120338 | CP08-353&CP08-354-P01-05 | SM | SM01 | 1 | 2800 | 480 | 5.8333 | 0.72917 | 1 | 2 | 8 | 2025-03-15 | 2025-03-15 |  |  |  | 2800 |  | 3
2025-05-31 | JOST24120338 | CP08-353&CP08-354-P02-05 | ST-4 | PP25-160T | 1 | 2800 | 300 | 9.3333 | 1.1667 | 1 | 2 | 8 | [5 empty] | 2800 |  | 3
2025-05-31 | JOST24120338 | CP08-353&CP08-354-P03-05 | ST-4 | PP20-110T | 1 | 2800 | 300 | 9.3333 | 1.1667 | 1 | 2 | 8 | [5 empty] | 2800 |  | 3
2025-05-31 | JOST24120338 | CP08-353&CP08-354-P04-05 | ST-4 | PP28-110T | 1 | 2800 | 300 | 9.3333 | 1.1667 | 1 | 2 | 8 | [5 empty] | 2800 |  | 3
2025-05-31 | JOST24120326 | CP08-265-P03-04 | ST-2 | PP06-040T | 1 | 3142 | 240 | 13.0917 | 1.6365 | 1 | 2 | 8 |  |  |  |  | 142 | 3000 |  | 3
2025-05-31 | JOST24120418 | CT10-015-P01-05 | ST-4 | PP24-160T | 1 | 14400 | 360 | 40 | 5 | 1 | 2 | 8 | [5 empty] | 14400 |  | 3
2025-06-05 | JOST24120418 | CT10-015-P02-05 | ST-4 | PP25-160T | 1 | 14400 | 360 | 40 | 5 | 1 | 2 | 8 | [5 empty] | 14400 |  | 3
2025-06-05 | JOST24120418 | CT10-015-P03-05 | ST-4 | PP20-110T | 1 | 14400 | 360 | 40 | 5 | 1 | 2 | 8 | [5 empty] | 14400 |  | 3
2025-06-05 | JOST24120418 | CT10-015-P04-05 | ST-4 | PP28-110T | 1 | 14400 | 360 | 40 | 5 | 1 | 2 | 8 | [5 empty] | 14400 |  | 3
2025-06-05 | JOST24120409 | CT10-001-P01-06 | ST-3 | PP09-160T | 1 | 6080 | 330 | 18.4242 | 2.303 | 1 | 2 | 8 | [5 empty] | 6080 |  | 3
2025-06-05 | JOST24120409 | CT10-001-P02-06 | ST-3 | PP18 | 1 | 6080 | 330 | 18.4242 | 2.303 | 1 | 2 | 8 | [5 empty] | 6080 |  | 3
2025-06-05 | JOST24120409 | CT10-001-P03-06 | ST-3 | PP17-110T | 1 | 6080 | 330 | 18.4242 | 2.303 | 1 | 2 | 8 | [5 empty] | 6080 |  | 3
2025-06-05 | JOST24120409 | CT10-001-P04-06 | ST-3 | PP16-110T | 1 | 6080 | 330 | 18.4242 | 2.303 | 1 | 2 | 8 | [5 empty] | 6080 |  | 3
2025-06-05 | JOST24120409 | CT10-001-P05-06 | ST-3 | PP27-110T | 2 | 6080 | 330 | 18.4242 | 2.303 | 1 | 2 | 8 | [5 empty] | 6080 |  | 3
2025-07-05 | JOTP24120398 | CP08-587-P02-04 | ST | PP05 | 1 | 150 | 300 | 0.5 | 0.0625 | 1 | 2 | 8 | [5 empty] | 150 |  | 3
2025-07-06 | JOTP24120398 | CP08-587-P03-04 | PB | PB01 | 1 | 150 | 50 | 3 | 0.375 | 1 | 2 | 8 | [5 empty] | 150 |  | 3
2025-07-07 | JOST24120366 | CP08-513-P02-07 | ST-4 | PP25-160T | 1 | 2450 | 360 | 6.8056 | 0.85069 | 1 | 2 | 8 |  |  |  |  | 1350 | 1100 |  | 3
2025-07-08 | JOST24120366 | CP08-513-P03-07 | ST-4 | PP20-110T | 1 | 2450 | 360 | 6.8056 | 0.85069 | 1 | 2 | 8 |  |  |  |  | 1350 | 1100 |  | 3
2025-07-09 | JOST24120366 | CP08-513-P04-07 | ST-4 | PP28-110T | 1 | 2450 | 360 | 6.8056 | 0.85069 | 1 | 2 | 8 |  |  |  |  | 1350 | 1100 |  | 3
2025-07-10 | JOST24120366 | CP08-513-P05-07 | ST-3 | TP03 | 1 | 2450 | 240 | 10.2083 | 1.276 | 1 | 2 | 8 |  |  |  |  | 625 | 1825 |  | 3
2025-07-11 | JOST24120366 | CP08-513-P06-07 | ST | OPT | 1 | 2450 | 420 | 5.8333 | 0.72917 | 1 | 2 | 8 | [5 empty] | 2450 |  | 3
2025-07-12 | JOST24120091 | CP08-544-P01-02 | ST | STICK LABEL | 1 | 1000 | 30 | 33.3333 | 4.1667 | 1 | 2 | 8 | [5 empty] | 1000 |  | 3
2025-07-13 | JOAW24100348 | CA16-011-P01-03 | FM | SW05 | 1 | 60000 | 450 | 133.3333 | 16.6667 | 1 | 2 | 8 |  |  |  |  | 22678 | 37322 |  | 3
2025-07-14 | JOAW24100348 | CA16-011-P02-03 | FM | OPT | 1 | 60000 | 900 | 66.6667 | 8.3333 | 1 | 2 | 8 |  |  |  |  | 5000 | 55000 |  | 3
2025-07-15 | JOST24100248 | CA16-010-P01-03 | ST | PP01-110T | 1 | 90909 | 3000 | 30.303 | 3.7879 | 1 | 2 | 8 |  |  |  |  | 20100 | 70809 |  | 3
2025-07-16 | JOST24100248 | CA16-010-P02-03 | ST-1 | VM01 | 1 | 90909 | 1000 | 90.909 | 11.3636 | 1 | 2 | 8 | [5 empty] | 90909 |  | 3
2025-07-17 | JOST24120207 | CV04-010-P01-08 | ST-1 | PP11-035T | 1 | 8270 | 480 | 17.2292 | 2.1536 | 1 | 2 | 8 | [5 empty] | 8270 |  | 3
2025-07-17 | JOST24120207 | CV04-010-P02-08 | ST-1 | PP11-035T | 1 | 8270 | 240 | 34.4583 | 4.3073 | 1 | 2 | 8 | [5 empty] | 8270 |  | 3
2025-07-17 | JOST24120207 | CV04-010-P03-08 | ST-2 | PP06-040T | 1 | 8270 | 240 | 34.4583 | 4.3073 | 1 | 2 | 8 | [5 empty] | 8270 |  | 3
2025-07-17 | JOST24120207 | CV04-010-P04-08 | ST-2 | PP15-080T | 1 | 8270 | 240 | 34.4583 | 4.3073 | 1 | 2 | 8 | [5 empty] | 8270 |  | 3
2025-07-17 | JOST24120207 | CV04-010-P05-08 | 0 | HAND BEND-JIG | 1 | 8270 | 240 | 34.4583 | 4.3073 | 1 | 2 | 8 | [5 empty] | 8270 |  | 3
2025-07-17 | JOST24120207 | CV04-010-P06-08 | 0 | PLIER BENDING | 1 | 8270 | 240 | 34.4583 | 4.3073 | 1 | 2 | 8 | [5 empty] | 8270 |  | 3
2025-07-17 | JOAW24120287 | CM18-001-P01-06 | WN | SW13 | 1 | 30000 | 150 | 200 | 25 | 1 | 2 | 8 |  |  |  |  | 24407 | 5593 |  | 3
2025-07-17 | JOAW24120287 | CM18-001-P02-06 | WN | PP23 | 1 | 30000 | 420 | 71.4286 | 8.9286 | 1 | 2 | 8 |  |  |  |  | 24813 | 5187 |  | 3
2025-07-17 | JOAW24120287 | CM18-001-P05-06 | WN | TW01 | 1 | 30000 | 450 | 66.6667 | 8.3333 | 1 | 2 | 8 | [5 empty] | 30000 |  | 3
2025-07-17 | JOAW24120251 | CD11-027D-P01-02 | ST | PP05-060T | 1 | 20000 | 240 | 83.3333 | 10.4167 | 1 | 2 | 8 | [5 empty] | 20000 |  | 3
2025-07-17 | JOTP24120184 | CP08-562-P01-05 | PB | SW14 | 1 | 802 | 120 | 6.6833 | 0.83542 | 1 | 2 | 8 | [5 empty] | 802 |  | 3
2025-07-17 | JOTP24120184 | CP08-562-P02-05 | PB | SW14 | 1 | 802 | 17 | 47.1765 | 5.8971 | 1 | 2 | 8 | [5 empty] | 802 |  | 3
2025-07-17 | JOTP24120184 | CP08-562-P03-05 | OPT | OPT | 1 | 802 | 50 | 16.04 | 2.005 | 1 | 2 | 8 | [5 empty] | 802 |  | 3
2025-07-17 | JOTP24120184 | CP08-562-P04-05 | OPT | OPT | 1 | 802 | 60 | 13.3667 | 1.6708 | 1 | 2 | 8 | [5 empty] | 802 |  | 3
2025-07-17 | JOAW24120209 | CV04-012-P01-04 | FM | FM01 | 1 | 16593 | 1200 | 13.8275 | 1.7284 | 1 | 2 | 8 |  |  |  |  | 2200 | 14393 |  | 3
2025-07-17 | JOAW24120209 | CV04-012-P02-04 | ST-2 | PP06-040T | 1 | 16593 | 360 | 46.0917 | 5.7615 | 1 | 2 | 8 | [5 empty] | 16593 |  | 3
2025-07-17 | JOAW24120249 | CD11-027B-P01-02 | WN | WS01 | 1 | 80000 | 2160 | 37.037 | 4.6296 | 1 | 2 | 8 | [5 empty] | 80000 |  | 3
2025-07-17 | JOST24120253 | CH04-002-P01-07 | ST-3 | PP25 | 1 | 5100 | 300 | 17 | 2.125 | 1 | 2 | 8 | [5 empty] | 5100 |  | 3
2025-07-17 | JOST24120253 | CH04-002-P02-07 | ST-3 | PP26-110T | 1 | 5100 | 300 | 17 | 2.125 | 1 | 2 | 8 | [5 empty] | 5100 |  | 3
2025-07-17 | JOST24120253 | CH04-002-P03-07 | ST-3 | PP20 | 1 | 5100 | 300 | 17 | 2.125 | 1 | 2 | 8 | [5 empty] | 5100 |  | 3
2025-07-17 | JOST24120253 | CH04-002-P04-07 | ST-3 | PP28-110T | 1 | 5100 | 300 | 17 | 2.125 | 1 | 2 | 8 | [5 empty] | 5100 |  | 3
2025-07-17 | JOST24120253 | CH04-002-P05-07 | ST-3 | SW01 | 1 | 5100 | 300 | 17 | 2.125 | 1 | 2 | 8 | [5 empty] | 5100 |  | 3
2025-07-17 | JOST24120253 | CH04-002-P06-07 | ST-1 | OPT PAINTING | 1 | 5100 | 120 | 42.5 | 5.3125 | 1 | 2 | 8 | [5 empty] | 5100 |  | 3
2025-07-17 | JOST24120431 | CC06-001-P01-04 | ST-2 | PP06-040T | 1 | 43210 | 2220 | 19.464 | 2.433 | 1 | 2 | 8 | [5 empty] | 43210 |  | 3
2025-07-17 | JOST24120431 | CC06-001-P02-04 | AL | TP08 | 1 | 43210 | 600 | 72.0167 | 9.0021 | 1 | 2 | 8 | [5 empty] | 43210 |  | 3
2025-07-17 | JOST24120431 | CC06-001-P03-04 | AL | DRY-1 | 1 | 43210 | 780 | 55.3974 | 6.9247 | 1 | 2 | 8 | [5 empty] | 43210 |  | 3
2025-07-17 | JOST24120372 | CP08-521-P01-02 | ST-2 | PP01-110T | 1 | 2604 | 3000 | 0.868 | 0.1085 | 1 | 2 | 8 | [5 empty] | 2604 |  | 3
2025-07-17 | JOST24120373 | CP08-522-P01-02 | ST-3 | PP01-110T | 1 | 3646 | 3000 | 1.2153 | 0.15192 | 1 | 2 | 8 | [5 empty] | 3646 |  | 3
2025-07-17 | JOTP24120376 | CP08-554A-P02-04 | TR | 1 | 1 | 400 | 20 | 20 | 2.5 | 1 | 2 | 8 | [5 empty] | 400 |  | 3
2025-07-17 | JOTP24120376 | CP08-554A-P03-04 | TR | PB02 | 1 | 400 | 30 | 13.3333 | 1.6667 | 1 | 2 | 8 | [5 empty] | 400 |  | 3
2025-07-17 | JOST25010145 | CM03-039-P02-03 | ST | VM01 | 1 | 2000 | 2000 | 1 | 0.125 | 1 | 2 | 8 | [5 empty] | 2000 |  | 3
2025-07-17 | JOST25010140 | CM03-027-P02-05 | ST | VM01 | 1 | 3550 | 3000 | 1.1833 | 0.14792 | 1 | 2 | 8 | [5 empty] | 3550 |  | 3
2025-07-17 | JOST25010140 | CM03-027-P04-05 | AL | CHECKING | 1 | 3550 | 600 | 5.9167 | 0.73958 | 1 | 2 | 8 | [5 empty] | 3550 |  | 3
2025-07-17 | JOTP25010142 | CM03-034-P01-05 | TR | TM05 | 1 | 300 | 81 | 3.7037 | 0.46296 | 1 | 2 | 8 |  |  |  |  | 1 | 299 |  | 3
2025-07-17 | JOTP25010142 | CM03-034-P02-05 | WN | DEBURR | 1 | 300 | 50 | 6 | 0.75 | 1 | 2 | 8 | [5 empty] | 300 |  | 3
2025-07-17 | JOTP25010142 | CM03-034-P03-05 | TR | APPLY OIL | 1 | 300 | 300 | 1 | 0.125 | 1 | 2 | 8 | [5 empty] | 300 |  | 3
2025-07-17 | JOTP25010142 | CM03-034-P04-05 | TR | PB04 | 1 | 300 | 200 | 1.5 | 0.1875 | 1 | 2 | 8 | [5 empty] | 300 |  | 3
2025-07-17 | JOST25010143 | CM03-037-P01-03 | ST-3 | PP04-060T | 1 | 5400 | 360 | 15 | 1.875 | 1 | 2 | 8 | [5 empty] | 5400 |  | 3
2025-07-17 | JOST25010143 | CM03-037-P02-03 | ST-3 | PP03-060T | 1 | 5400 | 360 | 15 | 1.875 | 1 | 2 | 8 | [5 empty] | 5400 |  | 3
2025-07-17 | JOTP25010064 | CP08-427-P01-03 | TR | TM06 | 1 | 550 | 28 | 19.6429 | 2.4554 | 1 | 2 | 8 | [5 empty] | 550 |  | 3
2025-07-17 | JOTP25010064 | CP08-427-P02-03 | TR | PB05 | 1 | 550 | 30 | 18.3333 | 2.2917 | 1 | 2 | 8 | [5 empty] | 550 |  | 3
2025-07-23 | JOTP25010063 | CP08-426-P01-02 | TR | TM03 | 1 | 672 | 60 | 11.2 | 1.4 | 1 | 2 | 8 | [5 empty] | 672 |  | 3
2025-07-23 | JOTP25010062 | CP08-425-P01-03 | TR | TM03 | 1 | 672 | 60 | 11.2 | 1.4 | 1 | 2 | 8 | [5 empty] | 672 |  | 3
2025-07-23 | JOTP25010062 | CP08-425-P02-03 | TR | PB08 | 1 | 672 | 120 | 5.6 | 0.7 | 1 | 2 | 8 | [5 empty] | 672 |  | 3
2025-07-23 | JOTP25010061 | CP08-423-P01-02 | TR | TM03 | 1 | 550 | 40 | 13.75 | 1.7188 | 1 | 2 | 8 | [5 empty] | 550 |  | 3
2025-07-23 | JOTP25010060 | CP08-422-P01-03 | TR | TM05 | 1 | 612 | 50 | 12.24 | 1.53 | 1 | 2 | 8 | [5 empty] | 612 |  | 3
2025-07-23 | JOTP25010060 | CP08-422-P02-03 | TR | PB08 | 1 | 612 | 72 | 8.5 | 1.0625 | 1 | 2 | 8 | [5 empty] | 612 |  | 3
2025-07-23 | JOTP25010059 | CP08-421-P01-03 | TR | TM05 | 1 | 612 | 90 | 6.8 | 0.85 | 1 | 2 | 8 | [5 empty] | 612 |  | 3
2025-07-23 | JOTP25010059 | CP08-421-P02-03 | TR | PB08 | 1 | 612 | 120 | 5.1 | 0.6375 | 1 | 2 | 8 | [5 empty] | 612 |  | 3
2025-07-23 | JOTP25010057 | CP08-419-P01-03 | TR | TM03 | 1 | 1104 | 72 | 15.3333 | 1.9167 | 1 | 2 | 8 | [5 empty] | 1104 |  | 3
2025-07-23 | JOTP25010057 | CP08-419-P02-03 | TR | PB07 | 1 | 1104 | 108 | 10.2222 | 1.2778 | 1 | 2 | 8 | [5 empty] | 1104 |  | 3
2025-07-23 | JOTP25010056 | CP08-418-P02-03 | TR | PB05 | 1 | 700 | 40 | 17.5 | 2.1875 | 1 | 2 | 8 | [5 empty] | 700
2025-07-23 | JOTP25010055 | CP08-417-P01-04 | SM | SM01 | 1 | 902 | 48 | 18.7917 | 2.349 | 1 | 2 | 8 | [5 empty] | 902
2025-07-23 | JOTP25010055 | CP08-417-P02-04 | TR | TM05 | 1 | 902 | 150 | 6.0133 | 0.75167 | 1 | 2 | 8 | [5 empty] | 902
2025-07-23 | JOTP25010055 | CP08-417-P03-04 | TR | PB08 | 1 | 902 | 120 | 7.5167 | 0.93958 | 1 | 2 | 8 | [5 empty] | 902
2025-07-23 | JOTP25010054 | CP08-416-P01-03 | TR | TM05 | 1 | 720 | 70 | 10.2857 | 1.2857 | 1 | 2 | 8 | [5 empty] | 720
2025-07-23 | JOTP25010054 | CP08-416-P02-03 | TR | PB04 | 1 | 720 | 40 | 18 | 2.25 | 1 | 2 | 8 | [5 empty] | 720
2025-07-23 | JOST25010051 | CP08-407-P01-07 | ST | PP29 | 1 | 350 | 120 | 2.9167 | 0.36458 | 1 | 2 | 8 | [5 empty] | 350
2025-07-23 | JOST25010051 | CP08-407-P02-07 | ST | PP33 | 1 | 350 | 120 | 2.9167 | 0.36458 | 1 | 2 | 8 | [5 empty] | 350
2025-07-23 | JOST25010051 | CP08-407-P03-07 | ST | TP03 | 1 | 350 | 60 | 5.8333 | 0.72917 | 1 | 2 | 8 | [5 empty] | 350
2025-07-23 | JOST25010051 | CP08-407-P04-07 | ST | TP09 | 1 | 350 | 120 | 2.9167 | 0.36458 | 1 | 2 | 8 | [5 empty] | 350
2025-07-23 | JOST25010051 | CP08-407-P05-07 | ST | PP33 | 1 | 350 | 120 | 2.9167 | 0.36458 | 1 | 2 | 8 | [5 empty] | 350
2025-07-23 | JOST25010051 | CP08-407-P06-07 | ST | SW01 | 1 | 350 | 80 | 4.375 | 0.54688 | 1 | 2 | 8 | [5 empty] | 350
2025-07-23 | JOST25010050 | CP08-400-P01-04 | ST-4 | PP24-160T | 1 | 1666 | 360 | 4.6278 | 0.57847 | 1 | 2 | 8 | [5 empty] | 1666
2025-07-23 | JOST25010050 | CP08-400-P02-04 | ST-4 | PP25-160T | 1 | 1666 | 360 | 4.6278 | 0.57847 | 1 | 2 | 8 | [5 empty] | 1666
2025-07-23 | JOST25010050 | CP08-400-P03-04 | ST-4 | PP28-110T | 1 | 1666 | 360 | 4.6278 | 0.57847 | 1 | 2 | 8 | [5 empty] | 1666
2025-07-23 | JOTP25010049 | CP08-344-P01-03 | TR | TM06 | 1 | 1666 | 50 | 33.32 | 4.165 | 1 | 2 | 8 | [5 empty] | 1666
2025-07-23 | JOTP25010049 | CP08-344-P02-03 | TR | PB04 | 1 | 640 | 120 | 5.3333 | 0.66667 | 1 | 2 | 8 | [5 empty] | 640
2025-07-28 | JOAW25010048 | CP08-297-P01-02 | FM | FM02 | 1 | 15217 | 2400 | 6.3404 | 0.79255 | 1 | 2 | 8 | [5 empty] | 15217
2025-07-28 | JOST25010046 | CP08-259-P01-04 | SM | SM01 | 1 | 900 | 120 | 7.5 | 0.9375 | 1 | 2 | 8 | [5 empty] | 900
2025-07-28 | JOST25010046 | CP08-259-P02-04 | ST-1 | PP10-080T | 1 | 900 | 360 | 2.5 | 0.3125 | 1 | 2 | 8 | [5 empty] | 900
2025-07-28 | JOST25010046 | CP08-259-P03-04 | ST-1 | PP04-060T | 1 | 900 | 240 | 3.75 | 0.46875 | 1 | 2 | 8 | [5 empty] | 900
2025-07-28 | JOST25010093 | CP08-515-P01-03 | ST-2 | PP10-080T | 1 | 3906 | 1800 | 2.17 | 0.27125 | 1 | 2 | 8 | [5 empty] | 3906
2025-07-28 | JOST25010093 | CP08-515-P02-03 | AL | TP04 | 1 | 3906 | 300 | 13.02 | 1.6275 | 1 | 2 | 8 | [5 empty] | 3906
2025-07-28 | JOST25010092 | CP08-512-P01-07 | ST-3 | PP09-160T | 1 | 2100 | 300 | 7 | 0.875 | 1 | 2 | 8 | [5 empty] | 2100
2025-07-28 | JOST25010092 | CP08-512-P02-07 | ST-3 | PP18-150T | 1 | 2100 | 300 | 7 | 0.875 | 1 | 2 | 8 | [5 empty] | 2100
2025-07-28 | JOST25010092 | CP08-512-P03-07 | ST-3 | PP21-110T | 1 | 2100 | 300 | 7 | 0.875 | 1 | 2 | 8 | [5 empty] | 2100
2025-07-28 | JOST25010092 | CP08-512-P04-07 | ST-3 | PP17-110T | 1 | 2100 | 300 | 7 | 0.875 | 1 | 2 | 8 | [5 empty] | 2100
2025-07-28 | JOST25010092 | CP08-512-P05-07 | ST-3 | PP16-110T | 1 | 2100 | 300 | 7 | 0.875 | 1 | 2 | 8 | [5 empty] | 2100
2025-07-28 | JOST25010092 | CP08-512-P06-07 | ST-3 | PP27-110T | 1 | 2100 | 300 | 7 | 0.875 | 1 | 2 | 8 | [5 empty] | 2100
2025-07-28 | JOST25010091 | CP08-511-P01-05 | SM | SM01 | 1 | 2220 | 240 | 9.25 | 1.1562 | 1 | 2 | 8 | [5 empty] | 2220
2025-07-28 | JOST25010091 | CP08-511-P02-05 | ST-3 | PP17-110T | 1 | 2220 | 240 | 9.25 | 1.1562 | 1 | 2 | 8 | [5 empty] | 2220
2025-07-28 | JOST25010091 | CP08-511-P03-05 | ST-3 | PP16-110T | 1 | 2220 | 240 | 9.25 | 1.1562 | 1 | 2 | 8 | [5 empty] | 2220
2025-07-28 | JOST25010091 | CP08-511-P04-05 | ST-3 | PP27-110T | 1 | 2220 | 240 | 9.25 | 1.1562 | 1 | 2 | 8 | [5 empty] | 2220
2025-07-28 | JOST25010089 | CP08-508-P01-09 | ST | SM01 | 1 | 1300 | 480 | 2.7083 | 0.33854 | 1 | 2 | 8 | [5 empty] | 1300
2025-07-28 | JOST25010089 | CP08-508-P02-09 | ST-4 | PP24-160T | 1 | 1300 | 240 | 5.4167 | 0.67708 | 1 | 2 | 8 | [5 empty] | 1300
2025-07-28 | JOST25010089 | CP08-508-P03-09 | ST-4 | PP25-160T | 1 | 1300 | 240 | 5.4167 | 0.67708 | 1 | 2 | 8 | [5 empty] | 1300
2025-07-28 | JOST25010089 | CP08-508-P04-09 | ST-4 | PP26-110T | 1 | 1300 | 240 | 5.4167 | 0.67708 | 1 | 2 | 8 | [5 empty] | 1300
2025-07-28 | JOST25010089 | CP08-508-P05-09 | ST-4 | PP28-110T | 1 | 1300 | 240 | 5.4167 | 0.67708 | 1 | 2 | 8 | [5 empty] | 1300
2025-07-28 | JOST25010089 | CP08-508-P06-09 | ST-4 | PP24-160T | 1 | 1300 | 240 | 5.4167 | 0.67708 | 1 | 2 | 8 | [5 empty] | 1300
2025-07-28 | JOST25010089 | CP08-508-P07-09 | ST-4 | PP25-160T | 1 | 1300 | 240 | 5.4167 | 0.67708 | 1 | 2 | 8 | [5 empty] | 1300
2025-07-28 | JOST25010089 | CP08-508-P08-09 | ST-4 | PP26-110T | 1 | 1300 | 240 | 5.4167 | 0.67708 | 1 | 2 | 8 | [5 empty] | 1300
2025-07-28 | JOST25010088 | CP08-507-P01-08 | ST-4 | PP24-160T | 1 | 300 | 240 | 1.25 | 0.15625 | 1 | 2 | 8 | [5 empty] | 300
2025-07-28 | JOST25010088 | CP08-507-P02-08 | ST-4 | PP25-160T | 1 | 300 | 240 | 1.25 | 0.15625 | 1 | 2 | 8 | [5 empty] | 300
2025-07-28 | JOST25010088 | CP08-507-P03-08 | ST-4 | PP26-110T | 1 | 300 | 240 | 1.25 | 0.15625 | 1 | 2 | 8 | [5 empty] | 300
2025-07-28 | JOST25010088 | CP08-507-P04-08 | ST-4 | PP28-110T | 1 | 300 | 240 | 1.25 | 0.15625 | 1 | 2 | 8 | [5 empty] | 300
2025-07-28 | JOST25010088 | CP08-507-P05-08 | ST-4 | PP24-160T | 1 | 300 | 240 | 1.25 | 0.15625 | 1 | 2 | 8 | [5 empty] | 300
2025-07-28 | JOST25010088 | CP08-507-P06-08 | ST-4 | PP25-160T | 1 | 300 | 240 | 1.25 | 0.15625 | 1 | 2 | 8 | [5 empty] | 300
2025-07-28 | JOST25010088 | CP08-507-P07-08 | ST-4 | PP26-110T | 1 | 300 | 240 | 1.25 | 0.15625 | 1 | 2 | 8 | [5 empty] | 300
2025-07-28 | JOST25010087 | CP08-506-P01-09 | ST | SM01 | 1 | 2500 | 480 | 5.2083 | 0.65104 | 1 | 2 | 8 | [5 empty] | 2500
2025-07-28 | JOST25010087 | CP08-506-P02-09 | ST-4 | PP24-160T | 1 | 2500 | 240 | 10.4167 | 1.3021 | 1 | 2 | 8 | [5 empty] | 2500
2025-07-28 | JOST25010087 | CP08-506-P03-09 | ST-4 | PP25-160T | 1 | 2500 | 240 | 10.4167 | 1.3021 | 1 | 2 | 8 | [5 empty] | 2500
2025-07-28 | JOST25010087 | CP08-506-P04-09 | ST-4 | PP26-110T | 1 | 2500 | 240 | 10.4167 | 1.3021 | 1 | 2 | 8 | [5 empty] | 2500
2025-07-28 | JOST25010087 | CP08-506-P05-09 | ST-4 | PP28-110T | 1 | 2500 | 240 | 10.4167 | 1.3021 | 1 | 2 | 8 | [5 empty] | 2500
2025-07-28 | JOST25010087 | CP08-506-P06-09 | ST-4 | PP24-160T | 1 | 2500 | 240 | 10.4167 | 1.3021 | 1 | 2 | 8 | [5 empty] | 2500
2025-07-28 | JOST25010087 | CP08-506-P07-09 | ST-4 | PP25-160T | 1 | 2500 | 240 | 10.4167 | 1.3021 | 1 | 2 | 8 | [5 empty] | 2500
2025-07-28 | JOST25010087 | CP08-506-P08-09 | ST-4 | PP26-110T | 1 | 2500 | 240 | 10.4167 | 1.3021 | 1 | 2 | 8 | [5 empty] | 2500
2025-07-28 | JOST25010085 | CP08-499B-P02-04 | 0 | PP21 | 1 | 250 | 180 | 1.3889 | 0.17361 | 1 | 2 | 8 | [5 empty] | 250
2025-07-28 | JOST25010085 | CP08-499B-P03-04 | 0 | PP30-200T | 1 | 250 | 180 | 1.3889 | 0.17361 | 1 | 2 | 8 | [5 empty] | 250
2025-07-28 | JOST25010083 | CP08-499-P01-02 | ST-3 | SW01 | 1 | 250 | 30 | 8.3333 | 1.0417 | 1 | 2 | 8 | [5 empty] | 250
2025-07-28 | JOST25010082 | CP08-496A-P01-05 | ST-4 | PP18-150T | 1 | 2000 | 240 | 8.3333 | 1.0417 | 1 | 2 | 8 | [5 empty] | 2000
2025-07-28 | JOST25010082 | CP08-496A-P02-05 | ST-4 | PP17-110T | 1 | 2000 | 240 | 8.3333 | 1.0417 | 1 | 2 | 8 | [5 empty] | 2000
2025-07-28 | JOST25010082 | CP08-496A-P03-05 | ST-4 | PP16-110T | 1 | 2000 | 240 | 8.3333 | 1.0417 | 1 | 2 | 8 | [5 empty] | 2000
2025-07-28 | JOST25010082 | CP08-496A-P04-05 | ST-4 | PP27-110T | 1 | 2000 | 240 | 8.3333 | 1.0417 | 1 | 2 | 8 | [5 empty] | 2000
2025-07-28 | JOTP25010081 | CP08-490-P01-04 | TR | TM02 | 1 | 105 | 80 | 1.3125 | 0.16406 | 1 | 2 | 8 | [5 empty] | 105
2025-07-28 | JOTP25010081 | CP08-490-P02-04 | WN | DEBURR | 1 | 105 | 14 | 7.5 | 0.9375 | 1 | 2 | 8 | [5 empty] | 105
2025-07-29 | JOTP25010081 | CP08-490-P03-04 | ST-1 | PAINTING | 1 | 105 | 50 | 2.1 | 0.2625 | 1 | 2 | 8 | [5 empty] | 105
2025-07-30 | JOTP25010080 | CP08-489-P01-05 | TR | TM02 | 1 | 192 | 80 | 2.4 | 0.3 | 1 | 2 | 8 | [5 empty] | 192
2025-07-31 | JOTP25010080 | CP08-489-P02-05 | WN | DEBURR | 1 | 192 | 15 | 12.8 | 1.6 | 1 | 2 | 8 | [5 empty] | 192
2025-08-01 | JOTP25010080 | CP08-489-P03-05 | TR | PB04 | 1 | 192 | 120 | 1.6 | 0.2 | 1 | 2 | 8 | [5 empty] | 192
2025-08-02 | JOTP25010080 | CP08-489-P04-05 | ST-1 | PAINTING | 1 | 192 | 15 | 12.8 | 1.6 | 1 | 2 | 8 | [5 empty] | 192
2025-08-03 | JOST25010079 | CP08-482-P03-04 | ST-3 | PP21-110T | 1 | 1740 | 240 | 7.25 | 0.90625 | 1 | 2 | 8 |  |  |  |  | 159 | 1581
2025-08-04 | JOST25010078 | CP08-457-P01-04 | ST-3 | PP25-160T | 1 | 1615 | 360 | 4.4861 | 0.56076 | 1 | 2 | 8 | [5 empty] | 1615
2025-08-05 | JOST25010078 | CP08-457-P02-04 | ST-3 | PP20-110T | 1 | 1615 | 360 | 4.4861 | 0.56076 | 1 | 2 | 8 | [5 empty] | 1615
2025-08-06 | JOST25010078 | CP08-457-P03-04 | ST-3 | PP28-110T | 1 | 1615 | 360 | 4.4861 | 0.56076 | 1 | 2 | 8 | [5 empty] | 1615
2025-08-11 | JOST25010073 | CP08-437-P01-05 | SM | SM01 | 1 | 1710 | 5400 | 0.31667 | 0.039583 | 1 | 2 | 8 | [5 empty] | 1710
2025-08-11 | JOST25010073 | CP08-437-P02-05 | ST-1 | PP03-060T | 1 | 1710 | 480 | 3.5625 | 0.44531 | 1 | 2 | 8 | [5 empty] | 1710
2025-08-11 | JOST25010073 | CP08-437-P03-05 | ST-1 | PP03-060T | 1 | 1710 | 360 | 4.75 | 0.59375 | 1 | 2 | 8 | [5 empty] | 1710
2025-08-11 | JOST25010073 | CP08-437-P04-05 | TR | PP22 | 1 | 1710 | 200 | 8.55 | 1.0688 | 1 | 2 | 8 | [5 empty] | 1710
2025-08-11 | JOTP25010074 | CP08-439-P01-06 | TR | TM06 | 1 | 130 | 18 | 7.2222 | 0.90278 | 1 | 2 | 8 | [5 empty] | 130
2025-08-11 | JOTP25010074 | CP08-439-P02-06 | TR | TM02 | 1 | 130 | 18 | 7.2222 | 0.90278 | 1 | 2 | 8 | [5 empty] | 130
2025-08-11 | JOTP25010074 | CP08-439-P03-06 | TR | PB05 | 1 | 130 | 18 | 7.2222 | 0.90278 | 1 | 2 | 8 | [5 empty] | 130
2025-08-11 | JOTP25010074 | CP08-439-P04-06 | TR | PB02 | 1 | 130 | 18 | 7.2222 | 0.90278 | 1 | 2 | 8 | [5 empty] | 130
2025-08-11 | JOTP25010074 | CP08-439-P05-06 | TR | PB03 | 1 | 130 | 18 | 7.2222 | 0.90278 | 1 | 2 | 8 | [5 empty] | 130
2025-08-11 | JOTP25010070 | CP08-435 &CP08-436-P01-02 | TR | TM06 | 1 | 1280 | 80 | 16 | 2 | 1 | 2 | 8 | [5 empty] | 1280
2025-08-11 | JOTP25010070 | CP08-435-P01-03 | TR | PB04 | 1 | 640 | 160 | 4 | 0.5 | 1 | 2 | 8 | [5 empty] | 640
2025-08-11 | JOTP25010070 | CP08-435-P02-03 | TR | PB03 | 1 | 640 | 120 | 5.3333 | 0.66667 | 1 | 2 | 8 | [5 empty] | 640
2025-08-11 | JOTP25010072 | CP08-436-P01-02 | TR | PB04 | 1 | 640 | 114 | 5.614 | 0.70175 | 1 | 2 | 8 | [5 empty] | 640
2025-08-11 | JOST25010068 | CP08-434-P01-04 | SM | SM01 | 1 | 770 | 5040 | 0.15278 | 0.019097 | 1 | 2 | 8 | [5 empty] | 770
2025-08-11 | JOST25010068 | CP08-434-P02-04 | ST-4 | PP21-110T | 1 | 770 | 300 | 2.5667 | 0.32083 | 1 | 2 | 8 | [5 empty] | 770
2025-08-11 | JOST25010068 | CP08-434-P03-04 | TR | PB08 | 1 | 770 | 100 | 7.7 | 0.9625 | 1 | 2 | 8 | [5 empty] | 770
2025-08-12 | JOST25010067 | CP08-433-P01-06 | SM | SM01 | 1 | 680 | 6120 | 0.11111 | 0.013889 | 1 | 2 | 8 | [5 empty] | 680
2025-08-13 | JOST25010067 | CP08-433-P02-06 | ST-4 | PP21-110T | 1 | 680 | 300 | 2.2667 | 0.28333 | 1 | 2 | 8 | [5 empty] | 680
2025-08-14 | JOST25010067 | CP08-433-P03-06 | ST-4 | PP21-110T | 1 | 680 | 300 | 2.2667 | 0.28333 | 1 | 2 | 8 | [5 empty] | 680
2025-08-15 | JOST25010067 | CP08-433-P04-06 | TR | PB08 | 1 | 680 | 132 | 5.1515 | 0.64394 | 1 | 2 | 8 | [5 empty] | 680
2025-08-16 | JOST25010067 | CP08-433-P05-06 | TR | PB08 | 1 | 680 | 96 | 7.0833 | 0.88542 | 1 | 2 | 8 | [5 empty] | 680
2025-08-17 | JOST25010047 | CP08-292-P01-06 | ST-3 | PP25-160T | 1 | 2200 | 360 | 6.1111 | 0.76389 | 1 | 2 | 8 | [5 empty] | 2200
2025-08-18 | JOST25010047 | CP08-292-P02-06 | ST-3 | PP26-110T | 1 | 2200 | 360 | 6.1111 | 0.76389 | 1 | 2 | 8 | [5 empty] | 2200
2025-08-19 | JOST25010047 | CP08-292-P03-06 | ST-3 | PP20-110T | 1 | 2200 | 360 | 6.1111 | 0.76389 | 1 | 2 | 8 | [5 empty] | 2200
2025-08-20 | JOST25010047 | CP08-292-P04-06 | ST-3 | PP28-110T | 1 | 2200 | 360 | 6.1111 | 0.76389 | 1 | 2 | 8 | [5 empty] | 2200
2025-08-21 | JOST25010047 | CP08-292-P05-06 | ST-3 | PP24-160T | 1 | 2200 | 360 | 6.1111 | 0.76389 | 1 | 2 | 8 | [5 empty] | 2200
2025-08-22 | JOST25010045 | CP08-258-P01-03 | ST | SM01 | 1 | 1767 | 240 | 7.3625 | 0.92031 | 1 | 2 | 8 | [5 empty] | 1767
2025-08-23 | JOST25010045 | CP08-258-P02-03 | ST | PP22-060T | 1 | 1767 | 250 | 7.068 | 0.8835 | 1 | 2 | 8 | [5 empty] | 1767
2025-08-24 | JOST25010044 | CP08-257-P01-05 | ST-1 | SM01 | 1 | 1072 | 240 | 4.4667 | 0.55833 | 1 | 2 | 8 | [5 empty] | 1072
2025-08-25 | JOST25010044 | CP08-257-P02-05 | ST-3 | PP10-080T | 1 | 1072 | 360 | 2.9778 | 0.37222 | 1 | 2 | 8 | [5 empty] | 1072
2025-08-26 | JOST25010044 | CP08-257-P03-05 | ST-3 | PP04-060T | 1 | 1072 | 360 | 2.9778 | 0.37222 | 1 | 2 | 8 | [5 empty] | 1072
2025-08-27 | JOST25010044 | CP08-257-P04-05 | ST-3 | PP03-060T | 1 | 1072 | 360 | 2.9778 | 0.37222 | 1 | 2 | 8 | [5 empty] | 1072
2025-08-28 | JOAW25010037 | CP08-231A-P01-03 | WN | WS01 | 1 | 1600 | 900 | 1.7778 | 0.22222 | 1 | 2 | 8 | [5 empty] | 1600
2025-08-29 | JOAW25010037 | CP08-231A-P02-03 | WN | JIG-HAND BEND | 1 | 1600 | 120 | 13.3333 | 1.6667 | 1 | 2 | 8 | [5 empty] | 1600
2025-08-30 | JOAW25010038 | CP08-231B-P01-06 | WN | WS01 | 1 | 3200 | 720 | 4.4444 | 0.55556 | 1 | 2 | 8 | [5 empty] | 3200
2025-08-31 | JOAW25010038 | CP08-231B-P02-06 | WN | PP23-060T | 1 | 3200 | 330 | 9.697 | 1.2121 | 1 | 2 | 8 | [5 empty] | 3200
2025-09-01 | JOAW25010038 | CP08-231B-P03-06 | WN | JIG-HAND BEND | 1 | 3200 | 240 | 13.3333 | 1.6667 | 1 | 2 | 8 | [5 empty] | 3200
2025-09-02 | JOAW25010038 | CP08-231B-P04-06 | WN | PP23-060T | 1 | 3200 | 420 | 7.619 | 0.95238 | 1 | 2 | 8 | [5 empty] | 3200
2025-09-03 | JOAW25010038 | CP08-231B-P05-06 | WN | PP23 | 1 | 3200 | 240 | 13.3333 | 1.6667 | 1 | 2 | 8 | [5 empty] | 3200
2025-09-04 | JOAW25010039 | CP08-231C-P01-03 | WN | WS01 | 1 | 1600 | 900 | 1.7778 | 0.22222 | 1 | 2 | 8 | [5 empty] | 1600
2025-09-05 | JOAW25010039 | CP08-231C-P02-03 | WN | JIG-HAND BEND | 1 | 1600 | 420 | 3.8095 | 0.47619 | 1 | 2 | 8 | [5 empty] | 1600
2025-09-06 | JOAW25010040 | CP08-231D-P01-02 | WN | WS01 | 1 | 7200 | 960 | 7.5 | 0.9375 | 1 | 2 | 8 | [5 empty] | 7200
2025-09-07 | JOAW25010041 | CP08-231E-P01-02 | WN | WS01 | 1 | 6400 | 720 | 8.8889 | 1.1111 | 1 | 2 | 8 | [5 empty] | 6400
2025-09-08 | JOAW25010042 | CP08-231F-P01-02 | WN | WS01 | 1 | 6400 | 900 | 7.1111 | 0.88889 | 1 | 2 | 8 | [5 empty] | 6400
2025-09-09 | JOAW25010042 | CP08-231G-P01-02 | WN | WS01 | 1 | 5600 | 840 | 6.6667 | 0.83333 | 1 | 2 | 8 | [5 empty] | 5600
2025-09-10 | JOST25010032 | CP08-180-P01-04 | ST-3 | PP09-160T | 1 | 897 | 220 | 4.0773 | 0.50966 | 1 | 2 | 8 | [5 empty] | 897
2025-09-11 | JOST25010032 | CP08-180-P02-04 | ST-3 | PP16-110T | 1 | 897 | 220 | 4.0773 | 0.50966 | 1 | 2 | 8 | [5 empty] | 897
2025-09-12 | JOST25010032 | CP08-180-P03-04 | ST-3 | PP27-110T | 1 | 897 | 220 | 4.0773 | 0.50966 | 1 | 2 | 8 | [5 empty] | 897
2025-09-13 | JOST25010031 | CP08-146-P01-04 | ST-1 | PP06 | 1 | 8163 | 1500 | 5.442 | 0.68025 | 1 | 2 | 8 | [5 empty] | 8163
2025-09-14 | JOST25010031 | CP08-146-P02-04 | ST-1 | PP13-060T | 1 | 8163 | 360 | 22.675 | 2.8344 | 1 | 2 | 8 | [5 empty] | 8163
2025-09-15 | JOST25010031 | CP08-146-P03-04 | ST-1 | PP11-035T | 1 | 8163 | 240 | 34.0125 | 4.2516 | 1 | 2 | 8 | [5 empty] | 8163
2025-09-16 | JOST25010030 | CP08-145-P01-06 | ST-3 | PP09-160T | 1 | 5000 | 300 | 16.6667 | 2.0833 | 1 | 2 | 8 | [5 empty] | 5000
2025-09-17 | JOST25010030 | CP08-145-P02-06 | ST-3 | PP18-150T | 1 | 5000 | 300 | 16.6667 | 2.0833 | 1 | 2 | 8 | [5 empty] | 5000
2025-09-18 | JOST25010030 | CP08-145-P03-06 | ST-3 | PP17-110T | 1 | 5000 | 300 | 16.6667 | 2.0833 | 1 | 2 | 8 | [5 empty] | 5000
2025-09-19 | JOST25010030 | CP08-145-P04-06 | ST-3 | PP16-110T | 1 | 5000 | 300 | 16.6667 | 2.0833 | 1 | 2 | 8 | [5 empty] | 5000
2025-09-20 | JOST25010030 | CP08-145-P05-06 | ST-3 | PP27-110T | 1 | 5000 | 300 | 16.6667 | 2.0833 | 1 | 2 | 8 | [5 empty] | 5000
2025-09-21 | JOST25010034 | CP08-221-P01-05 | ST-4 | PP24-160T | 1 | 1265 | 240 | 5.2708 | 0.65885 | 1 | 2 | 8 | [5 empty] | 1265
2025-09-22 | JOST25010034 | CP08-221-P02-05 | ST-4 | PP25-160T | 1 | 1265 | 240 | 5.2708 | 0.65885 | 1 | 2 | 8 | [5 empty] | 1265
2025-09-23 | JOST25010034 | CP08-221-P03-05 | ST-4 | PP20-110T | 1 | 1265 | 240 | 5.2708 | 0.65885 | 1 | 2 | 8 | [5 empty] | 1265
2025-09-24 | JOST25010034 | CP08-221-P04-05 | ST-4 | PP26-110T | 1 | 1265 | 240 | 5.2708 | 0.65885 | 1 | 2 | 8 | [5 empty] | 1265
2025-09-25 | JOST25010155 | CA01-051-P02-03 | ST-2 | PP07-016T | 1 | 46640 | 1260 | 37.0159 | 4.627 | 1 | 2 | 8 |  |  |  |  | 35563 | 11077
2025-09-26 | JOST25010132 | CT10-020-P02-06 | ST-4 | PP24-160T | 1 | 1800 | 300 | 6 | 0.75 | 1 | 2 | 8 | [5 empty] | 1800
2025-09-27 | JOST25010132 | CT10-020-P03-06 | ST-4 | PP25-160T | 1 | 1800 | 300 | 6 | 0.75 | 1 | 2 | 8 | [5 empty] | 1800
2025-09-28 | JOST25010132 | CT10-020-P04-06 | ST-4 | PP20-110T | 1 | 1800 | 300 | 6 | 0.75 | 1 | 2 | 8 | [5 empty] | 1800
2025-09-29 | JOST25010132 | CT10-020-P05-06 | ST-4 | PP28-110T | 1 | 1800 | 300 | 6 | 0.75 | 1 | 2 | 8 | [5 empty] | 1800
2025-09-30 | JOST25010133 | CT10-020-P01-06 | SM | SM01 | 1 | 1800 | 360 | 5 | 0.625 | 1 | 2 | 8 | [5 empty] | 1800
2025-10-01 | JOST25010133 | CT10-020-P02-06 | ST-4 | PP24-160T | 1 | 1800 | 300 | 6 | 0.75 | 1 | 2 | 8 | [5 empty] | 1800
2025-10-02 | JOST25010133 | CT10-020-P03-06 | ST-4 | PP25-160T | 1 | 1800 | 300 | 6 | 0.75 | 1 | 2 | 8 | [5 empty] | 1800
2025-10-03 | JOST25010133 | CT10-020-P04-06 | ST-4 | PP20-110T | 1 | 1800 | 300 | 6 | 0.75 | 1 | 2 | 8 | [5 empty] | 1800
2025-10-04 | JOST25010133 | CT10-020-P05-06 | ST-4 | PP28-110T | 1 | 1800 | 300 | 6 | 0.75 | 1 | 2 | 8 | [5 empty] | 1800
2025-10-05 | JOST25010134 | CT10-021-P01-04 | SM | SM01 | 1 | 1045 | 2280 | 0.45833 | 0.057292 | 1 | 2 | 8 | [5 empty] | 1045
2025-10-06 | JOST25010134 | CT10-021-P02-04 | ST-2 | PP15-080T | 1 | 1045 | 360 | 2.9028 | 0.36285 | 1 | 2 | 8 | [5 empty] | 1045
2025-10-07 | JOST25010134 | CT10-021-P03-04 | ST-2 | PP15-080T | 1 | 1045 | 360 | 2.9028 | 0.36285 | 1 | 2 | 8 | [5 empty] | 1045
2025-10-08 | JOST25010135 | CT10-025-P01-06 | ST-3 | PP09-160T | 1 | 2432 | 330 | 7.3697 | 0.92121 | 1 | 2 | 8 | [5 empty] | 2432
2025-10-09 | JOST25010135 | CT10-025-P02-06 | ST-3 | PP18-150T | 1 | 2432 | 330 | 7.3697 | 0.92121 | 1 | 2 | 8 | [5 empty] | 2432
2025-10-10 | JOST25010135 | CT10-025-P03-06 | ST-3 | PP17-110T | 1 | 2432 | 330 | 7.3697 | 0.92121 | 1 | 2 | 8 | [5 empty] | 2432
2025-10-11 | JOST25010135 | CT10-025-P04-06 | ST-3 | PP16-110T | 1 | 2432 | 330 | 7.3697 | 0.92121 | 1 | 2 | 8 | [5 empty] | 2432
2025-10-12 | JOST25010135 | CT10-025-P05-06 | ST-3 | PP27-110T | 1 | 2432 | 330 | 7.3697 | 0.92121 | 1 | 2 | 8 | [5 empty] | 2432
2025-10-13 | JOST25010131 | CT10-019-P01-08 | ST-3 | SM01 | 1 | 1400 | 240 | 5.8333 | 0.72917 | 1 | 2 | 8 | [5 empty] | 1400
2025-10-14 | JOST25010131 | CT10-019-P02-08 | ST-3 | PP09-160T | 1 | 1400 | 240 | 5.8333 | 0.72917 | 1 | 2 | 8 | [5 empty] | 1400
2025-10-15 | JOST25010131 | CT10-019-P03-08 | ST-3 | PP18-150T | 1 | 1400 | 240 | 5.8333 | 0.72917 | 1 | 2 | 8 | [5 empty] | 1400
2025-10-16 | JOST25010131 | CT10-019-P04-08 | ST-3 | TP03 | 1 | 1400 | 240 | 5.8333 | 0.72917 | 1 | 2 | 8 | [5 empty] | 1400
2025-10-17 | JOST25010131 | CT10-019-P05-08 | ST-3 | PP17-110T | 1 | 1400 | 240 | 5.8333 | 0.72917 | 1 | 2 | 8 | [5 empty] | 1400
2025-10-18 | JOST25010131 | CT10-019-P06-08 | ST-3 | PP16-110T | 1 | 1400 | 240 | 5.8333 | 0.72917 | 1 | 2 | 8 | [5 empty] | 1400
2025-10-19 | JOST25010131 | CT10-019-P07-08 | ST-3 | PP27-110T | 1 | 1400 | 240 | 5.8333 | 0.72917 | 1 | 2 | 8 | [5 empty] | 1400
2025-10-20 | JOST25010129 | CT10-016-P01-06 | SM | SM01 | 1 | 968 | 5280 | 0.18333 | 0.022917 | 1 | 2 | 8 | [5 empty] | 968
2025-10-21 | JOST25010129 | CT10-016-P02-06 | ST-3 | PP17-110T | 1 | 968 | 360 | 2.6889 | 0.33611 | 1 | 2 | 8 | [5 empty] | 968
2025-10-22 | JOST25010129 | CT10-016-P03-06 | ST-3 | PP16-110T | 1 | 968 | 240 | 4.0333 | 0.50417 | 1 | 2 | 8 | [5 empty] | 968
2025-10-23 | JOST25010129 | CT10-016-P04-06 | ST-3 | PP27-110T | 1 | 968 | 240 | 4.0333 | 0.50417 | 1 | 2 | 8 | [5 empty] | 968
2025-10-24 | JOST25010129 | CT10-016-P05-06 | ST-3 | TP03 | 1 | 968 | 300 | 3.2267 | 0.40333 | 1 | 2 | 8 | [5 empty] | 968
2025-10-25 | JOST25010128 | CT10-014-P01-06 | ST-3 | PP09-160T | 1 | 2128 | 330 | 6.4485 | 0.80606 | 1 | 2 | 8 |  |  |  |  | 1381 | 747
2025-10-26 | JOST25010128 | CT10-014-P02-06 | ST-3 | PP18 | 1 | 2128 | 330 | 6.4485 | 0.80606 | 1 | 2 | 8 |  |  |  |  | 1381 | 747
2025-10-27 | JOST25010128 | CT10-014-P03-06 | ST-3 | PP17-110T | 1 | 2128 | 330 | 6.4485 | 0.80606 | 1 | 2 | 8 |  |  |  |  | 1381 | 747
2025-10-28 | JOST25010128 | CT10-014-P04-06 | ST-3 | PP16-110T | 1 | 2128 | 330 | 6.4485 | 0.80606 | 1 | 2 | 8 |  |  |  |  | 1381 | 747
2025-10-29 | JOST25010128 | CT10-014-P05-06 | ST-3 | PP27-110T | 2 | 2128 | 330 | 6.4485 | 0.80606 | 1 | 2 | 8 |  |  |  |  | 1381 | 747
2025-10-30 | JOTP25010127 | CT10-009-P01-05 | ST-3 | SW01 | 1 | 300 | 60 | 5 | 0.625 | 1 | 2 | 8 | [5 empty] | 300
2025-10-31 | JOTP25010127 | CT10-009-P02-05 | ST-3 | SW01 | 1 | 300 | 40 | 7.5 | 0.9375 | 1 | 2 | 8 | [5 empty] | 300
2025-11-01 | JOTP25010127 | CT10-009-P03-05 | TR | PAINTING | 1 | 300 | 40 | 7.5 | 0.9375 | 1 | 2 | 8 | [5 empty] | 300
2025-11-02 | JOTP25010127 | CT10-009-P04-05 | ST-1 | PAINTING | 1 | 300 | 40 | 7.5 | 0.9375 | 1 | 2 | 8 | [5 empty] | 300
2025-11-03 | JOTP25010121 | CP08-594-P02-03 | ST | PP05 | 1 | 630 | 360 | 1.75 | 0.21875 | 1 | 2 | 8 | [5 empty] | 630
2025-11-04 | JOTP25010119 | CP08-584-P01-04 | PB | SW09 | 1 | 225 | 60 | 3.75 | 0.46875 | 1 | 2 | 8 | [5 empty] | 225
2025-11-05 | JOTP25010119 | CP08-584-P02-04 | PB | OPT | 1 | 225 | 30 | 7.5 | 0.9375 | 1 | 2 | 8 | [5 empty] | 225
2025-11-06 | JOTP25010119 | CP08-584-P03-04 | PB | OPT | 1 | 225 | 60 | 3.75 | 0.46875 | 1 | 2 | 8 | [5 empty] | 225
2025-11-07 | OST25010123 | CP08-601-P01-03 | ST | PP29 | 1 | 140 | 120 | 1.1667 | 0.14583 | 1 | 2 | 8 | [5 empty] | 140
2025-11-08 | OST25010123 | CP08-601-P02-03 | ST | PP33 | 1 | 140 | 120 | 1.1667 | 0.14583 | 1 | 2 | 8 | [5 empty] | 140
2025-11-09 | OST25010123 | CP08-601-P03-03 | ST | PP29 | 1 | 140 | 120 | 1.1667 | 0.14583 | 1 | 2 | 8 | [5 empty] | 140
2025-11-10 | JOST25010124 | CT10-003-P01-06 | ST-3 | PP18 | 1 | 600 | 240 | 2.5 | 0.3125 | 1 | 2 | 8 | [5 empty] | 600
2025-11-11 | JOST25010124 | CT10-003-P02-06 | ST-3 | PP17-110T | 1 | 600 | 240 | 2.5 | 0.3125 | 1 | 2 | 8 | [5 empty] | 600
2025-11-12 | JOST25010124 | CT10-003-P03-06 | ST-3 | PP16-110T | 1 | 600 | 240 | 2.5 | 0.3125 | 1 | 2 | 8 | [5 empty] | 600
2025-11-13 | JOST25010124 | CT10-003-P04-06 | ST-3 | PP27-110T | 1 | 600 | 240 | 2.5 | 0.3125 | 1 | 2 | 8 | [5 empty] | 600
2025-11-14 | JOST25010124 | CT10-003-P05-06 | ST-3 | SW01 | 1 | 600 | 240 | 2.5 | 0.3125 | 1 | 2 | 8 | [5 empty] | 600
2025-11-15 | JOTP25010126 | CT10-009-P01-05 | ST-3 | SW01 | 1 | 200 | 60 | 3.3333 | 0.41667 | 1 | 2 | 8 | [5 empty] | 200
2025-11-16 | JOTP25010126 | CT10-009-P02-05 | ST-3 | SW01 | 1 | 200 | 40 | 5 | 0.625 | 1 | 2 | 8 | [5 empty] | 200
2025-11-17 | JOTP25010126 | CT10-009-P03-05 | TR | PAINTING | 1 | 200 | 40 | 5 | 0.625 | 1 | 2 | 8 | [5 empty] | 200
2025-11-18 | JOTP25010126 | CT10-009-P04-05 | ST-1 | PAINTING | 1 | 200 | 40 | 5 | 0.625 | 1 | 2 | 8 | [5 empty] | 200
2025-11-19 | JOTP25010102 | CP08-565-P01-04 | TR | TM05 | 1 | 500 | 80 | 6.25 | 0.78125 | 1 | 2 | 8 | [5 empty] | 500
2025-11-20 | JOTP25010102 | CP08-565-P02-04 | PB | PB03 | 1 | 500 | 120 | 4.1667 | 0.52083 | 1 | 2 | 8 | [5 empty] | 500
2025-11-21 | JOTP25010102 | CP08-565-P03-04 | PB | PB01 | 1 | 500 | 90 | 5.5556 | 0.69444 | 1 | 2 | 8 | [5 empty] | 500
2025-11-22 | JOST25010101 | CP08-561-P01-04 | ST | PP25-160T | 1 | 650 | 360 | 1.8056 | 0.22569 | 1 | 2 | 8 | [5 empty] | 650
2025-11-23 | JOST25010101 | CP08-561-P02-04 | ST | PP26 | 1 | 650 | 300 | 2.1667 | 0.27083 | 1 | 2 | 8 | [5 empty] | 650
2025-11-24 | JOST25010101 | CP08-561-P03-04 | ST | PP20-110T | 1 | 650 | 300 | 2.1667 | 0.27083 | 1 | 2 | 8 | [5 empty] | 650
2025-11-25 | JOST25010100 | CP08-560-P01-04 | ST | PP09 | 1 | 405 | 360 | 1.125 | 0.14062 | 1 | 2 | 8 | [5 empty] | 405
2025-11-26 | JOST25010100 | CP08-560-P02-04 | ST | PP18 | 1 | 405 | 300 | 1.35 | 0.16875 | 1 | 2 | 8 | [5 empty] | 405
2025-11-27 | JOST25010100 | CP08-560-P03-04 | ST | PP27-110T | 1 | 405 | 300 | 1.35 | 0.16875 | 1 | 2 | 8 | [5 empty] | 405
2025-11-28 | JOST25010099 | CP08-559-P01-02 | ST | PP32 | 1 | 65052 | 1680 | 38.7214 | 4.8402 | 1 | 2 | 8 | [5 empty] | 65052
2025-11-29 | JOST25010098 | CP08-559-P01-02 | ST | PP32 | 1 | 52950 | 1680 | 31.5179 | 3.9397 | 1 | 2 | 8 | [5 empty] | 52950
2025-11-30 | JOST25010097 | CP08-558-P01-02 | ST | PP30-200T | 1 | 59259 | 1500 | 39.506 | 4.9383 | 1 | 2 | 8 | [5 empty] | 59259
2025-12-01 | JOST25010096 | CP08-555-P01-04 | TR | PP17-110T | 1 | 3200 | 240 | 13.3333 | 1.6667 | 1 | 2 | 8 | [5 empty] | 3200
2025-12-02 | JOST25010096 | CP08-555-P02-04 | ST | PP16-110T | 1 | 3200 | 240 | 13.3333 | 1.6667 | 1 | 2 | 8 | [5 empty] | 3200
2025-12-03 | JOST25010096 | CP08-555-P03-04 | ST | PP27-110T | 1 | 3200 | 240 | 13.3333 | 1.6667 | 1 | 2 | 8 | [5 empty] | 3200
2025-12-04 | JOST25010094 | CP08-539-P01-11 | ST-3 | PP09-160T | 1 | 1840 | 120 | 15.3333 | 1.9167 | 1 | 2 | 8 | [5 empty] | 1840
2025-12-05 | JOST25010094 | CP08-539-P02-11 | ST-3 | PP18-150T | 1 | 1840 | 120 | 15.3333 | 1.9167 | 1 | 2 | 8 | [5 empty] | 1840
2025-12-06 | JOST25010094 | CP08-539-P03-11 | ST-3 | PP17-110T | 1 | 1840 | 120 | 15.3333 | 1.9167 | 1 | 2 | 8 | [5 empty] | 1840
2025-12-07 | JOST25010094 | CP08-539-P04-11 | ST-3 | TP03 | 1 | 1840 | 120 | 15.3333 | 1.9167 | 1 | 2 | 8 | [5 empty] | 1840
2025-12-08 | JOST25010094 | CP08-539-P05-11 | ST-3 | PP16-110T | 1 | 1840 | 120 | 15.3333 | 1.9167 | 1 | 2 | 8 | [5 empty] | 1840
2025-12-09 | JOST25010094 | CP08-539-P06-11 | ST-3 | TP03 | 1 | 1840 | 120 | 15.3333 | 1.9167 | 1 | 2 | 8 | [5 empty] | 1840
2025-12-10 | JOST25010094 | CP08-539-P07-11 | ST-3 | PP17-110T | 1 | 1840 | 120 | 15.3333 | 1.9167 | 1 | 2 | 8 | [5 empty] | 1840
2025-12-11 | JOST25010094 | CP08-539-P08-11 | ST-3 | PP16-110T | 1 | 1840 | 120 | 15.3333 | 1.9167 | 1 | 2 | 8 | [5 empty] | 1840
2025-12-12 | JOST25010094 | CP08-539-P09-11 | ST-3 | PP27-110T | 1 | 1840 | 120 | 15.3333 | 1.9167 | 1 | 2 | 8 | [5 empty] | 1840
2025-12-13 | JOST25010094 | CP08-539-P10-11 | ST-3 | SW01 | 1 | 1840 | 120 | 15.3333 | 1.9167 | 1 | 2 | 8 | [5 empty] | 1840
2025-12-14 | JOST25010147 | CO02-017-P01-04 | SM | SM01 | 1 | 3150 | 2400 | 1.3125 | 0.16406 | 1 | 2 | 8 | [5 empty] | 3150
2025-12-15 | JOST25010147 | CO02-017-P02-04 | ST-1 | PP04-060T | 1 | 3150 | 360 | 8.75 | 1.0938 | 1 | 2 | 8 | [5 empty] | 3150
2025-12-16 | JOST25010147 | CO02-017-P03-04 | ST-1 | PP03-060T | 1 | 3150 | 240 | 13.125 | 1.6406 | 1 | 2 | 8 | [5 empty] | 3150
2025-12-17 | JOTP25010162 | CT10-006-P02-08 | ST-2 | PP14-080T | 1 | 200 | 240 | 0.83333 | 0.10417 | 1 | 2 | 8 | [5 empty] | 200
2025-12-18 | JOTP25010162 | CT10-006-P03-08 | ST-2 | PP14-080T | 1 | 200 | 240 | 0.83333 | 0.10417 | 1 | 2 | 8 | [5 empty] | 200
2025-12-19 | JOTP25010162 | CT10-006-P04-08 | ST-3 | PP22-060T | 1 | 200 | 240 | 0.83333 | 0.10417 | 1 | 2 | 8 | [5 empty] | 200
2025-12-20 | JOTP25010162 | CT10-006-P05-08 | TP | TP03 | 1 | 200 | 100 | 2 | 0.25 | 1 | 2 | 8 | [5 empty] | 200
2025-12-21 | JOTP25010162 | CT10-006-P06-08 | TR | PB04 | 1 | 200 | 80 | 2.5 | 0.3125 | 1 | 2 | 8 | [5 empty] | 200
2025-12-22 | JOTP25010162 | CT10-006-P07-08 | TR | PB03 | 1 | 200 | 240 | 0.83333 | 0.10417 | 1 | 2 | 8 | [5 empty] | 200
2025-12-23 | JOST24120403 | CP08-599-P01-04 | TP | SM01 | 1 | 104 | 240 | 0.43333 | 0.054167 | 1 | 2 | 8 | [5 empty] | 104
2025-12-24 | JOST24120403 | CP08-599-P02-04 | TP | SM01 | 1 | 104 | 360 | 0.28889 | 0.036111 | 1 | 2 | 8 | [5 empty] | 104
2025-12-25 | JOST24120403 | CP08-599-P03-04 | ST | PP24 | 1 | 104 | 180 | 0.57778 | 0.072222 | 1 | 2 | 8 | [5 empty] | 104
2025-12-26 | JOAW25010001 | CD11-027-P01-06 | WN | SW08 | 1 | 5000 | 120 | 41.6667 | 5.2083 | 1 | 2 | 8 | [5 empty] | 5000
2025-12-27 | JOAW25010001 | CD11-027-P02-06 | WN | PP23-060T | 1 | 5000 | 300 | 16.6667 | 2.0833 | 1 | 2 | 8 | [5 empty] | 5000
2025-12-28 | JOAW25010001 | CD11-027-P05-06 | WN | TW01 | 1 | 5000 | 400 | 12.5 | 1.5625 | 1 | 2 | 8 | [5 empty] | 5000
2025-12-29 | JOAW24100349 | CA16-011-P01-03 | FM | SW05 | 1 | 60000 | 450 | 133.3333 | 16.6667 | 1 | 2 | 8 | [5 empty] | 60000
2025-12-30 | JOAW24100349 | CA16-011-P02-03 | FM | OPT | 1 | 60000 | 900 | 66.6667 | 8.3333 | 1 | 2 | 8 | [5 empty] | 60000
2025-12-31 | JOST24120254 | CO02-001-P04-05 | ST-3 | PP10-080T | 1 | 10240 | 300 | 34.1333 | 4.2667 | 1 | 2 | 8 | [5 empty] | 10240
2026-01-01 | JOST24120255 | CO02-002-P02-04 | ST-1 | PP03-060T | 1 | 4167 | 720 | 5.7875 | 0.72344 | 1 | 2 | 8 |  |  |  |  | 1932 | 2235
2026-01-02 | JOST24120255 | CO02-002-P03-04 | ST-2 | PP01-110T | 1 | 4167 | 360 | 11.575 | 1.4469 | 1 | 2 | 8 | [5 empty] | 4167
2026-01-03 | JOST24120256 | CO02-003-P01-04 | SM | SM01 | 1 | 4332 | 4560 | 0.95 | 0.11875 | 1 | 2 | 8 | [5 empty] | 4332
2026-01-04 | JOST24120256 | CO02-003-P02-04 | ST-1 | PP03-060T | 1 | 4332 | 720 | 6.0167 | 0.75208 | 1 | 2 | 8 | [5 empty] | 4332
2026-01-05 | JOST24120256 | CO02-003-P03-04 | ST-4 | PP26-110T | 1 | 4332 | 450 | 9.6267 | 1.2033 | 1 | 2 | 8 | [5 empty] | 4332
2026-01-06 | JOST24120389 | CP08-567-P01-06 | ST | PP33 | 1 | 450 | 180 | 2.5 | 0.3125 | 1 | 2 | 8 | [5 empty] | 450
2026-01-07 | JOST24120389 | CP08-567-P02-06 | ST | PP29 | 1 | 450 | 180 | 2.5 | 0.3125 | 1 | 2 | 8 | [5 empty] | 450
2026-01-08 | JOST24120389 | CP08-567-P03-06 | ST | PP29 | 1 | 450 | 180 | 2.5 | 0.3125 | 1 | 2 | 8 | [5 empty] | 450
2026-01-09 | JOST24120389 | CP08-567-P04-06 | ST | PP30 | 1 | 450 | 180 | 2.5 | 0.3125 | 1 | 2 | 8 | [5 empty] | 450
2026-01-10 | JOST24120389 | CP08-567-P05-06 | ST | PP33 | 1 | 450 | 180 | 2.5 | 0.3125 | 1 | 2 | 8 | [5 empty] | 450
2026-01-11 | JOST24120388 | CP08-558-P01-02 | ST | PP30-200T | 1 | 60000 | 1500 | 40 | 5 | 1 | 2 | 8 | [5 empty] | 60000
2026-01-12 | JOST24120402 | CP08-598-P01-03 | ST | SM01 | 1 | 96 | 240 | 0.4 | 0.05 | 1 | 2 | 8 | [5 empty] | 96
2026-01-13 | JOST24120402 | CP08-598-P02-03 | ST | PP21 | 1 | 96 | 180 | 0.53333 | 0.066667 | 1 | 2 | 8 | [5 empty] | 96
2026-01-14 | JOST24120358 | CP08-504-P01-02 | ST-4 | PP29-250T | 1 | 216 | 120 | 1.8 | 0.225 | 1 | 2 | 8 | [5 empty] | 216
2026-01-15 | JOTP24120349 | CP08-428A-P01-03 | TR | TM03 | 1 | 450 | 47 | 9.5745 | 1.1968 | 1 | 2 | 8 | [5 empty] | 450
2026-01-16 | JOTP24120349 | CP08-428A-P02-03 | TR | PB07 | 1 | 450 | 96 | 4.6875 | 0.58594 | 1 | 2 | 8 | [5 empty] | 450
2026-01-17 | JOTP24120346 | CP08-427-P02-03 | TR | PB05 | 1 | 600 | 30 | 20 | 2.5 | 1 | 2 | 8 | [5 empty] | 600
2026-01-18 | JOST24120342 | CP08-369/CP08-370-P01-05 | SM | SM01 | 1 | 1680 | 360 | 4.6667 | 0.58333 | 1 | 2 | 8 | [5 empty] | 1680
2026-01-19 | JOST24120342 | CP08-369/CP08-370-P02-05 | ST-3 | PP25-160T | 1 | 1680 | 300 | 5.6 | 0.7 | 1 | 2 | 8 | [5 empty] | 1680
2026-01-20 | JOST24120342 | CP08-369/CP08-370-P03-05 | ST-4 | PP20-110T | 1 | 1680 | 300 | 5.6 | 0.7 | 1 | 2 | 8 | [5 empty] | 1680
2026-01-21 | JOST24120342 | CP08-369/CP08-370-P04-05 | ST-3 | PP28-110T | 1 | 1680 | 300 | 5.6 | 0.7 | 1 | 2 | 8 | [5 empty] | 1680
2026-01-22 | JOTP24120353 | CP08-440-P01-03 | TR | TM03 | 1 | 880 | 96 | 9.1667 | 1.1458 | 1 | 2 | 8 | [5 empty] | 880
2026-01-23 | JOTP24120353 | CP08-440-P02-03 | TR | PB01 | 1 | 880 | 180 | 4.8889 | 0.61111 | 1 | 2 | 8 | [5 empty] | 880
2026-01-24 | JOST24120363 | CP08-510-P01-05 | ST-4 | PP29-250T | 1 | 1500 | 150 | 10 | 1.25 | 1 | 2 | 8 | [5 empty] | 1500
2026-01-25 | JOST24120363 | CP08-510-P02-05 | ST-4 | PP30 | 1 | 1500 | 120 | 12.5 | 1.5625 | 1 | 2 | 8 | [5 empty] | 1500
2026-01-26 | JOST24120363 | CP08-510-P03-05 | ST-4 | PP29-250T | 1 | 1500 | 120 | 12.5 | 1.5625 | 1 | 2 | 8 | [5 empty] | 1500
2026-01-27 | JOST24120363 | CP08-510-P04-05 | ST-4 | PP30 | 1 | 1500 | 120 | 12.5 | 1.5625 | 1 | 2 | 8 | [5 empty] | 1500
2026-01-28 | JOST24120377 | CP08-554C-P01-04 | ST | PP29 | 1 | 405 | 360 | 1.125 | 0.14062 | 1 | 2 | 8 | [5 empty] | 405
2026-01-29 | JOST24120377 | CP08-554C-P02-04 | ST | PP30-200T | 1 | 405 | 360 | 1.125 | 0.14062 | 1 | 2 | 8 | [5 empty] | 405
2026-01-30 | JOST24120377 | CP08-554C-P03-04 | ST | PP21 | 1 | 405 | 240 | 1.6875 | 0.21094 | 1 | 2 | 8 | [5 empty] | 405
2026-01-31 | JOST24120340 | CP08-368-P01-02 | ST-3 | PP29 | 1 | 200 | 68 | 2.9412 | 0.36765 | 1 | 2 | 8 | [5 empty] | 200
2026-02-01 | JOST24120335 | CP08-350-P01-04 | ST-4 | PP25-160T | 1 | 4400 | 300 | 14.6667 | 1.8333 | 1 | 2 | 8 | [5 empty] | 4400
2026-02-02 | JOST24120335 | CP08-350-P02-04 | ST-3 | PP20-110T | 1 | 4400 | 300 | 14.6667 | 1.8333 | 1 | 2 | 8 | [5 empty] | 4400
2026-02-03 | JOST24120335 | CP08-350-P03-04 | ST-4 | PP28-110T | 1 | 4400 | 300 | 14.6667 | 1.8333 | 1 | 2 | 8 | [5 empty] | 4400
2026-02-04 | JOST24120325 | CP08-256-P01-02 | ST-1 | PP29 | 2 | 4186 | 240 | 17.4417 | 2.1802 | 1 | 2 | 8 | [5 empty] | 4186
2026-02-05 | JOAW24120316 | CP08-231A-P01-03 | WN | WS01 | 1 | 2000 | 900 | 2.2222 | 0.27778 | 1 | 2 | 8 | [5 empty] | 2000
2026-02-06 | JOAW24120316 | CP08-231A-P02-03 | WN | JIG-HAND BEND | 1 | 2000 | 120 | 16.6667 | 2.0833 | 1 | 2 | 8 | [5 empty] | 2000
2026-02-07 | JOAW24120317 | CP08-231B-P01-06 | WN | WS01 | 1 | 4000 | 720 | 5.5556 | 0.69444 | 1 | 2 | 8 | [5 empty] | 4000
2026-02-08 | JOAW24120317 | CP08-231B-P02-06 | WN | PP23-060T | 1 | 4000 | 330 | 12.1212 | 1.5152 | 1 | 2 | 8 | [5 empty] | 4000
2026-02-09 | JOAW24120317 | CP08-231B-P03-06 | WN | JIG-HAND BEND | 1 | 4000 | 240 | 16.6667 | 2.0833 | 1 | 2 | 8 | [5 empty] | 4000
2026-02-10 | JOAW24120317 | CP08-231B-P04-06 | WN | PP23-060T | 1 | 4000 | 420 | 9.5238 | 1.1905 | 1 | 2 | 8 | [5 empty] | 4000
2026-02-11 | JOAW24120317 | CP08-231B-P05-06 | WN | PP23 | 1 | 4000 | 240 | 16.6667 | 2.0833 | 1 | 2 | 8 | [5 empty] | 4000
2026-02-12 | JOAW24120318 | CP08-231C-P01-03 | WN | WS01 | 1 | 2000 | 900 | 2.2222 | 0.27778 | 1 | 2 | 8 | [5 empty] | 2000
2026-02-13 | JOAW24120318 | CP08-231C-P02-03 | WN | JIG-HAND BEND | 1 | 2000 | 420 | 4.7619 | 0.59524 | 1 | 2 | 8 | [5 empty] | 2000
2026-02-14 | JOAW24120319 | CP08-231D-P01-02 | WN | WS01 | 1 | 9000 | 960 | 9.375 | 1.1719 | 1 | 2 | 8 | [5 empty] | 9000
2026-02-15 | JOAW24120320 | CP08-231E-P01-02 | WN | WS01 | 1 | 8000 | 720 | 11.1111 | 1.3889 | 1 | 2 | 8 | [5 empty] | 8000
2026-02-16 | JOAW24120321 | CP08-231F-P01-02 | WN | WS01 | 1 | 8000 | 900 | 8.8889 | 1.1111 | 1 | 2 | 8 | [5 empty] | 8000
2026-02-17 | JOAW24120322 | CP08-231G-P01-02 | WN | WS01 | 1 | 7000 | 840 | 8.3333 | 1.0417 | 1 | 2 | 8 | [5 empty] | 7000
2026-02-18 | JOST24120306 | CP08-152-P01-05 | SM | SM01 | 1 | 1755 | 3120 | 0.5625 | 0.070312 | 1 | 2 | 8 | [5 empty] | 1755
2026-02-19 | JOST24120306 | CP08-152-P02-05 | ST-3 | PP28-110T | 1 | 1755 | 360 | 4.875 | 0.60938 | 1 | 2 | 8 | [5 empty] | 1755
2026-02-20 | JOST24120306 | CP08-152-P03-05 | ST-4 | PP20-110T | 1 | 1755 | 360 | 4.875 | 0.60938 | 1 | 2 | 8 | [5 empty] | 1755
2026-02-21 | JOST24120306 | CP08-152-P04-05 | ST-4 | PP26-110T | 1 | 1755 | 360 | 4.875 | 0.60938 | 1 | 2 | 8 | [5 empty] | 1755
2026-02-22 | JOST24120304 | CP08-080-P01-02 | ST-2 | PP01-110T | 1 | 1650 | 3000 | 0.55 | 0.06875 | 1 | 2 | 8 | [5 empty] | 1650
2026-02-23 | JOST24120303 | CP08-079-P01-02 | ST-3 | PP01-110T | 1 | 2601 | 3000 | 0.867 | 0.10837 | 1 | 2 | 8 | [5 empty] | 2601
2026-02-24 | JOST24120323 | CP08-254-P01-05 | ST-3 | PP25-160T | 1 | 2100 | 300 | 7 | 0.875 | 1 | 2 | 8 | [5 empty] | 2100
2026-02-25 | JOST24120323 | CP08-254-P02-05 | ST-3 | PP26-110T | 1 | 2100 | 300 | 7 | 0.875 | 1 | 2 | 8 | [5 empty] | 2100
2026-02-26 | JOST24120323 | CP08-254-P03-05 | ST-3 | PP20-110T | 1 | 2100 | 300 | 7 | 0.875 | 1 | 2 | 8 | [5 empty] | 2100
2026-02-27 | JOST24120323 | CP08-254-P04-05 | ST-3 | PP28-110T | 2 | 2100 | 300 | 7 | 0.875 | 1 | 2 | 8 | [5 empty] | 2100
2026-02-28 | JOST24120327 | CP08-293-P01-06 | ST-3 | PP25-160T | 1 | 2100 | 360 | 5.8333 | 0.72917 | 1 | 2 | 8 | [5 empty] | 2100
2026-03-01 | JOST24120327 | CP08-293-P02-06 | ST-3 | PP26-110T | 1 | 4000 | 360 | 11.1111 | 1.3889 | 1 | 2 | 8 | [5 empty] | 4000
2026-03-02 | JOST24120327 | CP08-293-P03-06 | ST-3 | PP20-110T | 1 | 4000 | 360 | 11.1111 | 1.3889 | 1 | 2 | 8 | [5 empty] | 4000
2026-03-03 | JOST24120327 | CP08-293-P04-06 | ST-3 | PP28-110T | 1 | 4000 | 360 | 11.1111 | 1.3889 | 1 | 2 | 8 | [5 empty] | 4000
2026-03-04 | JOST24120327 | CP08-293-P05-06 | ST-3 | PP24-160T | 2 | 4000 | 360 | 11.1111 | 1.3889 | 1 | 2 | 8 | [5 empty] | 4000
2026-03-05 | JOTP24120330 | CP08-339-P01-04 | TR | SM01 | 1 | 308 | 240 | 1.2833 | 0.16042 | 1 | 2 | 8 | [5 empty] | 308
2026-03-06 | JOTP24120330 | CP08-339-P02-04 | TR | TM03 | 1 | 308 | 100 | 3.08 | 0.385 | 1 | 2 | 8 | [5 empty] | 308
2026-03-07 | JOTP24120330 | CP08-339-P03-04 | TR | PB01 | 1 | 308 | 51 | 6.0392 | 0.7549 | 1 | 2 | 8 | [5 empty] | 308
2026-03-08 | JOST24120308 | CP08-154-P01-04 | SM | SM01 | 1 | 1750 | 12600 | 0.13889 | 0.017361 | 1 | 2 | 8 | [5 empty] | 1750
2026-03-09 | JOST24120308 | CP08-154-P02-04 | ST-4 | PP16-110T | 1 | 1750 | 360 | 4.8611 | 0.60764 | 1 | 2 | 8 | [5 empty] | 1750
2026-03-10 | JOST24120308 | CP08-154-P03-04 | ST-4 | PP17-110T | 1 | 1750 | 180 | 9.7222 | 1.2153 | 1 | 2 | 8 | [5 empty] | 1750
2026-03-11 | JOTP24120350 | CP08-428B-P01-03 | TR | TM06 | 1 | 342 | 65 | 5.2615 | 0.65769 | 1 | 2 | 8 | [5 empty] | 342
2026-03-12 | JOTP24120350 | CP08-428B-P02-03 | TR | PB04 | 1 | 342 | 72 | 4.75 | 0.59375 | 1 | 2 | 8 | [5 empty] | 342
2026-03-13 | JOTP24120351 | CP08-428C-P01-03 | TR | TM06 | 1 | 344 | 60 | 5.7333 | 0.71667 | 1 | 2 | 8 | [5 empty] | 344
2026-03-14 | JOTP24120351 | CP08-428C-P02-03 | TR | PB04 | 1 | 344 | 95 | 3.6211 | 0.45263 | 1 | 2 | 8 | [5 empty] | 344
2026-03-15 | JOTP24120352 | CP08-428D-P01-03 | TR | TM06 | 1 | 336 | 55 | 6.1091 | 0.76364 | 1 | 2 | 8 | [5 empty] | 336
2026-03-16 | JOTP24120352 | CP08-428D-P02-03 | TR | PB07 | 1 | 336 | 70 | 4.8 | 0.6 | 1 | 2 | 8 | [5 empty] | 336
2026-03-17 | JOTP24120375 | CP08-554-P01-06 | TR | SW14 | 1 | 400 | 93 | 4.3011 | 0.53763 | 1 | 2 | 8 | [5 empty] | 400
2026-03-18 | JOTP24120375 | CP08-554-P02-06 | TR | SW14 | 1 | 400 | 129 | 3.1008 | 0.3876 | 1 | 2 | 8 | [5 empty] | 400
2026-03-19 | JOTP24120375 | CP08-554-P03-06 | TR | SW14 | 1 | 400 | 12 | 33.3333 | 4.1667 | 1 | 2 | 8 | [5 empty] | 400
2026-03-20 | JOTP24120375 | CP08-554-P04-06 | TR | PAINTING | 1 | 400 | 12 | 33.3333 | 4.1667 | 1 | 2 | 8 | [5 empty] | 400
2026-03-21 | JOTP24120375 | CP08-554-P05-06 | TR | PACK & LABEL | 1 | 400 | 12 | 33.3333 | 4.1667 | 1 | 2 | 8 | [5 empty] | 400
2026-03-22 | JOST24120347 | CP08-428-P01-09 | ST-3 | SW01 | 1 | 115 | 90 | 1.2778 | 0.15972 | 1 | 2 | 8 | [5 empty] | 115
2026-03-23 | JOST24120347 | CP08-428-P02-09 | ST-3 | SW01 | 1 | 115 | 120 | 0.95833 | 0.11979 | 1 | 2 | 8 | [5 empty] | 115
2026-03-24 | JOST24120347 | CP08-428-P03-09 | ST-3 | SW01 | 1 | 115 | 120 | 0.95833 | 0.11979 | 1 | 2 | 8 | [5 empty] | 115
2026-03-25 | JOST24120347 | CP08-428-P04-09 | ST-3 | SW01 | 1 | 115 | 90 | 1.2778 | 0.15972 | 1 | 2 | 8 | [5 empty] | 115
2026-03-26 | JOST24120347 | CP08-428-P05-09 | ST-3 | SW01 | 1 | 115 | 40 | 2.875 | 0.35938 | 1 | 2 | 8 | [5 empty] | 115
2026-03-27 | JOST24120347 | CP08-428-P06-09 | ST-3 | SW01 | 1 | 115 | 30 | 3.8333 | 0.47917 | 1 | 2 | 8 | [5 empty] | 115
2026-03-28 | JOST24120347 | CP08-428-P07-09 | ST-3 | PAINTING | 1 | 115 | 17 | 6.7647 | 0.84559 | 1 | 2 | 8 | [5 empty] | 115
2026-03-29 | JOST24120347 | CP08-428-P08-09 | ST-3 | CLEAN | 1 | 115 | 60 | 1.9167 | 0.23958 | 1 | 2 | 8 | [5 empty] | 115
2026-03-30 | JOAW24120378 | CP08-556-P03-09 | TR | PB07 | 1 | 200 | 60 | 3.3333 | 0.41667 | 1 | 2 | 8 | [5 empty] | 200
2026-03-31 | JOAW24120378 | CP08-556-P04-09 | WN | SW06 | 1 | 200 | 60 | 3.3333 | 0.41667 | 1 | 2 | 8 | [5 empty] | 200
2026-04-01 | JOAW24120378 | CP08-556-P05-09 | WN | OPT | 1 | 200 | 50 | 4 | 0.5 | 1 | 2 | 8 | [5 empty] | 200
2026-04-02 | JOAW24120378 | CP08-556-P06-09 | WN | OPT | 1 | 200 | 50 | 4 | 0.5 | 1 | 2 | 8 | [5 empty] | 200
2026-04-03 | JOAW24120378 | CP08-556-P08-09 | WN | CHECKING | 1 | 200 | 8 | 25 | 3.125 | 1 | 2 | 8 | [5 empty] | 200
2026-04-04 | JOAW24120314 | CP08-231-P01-06 | WN | SW03 | 1 | 500 | 15 | 33.3333 | 4.1667 | 1 | 2 | 8 | [5 empty] | 500
2026-04-05 | JOAW24120314 | CP08-231-P02-06 | WN | SW03 | 1 | 500 | 12 | 41.6667 | 5.2083 | 1 | 2 | 8 | [5 empty] | 500
2026-04-06 | JOAW24120314 | CP08-231-P03-06 | WN | SW04 | 1 | 500 | 12 | 41.6667 | 5.2083 | 1 | 2 | 8 | [5 empty] | 500
2026-04-07 | JOAW24120314 | CP08-231-P04-06 | WN | TW03 | 1 | 500 | 12 | 41.6667 | 5.2083 | 1 | 2 | 8 | [5 empty] | 500
2026-04-08 | JOST25010174 | CP08-291-P01-02 | ST-1 | PP29 | 2 | 6000 | 240 | 25 | 3.125 | 1 | 2 | 8 | [5 empty] | 6000
2026-04-09 | JOST25010171 | CP08-087-P02-04 | ST-3 | PP21-110T | 1 | 9574 | 300 | 31.9133 | 3.9892 | 1 | 2 | 8 | [5 empty] | 9574
2026-04-10 | JOST25010171 | CP08-087-P03-04 | ST-3 | TP09 | 1 | 9574 | 120 | 79.7833 | 9.9729 | 1 | 2 | 8 | [5 empty] | 9574
2026-04-11 | JOST25010164 | CP08-012-P01-03 | ST-1 | PP14-080T | 1 | 20000 | 1800 | 11.1111 | 1.3889 | 1 | 2 | 8 | [5 empty] | 20000
2026-04-12 | JOST25010189 | CP08-502-P01-02 | ST-4 | PP24-160T | 1 | 1000 | 180 | 5.5556 | 0.69444 | 1 | 2 | 8 | [5 empty] | 1000
2026-04-13 | JOTP25010188 | CP08-500-P04-07 | TR | PB07 | 1 | 960 | 60 | 16 | 2 | 1 | 2 | 8 | [5 empty] | 960
2026-04-14 | JOTP25010188 | CP08-500-P05-07 | TR | PB01 | 1 | 960 | 60 | 16 | 2 | 1 | 2 | 8 | [5 empty] | 960
2026-04-15 | JOTP25010188 | CP08-500-P06-07 | TR | PB03 | 1 | 960 | 60 | 16 | 2 | 1 | 2 | 8 | [5 empty] | 960
2026-04-16 | JOST25010186 | CP08-496-P01-03 | 0 | STICK LABEL | 1 | 600 | 15 | 40 | 5 | 1 | 2 | 8 | [5 empty] | 600
2026-04-17 | JOST25010186 | CP08-496-P02-03 | 0 | STICK LABEL | 1 | 600 | 15 | 40 | 5 | 1 | 2 | 8 | [5 empty] | 600
2026-04-18 | JOST25010185 | CP08-496-P01-03 | 0 | STICK LABEL | 1 | 800 | 15 | 53.3333 | 6.6667 | 1 | 2 | 8 | [5 empty] | 800
2026-04-19 | JOST25010185 | CP08-496-P02-03 | 0 | STICK LABEL | 1 | 800 | 15 | 53.3333 | 6.6667 | 1 | 2 | 8 | [5 empty] | 800
2026-04-20 | JOTP25010184 | CP08-488-P01-05 | TR | TM02 | 1 | 105 | 80 | 1.3125 | 0.16406 | 1 | 2 | 8 | [5 empty] | 105
2026-04-21 | JOTP25010184 | CP08-488-P02-05 | WN | DEBURR | 1 | 105 | 80 | 1.3125 | 0.16406 | 1 | 2 | 8 | [5 empty] | 105
2026-04-22 | JOTP25010184 | CP08-488-P03-05 | TR | PB04 | 1 | 105 | 120 | 0.875 | 0.10938 | 1 | 2 | 8 | [5 empty] | 105
2026-04-23 | JOTP25010184 | CP08-488-P04-05 | ST-1 | PAINTING | 1 | 105 | 20 | 5.25 | 0.65625 | 1 | 2 | 8 | [5 empty] | 105
2026-04-24 | JOST25010176 | CP08-349-P01-04 | ST-4 | PP25-160T | 1 | 3100 | 300 | 10.3333 | 1.2917 | 1 | 2 | 8 | [5 empty] | 3100
2026-04-25 | JOST25010176 | CP08-349-P02-04 | ST-3 | PP20-110T | 1 | 3100 | 300 | 10.3333 | 1.2917 | 1 | 2 | 8 | [5 empty] | 3100
2026-04-26 | JOST25010176 | CP08-349-P03-04 | ST-4 | PP28-110T | 1 | 3100 | 300 | 10.3333 | 1.2917 | 1 | 2 | 8 | [5 empty] | 3100
2026-04-27 | JOAW25010175 | CP08-299-P01-03 | FM | FM03 | 1 | 5932 | 1800 | 3.2956 | 0.41194 | 1 | 2 | 8 | [5 empty] | 5932
2026-04-28 | JOAW25010175 | CP08-299-P02-03 | FM | VM01 | 1 | 5932 | 1000 | 5.932 | 0.7415 | 1 | 2 | 8 | [5 empty] | 5932
2026-04-29 | JOTP25010190 | CP08-505-P01-05 | TR | TM03 | 1 | 1080 | 102 | 10.5882 | 1.3235 | 1 | 2 | 8 | [5 empty] | 1080
2026-04-30 | JOTP25010190 | CP08-505-P02-05 | ST-3 | PP17-110T | 1 | 1080 | 300 | 3.6 | 0.45 | 1 | 2 | 8 | [5 empty] | 1080
2026-05-01 | JOTP25010190 | CP08-505-P03-05 | ST-2 | PP16-110T | 1 | 1080 | 300 | 3.6 | 0.45 | 1 | 2 | 8 | [5 empty] | 1080
2026-05-02 | JOTP25010190 | CP08-505-P04-05 | ST-2 | PP27-110T | 1 | 1080 | 300 | 3.6 | 0.45 | 1 | 2 | 8 | [5 empty] | 1080
2026-05-03 | JOST25010191 | CP08-516-P01-11 | ST-3 | PP09-160T | 1 | 1300 | 120 | 10.8333 | 1.3542 | 1 | 2 | 8 | [5 empty] | 1300
2026-05-04 | JOST25010191 | CP08-516-P02-11 | ST-3 | PP18-150T | 1 | 1300 | 120 | 10.8333 | 1.3542 | 1 | 2 | 8 | [5 empty] | 1300
2026-05-05 | JOST25010191 | CP08-516-P03-11 | ST-3 | PP17-110T | 1 | 1300 | 120 | 10.8333 | 1.3542 | 1 | 2 | 8 | [5 empty] | 1300
2026-05-06 | JOST25010191 | CP08-516-P04-11 | ST-3 | TP03 | 1 | 1300 | 120 | 10.8333 | 1.3542 | 1 | 2 | 8 | [5 empty] | 1300
2026-05-07 | JOST25010191 | CP08-516-P05-11 | ST-3 | PP16-110T | 1 | 1300 | 120 | 10.8333 | 1.3542 | 1 | 2 | 8 | [5 empty] | 1300
2026-05-08 | JOST25010191 | CP08-516-P06-11 | ST-3 | TP03 | 1 | 1300 | 120 | 10.8333 | 1.3542 | 1 | 2 | 8 | [5 empty] | 1300
2026-05-09 | JOST25010191 | CP08-516-P07-11 | ST-3 | PP17-110T | 1 | 1300 | 120 | 10.8333 | 1.3542 | 1 | 2 | 8 | [5 empty] | 1300
2026-05-10 | JOST25010191 | CP08-516-P08-11 | ST-3 | PP16-110T | 1 | 1300 | 120 | 10.8333 | 1.3542 | 1 | 2 | 8 | [5 empty] | 1300
2026-05-11 | JOST25010191 | CP08-516-P09-11 | ST-3 | PP27-110T | 1 | 1300 | 120 | 10.8333 | 1.3542 | 1 | 2 | 8 | [5 empty] | 1300
2026-05-12 | JOST25010191 | CP08-516-P10-11 | ST-3 | SW01 | 1 | 1300 | 120 | 10.8333 | 1.3542 | 1 | 2 | 8 | [5 empty] | 1300
2026-05-13 | JOST25010193 | CP08-518-P01-02 | ST-3 | PP01-110T | 1 | 5500 | 3000 | 1.8333 | 0.22917 | 1 | 2 | 8 | [5 empty] | 5500
2026-05-14 | JOST25010192 | CP08-517-P01-03 | ST-1 | PP10-080T | 1 | 3307 | 300 | 11.0233 | 1.3779 | 1 | 2 | 8 | [5 empty] | 3307
2026-05-15 | JOST25010192 | CP08-517-P02-03 | ST-3 | PP03-060T | 1 | 3307 | 240 | 13.7792 | 1.7224 | 1 | 2 | 8 | [5 empty] | 3307
2026-05-16 | JOST25010194 | CP08-523-P01-03 | ST-2 | PP10-080T | 1 | 4166 | 1800 | 2.3144 | 0.28931 | 1 | 2 | 8 | [5 empty] | 4166
2026-05-17 | JOST25010194 | CP08-523-P02-03 | AL | TP04 | 1 | 4166 | 300 | 13.8867 | 1.7358 | 1 | 2 | 8 | [5 empty] | 4166
2026-05-18 | JOAW25010218 | CA21-001-P01-04 | FM | FM01 | 1 | 127182 | 2400 | 52.9925 | 6.6241 | 1 | 2 | 8 |  |  |  |  | 65000 | 62182
2026-05-19 | JOST25010217 | CP16-042-P02-03 | ST-2 | PP03-060T | 1 | 2688 | 240 | 11.2 | 1.4 | 1 | 2 | 8 |  |  |  |  | 2 | 2686
2026-05-20 | JOST25010216 | CP16-030-P03-04 | ST-1 | PP05-060T | 1 | 5832 | 240 | 24.3 | 3.0375 | 1 | 2 | 8 | [5 empty] | 5832
2026-05-21 | JOST25010216 | CP16-009-P01-02 | FM | FM03 | 1 | 30769 | 2400 | 12.8204 | 1.6026 | 1 | 2 | 8 | [5 empty] | 30769
2026-05-22 | JOST25010213 | CO02-021-P01-06 | SM | SM01 | 1 | 279 | 240 | 1.1625 | 0.14531 | 1 | 2 | 8 | [5 empty] | 279
2026-05-23 | JOST25010213 | CO02-021-P02-06 | ST-3 | PP27-110T | 1 | 279 | 240 | 1.1625 | 0.14531 | 1 | 2 | 8 | [5 empty] | 279
2026-05-24 | JOST25010213 | CO02-021-P03-06 | ST-3 | PP16-110T | 1 | 279 | 360 | 0.775 | 0.096875 | 1 | 2 | 8 | [5 empty] | 279
2026-05-25 | JOST25010213 | CO02-021-P04-06 | ST-3 | PP17-110T | 1 | 279 | 360 | 0.775 | 0.096875 | 1 | 2 | 8 | [5 empty] | 279
2026-05-26 | JOST25010213 | CO02-021-P05-06 | ST-3 | PP18-150T | 1 | 279 | 360 | 0.775 | 0.096875 | 1 | 2 | 8 | [5 empty] | 279
2026-05-27 | JOAW25010210 | CJ01-003-P01-04 | ST-2 | PP07-016T | 1 | 5100 | 360 | 14.1667 | 1.7708 | 1 | 2 | 8 | [5 empty] | 5100
2026-05-28 | JOAW25010210 | CJ01-003-P02-04 | AL | BL04 | 1 | 5100 | 150 | 34 | 4.25 | 1 | 2 | 8 | [5 empty] | 5100
2026-05-29 | JOTP25010202 | CP08-585-P01-04 | PB | SW09 | 1 | 216 | 40.2 | 5.3731 | 0.67164 | 1 | 2 | 8 | [5 empty] | 216
2026-05-30 | JOTP25010202 | CP08-585-P02-04 | PB | OPT | 1 | 216 | 40.2 | 5.3731 | 0.67164 | 1 | 2 | 8 | [5 empty] | 216
2026-05-31 | JOTP25010202 | CP08-585-P03-04 | PB | OPT | 1 | 216 | 50.4 | 4.2857 | 0.53571 | 1 | 2 | 8 | [5 empty] | 216
2026-06-01 | JOTP25010201 | CP08-583B-P01-04 | PB | PB07 | 1 | 152 | 90 | 1.6889 | 0.21111 | 1 | 2 | 8 | [5 empty] | 152
2026-06-02 | JOTP25010201 | CP08-583B-P02-04 | PB | PB02 | 1 | 152 | 60 | 2.5333 | 0.31667 | 1 | 2 | 8 | [5 empty] | 152
2026-06-03 | JOTP25010201 | CP08-583B-P03-04 | PB | PB02 | 1 | 152 | 120 | 1.2667 | 0.15833 | 1 | 2 | 8 | [5 empty] | 152
2026-06-04 | JOTP25010200 | CP08-583A-P01-05 | TP | TM03 | 1 | 152 | 45 | 3.3778 | 0.42222 | 1 | 2 | 8 | [5 empty] | 152
2026-06-05 | JOTP25010200 | CP08-583A-P02-05 | PB | PB02 | 1 | 152 | 180 | 0.84444 | 0.10556 | 1 | 2 | 8 | [5 empty] | 152
2026-06-06 | JOTP25010200 | CP08-583A-P03-05 | PB | PB07 | 1 | 152 | 50.4 | 3.0159 | 0.37698 | 1 | 2 | 8 | [5 empty] | 152
2026-06-07 | JOTP25010200 | CP08-583A-P04-05 | PB | PB07 | 1 | 152 | 90 | 1.6889 | 0.21111 | 1 | 2 | 8 | [5 empty] | 152
2026-06-08 | JOST25010197 | CP08-559-P01-02 | ST | PP32 | 1 | 49924 | 1680 | 29.7167 | 3.7146 | 1 | 2 | 8 | [5 empty] | 49924
2026-06-09 | JOAW24120242 | CD11-026A-P01-02 | FM | FM03 | 1 | 60000 | 1200 | 50 | 6.25 | 1 | 2 | 8 | [5 empty] | 60000
2026-06-10 | JOAW24120244 | CD11-026B-P01-02 | WN | WS01 | 1 | 80000 | 2160 | 37.037 | 4.6296 | 1 | 2 | 8 | [5 empty] | 80000
2026-06-11 | JOAW24120246 | CD11-026C-P01-02 | WN | WS01 | 1 | 20000 | 2400 | 8.3333 | 1.0417 | 1 | 2 | 8 | [5 empty] | 20000
2026-06-12 | JOAW24120239 | CD11-026-P01-06 | WN | SW13 | 1 | 25000 | 120 | 208.3333 | 26.0417 | 1 | 2 | 8 |  |  |  |  | 5410 | 19590
2026-06-13 | JOAW24120239 | CD11-026-P02-06 | WN | PP23-060T | 1 | 25000 | 540 | 46.2963 | 5.787 | 1 | 2 | 8 |  |  |  |  | 5 | 24995
2026-06-14 | JOAW24120239 | CD11-026-P05-06 | WN | TW01 | 1 | 25000 | 420 | 59.5238 | 7.4405 | 1 | 2 | 8 | [5 empty] | 25000
2026-06-15 | JOTP25010226 | CT10-026A-P01-02 | TP | SW09 | 1 | 200 | 8 | 25 | 3.125 | 1 | 2 | 8 |  |  |  |  | 108 | 92
2026-06-16 | JOTP25010222 | CT10-026-P01-04 | TP | SW09 | 1 | 100 | 12 | 8.3333 | 1.0417 | 1 | 2 | 8 | [5 empty] | 100
2026-06-17 | JOTP25010222 | CT10-026-P02-04 | TP | OPT | 1 | 100 | 6 | 16.6667 | 2.0833 | 1 | 2 | 8 | [5 empty] | 100
2026-06-18 | JOTP25010222 | CT10-026-P03-04 | TP | OPT | 1 | 100 | 30 | 3.3333 | 0.41667 | 1 | 2 | 8 | [5 empty] | 100
2026-06-19 | JOTP25010239 | CT10-026I-P01-02 | TP | PB01 | 1 | 600 | 90 | 6.6667 | 0.83333 | 1 | 2 | 8 | [5 empty] | 600
2026-06-20 | JOTP25010238 | CT10-026H-P01-03 | TP | TP02 | 1 | 432 | 120 | 3.6 | 0.45 | 1 | 2 | 8 | [5 empty] | 432
2026-06-21 | JOTP25010238 | CT10-026H-P02-03 | TP | PB07 | 1 | 432 | 40 | 10.8 | 1.35 | 1 | 2 | 8 | [5 empty] | 432
2026-06-22 | JOTP25010237 | CT10-026G-P01-03 | TP | PB01 | 1 | 486 | 180 | 2.7 | 0.3375 | 1 | 2 | 8 | [5 empty] | 486
2026-06-23 | JOTP25010237 | CT10-026G-P02-03 | TP | PB01 | 1 | 486 | 180 | 2.7 | 0.3375 | 1 | 2 | 8 | [5 empty] | 486
2026-06-24 | JOTP25010236 | CT10-026F-P01-03 | TP | PB02 | 1 | 280 | 90 | 3.1111 | 0.38889 | 1 | 2 | 8 | [5 empty] | 280
2026-06-25 | JOTP25010236 | CT10-026F-P02-03 | TP | PB01 | 1 | 280 | 180 | 1.5556 | 0.19444 | 1 | 2 | 8 | [5 empty] | 280
2026-06-26 | JOTP25010235 | CT10-026E-P01-02 | TP | PB01 | 1 | 460 | 18 | 25.5556 | 3.1944 | 1 | 2 | 8 | [5 empty] | 460
2026-06-27 | JOTP25010234 | CT10-026D-P01-03 | TP | TM03 | 1 | 210 | 48 | 4.375 | 0.54688 | 1 | 2 | 8 | [5 empty] | 210
2026-06-28 | JOTP25010234 | CT10-026D-P02-03 | TP | PB01 | 1 | 210 | 50 | 4.2 | 0.525 | 1 | 2 | 8 | [5 empty] | 210
2026-06-29 | JOTP25010233 | CT10-026C-P01-03 | TP | TM03 | 1 | 648 | 51 | 12.7059 | 1.5882 | 1 | 2 | 8 | [5 empty] | 648
2026-06-30 | JOTP25010233 | CT10-026C-P02-03 | TP | PB01 | 1 | 648 | 90 | 7.2 | 0.9 | 1 | 2 | 8 | [5 empty] | 648
2026-07-01 | JOTP25010232 | CT10-026B-P01-03 | TP | TM03 | 1 | 220 | 80 | 2.75 | 0.34375 | 1 | 2 | 8 | [5 empty] | 220
2026-07-02 | JOTP25010232 | CT10-026B-P02-03 | TP | PB01 | 1 | 220 | 90 | 2.4444 | 0.30556 | 1 | 2 | 8 | [5 empty] | 220
2026-07-03 | JOTP25010231 | CT10-026A-C-P01-14 | 0 | 0 | 1 | 220 | 0 |  |  | 1 | 2 | 8 | [5 empty] | 220
2026-07-04 | JOTP25010231 | CT10-026A-C-P02-14 | 0 | 0 | 1 | 220 | 0 |  |  | 1 | 2 | 8 | [5 empty] | 220
2026-07-05 | JOTP25010231 | CT10-026A-C-P03-14 | 0 | 0 | 1 | 220 | 0 |  |  | 1 | 2 | 8 | [5 empty] | 220
2026-07-06 | JOTP25010231 | CT10-026A-C-P04-14 | 0 | 0 | 1 | 220 | 0 |  |  | 1 | 2 | 8 | [5 empty] | 220
2026-07-07 | JOTP25010231 | CT10-026A-C-P05-14 | 0 | 0 | 1 | 220 | 0 |  |  | 1 | 2 | 8 | [5 empty] | 220
2026-07-08 | JOTP25010231 | CT10-026A-C-P06-14 | 0 | 0 | 1 | 220 | 0 |  |  | 1 | 2 | 8 | [5 empty] | 220
2026-07-09 | JOTP25010231 | CT10-026A-C-P07-14 | 0 | 0 | 1 | 220 | 0 |  |  | 1 | 2 | 8 | [5 empty] | 220
2026-07-10 | JOTP25010231 | CT10-026A-C-P08-14 | 0 | 0 | 1 | 220 | 0 |  |  | 1 | 2 | 8 | [5 empty] | 220
2026-07-11 | JOTP25010231 | CT10-026A-C-P09-14 | 0 | 0 | 1 | 220 | 0 |  |  | 1 | 2 | 8 | [5 empty] | 220
2026-07-12 | JOTP25010231 | CT10-026A-C-P10-14 | 0 | 0 | 1 | 220 | 0 |  |  | 1 | 2 | 8 | [5 empty] | 220
2026-07-13 | JOTP25010231 | CT10-026A-C-P11-14 | 0 | 0 | 1 | 220 | 0 |  |  | 1 | 2 | 8 | [5 empty] | 220
2026-07-14 | JOTP25010231 | CT10-026A-C-P12-14 | 0 | 0 | 1 | 220 | 0 |  |  | 1 | 2 | 8 | [5 empty] | 220
2026-07-15 | JOTP25010231 | CT10-026A-C-P13-14 | 0 | 0 | 1 | 220 | 0 |  |  | 1 | 2 | 8 | [5 empty] | 220
2026-07-16 | JOST25010244 | CC09-004-P01-04 | SM | SM01 | 1 | 14355 | 11520 | 1.2461 | 0.15576 | 1 | 2 | 8 | [5 empty] | 14355
2026-07-17 | JOST25010244 | CC09-004-P02-04 | ST-1 | PP05-060T | 1 | 14355 | 900 | 15.95 | 1.9937 | 1 | 2 | 8 | [5 empty] | 14355
2026-07-18 | JOST25010244 | CC09-004-P03-04 | ST-1 | PP13-060T | 1 | 14355 | 480 | 29.9062 | 3.7383 | 1 | 2 | 8 | [5 empty] | 14355
2026-07-19 | JOTP25010229 | CT10-026A-B-P01-03 | TP | TM03 | 1 | 200 | 72 | 2.7778 | 0.34722 | 1 | 2 | 8 | [5 empty] | 200
2026-07-20 | JOTP25010229 | CT10-026A-B-P02-03 | TP | PB01 | 1 | 200 | 120 | 1.6667 | 0.20833 | 1 | 2 | 8 | [5 empty] | 200
2026-07-21 | JOTP25010228 | CT10-026A-A-P01-07 | TP | TM03 | 1 | 216 | 48 | 4.5 | 0.5625 | 1 | 2 | 8 | [5 empty] | 216
2026-07-22 | JOTP25010228 | CT10-026A-A-P02-07 | TP | PB01 | 1 | 216 | 120 | 1.8 | 0.225 | 1 | 2 | 8 | [5 empty] | 216
2026-07-23 | JOTP25010228 | CT10-026A-A-P03-07 | TP | PB01 | 1 | 216 | 60 | 3.6 | 0.45 | 1 | 2 | 8 | [5 empty] | 216
2026-07-24 | JOTP25010228 | CT10-026A-A-P04-07 | TP | PB01 | 1 | 216 | 60 | 3.6 | 0.45 | 1 | 2 | 8 | [5 empty] | 216
2026-07-25 | JOTP25010228 | CT10-026A-A-P05-07 | TP | PB01 | 1 | 216 | 60 | 3.6 | 0.45 | 1 | 2 | 8 | [5 empty] | 216
2026-07-26 | JOTP25010228 | CT10-026A-A-P06-07 | TP | SW09 | 1 | 216 | 90 | 2.4 | 0.3 | 1 | 2 | 8 | [5 empty] | 216
2026-07-27 | JOST25010220 | CP08-384-P01-03 | ST | SM01 | 1 | 2520 | 240 | 10.5 | 1.3125 | 1 | 2 | 8 | [5 empty] | 2520
2026-07-28 | JOST25010220 | CP08-384-P02-03 | ST | PP21 | 1 | 2520 | 180 | 14 | 1.75 | 1 | 2 | 8 | [5 empty] | 2520
2026-07-29 | JOST25010170 | CP08-086-P01-02 | ST-3 | SW01 | 1 | 1031 | 90 | 11.4556 | 1.4319 | 1 | 2 | 8 |  |  |  |  | 329 | 702
2026-07-30 | JOST25010212 | CM03-038-P01-03 | ST-3 | PP02-060T | 1 | 8776 | 360 | 24.3778 | 3.0472 | 1 | 2 | 8 |  |  |  |  | 3100 | 5676
2026-07-31 | JOST25010212 | CM03-038-P02-03 | ST-3 | PP05-060T | 1 | 8776 | 240 | 36.5667 | 4.5708 | 1 | 2 | 8 | [5 empty] | 8776
2026-08-01 | JOAW24120290 | CM18-001A-P01-02 | WN | WS01 | 1 | 75000 | 2160 | 34.7222 | 4.3403 | 1 | 2 | 8 | [5 empty] | 75000
2026-08-02 | JOAW24120292 | CM18-001B-P01-02 | FM | FM03 | 1 | 45000 | 1260 | 35.7143 | 4.4643 | 1 | 2 | 8 | [5 empty] | 45000
2026-08-03 | JOAW24120294 | CM18-001C-P01-02 | WN | WS01 | 1 | 15000 | 2400 | 6.25 | 0.78125 | 1 | 2 | 8 | [5 empty] | 15000
2026-08-04 | JOST24120258 | CO02-011-P01-06 | SM | SM01 | 1 | 1610 | 300 | 5.3667 | 0.67083 | 1 | 2 | 8 | [5 empty] | 1610
2026-08-05 | JOST24120258 | CO02-011-P02-06 | ST-3 | PP18-150T | 1 | 1610 | 300 | 5.3667 | 0.67083 | 1 | 2 | 8 | [5 empty] | 1610
2026-08-06 | JOST24120258 | CO02-011-P03-06 | ST-3 | PP17-110T | 1 | 1610 | 300 | 5.3667 | 0.67083 | 1 | 2 | 8 | [5 empty] | 1610
2026-08-07 | JOST24120258 | CO02-011-P04-06 | ST-3 | PP16-110T | 1 | 1610 | 300 | 5.3667 | 0.67083 | 1 | 2 | 8 | [5 empty] | 1610
2026-08-08 | JOST24120258 | CO02-011-P05-06 | ST-3 | PP27-110T | 1 | 1610 | 300 | 5.3667 | 0.67083 | 1 | 2 | 8 | [5 empty] | 1610
2026-08-09 | JOST24120260 | CO02-013-P02-04 | ST-1 | PP22-060T | 1 | 5976 | 360 | 16.6 | 2.075 | 1 | 2 | 8 | [5 empty] | 5976
2026-08-10 | JOST24120260 | CO02-013-P03-04 | ST-1 | PP10-080T | 1 | 5976 | 180 | 33.2 | 4.15 | 1 | 2 | 8 | [5 empty] | 5976
2026-08-11 | JOST24120261 | CO02-022-P01-07 | SM | SM01 | 1 | 315 | 1080 | 0.29167 | 0.036458 | 1 | 2 | 8 | [5 empty] | 315
2026-08-12 | JOST24120261 | CO02-022-P02-07 | ST-3 | PP09-160T | 1 | 315 | 240 | 1.3125 | 0.16406 | 1 | 2 | 8 | [5 empty] | 315
2026-08-13 | JOST24120261 | CO02-022-P03-07 | ST-3 | PP18-150T | 1 | 315 | 240 | 1.3125 | 0.16406 | 1 | 2 | 8 | [5 empty] | 315
2026-08-14 | JOST24120261 | CO02-022-P04-07 | ST-3 | PP17-110T | 1 | 315 | 240 | 1.3125 | 0.16406 | 1 | 2 | 8 | [5 empty] | 315
2026-08-15 | JOST24120261 | CO02-022-P05-07 | ST-3 | PP16-110T | 1 | 315 | 240 | 1.3125 | 0.16406 | 1 | 2 | 8 | [5 empty] | 315
2026-08-16 | JOST24120261 | CO02-022-P06-07 | ST-3 | PP27-110T | 1 | 315 | 240 | 1.3125 | 0.16406 | 1 | 2 | 8 | [5 empty] | 315
2026-08-17 | JOAW24120288 | CM18-001-P01-06 | WN | SW13 | 1 | 15000 | 150 | 100 | 12.5 | 1 | 2 | 8 | [5 empty] | 15000
2026-08-18 | JOAW24120288 | CM18-001-P02-06 | WN | PP23 | 1 | 15000 | 420 | 35.7143 | 4.4643 | 1 | 2 | 8 | [5 empty] | 15000
2026-08-19 | JOAW24120288 | CM18-001-P05-06 | WN | TW01 | 1 | 15000 | 450 | 33.3333 | 4.1667 | 1 | 2 | 8 | [5 empty] | 15000
2026-08-20 | JOAW24120247 | CD11-027-P01-06 | WN | SW08 | 1 | 15000 | 120 | 125 | 15.625 | 1 | 2 | 8 | [5 empty] | 15000
2026-08-21 | JOAW24120247 | CD11-027-P02-06 | WN | PP23-060T | 1 | 15000 | 300 | 50 | 6.25 | 1 | 2 | 8 | [5 empty] | 15000
2026-08-22 | JOAW24120247 | CD11-027-P05-06 | WN | TW01 | 1 | 15000 | 400 | 37.5 | 4.6875 | 1 | 2 | 8 | [5 empty] | 15000
2026-08-23 | JOTP25010245 | CP08-490-P01-04 | TR | TM02 | 1 | 45 | 80 | 0.5625 | 0.070312 | 1 | 2 | 8 | [5 empty] | 45
2026-08-24 | JOTP25010245 | CP08-490-P02-04 | WN | DEBURR | 1 | 45 | 14 | 3.2143 | 0.40179 | 1 | 2 | 8 | [5 empty] | 45
2026-08-25 | JOTP25010245 | CP08-490-P03-04 | ST-1 | PAINTING | 1 | 45 | 50 | 0.9 | 0.1125 | 1 | 2 | 8 | [5 empty] | 45
2026-08-26 | JOAW24120315 | CP08-231-P01-06 | WN | SW03 | 1 | 500 | 15 | 33.3333 | 4.1667 | 1 | 2 | 8 | [5 empty] | 500
2026-08-27 | JOAW24120315 | CP08-231-P02-06 | WN | SW03 | 1 | 500 | 12 | 41.6667 | 5.2083 | 1 | 2 | 8 | [5 empty] | 500
2026-08-28 | JOAW24120315 | CP08-231-P03-06 | WN | SW04 | 1 | 500 | 12 | 41.6667 | 5.2083 | 1 | 2 | 8 | [5 empty] | 500
2026-08-29 | JOAW24120315 | CP08-231-P04-06 | WN | TW03 | 1 | 500 | 12 | 41.6667 | 5.2083 | 1 | 2 | 8 | [5 empty] | 500
2026-08-30 | JOTP25010223 | CT10-026-P01-04 | TP | SW09 | 1 | 95 | 12 | 7.9167 | 0.98958 | 1 | 2 | 8 | [5 empty] | 95
2026-08-31 | JOTP25010223 | CT10-026-P02-04 | TP | OPT | 1 | 95 | 6 | 15.8333 | 1.9792 | 1 | 2 | 8 | [5 empty] | 95
2026-09-01 | JOTP25010223 | CT10-026-P03-04 | TP | OPT | 1 | 95 | 30 | 3.1667 | 0.39583 | 1 | 2 | 8 | [5 empty] | 95
2026-09-02 | JOTP25010053 | CP08-415A-P01-04 | TR | TM05 | 1 | 640 | 35 | 18.2857 | 2.2857 | 1 | 2 | 8 | [5 empty] | 640
2026-09-03 | JOTP25010053 | CP08-415A-P02-04 | TR | PB05 | 1 | 640 | 40 | 16 | 2 | 1 | 2 | 8 | [5 empty] | 640
2026-09-04 | JOTP25010053 | CP08-415A-P03-04 | WN | SW09 | 1 | 640 | 60 | 10.6667 | 1.3333 | 1 | 2 | 8 | [5 empty] | 640
2026-09-05 | JOAW24100350 | CA16-011-P01-03 | FM | SW05 | 1 | 60000 | 450 | 133.3333 | 16.6667 | 1 | 2 | 8 | [5 empty] | 60000
2026-09-06 | JOAW24100350 | CA16-011-P02-03 | FM | OPT | 1 | 60000 | 900 | 66.6667 | 8.3333 | 1 | 2 | 8 | [5 empty] | 60000
2026-09-07 | JOST24120348 | CP08-428-P01-09 | ST-3 | SW01 | 1 | 338 | 90 | 3.7556 | 0.46944 | 1 | 2 | 8 | [5 empty] | 338
2026-09-08 | JOST24120348 | CP08-428-P02-09 | ST-3 | SW01 | 1 | 338 | 120 | 2.8167 | 0.35208 | 1 | 2 | 8 | [5 empty] | 338
2026-09-09 | JOST24120348 | CP08-428-P03-09 | ST-3 | SW01 | 1 | 338 | 120 | 2.8167 | 0.35208 | 1 | 2 | 8 | [5 empty] | 338
2026-09-10 | JOST24120348 | CP08-428-P04-09 | ST-3 | SW01 | 1 | 338 | 90 | 3.7556 | 0.46944 | 1 | 2 | 8 | [5 empty] | 338
2026-09-11 | JOST24120348 | CP08-428-P05-09 | ST-3 | SW01 | 1 | 338 | 40 | 8.45 | 1.0562 | 1 | 2 | 8 | [5 empty] | 338
2026-09-12 | JOST24120348 | CP08-428-P06-09 | ST-3 | SW01 | 1 | 338 | 30 | 11.2667 | 1.4083 | 1 | 2 | 8 | [5 empty] | 338
2026-09-13 | JOST24120348 | CP08-428-P07-09 | ST-3 | PAINTING | 1 | 338 | 17 | 19.8824 | 2.4853 | 1 | 2 | 8 | [5 empty] | 338
2026-09-14 | JOST24120348 | CP08-428-P08-09 | ST-3 | CLEAN | 1 | 338 | 60 | 5.6333 | 0.70417 | 1 | 2 | 8 | [5 empty] | 338
2026-09-15 | JOAW25010167 | CP08-068-P01-02 | FM | FM01 | 1 | 19230 | 1800 | 10.6833 | 1.3354 | 1 | 2 | 8 | [5 empty] | 19230
2026-09-16 | JOAW25010169 | CP08-082-P01-02 | FM | FM01 | 1 | 238095 | 1800 | 132.275 | 16.5344 | 1 | 2 | 8 | [5 empty] | 238095
2026-09-17 | JOTP25010137 | CT10-027A-P01-04 | TP | TM03 | 1 | 184 | 24 | 7.6667 | 0.95833 | 1 | 2 | 8 | [5 empty] | 184
2026-09-18 | JOTP25010137 | CT10-027A-P02-04 | TP | PB02 | 1 | 184 | 180 | 1.0222 | 0.12778 | 1 | 2 | 8 | [5 empty] | 184
2026-09-19 | JOTP25010137 | CT10-027A-P03-04 | TP | PB07 | 1 | 184 | 30 | 6.1333 | 0.76667 | 1 | 2 | 8 | [5 empty] | 184
2026-09-20 | JOTP25010138 | CT10-027B-P01-03 | TP | TM03 | 1 | 180 | 54 | 3.3333 | 0.41667 | 1 | 2 | 8 | [5 empty] | 180
2026-09-21 | JOTP25010138 | CT10-027B-P02-03 | TP | PB01 | 1 | 180 | 60 | 3 | 0.375 | 1 | 2 | 8 | [5 empty] | 180
2026-09-22 | JOTP25010246 | CP08-571-P01-05 | TR | SM01 | 1 | 720 | 360 | 2 | 0.25 | 1 | 2 | 8 | [5 empty] | 720
2026-09-23 | JOTP25010246 | CP08-571-P02-05 | TR | TM03 | 1 | 720 | 72 | 10 | 1.25 | 1 | 2 | 8 | [5 empty] | 720
2026-09-24 | JOTP25010246 | CP08-571-P03-05 | PB | PB08 | 1 | 720 | 120 | 6 | 0.75 | 1 | 2 | 8 | [5 empty] | 720
2026-09-25 | JOTP25010246 | CP08-571-P04-05 | PB | PB04 | 1 | 720 | 90 | 8 | 1 | 1 | 2 | 8 | [5 empty] | 720
2026-09-26 | JOST25010253 | CP16-032-P01-04 | SM | SM01 | 1 | 729 | 19440 | 0.0375 | 0.0046875 | 1 | 2 | 8 | [5 empty] | 729
2026-09-27 | JOST25010253 | CP16-032-P02-04 | ST-1 | PP11 | 1 | 729 | 360 | 2.025 | 0.25312 | 1 | 2 | 8 | [5 empty] | 729
2026-09-28 | JOST25010253 | CP16-032-P03-04 | ST-1 | PP05-060T | 1 | 729 | 240 | 3.0375 | 0.37969 | 1 | 2 | 8 | [5 empty] | 729
2026-09-29 | JOAW25010252 | CM17-005-P01-05 | FM | FM02 | 1 | 41584 | 2400 | 17.3267 | 2.1658 | 1 | 2 | 8 | [5 empty] | 41584
2026-09-30 | JOAW25010252 | CM17-005-P04-05 | AL | CHECK | 1 | 41584 | 270 | 154.0148 | 19.2519 | 1 | 2 | 8 | [5 empty] | 41584
2026-10-01 | JOST25010250 | CM10-009-P01-05 | ST-2 | PP19-110T | 1 | 32258 | 1500 | 21.5053 | 2.6882 | 1 | 2 | 8 | [5 empty] | 32258
2026-10-02 | JOST25010250 | CM10-009-P02-05 | AL | TP09 | 1 | 32258 | 420 | 76.8048 | 9.6006 | 1 | 2 | 8 | [5 empty] | 32258
2026-10-03 | JOST25010250 | CM10-009-P04-05 | AL | CHECKING | 1 | 32258 | 1200 | 26.8817 | 3.3602 | 1 | 2 | 8 | [5 empty] | 32258
2026-10-04 | JOST25010249 | CM10-009-P01-05 | ST-2 | PP19-110T | 1 | 32258 | 1500 | 21.5053 | 2.6882 | 1 | 2 | 8 | [5 empty] | 32258
2026-10-05 | JOST25010249 | CM10-009-P02-05 | AL | TP09 | 1 | 32258 | 420 | 76.8048 | 9.6006 | 1 | 2 | 8 | [5 empty] | 32258
2026-10-06 | JOST25010249 | CM10-009-P04-05 | AL | CHECKING | 1 | 32258 | 1200 | 26.8817 | 3.3602 | 1 | 2 | 8 | [5 empty] | 32258
2026-10-07 | JOST25010248 | CM10-009-P01-05 | ST-2 | PP19-110T | 1 | 9217 | 1500 | 6.1447 | 0.76808 | 1 | 2 | 8 | [5 empty] | 9217
2026-10-08 | JOST25010248 | CM10-009-P02-05 | AL | TP09 | 1 | 9217 | 420 | 21.9452 | 2.7432 | 1 | 2 | 8 | [5 empty] | 9217
2026-10-09 | JOST25010248 | CM10-009-P04-05 | AL | CHECKING | 1 | 9217 | 1200 | 7.6808 | 0.9601 | 1 | 2 | 8 | [5 empty] | 9217
2026-10-10 | JOAW25010251 | CM17-002-P01-04 | FM | FM02 | 1 | 43697 | 3600 | 12.1381 | 1.5173 | 1 | 2 | 8 | [5 empty] | 43697
2026-10-11 | JOTP25010179 | CP08-428A-P01-03 | TR | TM03 | 1 | 639 | 47 | 13.5957 | 1.6995 | 1 | 2 | 8 | [5 empty] | 639
2026-10-12 | JOTP25010179 | CP08-428A-P02-03 | TR | PB07 | 1 | 639 | 96 | 6.6562 | 0.83203 | 1 | 2 | 8 | [5 empty] | 639
2026-10-13 | JOTP25010180 | CP08-428B-P01-03 | TR | TM06 | 1 | 636 | 65 | 9.7846 | 1.2231 | 1 | 2 | 8 | [5 empty] | 636
2026-10-14 | JOTP25010180 | CP08-428B-P02-03 | TR | PB04 | 1 | 636 | 72 | 8.8333 | 1.1042 | 1 | 2 | 8 | [5 empty] | 636
2026-10-15 | JOTP25010181 | CP08-428C-P01-03 | TR | TM06 | 1 | 632 | 60 | 10.5333 | 1.3167 | 1 | 2 | 8 | [5 empty] | 632
2026-10-16 | JOTP25010181 | CP08-428C-P02-03 | TR | PB04 | 1 | 632 | 95 | 6.6526 | 0.83158 | 1 | 2 | 8 | [5 empty] | 632
2026-10-17 | JOTP25010182 | CP08-428D-P01-03 | TR | TM06 | 1 | 640 | 55 | 11.6364 | 1.4545 | 1 | 2 | 8 | [5 empty] | 640
2026-10-18 | JOTP25010182 | CP08-428D-P02-03 | TR | PB07 | 1 | 640 | 70 | 9.1429 | 1.1429 | 1 | 2 | 8 | [5 empty] | 640
2026-10-19 | JOST25010195 | CP08-544-P01-02 | ST | STICK LABEL | 1 | 1050 | 30 | 35 | 4.375 | 1 | 2 | 8 | [5 empty] | 1050
2026-10-20 | JOTP25010227 | CT10-026A-P01-02 | TP | SW09 | 1 | 220 | 8 | 27.5 | 3.4375 | 1 | 2 | 8 | [5 empty] | 220
2026-10-21 | JOAW25010036 | CP08-231-P01-06 | WN | SW03 | 1 | 800 | 15 | 53.3333 | 6.6667 | 1 | 2 | 8 | [5 empty] | 800
2026-10-22 | JOAW25010036 | CP08-231-P02-06 | WN | SW03 | 1 | 800 | 12 | 66.6667 | 8.3333 | 1 | 2 | 8 | [5 empty] | 800
2026-10-23 | JOAW25010036 | CP08-231-P03-06 | WN | SW04 | 1 | 800 | 12 | 66.6667 | 8.3333 | 1 | 2 | 8 | [5 empty] | 800
2026-10-24 | JOAW25010036 | CP08-231-P04-06 | WN | TW03 | 1 | 800 | 12 | 66.6667 | 8.3333 | 1 | 2 | 8 | [5 empty] | 800
2026-10-25 | JOAW24120240 | CD11-026-P01-06 | WN | SW13 | 1 | 20000 | 120 | 166.6667 | 20.8333 | 1 | 2 | 8 | [5 empty] | 20000
2026-10-26 | JOAW24120240 | CD11-026-P02-06 | WN | PP23-060T | 1 | 20000 | 540 | 37.037 | 4.6296 | 1 | 2 | 8 | [5 empty] | 20000
2026-10-27 | JOAW24120240 | CD11-026-P05-06 | WN | TW01 | 1 | 20000 | 420 | 47.619 | 5.9524 | 1 | 2 | 8 | [5 empty] | 20000
2026-10-28 | JOAW24120164 | CA16-011-P01-03 | FM | SW05 | 1 | 60000 | 450 | 133.3333 | 16.6667 | 1 | 2 | 8 | [5 empty] | 60000
2026-10-29 | JOAW24120164 | CA16-011-P02-03 | FM | OPT | 1 | 60000 | 900 | 66.6667 | 8.3333 | 1 | 2 | 8 | [5 empty] | 60000
2026-10-30 | JOST24120163 | CA16-010-P01-03 | ST | PP01-110T | 1 | 79545 | 3000 | 26.515 | 3.3144 | 1 | 2 | 8 | [5 empty] | 79545
2026-10-31 | JOST24120163 | CA16-010-P02-03 | ST-1 | VM01 | 1 | 79545 | 1000 | 79.545 | 9.9431 | 1 | 2 | 8 | [5 empty] | 79545
2026-11-01 | JOAW25010303 | CS18-010-P01-03 | WN | SW06 | 1 | 300 | 18 | 16.6667 | 2.0833 | 1 | 2 | 8 |  |  |  |  | 83 | 217
2026-11-02 | JOAW25010303 | CS18-010-P02-03 | WN | TW01 | 1 | 300 | 18 | 16.6667 | 2.0833 | 1 | 2 | 8 |  |  |  |  | 83 | 217
2026-11-03 | JOAW25010298 | CS18-006-P01-03 | WN | SW06 | 1 | 350 | 15 | 23.3333 | 2.9167 | 1 | 2 | 8 | [5 empty] | 350
2026-11-04 | JOAW25010298 | CS18-006-P02-03 | WN | TW01 | 1 | 350 | 15 | 23.3333 | 2.9167 | 1 | 2 | 8 | [5 empty] | 350
2026-11-05 | JOST25010255 | CP08-499A-P01-06 | ST-4 | PP29-250T | 1 | 300 | 120 | 2.5 | 0.3125 | 1 | 2 | 8 | [5 empty] | 300
2026-11-06 | JOST25010255 | CP08-499A-P02-06 | ST-4 | PP30 | 1 | 300 | 120 | 2.5 | 0.3125 | 1 | 2 | 8 | [5 empty] | 300
2026-11-07 | JOST25010255 | CP08-499A-P03-06 | ST-3 | TP03 | 1 | 300 | 120 | 2.5 | 0.3125 | 1 | 2 | 8 | [5 empty] | 300
2026-11-08 | JOST25010255 | CP08-499A-P04-06 | AL | TP09 | 1 | 300 | 120 | 2.5 | 0.3125 | 1 | 2 | 8 | [5 empty] | 300
2026-11-09 | JOST25010255 | CP08-499A-P05-06 | TR | PB05 | 1 | 300 | 60 | 5 | 0.625 | 1 | 2 | 8 | [5 empty] | 300
2026-11-10 | JOST25010256 | CP08-499-P01-02 | ST-3 | SW01 | 1 | 300 | 30 | 10 | 1.25 | 1 | 2 | 8 | [5 empty] | 300
2026-11-11 | JOST25010309 | CN08-001-P01-04 | ST | PP14 | 1 | 46428 | 1200 | 38.69 | 4.8362 | 1 | 2 | 8 | [5 empty] | 46428
2026-11-12 | JOST25010309 | CN08-001-P02-04 | ST | TP09 | 1 | 46428 | 480 | 96.725 | 12.0906 | 1 | 2 | 8 | [5 empty] | 46428
2026-11-13 | JOST25010292 | CT10-018-P01-07 | ST-3 | PP27-110T | 1 | 210 | 120 | 1.75 | 0.21875 | 1 | 2 | 8 | [5 empty] | 210
2026-11-14 | JOST25010292 | CT10-018-P02-07 | ST-3 | PP16-110T | 1 | 210 | 120 | 1.75 | 0.21875 | 1 | 2 | 8 | [5 empty] | 210
2026-11-15 | JOST25010292 | CT10-018-P03-07 | ST-3 | PP17-110T | 1 | 210 | 120 | 1.75 | 0.21875 | 1 | 2 | 8 | [5 empty] | 210
2026-11-16 | JOST25010292 | CT10-018-P04-07 | ST-3 | TP03 | 1 | 210 | 120 | 1.75 | 0.21875 | 1 | 2 | 8 | [5 empty] | 210
2026-11-17 | JOST25010292 | CT10-018-P05-07 | ST-3 | PP18 | 1 | 210 | 120 | 1.75 | 0.21875 | 1 | 2 | 8 | [5 empty] | 210
2026-11-18 | JOST25010292 | CT10-018-P06-07 | ST | SW01 | 1 | 210 | 120 | 1.75 | 0.21875 | 1 | 2 | 8 | [5 empty] | 210
2026-11-19 | JOST25010291 | CT10-015-P01-05 | ST-4 | PP24-160T | 1 | 14400 | 360 | 40 | 5 | 1 | 2 | 8 | [5 empty] | 14400
2026-11-20 | JOST25010291 | CT10-015-P02-05 | ST-4 | PP25-160T | 1 | 14400 | 360 | 40 | 5 | 1 | 2 | 8 | [5 empty] | 14400
2026-11-21 | JOST25010291 | CT10-015-P03-05 | ST-4 | PP20-110T | 1 | 14400 | 360 | 40 | 5 | 1 | 2 | 8 | [5 empty] | 14400
2026-11-22 | JOST25010291 | CT10-015-P04-05 | ST-4 | PP28-110T | 1 | 14400 | 360 | 40 | 5 | 1 | 2 | 8 | [5 empty] | 14400
2026-11-23 | JOST25010290 | CT10-015-P01-05 | ST-4 | PP24-160T | 1 | 14400 | 360 | 40 | 5 | 1 | 2 | 8 |  |  |  |  | 8412 | 5988
2026-11-24 | JOST25010290 | CT10-015-P02-05 | ST-4 | PP25-160T | 1 | 14400 | 360 | 40 | 5 | 1 | 2 | 8 |  |  |  |  | 8412 | 5988
2026-11-25 | JOST25010290 | CT10-015-P03-05 | ST-4 | PP20-110T | 1 | 14400 | 360 | 40 | 5 | 1 | 2 | 8 |  |  |  |  | 8412 | 5988
2026-11-26 | JOST25010290 | CT10-015-P04-05 | ST-4 | PP28-110T | 1 | 14400 | 360 | 40 | 5 | 1 | 2 | 8 |  |  |  |  | 8412 | 5988
2026-11-27 | JOST25010288 | CT10-005-P01-07 | ST-3 | PP27-110T | 1 | 500 | 120 | 4.1667 | 0.52083 | 1 | 2 | 8 | [5 empty] | 500
2026-11-28 | JOST25010288 | CT10-005-P02-07 | ST-3 | PP16-110T | 1 | 500 | 120 | 4.1667 | 0.52083 | 1 | 2 | 8 | [5 empty] | 500
2026-11-29 | JOST25010288 | CT10-005-P03-07 | ST-3 | PP17-110T | 1 | 500 | 120 | 4.1667 | 0.52083 | 1 | 2 | 8 | [5 empty] | 500
2026-11-30 | JOST25010288 | CT10-005-P04-07 | ST-3 | TP03 | 1 | 500 | 120 | 4.1667 | 0.52083 | 1 | 2 | 8 | [5 empty] | 500
2026-12-01 | JOST25010288 | CT10-005-P05-07 | ST-3 | PP18-150T | 1 | 500 | 120 | 4.1667 | 0.52083 | 1 | 2 | 8 | [5 empty] | 500
2026-12-02 | JOST25010288 | CT10-005-P06-07 | ST-3 | SW01 | 1 | 500 | 120 | 4.1667 | 0.52083 | 1 | 2 | 8 | [5 empty] | 500
2026-12-03 | JOTP25010287 | CP08-563A-P01-03 | TR | TM05 | 1 | 760 | 60 | 12.6667 | 1.5833 | 1 | 2 | 8 | [5 empty] | 760
2026-12-04 | JOTP25010287 | CP08-563A-P02-03 | PB | PB08 | 1 | 760 | 90 | 8.4444 | 1.0556 | 1 | 2 | 8 | [5 empty] | 760
2026-12-05 | JOTP25010286 | CP08-563-P01-04 | PB | SW09 | 1 | 760 | 120 | 6.3333 | 0.79167 | 1 | 2 | 8 | [5 empty] | 760
2026-12-06 | JOTP25010286 | CP08-563-P02-04 | PB | OPT | 1 | 760 | 36 | 21.1111 | 2.6389 | 1 | 2 | 8 | [5 empty] | 760
2026-12-07 | JOTP25010286 | CP08-563-P03-04 | TP | OPT | 1 | 760 | 80 | 9.5 | 1.1875 | 1 | 2 | 8 | [5 empty] | 760
2026-12-08 | JOTP25010282 | CP08-562A-P01-03 | TR | TM03 | 1 | 804 | 40 | 20.1 | 2.5125 | 1 | 2 | 8 | [5 empty] | 804
2026-12-09 | JOTP25010282 | CP08-562A-P02-03 | PB | PB05 | 1 | 804 | 120 | 6.7 | 0.8375 | 1 | 2 | 8 | [5 empty] | 804
2026-12-10 | JOTP25010283 | CP08-562B-P01-03 | TR | TM03 | 1 | 812 | 60 | 13.5333 | 1.6917 | 1 | 2 | 8 | [5 empty] | 812
2026-12-11 | JOTP25010283 | CP08-562B-P02-03 | PB | PB04 | 1 | 812 | 100 | 8.12 | 1.015 | 1 | 2 | 8 | [5 empty] | 812
2026-12-12 | JOTP25010284 | CP08-562C-P01-05 | TR | TM03 | 1 | 800 | 44 | 18.1818 | 2.2727 | 1 | 2 | 8 | [5 empty] | 800
2026-12-13 | JOTP25010284 | CP08-562C-P02-05 | PB | PB04 | 1 | 800 | 120 | 6.6667 | 0.83333 | 1 | 2 | 8 | [5 empty] | 800
2026-12-14 | JOTP25010284 | CP08-562C-P03-05 | PB | PB08 | 1 | 800 | 90 | 8.8889 | 1.1111 | 1 | 2 | 8 | [5 empty] | 800
2026-12-15 | JOTP25010284 | CP08-562C-P04-05 | PB | PB04 | 1 | 800 | 120 | 6.6667 | 0.83333 | 1 | 2 | 8 | [5 empty] | 800
2026-12-16 | JOTP25010285 | CP08-562D-P01-03 | TR | TM03 | 1 | 805 | 35 | 23 | 2.875 | 1 | 2 | 8 | [5 empty] | 805
2026-12-17 | JOTP25010285 | CP08-562D-P02-03 | PB | PB07 | 1 | 805 | 100 | 8.05 | 1.0063 | 1 | 2 | 8 | [5 empty] | 805
2026-12-18 | JOTP25010286 | CP08-563-P01-04 | PB | SW09 | 1 | 760 | 120 | 6.3333 | 0.79167 | 1 | 2 | 8 | [5 empty] | 760
2026-12-19 | JOTP25010286 | CP08-563-P02-04 | PB | OPT | 1 | 760 | 36 | 21.1111 | 2.6389 | 1 | 2 | 8 | [5 empty] | 760
2026-12-20 | JOTP25010286 | CP08-563-P03-04 | TP | OPT | 1 | 760 | 80 | 9.5 | 1.1875 | 1 | 2 | 8 | [5 empty] | 760
2026-12-21 | JOTP25010281 | CP08-562-P01-05 | PB | SW14 | 1 | 802 | 120 | 6.6833 | 0.83542 | 1 | 2 | 8 | [5 empty] | 802
2026-12-22 | JOTP25010281 | CP08-562-P02-05 | PB | SW14 | 1 | 802 | 17 | 47.1765 | 5.8971 | 1 | 2 | 8 | [5 empty] | 802
2026-12-23 | JOTP25010281 | CP08-562-P03-05 | OPT | OPT | 1 | 802 | 50 | 16.04 | 2.005 | 1 | 2 | 8 | [5 empty] | 802
2026-12-24 | JOTP25010281 | CP08-562-P04-05 | OPT | OPT | 1 | 802 | 60 | 13.3667 | 1.6708 | 1 | 2 | 8 | [5 empty] | 802
2026-12-25 | JOAW25010276 | CP08-557C-P01-04 | WN | WS01 | 1 | 1000 | 900 | 1.1111 | 0.13889 | 1 | 2 | 8 | [5 empty] | 1000
2026-12-26 | JOAW25010276 | CP08-557C-P02-04 | WN | JIG BENDING | 1 | 1000 | 240 | 4.1667 | 0.52083 | 1 | 2 | 8 | [5 empty] | 1000
2026-12-27 | JOAW25010276 | CP08-557C-P03-04 | WN | JIG BENDING | 1 | 1000 | 240 | 4.1667 | 0.52083 | 1 | 2 | 8 | [5 empty] | 1000
2026-12-28 | JOAW25010277 | CP08-557D-P01-03 | WN | WS01 | 1 | 1000 | 5700 | 0.17544 | 0.02193 | 1 | 2 | 8 | [5 empty] | 1000
2026-12-29 | JOAW25010277 | CP08-557D-P02-03 | WN | JIG BENDING | 1 | 1000 | 120 | 8.3333 | 1.0417 | 1 | 2 | 8 | [5 empty] | 1000
2026-12-30 | JOAW25010278 | CP08-557E-P01-02 | WN | WS01 | 1 | 6000 | 4800 | 1.25 | 0.15625 | 1 | 2 | 8 | [5 empty] | 6000
2026-12-31 | JOAW25010279 | CP08-557F-P01-02 | WN | WS01 | 1 | 5000 | 900 | 5.5556 | 0.69444 | 1 | 2 | 8 | [5 empty] | 5000
2027-01-01 | JOAW25010275 | CP08-557-P01-09 | WN | SW04 | 1 | 1000 | 30 | 33.3333 | 4.1667 | 1 | 2 | 8 | [5 empty] | 1000
2027-01-02 | JOAW25010275 | CP08-557-P02-09 | WN | PP23-060T | 1 | 1000 | 180 | 5.5556 | 0.69444 | 1 | 2 | 8 | [5 empty] | 1000
2027-01-03 | JOAW25010275 | CP08-557-P03-09 | TR | SW06 | 1 | 1000 | 50 | 20 | 2.5 | 1 | 2 | 8 | [5 empty] | 1000
2027-01-04 | JOAW25010275 | CP08-557-P04-09 | TR | SW05 | 1 | 1000 | 120 | 8.3333 | 1.0417 | 1 | 2 | 8 | [5 empty] | 1000
2027-01-05 | JOAW25010275 | CP08-557-P05-09 | WN | TW02 | 1 | 1000 | 90 | 11.1111 | 1.3889 | 1 | 2 | 8 | [5 empty] | 1000
2027-01-06 | JOAW25010275 | CP08-557-P06-09 | WN | OPT | 1 | 1000 | 90 | 11.1111 | 1.3889 | 1 | 2 | 8 | [5 empty] | 1000
2027-01-07 | JOAW25010275 | CP08-557-P08-09 | AL | CHECKING | 1 | 1000 | 15 | 66.6667 | 8.3333 | 1 | 2 | 8 | [5 empty] | 1000
2027-01-08 | JOTP25010272 | CP08-554A-P01-04 | TR | TM05 | 1 | 500 | 60 | 8.3333 | 1.0417 | 1 | 2 | 8 | [5 empty] | 500
2027-01-09 | JOTP25010272 | CP08-554A-P02-04 | TR | 1 | 1 | 500 | 20 | 25 | 3.125 | 1 | 2 | 8 | [5 empty] | 500
2027-01-10 | JOTP25010272 | CP08-554A-P03-04 | TR | PB02 | 1 | 500 | 30 | 16.6667 | 2.0833 | 1 | 2 | 8 | [5 empty] | 500
2027-01-11 | JOST25010273 | CP08-554C-P01-04 | ST | PP29 | 1 | 510 | 360 | 1.4167 | 0.17708 | 1 | 2 | 8 | [5 empty] | 510
2027-01-12 | JOST25010273 | CP08-554C-P02-04 | ST | PP30-200T | 1 | 510 | 360 | 1.4167 | 0.17708 | 1 | 2 | 8 | [5 empty] | 510
2027-01-13 | JOST25010273 | CP08-554C-P03-04 | ST | PP21 | 1 | 510 | 240 | 2.125 | 0.26562 | 1 | 2 | 8 | [5 empty] | 510
2027-01-14 | JOTP25010269 | CP08-553D-P01-03 | TR | TM06 | 1 | 480 | 100 | 4.8 | 0.6 | 1 | 2 | 8 | [5 empty] | 480
2027-01-15 | JOTP25010269 | CP08-553D-P02-03 | TR | PB01 | 1 | 480 | 240 | 2 | 0.25 | 1 | 2 | 8 | [5 empty] | 480
2027-01-16 | JOTP25010270 | CP08-553E-P01-03 | TR | TM06 | 1 | 480 | 200 | 2.4 | 0.3 | 1 | 2 | 8 | [5 empty] | 480
2027-01-17 | JOTP25010270 | CP08-553E-P02-03 | TR | PB01 | 1 | 480 | 240 | 2 | 0.25 | 1 | 2 | 8 | [5 empty] | 480
2027-01-18 | JOTP25010266 | CP08-552A-P01-04 | TR | TM06 | 1 | 684 | 120 | 5.7 | 0.7125 | 1 | 2 | 8 | [5 empty] | 684
2027-01-19 | JOTP25010266 | CP08-552A-P02-04 | TR | RL1 | 1 | 684 | 30 | 22.8 | 2.85 | 1 | 2 | 8 | [5 empty] | 684
2027-01-20 | JOTP25010266 | CP08-552A-P03-04 | TR | PB02 | 1 | 684 | 30 | 22.8 | 2.85 | 1 | 2 | 8 | [5 empty] | 684
2027-01-21 | JOST25010267 | CP08-552B-P01-04 | ST | PP30-200T | 1 | 561 | 240 | 2.3375 | 0.29219 | 1 | 2 | 8 | [5 empty] | 561
2027-01-22 | JOST25010267 | CP08-552B-P02-04 | ST | PP29 | 1 | 561 | 120 | 4.675 | 0.58437 | 1 | 2 | 8 | [5 empty] | 561
2027-01-23 | JOST25010267 | CP08-552B-P03-04 | ST | PP21 | 1 | 561 | 240 | 2.3375 | 0.29219 | 1 | 2 | 8 | [5 empty] | 561
2027-01-24 | JOTP25010268 | CP08-553-P01-07 | TR | SW14 | 1 | 162 | 60 | 2.7 | 0.3375 | 1 | 2 | 8 | [5 empty] | 162
2027-01-25 | JOTP25010268 | CP08-553-P02-07 | TR | SW14 | 1 | 162 | 60 | 2.7 | 0.3375 | 1 | 2 | 8 | [5 empty] | 162
2027-01-26 | JOTP25010268 | CP08-553-P03-07 | TR | SW14 | 1 | 162 | 60 | 2.7 | 0.3375 | 1 | 2 | 8 | [5 empty] | 162
2027-01-27 | JOTP25010268 | CP08-553-P04-07 | TR | SW14 | 1 | 162 | 12 | 13.5 | 1.6875 | 1 | 2 | 8 | [5 empty] | 162
2027-01-28 | JOTP25010268 | CP08-553-P05-07 | TR | PAINTING | 1 | 162 | 12 | 13.5 | 1.6875 | 1 | 2 | 8 | [5 empty] | 162
2027-01-29 | JOTP25010268 | CP08-553-P06-07 | TR | PACK & LABEL | 1 | 162 | 12 | 13.5 | 1.6875 | 1 | 2 | 8 | [5 empty] | 162
2027-01-30 | JOTP25010265 | CP08-552-P01-07 | TR | SW14 | 1 | 162 | 60 | 2.7 | 0.3375 | 1 | 2 | 8 | [5 empty] | 162
2027-01-31 | JOTP25010265 | CP08-552-P02-07 | TR | SW14 | 1 | 162 | 60 | 2.7 | 0.3375 | 1 | 2 | 8 | [5 empty] | 162
2027-02-01 | JOTP25010265 | CP08-552-P03-07 | TR | SW14 | 1 | 162 | 60 | 2.7 | 0.3375 | 1 | 2 | 8 | [5 empty] | 162
2027-02-02 | JOTP25010265 | CP08-552-P04-07 | TR | SW14 | 1 | 162 | 12 | 13.5 | 1.6875 | 1 | 2 | 8 | [5 empty] | 162
2027-02-03 | JOTP25010265 | CP08-552-P05-07 | TR | PAINTING | 1 | 162 | 12 | 13.5 | 1.6875 | 1 | 2 | 8 | [5 empty] | 162
2027-02-04 | JOTP25010265 | CP08-552-P06-07 | TR | PACK & LABEL | 1 | 162 | 12 | 13.5 | 1.6875 | 1 | 2 | 8 | [5 empty] | 162
2027-02-05 | JOTP25010259 | CP08-323A-P01-04 | SM | SM01 | 1 | 45 | 240 | 0.1875 | 0.023438 | 1 | 2 | 8 | [5 empty] | 45
2027-02-06 | JOTP25010259 | CP08-323A-P02-04 | TR | TM03 | 1 | 45 | 82 | 0.54878 | 0.068598 | 1 | 2 | 8 | [5 empty] | 45
2027-02-07 | JOTP25010259 | CP08-323A-P03-04 | TR | PB05 | 1 | 45 | 25 | 1.8 | 0.225 | 1 | 2 | 8 | [5 empty] | 45
2027-02-08 | JOST25010258 | CP08-323-P01-02 | ST-3 | PP09-160T | 1 | 45 | 120 | 0.375 | 0.046875 | 1 | 2 | 8 | [5 empty] | 45
2027-02-09 | JOAW25010257 | CP08-300-P01-03 | FM | FM03 | 1 | 17241 | 1800 | 9.5783 | 1.1973 | 1 | 2 | 8 | [5 empty] | 17241
2027-02-10 | JOAW25010257 | CP08-300-P02-03 | FM | VM01 | 1 | 17241 | 1000 | 17.241 | 2.1551 | 1 | 2 | 8 | [5 empty] | 17241
2027-02-11 | JOST25010264 | CP08-483-P01-04 | SM | SM01 | 1 | 2050 | 205 | 10 | 1.25 | 1 | 2 | 8 | [5 empty] | 2050
2027-02-12 | JOST25010264 | CP08-483-P02-04 | ST-2 | PP10-080T | 1 | 2050 | 360 | 5.6944 | 0.71181 | 1 | 2 | 8 | [5 empty] | 2050
2027-02-13 | JOST25010264 | CP08-483-P03-04 | ST-3 | PP21-110T | 1 | 2050 | 240 | 8.5417 | 1.0677 | 1 | 2 | 8 | [5 empty] | 2050
2027-02-14 | JOTP25010262 | CP08-421-P01-03 | TR | TM05 | 1 | 900 | 90 | 10 | 1.25 | 1 | 2 | 8 | [5 empty] | 900
2027-02-15 | JOTP25010262 | CP08-421-P02-03 | TR | PB08 | 1 | 900 | 120 | 7.5 | 0.9375 | 1 | 2 | 8 | [5 empty] | 900
2027-02-16 | JOTP25010263 | CP08-422-P01-03 | TR | TM05 | 1 | 900 | 50 | 18 | 2.25 | 1 | 2 | 8 | [5 empty] | 900
2027-02-17 | JOTP25010263 | CP08-422-P02-03 | TR | PB08 | 1 | 900 | 72 | 12.5 | 1.5625 | 1 | 2 | 8 | [5 empty] | 900
2027-02-18 | JOST25010261 | CP08-369/CP08-370-P01-05 | SM | SM01 | 1 | 2800 | 360 | 7.7778 | 0.97222 | 1 | 2 | 8 | [5 empty] | 2800
2027-02-19 | JOST25010261 | CP08-369/CP08-370-P02-05 | ST-3 | PP25-160T | 1 | 2800 | 300 | 9.3333 | 1.1667 | 1 | 2 | 8 | [5 empty] | 2800
2027-02-20 | JOST25010261 | CP08-369/CP08-370-P03-05 | ST-4 | PP20-110T | 1 | 2800 | 300 | 9.3333 | 1.1667 | 1 | 2 | 8 | [5 empty] | 2800
2027-02-21 | JOST25010261 | CP08-369/CP08-370-P04-05 | ST-3 | PP28-110T | 1 | 2800 | 300 | 9.3333 | 1.1667 | 1 | 2 | 8 | [5 empty] | 2800
2027-02-22 | JOST25010250 | CM10-009-P01-05 | ST-2 | PP19-110T | 1 | 32258 | 1500 | 21.5053 | 2.6882 | 1 | 2 | 8 | [5 empty] | 32258
2027-02-23 | JOST25010250 | CM10-009-P02-05 | AL | TP09 | 1 | 32258 | 420 | 76.8048 | 9.6006 | 1 | 2 | 8 | [5 empty] | 32258
2027-02-24 | JOST25010250 | CM10-009-P04-05 | AL | CHECKING | 1 | 32258 | 1200 | 26.8817 | 3.3602 | 1 | 2 | 8 | [5 empty] | 32258
2027-02-25 | JOTP25010271 | CP08-554-P01-06 | TR | SW14 | 1 | 500 | 93 | 5.3763 | 0.67204 | 1 | 2 | 8 | [5 empty] | 500
2027-02-26 | JOTP25010271 | CP08-554-P02-06 | TR | SW14 | 1 | 500 | 129 | 3.876 | 0.4845 | 1 | 2 | 8 | [5 empty] | 500
2027-02-27 | JOTP25010271 | CP08-554-P03-06 | TR | SW14 | 1 | 500 | 12 | 41.6667 | 5.2083 | 1 | 2 | 8 | [5 empty] | 500
2027-02-28 | JOTP25010271 | CP08-554-P04-06 | TR | PAINTING | 1 | 500 | 12 | 41.6667 | 5.2083 | 1 | 2 | 8 | [5 empty] | 500
2027-03-01 | JOTP25010271 | CP08-554-P05-06 | TR | PACK & LABEL | 1 | 500 | 12 | 41.6667 | 5.2083 | 1 | 2 | 8 | [5 empty] | 500
2027-03-02 | JOST25010274 | CP08-555-P01-04 | TR | PP17-110T | 1 | 2600 | 240 | 10.8333 | 1.3542 | 1 | 2 | 8 | [5 empty] | 2600
2027-03-03 | JOST25010274 | CP08-555-P02-04 | ST | PP16-110T | 1 | 2600 | 240 | 10.8333 | 1.3542 | 1 | 2 | 8 | [5 empty] | 2600
2027-03-04 | JOST25010274 | CP08-555-P03-04 | ST | PP27-110T | 1 | 2600 | 240 | 10.8333 | 1.3542 | 1 | 2 | 8 | [5 empty] | 2600
2027-03-05 | JOST25010280 | CP08-560-P01-04 | ST | PP09 | 1 | 405 | 360 | 1.125 | 0.14062 | 1 | 2 | 8 | [5 empty] | 405
2027-03-06 | JOST25010280 | CP08-560-P02-04 | ST | PP18 | 1 | 405 | 300 | 1.35 | 0.16875 | 1 | 2 | 8 | [5 empty] | 405
2027-03-07 | JOST25010280 | CP08-560-P03-04 | ST | PP27-110T | 1 | 405 | 300 | 1.35 | 0.16875 | 1 | 2 | 8 | [5 empty] | 405
2027-03-08 | JOST25010221 | CT10-022-P01-02 | ST-1 | PP19-110T | 1 | 10204 | 1800 | 5.6689 | 0.70861 | 1 | 2 | 8 | [5 empty] | 10204
2027-03-09 | JOST25010205 | CP08-604-P01-03 | PB | TM03 | 1 | 200 | 85 | 2.3529 | 0.29412 | 1 | 2 | 8 | [5 empty] | 200
2027-03-10 | JOST25010205 | CP08-604-P02-03 | PB | PB01 | 1 | 200 | 180 | 1.1111 | 0.13889 | 1 | 2 | 8 | [5 empty] | 200
2027-03-11 | JOST25010196 | CP08-558-P01-02 | ST | PP30-200T | 1 | 55555 | 1500 | 37.0367 | 4.6296 | 1 | 2 | 8 | [5 empty] | 55555
2027-03-12 | JOTP25010199 | CP08-583-P01-04 | PB | SW09 | 1 | 152 | 90 | 1.6889 | 0.21111 | 1 | 2 | 8 | [5 empty] | 152
2027-03-13 | JOTP25010199 | CP08-583-P02-04 | PB | OPT | 1 | 152 | 60 | 2.5333 | 0.31667 | 1 | 2 | 8 | [5 empty] | 152
2027-03-14 | JOTP25010199 | CP08-583-P03-04 | PB | OPT | 1 | 152 | 60 | 2.5333 | 0.31667 | 1 | 2 | 8 | [5 empty] | 152
2027-03-15 | JOST25010183 | CP08-456-P01-04 | ST-3 | PP25-160T | 1 | 1200 | 360 | 3.3333 | 0.41667 | 1 | 2 | 8 | [5 empty] | 1200
2027-03-16 | JOST25010183 | CP08-456-P02-04 | ST-3 | PP20-110T | 1 | 1200 | 360 | 3.3333 | 0.41667 | 1 | 2 | 8 | [5 empty] | 1200
2027-03-17 | JOST25010183 | CP08-456-P03-04 | ST-3 | PP28-110T | 1 | 1200 | 360 | 3.3333 | 0.41667 | 1 | 2 | 8 | [5 empty] | 1200
2027-03-18 | JOST25010187 | CP08-496-P01-03 | 0 | STICK LABEL | 1 | 700 | 15 | 46.6667 | 5.8333 | 1 | 2 | 8 | [5 empty] | 700
2027-03-19 | JOST25010187 | CP08-496-P02-03 | 0 | STICK LABEL | 1 | 700 | 15 | 46.6667 | 5.8333 | 1 | 2 | 8 | [5 empty] | 700
2027-03-20 | JOST25010172 | CP08-256-P01-02 | ST-1 | PP29 | 1 | 4200 | 240 | 17.5 | 2.1875 | 1 | 2 | 8 | [5 empty] | 4200
2027-03-21 | JOST25010173 | CP08-289-P01-06 | ST-2 | PP01-110T | 1 | 25806 | 450 | 57.3467 | 7.1683 | 1 | 2 | 8 | [5 empty] | 25806
2027-03-22 | JOST25010173 | CP08-289-P02-06 | ST-2 | PP15-080T | 1 | 25806 | 450 | 57.3467 | 7.1683 | 1 | 2 | 8 | [5 empty] | 25806
2027-03-23 | JOST25010173 | CP08-289-P04-06 | ST-4 | TP08 | 1 | 25806 | 360 | 71.6833 | 8.9604 | 1 | 2 | 8 | [5 empty] | 25806
2027-03-24 | JOST25010173 | CP08-289-P05-06 | AL | CHECKING | 1 | 25806 | 360 | 71.6833 | 8.9604 | 1 | 2 | 8 | [5 empty] | 25806
2027-03-25 | JOAW25020001 | CD11-029-P01-06 | 0 | SW08 | 1 | 3000 | 34.8 | 86.2069 | 10.7759 | 1 | 2 | 8 | [5 empty] | 3000
2027-03-26 | JOAW25020001 | CD11-029-P02-06 | 0 | LV01 | 1 | 3000 | 420 | 7.1429 | 0.89286 | 1 | 2 | 8 | [5 empty] | 3000
2027-03-27 | JOAW25020001 | CD11-029-P03-06 | 0 | PP05-060T | 1 | 3000 | 180 | 16.6667 | 2.0833 | 1 | 2 | 8 | [5 empty] | 3000
2027-03-28 | JOAW25020001 | CD11-029-P04-06 | 0 | OPT | 1 | 3000 | 120 | 25 | 3.125 | 1 | 2 | 8 | [5 empty] | 3000
2027-03-29 | JOAW25020001 | CD11-029A-P01-02 | 0 | WS02 | 1 | 39000 | 2700 | 14.4444 | 1.8056 | 1 | 2 | 8 | [5 empty] | 39000
2027-03-30 | JOAW25020001 | CD11-029B-P01-02 | 0 | WS02 | 1 | 81000 | 2700 | 30 | 3.75 | 1 | 2 | 8 | [5 empty] | 81000
2027-03-31 | JOST25010260 | CP08-353&CP08-354-P01-05 | SM | SM01 | 1 | 2800 | 480 | 5.8333 | 0.72917 | 1 | 2 | 8 | [5 empty] | 2800
2027-04-01 | JOST25010260 | CP08-353&CP08-354-P02-05 | ST-4 | PP25-160T | 1 | 2800 | 300 | 9.3333 | 1.1667 | 1 | 2 | 8 | [5 empty] | 2800
2027-04-02 | JOST25010260 | CP08-353&CP08-354-P03-05 | ST-4 | PP20-110T | 1 | 2800 | 300 | 9.3333 | 1.1667 | 1 | 2 | 8 | [5 empty] | 2800
2027-04-03 | JOST25010260 | CP08-353&CP08-354-P04-05 | ST-4 | PP28-110T | 1 | 2800 | 300 | 9.3333 | 1.1667 | 1 | 2 | 8 | [5 empty] | 2800
2027-04-04 | JOTP25010219 | CP08-609-P01-05 | TR | TM03 | 1 | 108 | 30 | 3.6 | 0.45 | 1 | 2 | 8 | [5 empty] | 108
2027-04-05 | JOTP25010219 | CP08-609-P02-05 | ST | PP31 | 1 | 108 | 120 | 0.9 | 0.1125 | 1 | 2 | 8 | [5 empty] | 108
2027-04-06 | JOTP25010219 | CP08-609-P03-05 | ST | PP31 | 1 | 108 | 120 | 0.9 | 0.1125 | 1 | 2 | 8 | [5 empty] | 108
2027-04-07 | JOTP25010219 | CP08-609-P04-05 | PB | PB07 | 1 | 108 | 60 | 1.8 | 0.225 | 1 | 2 | 8 | [5 empty] | 108
2027-04-08 | JOTP25010052 | CP08-415-P01-04 | ST-3 | SW09 | 1 | 640 | 60 | 10.6667 | 1.3333 | 1 | 2 | 8 | [5 empty] | 640
2027-04-09 | JOTP25010052 | CP08-415-P02-04 | ST-1 | PAINTING | 1 | 640 | 30 | 21.3333 | 2.6667 | 1 | 2 | 8 | [5 empty] | 640
2027-04-10 | JOTP25010052 | CP08-415-P03-04 | ST-3 | CLEAN | 1 | 640 | 30 | 21.3333 | 2.6667 | 1 | 2 | 8 | [5 empty] | 640
2027-04-11 | JOAW25010149 | CD06-006-P01-04 | FM | FM02 | 1 | 12500 | 2400 | 5.2083 | 0.65104 | 1 | 2 | 8 | [5 empty] | 12500
2027-04-12 | JOTP25010224 | CT10-026-P01-04 | TP | SW09 | 1 | 120 | 12 | 10 | 1.25 | 1 | 2 | 8 | [5 empty] | 120
2027-04-13 | JOTP25010224 | CT10-026-P02-04 | TP | OPT | 1 | 120 | 6 | 20 | 2.5 | 1 | 2 | 8 | [5 empty] | 120
2027-04-14 | JOTP25010224 | CT10-026-P03-04 | TP | OPT | 1 | 120 | 30 | 4 | 0.5 | 1 | 2 | 8 | [5 empty] | 120
2027-04-15 | JOST25010177 | CP08-428-P01-09 | ST-3 | SW01 | 1 | 280 | 90 | 3.1111 | 0.38889 | 1 | 2 | 8 | [5 empty] | 280
2027-04-16 | JOST25010177 | CP08-428-P02-09 | ST-3 | SW01 | 1 | 280 | 120 | 2.3333 | 0.29167 | 1 | 2 | 8 | [5 empty] | 280
2027-04-17 | JOST25010177 | CP08-428-P03-09 | ST-3 | SW01 | 1 | 280 | 120 | 2.3333 | 0.29167 | 1 | 2 | 8 | [5 empty] | 280
2027-04-18 | JOST25010177 | CP08-428-P04-09 | ST-3 | SW01 | 1 | 280 | 90 | 3.1111 | 0.38889 | 1 | 2 | 8 | [5 empty] | 280
2027-04-19 | JOST25010177 | CP08-428-P05-09 | ST-3 | SW01 | 1 | 280 | 40 | 7 | 0.875 | 1 | 2 | 8 | [5 empty] | 280
2027-04-20 | JOST25010177 | CP08-428-P06-09 | ST-3 | SW01 | 1 | 280 | 30 | 9.3333 | 1.1667 | 1 | 2 | 8 | [5 empty] | 280
2027-04-21 | JOST25010177 | CP08-428-P07-09 | ST-3 | PAINTING | 1 | 280 | 17 | 16.4706 | 2.0588 | 1 | 2 | 8 | [5 empty] | 280
2027-04-22 | JOST25010177 | CP08-428-P08-09 | ST-3 | CLEAN | 1 | 280 | 60 | 4.6667 | 0.58333 | 1 | 2 | 8 | [5 empty] | 280
2027-04-23 | JOTP25010136 | CT10-027-P01-04 | TP | SW09 | 1 | 180 | 45 | 4 | 0.5 | 1 | 2 | 8 | [5 empty] | 180
2027-04-24 | JOTP25010136 | CT10-027-P02-04 | TP | OPT | 1 | 180 | 30 | 6 | 0.75 | 1 | 2 | 8 | [5 empty] | 180
2027-04-25 | JOTP25010136 | CT10-027-P03-04 | TP | OPT | 1 | 180 | 60 | 3 | 0.375 | 1 | 2 | 8 | [5 empty] | 180
2027-04-26 | JOTP25010136 | CV02-066-P02-04 | ST | PP13 | 1 | 8333 | 480 | 17.3604 | 2.1701 | 1 | 2 | 8 | [5 empty] | 8333
2027-04-27 | JOTP25010136 | CV02-066-P03-04 | ST | PP04 | 1 | 83333 | 360 | 231.4806 | 28.9351 | 1 | 2 | 8 | [5 empty] | 83333
2027-04-28 | JOST24100368 | CV04-008-P01-05 | ST-1 | PP14-080T | 1 | 41647 | 1800 | 23.1372 | 2.8922 | 1 | 2 | 8 |  |  |  |  | 6994 | 34653
2027-04-29 | JOST24100368 | CV04-008-P02-05 | ST-2 | PP06-040T | 1 | 41647 | 360 | 115.6861 | 14.4608 | 1 | 2 | 8 |  |  |  |  | 1045 | 40602
2027-04-30 | JOST24100368 | CV04-008-P03-05 | ST-1 | PP11-035T | 1 | 41647 | 360 | 115.6861 | 14.4608 | 1 | 2 | 8 |  |  |  |  | 4 | 41643
2027-05-01 | JOTP25020006 | CP08-569-P01-05 | ST | SM01 | 1 | 240 | 180 | 1.3333 | 0.16667 | 1 | 2 | 8
2027-05-02 | JOTP25020006 | CP08-569-P02-05 | TR | TM05 | 1 | 240 | 38 | 6.3158 | 0.78947 | 1 | 2 | 8
2027-05-03 | JOTP25020006 | CP08-569-P03-05 | PB | PB03 | 1 | 240 | 75 | 3.2 | 0.4 | 1 | 2 | 8
2027-05-04 | JOTP25020006 | CP08-569-P04-05 | PB | PB03 | 1 | 240 | 75 | 3.2 | 0.4 | 1 | 2 | 8
2027-05-05 | JOTP25020005 | CP08-610-P01-07 | TR | TM03 | 1 | 165 | 30 | 5.5 | 0.6875 | 1 | 2 | 8
2027-05-06 | JOTP25020005 | CP08-610-P02-07 | PB | PB02 | 1 | 165 | 180 | 0.91667 | 0.11458 | 1 | 2 | 8
2027-05-07 | JOTP25020005 | CP08-610-P03-07 | PB | PB03 | 1 | 165 | 180 | 0.91667 | 0.11458 | 1 | 2 | 8
2027-05-08 | JOTP25020005 | CP08-610-P04-07 | PB | PB08 | 1 | 165 | 180 | 0.91667 | 0.11458 | 1 | 2 | 8
2027-05-09 | JOTP25020005 | CP08-610-P05-07 | PB | PB04 | 1 | 165 | 180 | 0.91667 | 0.11458 | 1 | 2 | 8
2027-05-10 | JOTP25020005 | CP08-610-P06-07 | PB | PB07 | 1 | 165 | 40 | 4.125 | 0.51562 | 1 | 2 | 8
2027-05-11 | JOST25010073 | CP08-437-P01-05 | SM | SM01 | 1 | 1710 | 5400 | 0.31667 | 0.039583 | 1 | 2 | 8
2027-05-12 | JOST25010073 | CP08-437-P02-05 | ST-1 | PP03-060T | 1 | 1710 | 480 | 3.5625 | 0.44531 | 1 | 2 | 8
2027-05-13 | JOST25010073 | CP08-437-P03-05 | ST-1 | PP03-060T | 1 | 1710 | 360 | 4.75 | 0.59375 | 1 | 2 | 8
2027-05-14 | JOST25010073 | CP08-437-P04-05 | TR | PP22 | 1 | 1710 | 200 | 8.55 | 1.0688 | 1 | 2 | 8
2027-05-15 | JOST25020075 | CT10-001-P01-06 | ST-3 | PP09-160T | 1 | 6080 | 330 | 18.4242 | 2.303 | 1 | 2 | 8 | [5 empty] | 6080 | 18.4242
2027-05-16 | JOST25020075 | CT10-001-P02-06 | ST-3 | PP18 | 1 | 6080 | 330 | 18.4242 | 2.303 | 1 | 2 | 8 | [5 empty] | 6080 | 18.4242
2027-05-17 | JOST25020075 | CT10-001-P03-06 | ST-3 | PP17-110T | 1 | 6080 | 330 | 18.4242 | 2.303 | 1 | 2 | 8 | [5 empty] | 6080 | 18.4242
2027-05-18 | JOST25020075 | CT10-001-P04-06 | ST-3 | PP16-110T | 1 | 6080 | 330 | 18.4242 | 2.303 | 1 | 2 | 8 | [5 empty] | 6080 | 18.4242
2027-05-19 | JOST25020075 | CT10-001-P05-06 | ST-3 | PP27-110T | 1 | 6080 | 330 | 18.4242 | 2.303 | 1 | 2 | 8 | [5 empty] | 6080 | 18.4242
2027-05-20 | JOST25020008 | CP08-032-P01-03 | ST-3 | PP09-160T | 1 | 804 | 300 | 2.68 | 0.335 | 1 | 2 | 8 | [5 empty] | 804
2027-05-21 | JOST25020008 | CP08-032-P02-03 | ST-3 | PP16-110T | 1 | 804 | 300 | 2.68 | 0.335 | 1 | 2 | 8
2027-05-22 | JOAW25020058 | CP08-556B-P01-05 | WN | WS01 | 1 | 200 | 600 | 0.33333 | 0.041667 | 1 | 2 | 8
2027-05-23 | JOAW25020058 | CP08-556B-P02-05 | WN | JIG BENDING | 1 | 200 | 180 | 1.1111 | 0.13889 | 1 | 2 | 8
2027-05-24 | JOAW25020058 | CP08-556B-P03-05 | WN | JIG BENDING | 1 | 200 | 180 | 1.1111 | 0.13889 | 1 | 2 | 8
2027-05-25 | JOAW25020058 | CP08-556B-P04-05 | WN | PP23-060T | 1 | 200 | 120 | 1.6667 | 0.20833 | 1 | 2 | 8
2027-05-26 | JOAW25020059 | CP08-556C-P01-03 | WN | WS01 | 1 | 400 | 4800 | 0.083333 | 0.010417 | 1 | 2 | 8
2027-05-27 | JOAW25020059 | CP08-556C-P02-03 | 0 | JIG BENDING | 1 | 400 | 120 | 3.3333 | 0.41667 | 1 | 2 | 8
2027-05-28 | JOAW25020060 | CP08-556D-P01-02 | WN | WS01 | 1 | 2000 | 5700 | 0.35088 | 0.04386 | 1 | 2 | 8
2027-05-29 | JOAW25020061 | CP08-556E-P01-02 | WN | WS01 | 1 | 1000 | 600 | 1.6667 | 0.20833 | 1 | 2 | 8
2027-05-30 | JOST25020152 | CP08-602-P01-04 | ST | PP33 | 1 | 173 | 120 | 1.4417 | 0.18021 | 1 | 2 | 8
2027-05-31 | JOST25020152 | CP08-602-P02-04 | ST | PP33 | 1 | 173 | 120 | 1.4417 | 0.18021 | 1 | 2 | 8
2027-06-01 | JOST25020152 | CP08-602-P03-04 | ST | PP33 | 1 | 173 | 120 | 1.4417 | 0.18021 | 1 | 2 | 8
2027-06-02 | JOST25020010 | CP08-120-P01-04 | ST | SM01 | 1 | 90 | 240 | 0.375 | 0.046875 | 1 | 2 | 8
2027-06-03 | JOST25020010 | CP08-120-P02-04 | ST | PP04 | 1 | 90 | 240 | 0.375 | 0.046875 | 1 | 2 | 8
2027-06-04 | JOST25020010 | CP08-120-P03-04 | ST | PP04 | 1 | 90 | 240 | 0.375 | 0.046875 | 1 | 2 | 8
2027-06-05 | JOAW25020134 | CS18-007A-P01-04 | WN | WS01 | 1 | 600 | 900 | 0.66667 | 0.083333 | 1 | 2 | 8
2027-06-06 | JOAW25020134 | CS18-007A-P02-04 | WN | JIG BENDING | 1 | 600 | 180 | 3.3333 | 0.41667 | 1 | 2 | 8
2027-06-07 | JOAW25020134 | CS18-007A-P03-04 | WN | PP23-060T | 1 | 600 | 240 | 2.5 | 0.3125 | 1 | 2 | 8
2027-06-08 | JOAW25020135 | CS18-007B-P01-02 | WN | WS01 | 1 | 600 | 600 | 1 | 0.125 | 1 | 2 | 8
2027-06-09 | JOAW25020136 | CS18-007C-P01-02 | WN | WS01 | 1 | 800 | 720 | 1.1111 | 0.13889 | 1 | 2 | 8
2027-06-10 | JOAW25020137 | CS18-007D-P01-03 | WN | WS01 | 1 | 200 | 600 | 0.33333 | 0.041667 | 1 | 2 | 8
2027-06-11 | JOAW25020137 | CS18-007D-P02-03 | WN | JIG BENDING | 1 | 200 | 120 | 1.6667 | 0.20833 | 1 | 2 | 8
2027-06-12 | JOAW25020099 | CA25-001-P01-04 | AL | CM03 | 1 | 4250 | 72 | 59.0278 | 7.3785 | 1 | 2 | 8
2027-06-13 | JOAW25020099 | CA25-001-P02-04 | AL | BDS01 | 1 | 4250 | 600 | 7.0833 | 0.88542 | 1 | 2 | 8
2027-06-14 | JOAW25020099 | CA25-001-P03-04 | AL | ALDG | 1 | 4250 | 1200 | 3.5417 | 0.44271 | 1 | 2 | 8
2027-06-15 | JOAW25020143 | CU01-002-P01-04 | 0 | CM05 | 1 | 990 | 150 | 6.6 | 0.825 | 1 | 2 | 8
2027-06-16 | JOAW25020143 | CU01-002-P02-04 | 0 | BDS01 | 1 | 990 | 600 | 1.65 | 0.20625 | 1 | 2 | 8
2027-06-22 | JOST25020044 | CP08-509-P01-04 | ST-3 | PP17-110T | 1 | 6094 | 360 | 16.9278 | 2.116 | 1 | 2 | 8
2027-06-23 | JOST25020044 | CP08-509-P02-04 | ST-3 | PP16-110T | 1 | 6094 | 360 | 16.9278 | 2.116 | 1 | 2 | 8
2027-06-24 | JOST25020044 | CP08-509-P03-04 | ST-3 | PP27-110T | 1 | 6094 | 360 | 16.9278 | 2.116 | 1 | 2 | 8
2027-06-25 | JOAW25020067 | CP08-572-P01-03 | FM | FM02 | 1 | 100000 | 1260 | 79.3651 | 9.9206 | 1 | 2 | 8
2027-06-27 | JOST25020091 | CT10-015-P01-05 | ST-4 | PP24-160T | 1 | 14400 | 360 | 40 | 5 | 1 | 2 | 8
2027-06-28 | JOST25020091 | CT10-015-P02-05 | ST-4 | PP25-160T | 1 | 14400 | 360 | 40 | 5 | 1 | 2 | 8
2027-06-29 | JOST25020091 | CT10-015-P03-05 | ST-4 | PP20-110T | 1 | 14400 | 360 | 40 | 5 | 1 | 2 | 8
2027-06-30 | JOST25020091 | CT10-015-P04-05 | ST-4 | PP28-110T | 1 | 14400 | 360 | 40 | 5 | 1 | 2 | 8
2027-07-01 | JOTP25020157 | CU01-055A-P01-03 | TP | TM03 | 1 | 105 | 18 | 5.8333 | 0.72917 | 1 | 2 | 8
2027-07-02 | JOTP25020157 | CU01-055A-P02-03 | PB | PB07 | 1 | 105 | 45 | 2.3333 | 0.29167 | 1 | 2 | 8
2027-07-03 | JOTP25020156 | CU01-054B-P01-03 | TP | TM03 | 1 | 300 | 120 | 2.5 | 0.3125 | 1 | 2 | 8
2027-07-04 | JOTP25020156 | CU01-054B-P02-03 | PB | PB02 | 1 | 300 | 180 | 1.6667 | 0.20833 | 1 | 2 | 8
2027-07-05 | JOTP25020155 | CU01-054F-P01-02 | PB | SW09 | 1 | 205 | 60 | 3.4167 | 0.42708 | 1 | 2 | 8
2027-07-06 | JOTP25020154 | CU01-054E-P01-02 | PB | SW09 | 1 | 210 | 60 | 3.5 | 0.4375 | 1 | 2 | 8
2027-07-07 | JOAW25020153 | CC02-007-P01-04 | FM | FM02 | 1 | 23455 | 3000 | 7.8183 | 0.97729 | 1 | 2 | 8
2027-07-08 | JOAW25020153 | CC02-007-P02-04 | 0 | 0 | 1 | 23455 | 0 |  |  | 1 | 2 | 8
2027-07-09 | JOAW25020153 | CC02-007-P03-04 | 0 | 0 | 1 | 23455 | 0 |  |  | 1 | 2 | 8
2027-07-10 | JOAW25020150 | CM03-001-P01-04 | FM | FM02 | 1 | 43145 | 1080 | 39.9491 | 4.9936 | 1 | 2 | 8
2027-07-11 | JOAW25020150 | CM03-001-P02-04 | ST | VM04 | 1 | 43145 | 250 | 172.58 | 21.5725 | 1 | 2 | 8
2027-07-12 | JOAW25020150 | CM03-001-P03-04 | AL | CHECKING | 1 | 43145 | 250 | 172.58 | 21.5725 | 1 | 2 | 8
2027-07-13 | JOAW25020142 | CS18-008D-P01-03 | WN | WS01 | 1 | 200 | 480 | 0.41667 | 0.052083 | 1 | 2 | 8
2027-07-14 | JOAW25020142 | CS18-008D-P02-03 | WN | JIG BENDING | 1 | 200 | 240 | 0.83333 | 0.10417 | 1 | 2 | 8
2027-07-15 | JOAW25020141 | CS18-008C-P01-02 | WN | WS01 | 1 | 800 | 720 | 1.1111 | 0.13889 | 1 | 2 | 8
2027-07-16 | JOAW25020140 | CS18-008B-P01-02 | WN | WS01 | 1 | 600 | 900 | 0.66667 | 0.083333 | 1 | 2 | 8
2027-07-17 | JOAW25020139 | CS18-008A-P01-04 | WN | WS01 | 1 | 600 | 1200 | 0.5 | 0.0625 | 1 | 2 | 8
2027-07-18 | JOAW25020139 | CS18-008A-P02-04 | WN | JIG BENDING | 1 | 600 | 340 | 1.7647 | 0.22059 | 1 | 2 | 8
2027-07-19 | JOAW25020139 | CS18-008A-P03-04 | WN | PP23-060T | 1 | 600 | 480 | 1.25 | 0.15625 | 1 | 2 | 8
2027-07-20 | JOAW25020104 | CD11-002C-P01-02 | WN | WS01 | 1 | 7200 | 3000 | 2.4 | 0.3 | 1 | 2 | 8
2027-07-21 | JOAW25020103 | CD11-002B-P01-02 | WN | WS01 | 1 | 79200 | 3000 | 26.4 | 3.3 | 1 | 2 | 8
2027-07-22 | JOAW25020102 | CD11-002A-P01-02 | WN | WS01 | 1 | 136800 | 3000 | 45.6 | 5.7 | 1 | 2 | 8
2027-07-23 | JOST25020097 | CT10-025-P01-06 | ST-3 | PP09-160T | 1 | 2128 | 330 | 6.4485 | 0.80606 | 1 | 2 | 8
2027-07-24 | JOST25020097 | CT10-025-P02-06 | ST-3 | PP18-150T | 1 | 2128 | 330 | 6.4485 | 0.80606 | 1 | 2 | 8
2027-07-25 | JOST25020097 | CT10-025-P03-06 | ST-3 | PP17-110T | 1 | 2128 | 330 | 6.4485 | 0.80606 | 1 | 2 | 8
2027-07-26 | JOST25020097 | CT10-025-P04-06 | ST-3 | PP16-110T | 1 | 2128 | 330 | 6.4485 | 0.80606 | 1 | 2 | 8
2027-07-27 | JOST25020097 | CT10-025-P05-06 | ST-3 | PP27-110T | 2 | 2128 | 330 | 6.4485 | 0.80606 | 1 | 2 | 8
2027-07-28 | JOST25020092 | CT10-015-P01-05 | ST-4 | PP24-160T | 1 | 14400 | 360 | 40 | 5 | 1 | 2 | 8
2027-07-29 | JOST25020092 | CT10-015-P02-05 | ST-4 | PP25-160T | 1 | 14400 | 360 | 40 | 5 | 1 | 2 | 8
2027-07-30 | JOST25020092 | CT10-015-P03-05 | ST-4 | PP20-110T | 1 | 14400 | 360 | 40 | 5 | 1 | 2 | 8
2027-07-31 | JOST25020092 | CT10-015-P04-05 | ST-4 | PP28-110T | 1 | 14400 | 360 | 40 | 5 | 1 | 2 | 8
2027-08-01 | JOST25020039 | CP08-499A-P01-06 | ST-4 | PP29-250T | 1 | 630 | 120 | 5.25 | 0.65625 | 1 | 2 | 8
2027-08-02 | JOST25020039 | CP08-499A-P02-06 | ST-4 | PP30 | 1 | 630 | 120 | 5.25 | 0.65625 | 1 | 2 | 8
2027-08-03 | JOST25020039 | CP08-499A-P03-06 | ST-3 | TP03 | 1 | 630 | 120 | 5.25 | 0.65625 | 1 | 2 | 8
2027-08-04 | JOST25020039 | CP08-499A-P04-06 | AL | TP09 | 1 | 630 | 120 | 5.25 | 0.65625 | 1 | 2 | 8
2027-08-05 | JOST25020039 | CP08-499A-P05-06 | TR | PB05 | 1 | 630 | 60 | 10.5 | 1.3125 | 1 | 2 | 8
2027-08-06 | JOST25020041 | CP08-499B-P01-04 | 0 | PP30-200T | 1 | 722 | 180 | 4.0111 | 0.50139 | 1 | 2 | 8
2027-08-07 | JOST25020041 | CP08-499B-P02-04 | 0 | PP21 | 1 | 722 | 180 | 4.0111 | 0.50139 | 1 | 2 | 8
2027-08-08 | JOST25020041 | CP08-499B-P03-04 | 0 | PP30-200T | 1 | 722 | 180 | 4.0111 | 0.50139 | 1 | 2 | 8
2027-08-09 | JOST25020076 | CT10-001-P01-06 | ST-3 | PP09-160T | 1 | 6080 | 330 | 18.4242 | 2.303 | 1 | 2 | 8
2027-08-10 | JOST25020076 | CT10-001-P02-06 | ST-3 | PP18 | 1 | 6080 | 330 | 18.4242 | 2.303 | 1 | 2 | 8
2027-08-11 | JOST25020076 | CT10-001-P03-06 | ST-3 | PP17-110T | 1 | 6080 | 330 | 18.4242 | 2.303 | 1 | 2 | 8
2027-08-12 | JOST25020076 | CT10-001-P04-06 | ST-3 | PP16-110T | 1 | 6080 | 330 | 18.4242 | 2.303 | 1 | 2 | 8
2027-08-13 | JOST25020076 | CT10-001-P05-06 | ST-3 | PP27-110T | 2 | 6080 | 330 | 18.4242 | 2.303 | 1 | 2 | 8
2027-08-14 | JOST25020089 | CT10-014-P01-06 | ST-3 | PP09-160T | 1 | 1824 | 330 | 5.5273 | 0.69091 | 1 | 2 | 8 | [5 empty] | 1824
2027-08-15 | JOST25020089 | CT10-014-P02-06 | ST-3 | PP18 | 1 | 1824 | 330 | 5.5273 | 0.69091 | 1 | 2 | 8 | [5 empty] | 1824
2027-08-16 | JOST25020089 | CT10-014-P03-06 | ST-3 | PP17-110T | 1 | 1824 | 330 | 5.5273 | 0.69091 | 1 | 2 | 8 | [5 empty] | 1824
2027-08-17 | JOST25020089 | CT10-014-P04-06 | ST-3 | PP16-110T | 1 | 1824 | 330 | 5.5273 | 0.69091 | 1 | 2 | 8 | [5 empty] | 1824
2027-08-18 | JOST25020089 | CT10-014-P05-06 | ST-3 | PP27-110T | 2 | 1824 | 330 | 5.5273 | 0.69091 | 1 | 2 | 8 | [5 empty] | 1824
2027-08-19 | JOAW25020057 | CP08-556-P01-09 | TR | SW04 | 1 | 200 | 16.7 | 11.976 | 1.497 | 1 | 2 | 8
2027-08-20 | JOAW25020057 | CP08-556-P02-09 | WN | TW02 | 1 | 200 | 60 | 3.3333 | 0.41667 | 1 | 2 | 8
2027-08-21 | JOAW25020057 | CP08-556-P03-09 | TR | PB07 | 1 | 200 | 60 | 3.3333 | 0.41667 | 1 | 2 | 8
2027-08-22 | JOAW25020057 | CP08-556-P04-09 | WN | SW06 | 1 | 200 | 60 | 3.3333 | 0.41667 | 1 | 2 | 8
2027-08-23 | JOAW25020057 | CP08-556-P05-09 | WN | OPT | 1 | 200 | 50 | 4 | 0.5 | 1 | 2 | 8
2027-08-24 | JOAW25020057 | CP08-556-P06-09 | WN | OPT | 1 | 200 | 50 | 4 | 0.5 | 1 | 2 | 8
2027-08-26 | JOAW25020057 | CP08-556-P08-09 | WN | CHECKING | 1 | 200 | 8 | 25 | 3.125 | 1 | 2 | 8
2027-08-27 | JOTP25020086 | CT10-009B-P01-06 | TR | TM03 | 1 | 1144 | 90 | 12.7111 | 1.5889 | 1 | 2 | 8
2027-08-28 | JOTP25020086 | CT10-009B-P02-06 | ST-1 | PP31 | 1 | 1144 | 360 | 3.1778 | 0.39722 | 1 | 2 | 8
2027-08-29 | JOTP25020086 | CT10-009B-P03-06 | ST-1 | PP31 | 1 | 1144 | 360 | 3.1778 | 0.39722 | 1 | 2 | 8
2027-08-30 | JOTP25020086 | CT10-009B-P04-06 | ST-3 | TP03 | 1 | 1144 | 120 | 9.5333 | 1.1917 | 1 | 2 | 8
2027-08-31 | JOTP25020086 | CT10-009B-P05-06 | TR | PB01 | 1 | 1144 | 120 | 9.5333 | 1.1917 | 1 | 2 | 8
2027-09-01 | JOTP25020087 | CT10-009C-P01-07 | TR | TM03 | 1 | 520 | 36 | 14.4444 | 1.8056 | 1 | 2 | 8
2027-09-02 | JOTP25020087 | CT10-009C-P02-07 | TR | PB02 | 1 | 520 | 100 | 5.2 | 0.65 | 1 | 2 | 8
2027-09-03 | JOTP25020087 | CT10-009C-P03-07 | TR | PB03 | 1 | 520 | 100 | 5.2 | 0.65 | 1 | 2 | 8
2027-09-04 | JOTP25020087 | CT10-009C-P04-07 | TR | PB04 | 1 | 520 | 40 | 13 | 1.625 | 1 | 2 | 8
2027-09-05 | JOTP25020087 | CT10-009C-P05-07 | TR | PB05 | 1 | 520 | 50 | 10.4 | 1.3 | 1 | 2 | 8
2027-09-06 | JOTP25020087 | CT10-009C-P06-07 | TR | SW09 | 0 | 520 | 35 | 14.8571 | 1.8571 | 1 | 2 | 8
2027-09-07 | JOST25020014 | CP08-219B-P01-04 | SM | SM01 | 1 | 3588 | 9360 | 0.38333 | 0.047917 | 1 | 2 | 8
2027-09-08 | JOST25020014 | CP08-219B-P02-04 | ST-2 | PP13-060T | 1 | 3588 | 600 | 5.98 | 0.7475 | 1 | 2 | 8
2027-09-09 | JOST25020014 | CP08-219B-P03-04 | ST-1 | PP03-060T | 1 | 3588 | 360 | 9.9667 | 1.2458 | 1 | 2 | 8
2027-09-10 | JOST25020161 | CM03-040-P01-02 | ST-4 | PP30-200T | 1 | 18116 | 1200 | 15.0967 | 1.8871 | 1 | 2 | 8
2027-09-12 | JOTP25020195 | CP08-608A-P01-03 | TR | TM03 | 1 | 99 | 60 | 1.65 | 0.20625 | 1 | 2 | 8
2027-09-13 | JOTP25020195 | CP08-608A-P02-03 | PB | PB07 | 1 | 99 | 50.4 | 1.9643 | 0.24554 | 1 | 2 | 8
2027-09-14 | JOST25020209 | CP08-600-P01-03 | ST | PP29 | 1 | 146 | 120 | 1.2167 | 0.15208 | 1 | 2 | 8
2027-09-15 | JOST25020209 | CP08-600-P02-03 | ST | PP33 | 1 | 146 | 120 | 1.2167 | 0.15208 | 1 | 2 | 8
2027-09-16 | JOST25020167 | CP08-031-P01-04 | ST-3 | PP09-160T | 1 | 906 | 240 | 3.775 | 0.47187 | 1 | 2 | 8
2027-09-18 | JOST25020167 | CP08-031-P02-04 | ST-3 | PP16-110T | 1 | 906 | 240 | 3.775 | 0.47187 | 1 | 2 | 8
2027-09-19 | JOST25020167 | CP08-031-P03-04 | ST-3 | PP27-110T | 1 | 906 | 240 | 3.775 | 0.47187 | 1 | 2 | 8
2027-09-21 | JOTP25020194 | CP08-608A-P01-03 | TR | TM03 | 1 | 99 | 60 | 1.65 | 0.20625 | 1 | 2 | 8
2027-09-22 | JOTP25020194 | CP08-608A-P02-03 | PB | PB07 | 1 | 99 | 50.4 | 1.9643 | 0.24554 | 1 | 2 | 8
2027-09-23 | JOST25020207 | CA24-002-P01-03 | ST-2 | PP19-110T | 1 | 10576 | 1800 | 5.8756 | 0.73444 | 1 | 2 | 8
2027-09-24 | JOST25020207 | CA24-002-P02-03 | ST-1 | PP05-060T | 1 | 10576 | 240 | 44.0667 | 5.5083 | 1 | 2 | 8
2027-09-25 | JOST25020207 | CA24-002-P03-04 | ST-2 | VM01 | 1 | 10576 | 1000 | 10.576 | 1.322 | 1 | 2 | 8
2027-09-26 | JOST25020016 | CP08-305-P01-03 | ST-2 | PP10-080T | 1 | 1041 | 1500 | 0.694 | 0.08675 | 1 | 2 | 8
2027-09-27 | JOST25020016 | CP08-305-P02-03 | AL | TP04 | 1 | 1041 | 300 | 3.47 | 0.43375 | 1 | 2 | 8