## Jobs PlanningDetails
VP/PRD/PI.F12
Rev :01
Date : 15/08/24
Date Print :
LCD_DATE | JOBCODE | PROCESS_CODE | RSC LOCATION *Filter Check Mc Availability* Any Job Crash* '=IFERROR(VLOOKUP(C3,MasterProcess!G:O,8,FALSE),0) | MACHINE_ID | NUMBER_OPERATOR | JOB_EXPECT | OUTPUT_PER_HOUR | HOURS NEEDED | DAYS NEEDED 16hrs | SETTING_HOUR | BREAK_HOUR | NO_PRODUCTION_HOUR | PLANNED_START | PLANNED_END | LATEST COMPLETION DATE | Accumulated Actual Daily Output Qty | Bal Qty | BAL HR | BAL DAYS | PRIORITY
2024-09-24 | JOAW24090215 | CD11-027-P05-06 | WN | TW01 | 1 | 10000 | 400 | 25 | 1.0417 | 0.041667 | 0.083333 | 0.33333 | 2024-11-13 08:30 | 2024-11-14 20:30 | 25/12/2024 8:30:00 AM | 9969 | 31 |  |  | 1
2024-12-02 | JOST24120021 | CM10-009-P04-05 | AL | CHECKING | 1 | 41613 | 1200 | 34.6775 | 4.3347 | 0.041667 | 0.083333 | 0.33333 | 2024-12-23 08:30 | 2024-12-28 03:32 | 2025-01-30 08:30 | 17400 | 24213 |  |  | 2
2024-12-06 | JOAW24120118 | CD11-026-P05-06 | WN | TW01 | 1 | 15000 | 420 | 35.7143 | 4.4643 | 0.041667 | 0.083333 | 0.33333 | 2025-01-09 08:30 | 2025-01-14 06:39 | 2025-02-16 08:30 |  | 15000 |  |  | 3
2024-12-18 | JOAW24120201 | CM03-001-P02-04 | ST | VM04 | 1 | 100806 | 250 | 403.224 | 50.403 | 0.041667 | 0.083333 | 0.33333 | 2025-01-10 08:30 | 2025-03-02 05:10 | 2025-02-24 08:30 | 100806 | 0 |  |  | 1
2024-12-18 | JOAW24120201 | CM03-001-P03-04 | AL | CHECKING | 1 | 100806 | 250 | 403.224 | 50.403 | 0.041667 | 0.083333 | 0.33333 | 2025-01-10 08:30 | 2025-03-02 05:10 | 2025-02-24 08:30 | 57547 | 43259 |  |  | 2
2024-12-18 | JOST24120090 | CP08-544-P01-02 | ST | STICK LABEL | 1 | 1100 | 30 | 36.6667 | 4.5833 | 0.041667 | 0.083333 | 0.33333 | 2025-01-13 08:30 | 2025-01-18 09:30 | 2025-01-27 08:30 | 428 | 672 |  |  | 3
2024-12-22 | JOST24120092 | CP08-545-P01-02 | ST | STICK LABEL | 1 | 500 | 18 | 27.7778 | 3.4722 | 0.041667 | 0.083333 | 0.33333 | 2025-01-23 08:30 | 2025-01-27 06:50 | 2025-02-06 08:30 |  | 500 |  |  | 1
2024-12-22 | JOST24120047 | CP08-046-P03-04 | AL | CHECKING | 1 | 30120 | 1800 | 16.7333 | 2.0917 | 0.041667 | 0.083333 | 0.33333 | 2025-01-17 08:30 | 2025-01-19 21:42 | 2025-02-25 08:30 |  | 30120 |  |  | 3
2024-12-22 | JOTP24110201 | CP08-553-P05-07 | TR | PAINTING | 1 | 252 | 12 | 21 | 2.625 | 0.041667 | 0.083333 | 0.33333 | 2025-01-20 08:30 | 2025-01-23 10:30 | 2025-02-03 08:30 | 211 | 41 |  |  | 2
2024-12-22 | JOTP24110201 | CP08-553-P06-07 | TR | PACK & LABEL | 1 | 252 | 12 | 21 | 2.625 | 0.041667 | 0.083333 | 0.33333 | 2025-01-20 08:30 | 2025-01-23 10:30 | 2025-02-03 08:30 | 182 | 70 |  |  | 3
2024-12-30 | JOST24120179 | CP08-289-P04-06 | ST-4 | TP08 | 1 | 28632 | 360 | 79.5333 | 9.9417 | 0.041667 | 0.083333 | 0.33333 | 2025-01-24 08:30 | 2025-02-03 18:06 | 2025-02-28 08:30 | 5990 | 22642 |  |  | 1
2024-12-30 | JOST24120179 | CP08-289-P05-06 | AL | CHECKING | 1 | 28632 | 360 | 79.5333 | 9.9417 | 0.041667 | 0.083333 | 0.33333 | 2025-01-24 08:30 | 2025-02-03 18:06 | 2025-02-28 08:30 | 5990 | 22642 |  |  | 2
2025-01-02 | JOST24120433 | CH04-002-P01-07 | ST-3 | PP25 | 1 | 5900 | 300 | 19.6667 | 2.4583 | 0.041667 | 0.083333 | 0.33333 | 2025-01-24 08:30 | 2025-01-27 06:30 | 2025-02-14 08:30 |  | 5900 |  |  | 3
2025-01-02 | JOST24120433 | CH04-002-P02-07 | ST-3 | PP26-110T | 1 | 5900 | 300 | 19.6667 | 2.4583 | 0.041667 | 0.083333 | 0.33333 | 2025-01-24 08:30 | 2025-01-27 06:30 | 2025-02-14 08:30 |  | 5900 |  |  | 2
2025-01-02 | JOST24120433 | CH04-002-P03-07 | ST-3 | PP20 | 1 | 5900 | 300 | 19.6667 | 2.4583 | 0.041667 | 0.083333 | 0.33333 | 2025-01-24 08:30 | 2025-01-27 06:30 | 2025-02-14 08:30 |  | 5900 |  |  | 2
2025-01-02 | JOST24120433 | CH04-002-P04-07 | ST-3 | PP28-110T | 1 | 5900 | 300 | 19.6667 | 2.4583 | 0.041667 | 0.083333 | 0.33333 | 2025-01-24 08:30 | 2025-01-27 06:30 | 2025-02-14 08:30 |  | 5900 |  |  | 2
2025-01-02 | JOST24120433 | CH04-002-P05-07 | ST-3 | SW01 | 1 | 5900 | 300 | 19.6667 | 2.4583 | 0.041667 | 0.083333 | 0.33333 | 2025-01-24 08:30 | 2025-01-27 06:30 | 2025-02-14 08:30 |  | 5900 |  |  | 2
2025-01-02 | JOST24120433 | CH04-002-P06-07 | ST-1 | OPT PAINTING | 1 | 5900 | 120 | 49.1667 | 6.1458 | 0.041667 | 0.083333 | 0.33333 | 2025-01-24 08:30 | 2025-01-30 23:00 | 2025-02-14 08:30 |  | 5900 |  |  | 1
2025-01-03 | JOST24120408 | CT10-001-P01-06 | ST-3 | PP09-160T | 1 | 6080 | 330 | 18.4242 | 2.303 | 0.041667 | 0.083333 | 0.33333 | 2025-01-27 08:30 | 2025-01-30 02:46 | 2025-02-07 08:30 | 6042 | 38 |  |  | 3
2025-01-03 | JOST24120408 | CT10-001-P02-06 | ST-3 | PP18 | 1 | 6080 | 330 | 18.4242 | 2.303 | 0.041667 | 0.083333 | 0.33333 | 2025-01-27 08:30 | 2025-01-30 02:46 | 2025-02-07 08:30 | 6042 | 38 |  |  | 2
2025-01-03 | JOST24120408 | CT10-001-P03-06 | ST-3 | PP17-110T | 1 | 6080 | 330 | 18.4242 | 2.303 | 0.041667 | 0.083333 | 0.33333 | 2025-01-27 08:30 | 2025-01-30 02:46 | 2025-02-07 08:30 | 6042 | 38 |  |  | 3
2025-01-03 | JOST24120408 | CT10-001-P04-06 | ST-3 | PP16-110T | 1 | 6080 | 330 | 18.4242 | 2.303 | 0.041667 | 0.083333 | 0.33333 | 2025-01-27 08:30 | 2025-01-30 02:46 | 2025-02-07 08:30 | 6042 | 38 |  |  | 3
2025-01-03 | JOST24120408 | CT10-001-P05-06 | ST-3 | PP27-110T | 2 | 6080 | 330 | 18.4242 | 2.303 | 0.041667 | 0.083333 | 0.33333 | 2025-01-27 08:30 | 2025-01-30 02:46 | 2025-02-07 08:30 | 6042 | 38 |  |  | 3
2025-01-03 | JOAW24120119 | CD11-026-P05-06 | WN | TW01 | 1 | 15000 | 420 | 35.7143 | 4.4643 | 0.041667 | 0.083333 | 0.33333 | 2025-01-30 08:30 | 2025-02-04 06:39 | 2025-03-09 08:30 |  | 15000 |  |  | 3
2025-01-03 | JOAW24120383 | CP08-557-P08-09 | AL | CHECKING | 1 | 1000 | 15 | 66.6667 | 8.3333 | 0.041667 | 0.083333 | 0.33333 | 2025-01-24 08:30 | 2025-02-02 03:30 | 2025-02-24 08:30 |  | 1000 |  |  | 2
2025-01-03 | JOST24120359 | CP08-504A-P02-04 | ST-4 | PP24-160T | 1 | 216 | 300 | 0.72 | 0.09 | 0.041667 | 0.083333 | 0.33333 | 2025-01-27 08:30 | 2025-01-27 21:40 | 2025-02-10 08:30 |  | 216 |  |  | 2
2025-01-03 | JOST24120359 | CP08-504A-P03-04 | ST-4 | PP24-160T | 1 | 216 | 300 | 0.72 | 0.09 | 0.041667 | 0.083333 | 0.33333 | 2025-01-27 08:30 | 2025-01-27 21:40 | 2025-02-10 08:30 |  | 216 |  |  | 2
2025-01-03 | JOST24120337 | CP08-352-P02-04 | ST-4 | PP26-110T | 1 | 5440 | 360 | 15.1111 | 1.8889 | 0.041667 | 0.083333 | 0.33333 | 2025-01-27 08:30 | 2025-01-29 16:50 | 2025-02-10 08:30 |  | 5440 |  |  | 3
2025-01-03 | JOST24120337 | CP08-352-P03-04 | ST-4 | PP28-110T | 1 | 5440 | 360 | 15.1111 | 1.8889 | 0.041667 | 0.083333 | 0.33333 | 2025-01-27 08:30 | 2025-01-29 16:50 | 2025-02-10 08:30 |  | 5440 |  |  | 3
2025-01-03 | JOST24120338 | CP08-353&CP08-354-P01-05 | SM | SM01 | 1 | 2800 | 480 | 5.8333 | 0.72917 | 0.041667 | 0.083333 | 0.33333 | 2025-01-31 08:30 | 2025-02-01 13:00 | 2025-02-14 08:30 |  | 2800 |  |  | 1
2025-01-03 | JOST24120338 | CP08-353&CP08-354-P02-05 | ST-4 | PP25-160T | 1 | 2800 | 300 | 9.3333 | 1.1667 | 0.041667 | 0.083333 | 0.33333 | 2025-01-31 08:30 | 2025-02-01 23:30 | 2025-02-14 08:30 |  | 2800 |  |  | 1
2025-01-03 | JOST24120338 | CP08-353&CP08-354-P03-05 | ST-4 | PP20-110T | 1 | 2800 | 300 | 9.3333 | 1.1667 | 0.041667 | 0.083333 | 0.33333 | 2025-01-31 08:30 | 2025-02-01 23:30 | 2025-02-14 08:30 |  | 2800 |  |  | 3
2025-01-03 | JOST24120338 | CP08-353&CP08-354-P04-05 | ST-4 | PP28-110T | 1 | 2800 | 300 | 9.3333 | 1.1667 | 0.041667 | 0.083333 | 0.33333 | 2025-01-31 08:30 | 2025-02-01 23:30 | 2025-02-14 08:30 |  | 2800 |  |  | 1
2025-01-03 | JOST24120326 | CP08-265-P03-04 | ST-2 | PP06-040T | 1 | 3142 | 240 | 13.0917 | 1.6365 | 0.041667 | 0.083333 | 0.33333 | 2025-01-10 08:30 | 2025-01-12 10:46 | 2025-01-22 08:30 | 142 | 3000 |  |  | 2
2025-01-07 | JOST24120418 | CT10-015-P01-05 | ST-4 | PP24-160T | 1 | 14400 | 360 | 40 | 5 | 0.041667 | 0.083333 | 0.33333 | 2025-02-03 08:30 | 2025-02-08 19:30 | 2025-02-17 08:30 |  | 14400 |  |  | 3
2025-01-07 | JOST24120418 | CT10-015-P02-05 | ST-4 | PP25-160T | 1 | 14400 | 360 | 40 | 5 | 0.041667 | 0.083333 | 0.33333 | 2025-02-03 08:30 | 2025-02-08 19:30 | 2025-02-17 08:30 |  | 14400 |  |  | 1
2025-01-07 | JOST24120418 | CT10-015-P03-05 | ST-4 | PP20-110T | 1 | 14400 | 360 | 40 | 5 | 0.041667 | 0.083333 | 0.33333 | 2025-02-03 08:30 | 2025-02-08 19:30 | 2025-02-17 08:30 |  | 14400 |  |  | 2
2025-01-07 | JOST24120418 | CT10-015-P04-05 | ST-4 | PP28-110T | 1 | 14400 | 360 | 40 | 5 | 0.041667 | 0.083333 | 0.33333 | 2025-02-03 08:30 | 2025-02-08 19:30 | 2025-02-17 08:30 |  | 14400 |  |  | 3
2025-01-07 | JOST24120409 | CT10-001-P01-06 | ST-3 | PP09-160T | 1 | 6080 | 330 | 18.4242 | 2.303 | 0.041667 | 0.083333 | 0.33333 | 2025-02-03 08:30 | 2025-02-06 02:46 | 2025-02-14 08:30 |  | 6080 |  |  | 1
2025-01-07 | JOST24120409 | CT10-001-P02-06 | ST-3 | PP18 | 1 | 6080 | 330 | 18.4242 | 2.303 | 0.041667 | 0.083333 | 0.33333 | 2025-02-03 08:30 | 2025-02-06 02:46 | 2025-02-14 08:30 |  | 6080 |  |  | 3
2025-01-07 | JOST24120409 | CT10-001-P03-06 | ST-3 | PP17-110T | 1 | 6080 | 330 | 18.4242 | 2.303 | 0.041667 | 0.083333 | 0.33333 | 2025-02-03 08:30 | 2025-02-06 02:46 | 2025-02-14 08:30 |  | 6080 |  |  | 2
2025-01-07 | JOST24120409 | CT10-001-P04-06 | ST-3 | PP16-110T | 1 | 6080 | 330 | 18.4242 | 2.303 | 0.041667 | 0.083333 | 0.33333 | 2025-02-03 08:30 | 2025-02-06 02:46 | 2025-02-14 08:30 |  | 6080 |  |  | 3
2025-01-07 | JOST24120409 | CT10-001-P05-06 | ST-3 | PP27-110T | 2 | 6080 | 330 | 18.4242 | 2.303 | 0.041667 | 0.083333 | 0.33333 | 2025-02-03 08:30 | 2025-02-06 02:46 | 2025-02-14 08:30 |  | 6080 |  |  | 1
2025-01-07 | JOTP24120398 | CP08-587-P02-04 | ST | PP05 | 1 | 150 | 300 | 0.5 | 0.0625 | 0.041667 | 0.083333 | 0.33333 | 2025-01-15 08:30 | 2025-01-15 21:00 | 2025-01-22 08:30 |  | 150 |  |  | 2
2025-01-07 | JOTP24120398 | CP08-587-P03-04 | PB | PB01 | 1 | 150 | 50 | 3 | 0.375 | 0.041667 | 0.083333 | 0.33333 | 2025-01-15 08:30 | 2025-01-16 04:30 | 2025-01-22 08:30 |  | 150 |  |  | 3
2025-01-07 | JOST24120366 | CP08-513-P02-07 | ST-4 | PP25-160T | 1 | 2450 | 360 | 6.8056 | 0.85069 | 0.041667 | 0.083333 | 0.33333 | 2025-02-03 08:30 | 2025-02-04 15:55 | 2025-02-17 08:30 | 1350 | 1100 |  |  | 2
2025-01-07 | JOST24120366 | CP08-513-P03-07 | ST-4 | PP20-110T | 1 | 2450 | 360 | 6.8056 | 0.85069 | 0.041667 | 0.083333 | 0.33333 | 2025-02-03 08:30 | 2025-02-04 15:55 | 2025-02-17 08:30 | 1350 | 1100 |  |  | 2
2025-01-07 | JOST24120366 | CP08-513-P04-07 | ST-4 | PP28-110T | 1 | 2450 | 360 | 6.8056 | 0.85069 | 0.041667 | 0.083333 | 0.33333 | 2025-02-03 08:30 | 2025-02-04 15:55 | 2025-02-17 08:30 | 1350 | 1100 |  |  | 2
2025-01-07 | JOST24120366 | CP08-513-P05-07 | ST-3 | TP03 | 1 | 2450 | 240 | 10.2083 | 1.276 | 0.041667 | 0.083333 | 0.33333 | 2025-02-03 08:30 | 2025-02-05 02:08 | 2025-02-17 08:30 | 625 | 1825 |  |  | 2
2025-01-07 | JOST24120366 | CP08-513-P06-07 | ST | OPT | 1 | 2450 | 420 | 5.8333 | 0.72917 | 0.041667 | 0.083333 | 0.33333 | 2025-02-03 08:30 | 2025-02-04 13:00 | 2025-02-17 08:30 |  | 2450 |  |  | 1
2025-01-07 | JOST24120091 | CP08-544-P01-02 | ST | STICK LABEL | 1 | 1000 | 30 | 33.3333 | 4.1667 | 0.041667 | 0.083333 | 0.33333 | 2025-02-03 08:30 | 2025-02-07 23:30 | 2025-02-24 08:30 |  | 1000 |  |  | 3
2025-01-07 | JOAW24100348 | CA16-011-P01-03 | FM | SW05 | 1 | 60000 | 450 | 133.3333 | 16.6667 | 0.041667 | 0.083333 | 0.33333 | 2025-02-05 08:30 | 2025-02-22 11:30 | 2025-02-21 08:30 | 22678 | 37322 |  |  | 2
2025-01-07 | JOAW24100348 | CA16-011-P02-03 | FM | OPT | 1 | 60000 | 900 | 66.6667 | 8.3333 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 15:00 | 2025-02-19 10:00 | 2025-02-21 08:30 | 5000 | 55000 |  |  | 3
2025-01-07 | JOST24100248 | CA16-010-P01-03 | ST | PP01-110T | 1 | 90909 | 3000 | 30.303 | 3.7879 | 0.041667 | 0.083333 | 0.33333 | 2025-02-06 08:30 | 2025-02-10 14:25 | 2025-02-27 08:30 | 20100 | 70809 |  |  | 3
2025-01-07 | JOST24100248 | CA16-010-P02-03 | ST-1 | VM01 | 1 | 90909 | 1000 | 90.909 | 11.3636 | 0.041667 | 0.083333 | 0.33333 | 2025-02-06 08:30 | 2025-02-18 04:14 | 2025-02-27 08:30 |  | 90909 |  |  | 3
2025-01-07 | JOST24120207 | CV04-010-P01-08 | ST-1 | PP11-035T | 1 | 8270 | 480 | 17.2292 | 2.1536 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-12 23:11 | 2025-03-24 08:30 |  | 8270 |  |  | 3
2025-01-07 | JOST24120207 | CV04-010-P02-08 | ST-1 | PP11-035T | 1 | 8270 | 240 | 34.4583 | 4.3073 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-15 02:52 | 2025-03-24 08:30 |  | 8270 |  |  | 2
2025-01-07 | JOST24120207 | CV04-010-P03-08 | ST-2 | PP06-040T | 1 | 8270 | 240 | 34.4583 | 4.3073 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-15 02:52 | 2025-03-24 08:30 |  | 8270 |  |  | 2
2025-01-07 | JOST24120207 | CV04-010-P04-08 | ST-2 | PP15-080T | 1 | 8270 | 240 | 34.4583 | 4.3073 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-15 02:52 | 2025-03-24 08:30 |  | 8270 |  |  | 2
2025-01-07 | JOST24120207 | CV04-010-P05-08 | 0 | HAND BEND-JIG | 1 | 8270 | 240 | 34.4583 | 4.3073 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-15 02:52 | 2025-03-24 08:30 |  | 8270 |  |  | 1
2025-01-07 | JOST24120207 | CV04-010-P06-08 | 0 | PLIER BENDING | 1 | 8270 | 240 | 34.4583 | 4.3073 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-15 02:52 | 2025-03-24 08:30 |  | 8270 |  |  | 2
2025-01-08 | JOAW24120287 | CM18-001-P01-06 | WN | SW13 | 1 | 30000 | 150 | 200 | 25 | 0.041667 | 0.083333 | 0.33333 | 2025-01-28 08:30 | 2025-02-22 19:30 | 2025-03-17 08:30 | 24407 | 5593 |  |  | 3
2025-01-08 | JOAW24120287 | CM18-001-P02-06 | WN | PP23 | 1 | 30000 | 420 | 71.4286 | 8.9286 | 0.041667 | 0.083333 | 0.33333 | 2025-01-28 08:30 | 2025-02-06 17:47 | 2025-03-17 08:30 | 24813 | 5187 |  |  | 1
2025-01-08 | JOAW24120287 | CM18-001-P05-06 | WN | TW01 | 1 | 30000 | 450 | 66.6667 | 8.3333 | 0.041667 | 0.083333 | 0.33333 | 2025-01-28 08:30 | 2025-02-06 03:30 | 2025-03-17 08:30 |  | 30000 |  |  | 2
2025-01-08 | JOAW24120251 | CD11-027D-P01-02 | ST | PP05-060T | 1 | 20000 | 240 | 83.3333 | 10.4167 | 0.041667 | 0.083333 | 0.33333 | 2025-02-03 08:30 | 2025-02-14 05:30 | 2025-02-24 08:30 |  | 20000 |  |  | 3
2025-01-08 | JOTP24120184 | CP08-562-P01-05 | PB | SW14 | 1 | 802 | 120 | 6.6833 | 0.83542 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 15:33 | 2025-02-24 08:30 |  | 802 |  |  | 1
2025-01-08 | JOTP24120184 | CP08-562-P02-05 | PB | SW14 | 1 | 802 | 17 | 47.1765 | 5.8971 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-16 17:02 | 2025-02-24 08:30 |  | 802 |  |  | 3
2025-01-08 | JOTP24120184 | CP08-562-P03-05 | OPT | OPT | 1 | 802 | 50 | 16.04 | 2.005 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-12 19:37 | 2025-02-24 08:30 |  | 802 |  |  | 2
2025-01-08 | JOTP24120184 | CP08-562-P04-05 | OPT | OPT | 1 | 802 | 60 | 13.3667 | 1.6708 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-12 11:36 | 2025-02-24 08:30 |  | 802 |  |  | 3
2025-01-08 | JOAW24120209 | CV04-012-P01-04 | FM | FM01 | 1 | 16593 | 1200 | 13.8275 | 1.7284 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-12 12:59 | 2025-03-24 08:30 | 2200 | 14393 |  |  | 1
2025-01-08 | JOAW24120209 | CV04-012-P02-04 | ST-2 | PP06-040T | 1 | 16593 | 360 | 46.0917 | 5.7615 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-16 13:46 | 2025-03-24 08:30 |  | 16593 |  |  | 2
2025-01-08 | JOAW24120249 | CD11-027B-P01-02 | WN | WS01 | 1 | 80000 | 2160 | 37.037 | 4.6296 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-15 10:37 | 2025-02-24 08:30 |  | 80000 |  |  | 3
2025-01-09 | JOST24120253 | CH04-002-P01-07 | ST-3 | PP25 | 1 | 5100 | 300 | 17 | 2.125 | 0.041667 | 0.083333 | 0.33333 | 2025-02-06 08:30 | 2025-02-08 22:30 | 2025-02-26 08:30 |  | 5100 |  |  | 2
2025-01-09 | JOST24120253 | CH04-002-P02-07 | ST-3 | PP26-110T | 1 | 5100 | 300 | 17 | 2.125 | 0.041667 | 0.083333 | 0.33333 | 2025-02-06 08:30 | 2025-02-08 22:30 | 2025-02-26 08:30 |  | 5100 |  |  | 2
2025-01-09 | JOST24120253 | CH04-002-P03-07 | ST-3 | PP20 | 1 | 5100 | 300 | 17 | 2.125 | 0.041667 | 0.083333 | 0.33333 | 2025-02-06 08:30 | 2025-02-08 22:30 | 2025-02-26 08:30 |  | 5100 |  |  | 2
2025-01-09 | JOST24120253 | CH04-002-P04-07 | ST-3 | PP28-110T | 1 | 5100 | 300 | 17 | 2.125 | 0.041667 | 0.083333 | 0.33333 | 2025-02-06 08:30 | 2025-02-08 22:30 | 2025-02-26 08:30 |  | 5100 |  |  | 1
2025-01-09 | JOST24120253 | CH04-002-P05-07 | ST-3 | SW01 | 1 | 5100 | 300 | 17 | 2.125 | 0.041667 | 0.083333 | 0.33333 | 2025-02-06 08:30 | 2025-02-08 22:30 | 2025-02-26 08:30 |  | 5100 |  |  | 2
2025-01-09 | JOST24120253 | CH04-002-P06-07 | ST-1 | OPT PAINTING | 1 | 5100 | 120 | 42.5 | 5.3125 | 0.041667 | 0.083333 | 0.33333 | 2025-02-06 08:30 | 2025-02-12 03:00 | 2025-02-26 08:30 |  | 5100 |  |  | 3
2025-01-09 | JOST24120431 | CC06-001-P01-04 | ST-2 | PP06-040T | 1 | 43210 | 2220 | 19.464 | 2.433 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-13 05:54 | 2025-03-03 08:30 |  | 43210 |  |  | 1
2025-01-09 | JOST24120431 | CC06-001-P02-04 | AL | TP08 | 1 | 43210 | 600 | 72.0167 | 9.0021 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-19 19:33 | 2025-03-03 08:30 |  | 43210 |  |  | 2
2025-01-09 | JOST24120431 | CC06-001-P03-04 | AL | DRY-1 | 1 | 43210 | 780 | 55.3974 | 6.9247 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-17 17:42 | 2025-03-03 08:30 |  | 43210 |  |  | 3
2025-01-09 | JOST24120372 | CP08-521-P01-02 | ST-2 | PP01-110T | 1 | 2604 | 3000 | 0.868 | 0.1085 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-10 22:06 | 2025-02-24 08:30 |  | 2604 |  |  | 1
2025-01-09 | JOST24120373 | CP08-522-P01-02 | ST-3 | PP01-110T | 1 | 3646 | 3000 | 1.2153 | 0.15192 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-10 23:09 | 2025-02-24 08:30 |  | 3646 |  |  | 3
2025-01-09 | JOTP24120376 | CP08-554A-P02-04 | TR | 1 | 1 | 400 | 20 | 20 | 2.5 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-13 07:30 | 2025-02-24 08:30 |  | 400 |  |  | 2
2025-01-09 | JOTP24120376 | CP08-554A-P03-04 | TR | PB02 | 1 | 400 | 30 | 13.3333 | 1.6667 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-12 11:30 | 2025-02-24 08:30 |  | 400 |  |  | 3
2025-01-09 | JOST25010145 | CM03-039-P02-03 | ST | VM01 | 1 | 2000 | 2000 | 1 | 0.125 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-10 22:30 | 2025-02-24 08:30 |  | 2000 |  |  | 1
2025-01-09 | JOST25010140 | CM03-027-P02-05 | ST | VM01 | 1 | 3550 | 3000 | 1.1833 | 0.14792 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-10 23:03 | 2025-03-17 08:30 |  | 3550 |  |  | 2
2025-01-09 | JOST25010140 | CM03-027-P04-05 | AL | CHECKING | 1 | 3550 | 600 | 5.9167 | 0.73958 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 13:15 | 2025-03-17 08:30 |  | 3550 |  |  | 3
2025-01-09 | JOTP25010142 | CM03-034-P01-05 | TR | TM05 | 1 | 300 | 81 | 3.7037 | 0.46296 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 06:37 | 2025-02-27 08:30 | 1 | 299 |  |  | 2
2025-01-09 | JOTP25010142 | CM03-034-P02-05 | WN | DEBURR | 1 | 300 | 50 | 6 | 0.75 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 13:30 | 2025-02-27 08:30 |  | 300 |  |  | 2
2025-01-09 | JOTP25010142 | CM03-034-P03-05 | TR | APPLY OIL | 1 | 300 | 300 | 1 | 0.125 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-13 22:30 | 2025-02-27 08:30 |  | 300 |  |  | 2
2025-01-09 | JOTP25010142 | CM03-034-P04-05 | TR | PB04 | 1 | 300 | 200 | 1.5 | 0.1875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 | 2025-02-27 08:30 |  | 300 |  |  | 2
2025-01-09 | JOST25010143 | CM03-037-P01-03 | ST-3 | PP04-060T | 1 | 5400 | 360 | 15 | 1.875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-15 16:30 | 2025-02-27 08:30 |  | 5400 |  |  | 1
2025-01-09 | JOST25010143 | CM03-037-P02-03 | ST-3 | PP03-060T | 1 | 5400 | 360 | 15 | 1.875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-15 16:30 | 2025-02-27 08:30 |  | 5400 |  |  | 3
2025-01-09 | JOTP25010064 | CP08-427-P01-03 | TR | TM06 | 1 | 550 | 28 | 19.6429 | 2.4554 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-24 06:26 | 2025-03-07 08:30 |  | 550 |  |  | 2
2025-01-09 | JOTP25010064 | CP08-427-P02-03 | TR | PB05 | 1 | 550 | 30 | 18.3333 | 2.2917 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-24 02:30 | 2025-03-07 08:30 |  | 550 |  |  | 3
2025-01-09 | JOTP25010063 | CP08-426-P01-02 | TR | TM03 | 1 | 672 | 60 | 11.2 | 1.4 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-19 05:06 | 2025-03-03 08:30 |  | 672 |  |  | 3
2025-01-09 | JOTP25010062 | CP08-425-P01-03 | TR | TM03 | 1 | 672 | 60 | 11.2 | 1.4 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-19 05:06 | 2025-03-03 08:30 |  | 672 |  |  | 3
2025-01-09 | JOTP25010062 | CP08-425-P02-03 | TR | PB08 | 1 | 672 | 120 | 5.6 | 0.7 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 12:18 | 2025-03-03 08:30 |  | 672 |  |  | 3
2025-01-09 | JOTP25010061 | CP08-423-P01-02 | TR | TM03 | 1 | 550 | 40 | 13.75 | 1.7188 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-23 12:45 | 2025-03-07 08:30 |  | 550 |  |  | 2
2025-01-09 | JOTP25010060 | CP08-422-P01-03 | TR | TM05 | 1 | 612 | 50 | 12.24 | 1.53 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-19 08:13 | 2025-03-03 08:30 |  | 612 |  |  | 2
2025-01-09 | JOTP25010060 | CP08-422-P02-03 | TR | PB08 | 1 | 612 | 72 | 8.5 | 1.0625 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 21:00 | 2025-03-03 08:30 |  | 612 |  |  | 2
2025-01-09 | JOTP25010059 | CP08-421-P01-03 | TR | TM05 | 1 | 612 | 90 | 6.8 | 0.85 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 15:54 | 2025-03-03 08:30 |  | 612 |  |  | 1
2025-01-09 | JOTP25010059 | CP08-421-P02-03 | TR | PB08 | 1 | 612 | 120 | 5.1 | 0.6375 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 10:48 | 2025-03-03 08:30 |  | 612 |  |  | 2
2025-01-09 | JOTP25010057 | CP08-419-P01-03 | TR | TM03 | 1 | 1104 | 72 | 15.3333 | 1.9167 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-19 17:30 | 2025-03-03 08:30 |  | 1104 |  |  | 3
2025-01-09 | JOTP25010057 | CP08-419-P02-03 | TR | PB07 | 1 | 1104 | 108 | 10.2222 | 1.2778 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-19 02:10 | 2025-03-03 08:30 |  | 1104 |  |  | 1
2025-01-09 | JOTP25010056 | CP08-418-P02-03 | TR | PB05 | 1 | 700 | 40 | 17.5 | 2.1875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-13 | 2025-02-24 08:30 |  | 700 |  |  | 2
2025-01-09 | JOTP25010055 | CP08-417-P01-04 | SM | SM01 | 1 | 902 | 48 | 18.7917 | 2.349 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-16 03:52 | 2025-02-27 08:30 |  | 902 |  |  | 3
2025-01-09 | JOTP25010055 | CP08-417-P02-04 | TR | TM05 | 1 | 902 | 150 | 6.0133 | 0.75167 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 13:32 | 2025-02-27 08:30 |  | 902 |  |  | 1
2025-01-09 | JOTP25010055 | CP08-417-P03-04 | TR | PB08 | 1 | 902 | 120 | 7.5167 | 0.93958 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 18:03 | 2025-02-27 08:30 |  | 902 |  |  | 3
2025-01-09 | JOTP25010054 | CP08-416-P01-03 | TR | TM05 | 1 | 720 | 70 | 10.2857 | 1.2857 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-26 02:21 | 2025-03-10 08:30 |  | 720 |  |  | 2
2025-01-09 | JOTP25010054 | CP08-416-P02-03 | TR | PB04 | 1 | 720 | 40 | 18 | 2.25 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-27 01:30 | 2025-03-10 08:30 |  | 720 |  |  | 3
2025-01-09 | JOST25010051 | CP08-407-P01-07 | ST | PP29 | 1 | 350 | 120 | 2.9167 | 0.36458 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 04:15 | 2025-03-03 08:30 |  | 350 |  |  | 1
2025-01-09 | JOST25010051 | CP08-407-P02-07 | ST | PP33 | 1 | 350 | 120 | 2.9167 | 0.36458 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 04:15 | 2025-03-03 08:30 |  | 350 |  |  | 2
2025-01-09 | JOST25010051 | CP08-407-P03-07 | ST | TP03 | 1 | 350 | 60 | 5.8333 | 0.72917 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 13:00 | 2025-03-03 08:30 |  | 350 |  |  | 3
2025-01-09 | JOST25010051 | CP08-407-P04-07 | ST | TP09 | 1 | 350 | 120 | 2.9167 | 0.36458 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 04:15 | 2025-03-03 08:30 |  | 350 |  |  | 2
2025-01-09 | JOST25010051 | CP08-407-P05-07 | ST | PP33 | 1 | 350 | 120 | 2.9167 | 0.36458 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 04:15 | 2025-03-03 08:30 |  | 350 |  |  | 2
2025-01-09 | JOST25010051 | CP08-407-P06-07 | ST | SW01 | 1 | 350 | 80 | 4.375 | 0.54688 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 08:38 | 2025-03-03 08:30 |  | 350 |  |  | 2
2025-01-09 | JOST25010050 | CP08-400-P01-04 | ST-4 | PP24-160T | 1 | 1666 | 360 | 4.6278 | 0.57847 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 09:23 | 2025-03-10 08:30 |  | 1666 |  |  | 2
2025-01-09 | JOST25010050 | CP08-400-P02-04 | ST-4 | PP25-160T | 1 | 1666 | 360 | 4.6278 | 0.57847 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 09:23 | 2025-03-10 08:30 |  | 1666 |  |  | 1
2025-01-09 | JOST25010050 | CP08-400-P03-04 | ST-4 | PP28-110T | 1 | 1666 | 360 | 4.6278 | 0.57847 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 09:23 | 2025-03-10 08:30 |  | 1666 |  |  | 3
2025-01-09 | JOTP25010049 | CP08-344-P01-03 | TR | TM06 | 1 | 1666 | 50 | 33.32 | 4.165 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-21 23:28 | 2025-03-03 08:30 |  | 1666 |  |  | 2
2025-01-09 | JOTP25010049 | CP08-344-P02-03 | TR | PB04 | 1 | 640 | 120 | 5.3333 | 0.66667 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 11:30 | 2025-03-03 08:30 |  | 640 |  |  | 3
2025-01-09 | JOAW25010048 | CP08-297-P01-02 | FM | FM02 | 1 | 15217 | 2400 | 6.3404 | 0.79255 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 14:31 | 2025-03-03 08:30 |  | 15217 |  |  | 3
2025-01-09 | JOST25010046 | CP08-259-P01-04 | SM | SM01 | 1 | 900 | 120 | 7.5 | 0.9375 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 18:00 | 2025-02-24 08:30 |  | 900 |  |  | 3
2025-01-09 | JOST25010046 | CP08-259-P02-04 | ST-1 | PP10-080T | 1 | 900 | 360 | 2.5 | 0.3125 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 03:00 | 2025-02-24 08:30 |  | 900 |  |  | 3
2025-01-09 | JOST25010046 | CP08-259-P03-04 | ST-1 | PP04-060T | 1 | 900 | 240 | 3.75 | 0.46875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 06:45 | 2025-02-24 08:30 |  | 900 |  |  | 2
2025-01-10 | JOST25010093 | CP08-515-P01-03 | ST-2 | PP10-080T | 1 | 3906 | 1800 | 2.17 | 0.27125 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 02:01 | 2025-03-03 08:30 |  | 3906 |  |  | 2
2025-01-10 | JOST25010093 | CP08-515-P02-03 | AL | TP04 | 1 | 3906 | 300 | 13.02 | 1.6275 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-19 10:34 | 2025-03-03 08:30 |  | 3906 |  |  | 2
2025-01-10 | JOST25010092 | CP08-512-P01-07 | ST-3 | PP09-160T | 1 | 2100 | 300 | 7 | 0.875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 16:30 | 2025-03-10 08:30 |  | 2100 |  |  | 3
2025-01-10 | JOST25010092 | CP08-512-P02-07 | ST-3 | PP18-150T | 1 | 2100 | 300 | 7 | 0.875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 16:30 | 2025-03-10 08:30 |  | 2100 |  |  | 3
2025-01-10 | JOST25010092 | CP08-512-P03-07 | ST-3 | PP21-110T | 1 | 2100 | 300 | 7 | 0.875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 16:30 | 2025-03-10 08:30 |  | 2100 |  |  | 1
2025-01-10 | JOST25010092 | CP08-512-P04-07 | ST-3 | PP17-110T | 1 | 2100 | 300 | 7 | 0.875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 16:30 | 2025-03-10 08:30 |  | 2100 |  |  | 1
2025-01-10 | JOST25010092 | CP08-512-P05-07 | ST-3 | PP16-110T | 1 | 2100 | 300 | 7 | 0.875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 16:30 | 2025-03-10 08:30 |  | 2100 |  |  | 3
2025-01-10 | JOST25010092 | CP08-512-P06-07 | ST-3 | PP27-110T | 1 | 2100 | 300 | 7 | 0.875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 16:30 | 2025-03-10 08:30 |  | 2100 |  |  | 1
2025-01-10 | JOST25010091 | CP08-511-P01-05 | SM | SM01 | 1 | 2220 | 240 | 9.25 | 1.1562 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 23:15 | 2025-03-03 08:30 |  | 2220 |  |  | 2
2025-01-10 | JOST25010091 | CP08-511-P02-05 | ST-3 | PP17-110T | 1 | 2220 | 240 | 9.25 | 1.1562 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 23:15 | 2025-03-03 08:30 |  | 2220 |  |  | 3
2025-01-10 | JOST25010091 | CP08-511-P03-05 | ST-3 | PP16-110T | 1 | 2220 | 240 | 9.25 | 1.1562 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 23:15 | 2025-03-03 08:30 |  | 2220 |  |  | 1
2025-01-10 | JOST25010091 | CP08-511-P04-05 | ST-3 | PP27-110T | 1 | 2220 | 240 | 9.25 | 1.1562 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 23:15 | 2025-03-03 08:30 |  | 2220 |  |  | 2
2025-01-10 | JOST25010089 | CP08-508-P01-09 | ST | SM01 | 1 | 1300 | 480 | 2.7083 | 0.33854 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-22 03:38 | 2025-03-07 08:30 |  | 1300 |  |  | 3
2025-01-10 | JOST25010089 | CP08-508-P02-09 | ST-4 | PP24-160T | 1 | 1300 | 240 | 5.4167 | 0.67708 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-22 11:45 | 2025-03-07 08:30 |  | 1300 |  |  | 1
2025-01-10 | JOST25010089 | CP08-508-P03-09 | ST-4 | PP25-160T | 1 | 1300 | 240 | 5.4167 | 0.67708 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-22 11:45 | 2025-03-07 08:30 |  | 1300 |  |  | 3
2025-01-10 | JOST25010089 | CP08-508-P04-09 | ST-4 | PP26-110T | 1 | 1300 | 240 | 5.4167 | 0.67708 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-22 11:45 | 2025-03-07 08:30 |  | 1300 |  |  | 2
2025-01-10 | JOST25010089 | CP08-508-P05-09 | ST-4 | PP28-110T | 1 | 1300 | 240 | 5.4167 | 0.67708 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-22 11:45 | 2025-03-07 08:30 |  | 1300 |  |  | 3
2025-01-10 | JOST25010089 | CP08-508-P06-09 | ST-4 | PP24-160T | 1 | 1300 | 240 | 5.4167 | 0.67708 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-22 11:45 | 2025-03-07 08:30 |  | 1300 |  |  | 1
2025-01-10 | JOST25010089 | CP08-508-P07-09 | ST-4 | PP25-160T | 1 | 1300 | 240 | 5.4167 | 0.67708 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-22 11:45 | 2025-03-07 08:30 |  | 1300 |  |  | 2
2025-01-10 | JOST25010089 | CP08-508-P08-09 | ST-4 | PP26-110T | 1 | 1300 | 240 | 5.4167 | 0.67708 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-22 11:45 | 2025-03-07 08:30 |  | 1300 |  |  | 3
2025-01-10 | JOST25010088 | CP08-507-P01-08 | ST-4 | PP24-160T | 1 | 300 | 240 | 1.25 | 0.15625 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-17 23:15 | 2025-03-03 08:30 |  | 300 |  |  | 2
2025-01-10 | JOST25010088 | CP08-507-P02-08 | ST-4 | PP25-160T | 1 | 300 | 240 | 1.25 | 0.15625 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-17 23:15 | 2025-03-03 08:30 |  | 300 |  |  | 2
2025-01-10 | JOST25010088 | CP08-507-P03-08 | ST-4 | PP26-110T | 1 | 300 | 240 | 1.25 | 0.15625 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-17 23:15 | 2025-03-03 08:30 |  | 300 |  |  | 2
2025-01-10 | JOST25010088 | CP08-507-P04-08 | ST-4 | PP28-110T | 1 | 300 | 240 | 1.25 | 0.15625 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-17 23:15 | 2025-03-03 08:30 |  | 300 |  |  | 2
2025-01-10 | JOST25010088 | CP08-507-P05-08 | ST-4 | PP24-160T | 1 | 300 | 240 | 1.25 | 0.15625 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-17 23:15 | 2025-03-03 08:30 |  | 300 |  |  | 1
2025-01-10 | JOST25010088 | CP08-507-P06-08 | ST-4 | PP25-160T | 1 | 300 | 240 | 1.25 | 0.15625 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-17 23:15 | 2025-03-03 08:30 |  | 300 |  |  | 3
2025-01-10 | JOST25010088 | CP08-507-P07-08 | ST-4 | PP26-110T | 1 | 300 | 240 | 1.25 | 0.15625 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-17 23:15 | 2025-03-03 08:30 |  | 300 |  |  | 2
2025-01-10 | JOST25010087 | CP08-506-P01-09 | ST | SM01 | 1 | 2500 | 480 | 5.2083 | 0.65104 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 11:08 | 2025-03-03 08:30 |  | 2500 |  |  | 3
2025-01-10 | JOST25010087 | CP08-506-P02-09 | ST-4 | PP24-160T | 1 | 2500 | 240 | 10.4167 | 1.3021 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-19 02:45 | 2025-03-03 08:30 |  | 2500 |  |  | 3
2025-01-10 | JOST25010087 | CP08-506-P03-09 | ST-4 | PP25-160T | 1 | 2500 | 240 | 10.4167 | 1.3021 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-19 02:45 | 2025-03-03 08:30 |  | 2500 |  |  | 3
2025-01-10 | JOST25010087 | CP08-506-P04-09 | ST-4 | PP26-110T | 1 | 2500 | 240 | 10.4167 | 1.3021 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-19 02:45 | 2025-03-03 08:30 |  | 2500 |  |  | 3
2025-01-10 | JOST25010087 | CP08-506-P05-09 | ST-4 | PP28-110T | 1 | 2500 | 240 | 10.4167 | 1.3021 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-19 02:45 | 2025-03-03 08:30 |  | 2500 |  |  | 2
2025-01-10 | JOST25010087 | CP08-506-P06-09 | ST-4 | PP24-160T | 1 | 2500 | 240 | 10.4167 | 1.3021 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-19 02:45 | 2025-03-03 08:30 |  | 2500 |  |  | 2
2025-01-10 | JOST25010087 | CP08-506-P07-09 | ST-4 | PP25-160T | 1 | 2500 | 240 | 10.4167 | 1.3021 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-19 02:45 | 2025-03-03 08:30 |  | 2500 |  |  | 2
2025-01-10 | JOST25010087 | CP08-506-P08-09 | ST-4 | PP26-110T | 1 | 2500 | 240 | 10.4167 | 1.3021 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-19 02:45 | 2025-03-03 08:30 |  | 2500 |  |  | 3
2025-01-10 | JOST25010085 | CP08-499B-P02-04 | 0 | PP21 | 1 | 250 | 180 | 1.3889 | 0.17361 | 0.041667 | 0.083333 | 0.33333 | 2025-01-31 08:30 | 2025-01-31 23:40 | 2025-02-14 08:30 |  | 250 |  |  | 2
2025-01-10 | JOST25010085 | CP08-499B-P03-04 | 0 | PP30-200T | 1 | 250 | 180 | 1.3889 | 0.17361 | 0.041667 | 0.083333 | 0.33333 | 2025-01-31 08:30 | 2025-01-31 23:40 | 2025-02-14 08:30 |  | 250 |  |  | 2
2025-01-10 | JOST25010083 | CP08-499-P01-02 | ST-3 | SW01 | 1 | 250 | 30 | 8.3333 | 1.0417 | 0.041667 | 0.083333 | 0.33333 | 2025-02-14 08:30 | 2025-02-15 20:30 | 2025-02-28 08:30 |  | 250 |  |  | 2
2025-01-10 | JOST25010082 | CP08-496A-P01-05 | ST-4 | PP18-150T | 1 | 2000 | 240 | 8.3333 | 1.0417 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 20:30 | 2025-02-24 08:30 |  | 2000 |  |  | 3
2025-01-10 | JOST25010082 | CP08-496A-P02-05 | ST-4 | PP17-110T | 1 | 2000 | 240 | 8.3333 | 1.0417 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 20:30 | 2025-02-24 08:30 |  | 2000 |  |  | 3
2025-01-10 | JOST25010082 | CP08-496A-P03-05 | ST-4 | PP16-110T | 1 | 2000 | 240 | 8.3333 | 1.0417 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 20:30 | 2025-02-24 08:30 |  | 2000 |  |  | 1
2025-01-10 | JOST25010082 | CP08-496A-P04-05 | ST-4 | PP27-110T | 1 | 2000 | 240 | 8.3333 | 1.0417 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 20:30 | 2025-02-24 08:30 |  | 2000 |  |  | 1
2025-01-10 | JOTP25010081 | CP08-490-P01-04 | TR | TM02 | 1 | 105 | 80 | 1.3125 | 0.16406 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-17 23:26 | 2025-03-03 08:30 |  | 105 |  |  | 3
2025-01-10 | JOTP25010081 | CP08-490-P02-04 | WN | DEBURR | 1 | 105 | 14 | 7.5 | 0.9375 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 18:00 | 2025-03-03 08:30 |  | 105 |  |  | 1
2025-01-10 | JOTP25010081 | CP08-490-P03-04 | ST-1 | PAINTING | 1 | 105 | 50 | 2.1 | 0.2625 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 01:48 | 2025-03-03 08:30 |  | 105 |  |  | 2
2025-01-10 | JOTP25010080 | CP08-489-P01-05 | TR | TM02 | 1 | 192 | 80 | 2.4 | 0.3 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 02:42 | 2025-03-03 08:30 |  | 192 |  |  | 3
2025-01-10 | JOTP25010080 | CP08-489-P02-05 | WN | DEBURR | 1 | 192 | 15 | 12.8 | 1.6 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-19 09:54 | 2025-03-03 08:30 |  | 192 |  |  | 1
2025-01-10 | JOTP25010080 | CP08-489-P03-05 | TR | PB04 | 1 | 192 | 120 | 1.6 | 0.2 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 00:18 | 2025-03-03 08:30 |  | 192 |  |  | 2
2025-01-10 | JOTP25010080 | CP08-489-P04-05 | ST-1 | PAINTING | 1 | 192 | 15 | 12.8 | 1.6 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-19 09:54 | 2025-03-03 08:30 |  | 192 |  |  | 3
2025-01-10 | JOST25010079 | CP08-482-P03-04 | ST-3 | PP21-110T | 1 | 1740 | 240 | 7.25 | 0.90625 | 0.041667 | 0.083333 | 0.33333 | 2025-02-03 08:30 | 2025-02-04 17:15 | 2025-02-17 08:30 | 159 | 1581 |  |  | 1
2025-01-10 | JOST25010078 | CP08-457-P01-04 | ST-3 | PP25-160T | 1 | 1615 | 360 | 4.4861 | 0.56076 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 08:58 | 2025-03-03 08:30 |  | 1615 |  |  | 3
2025-01-10 | JOST25010078 | CP08-457-P02-04 | ST-3 | PP20-110T | 1 | 1615 | 360 | 4.4861 | 0.56076 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 08:58 | 2025-03-03 08:30 |  | 1615 |  |  | 2
2025-01-10 | JOST25010078 | CP08-457-P03-04 | ST-3 | PP28-110T | 1 | 1615 | 360 | 4.4861 | 0.56076 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 08:58 | 2025-03-03 08:30 |  | 1615 |  |  | 3
2025-01-10 | JOST25010073 | CP08-437-P01-05 | SM | SM01 | 1 | 1710 | 5400 | 0.31667 | 0.039583 | 0.041667 | 0.083333 | 0.33333 | 2025-02-14 08:30 | 2025-02-14 20:27 | 2025-02-28 08:30 |  | 1710 |  |  | 1
2025-01-10 | JOST25010073 | CP08-437-P02-05 | ST-1 | PP03-060T | 1 | 1710 | 480 | 3.5625 | 0.44531 | 0.041667 | 0.083333 | 0.33333 | 2025-02-14 08:30 | 2025-02-15 06:11 | 2025-02-28 08:30 |  | 1710 |  |  | 2
2025-01-10 | JOST25010073 | CP08-437-P03-05 | ST-1 | PP03-060T | 1 | 1710 | 360 | 4.75 | 0.59375 | 0.041667 | 0.083333 | 0.33333 | 2025-02-14 08:30 | 2025-02-15 09:45 | 2025-02-28 08:30 |  | 1710 |  |  | 3
2025-01-10 | JOST25010073 | CP08-437-P04-05 | TR | PP22 | 1 | 1710 | 200 | 8.55 | 1.0688 | 0.041667 | 0.083333 | 0.33333 | 2025-02-14 08:30 | 2025-02-15 21:09 | 2025-02-28 08:30 |  | 1710 |  |  | 2
2025-01-10 | JOTP25010074 | CP08-439-P01-06 | TR | TM06 | 1 | 130 | 18 | 7.2222 | 0.90278 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 17:10 | 2025-03-03 08:30 |  | 130 |  |  | 2
2025-01-10 | JOTP25010074 | CP08-439-P02-06 | TR | TM02 | 1 | 130 | 18 | 7.2222 | 0.90278 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 17:10 | 2025-03-03 08:30 |  | 130 |  |  | 2
2025-01-10 | JOTP25010074 | CP08-439-P03-06 | TR | PB05 | 1 | 130 | 18 | 7.2222 | 0.90278 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 17:10 | 2025-03-03 08:30 |  | 130 |  |  | 2
2025-01-10 | JOTP25010074 | CP08-439-P04-06 | TR | PB02 | 1 | 130 | 18 | 7.2222 | 0.90278 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 17:10 | 2025-03-03 08:30 |  | 130 |  |  | 1
2025-01-10 | JOTP25010074 | CP08-439-P05-06 | TR | PB03 | 1 | 130 | 18 | 7.2222 | 0.90278 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 17:10 | 2025-03-03 08:30 |  | 130 |  |  | 3
2025-01-10 | JOTP25010070 | CP08-435 &CP08-436-P01-02 | TR | TM06 | 1 | 1280 | 80 | 16 | 2 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-23 19:30 | 2025-03-07 08:30 |  | 1280 |  |  | 2
2025-01-10 | JOTP25010070 | CP08-435-P01-03 | TR | PB04 | 1 | 640 | 160 | 4 | 0.5 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-22 07:30 | 2025-03-07 08:30 |  | 640 |  |  | 3
2025-01-10 | JOTP25010070 | CP08-435-P02-03 | TR | PB03 | 1 | 640 | 120 | 5.3333 | 0.66667 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-22 11:30 | 2025-03-07 08:30 |  | 640 |  |  | 3
2025-01-10 | JOTP25010072 | CP08-436-P01-02 | TR | PB04 | 1 | 640 | 114 | 5.614 | 0.70175 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-22 12:21 | 2025-03-07 08:30 |  | 640 |  |  | 3
2025-01-10 | JOST25010068 | CP08-434-P01-04 | SM | SM01 | 1 | 770 | 5040 | 0.15278 | 0.019097 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-13 19:57 | 2025-02-27 08:30 |  | 770 |  |  | 3
2025-01-10 | JOST25010068 | CP08-434-P02-04 | ST-4 | PP21-110T | 1 | 770 | 300 | 2.5667 | 0.32083 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 03:12 | 2025-02-27 08:30 |  | 770 |  |  | 2
2025-01-10 | JOST25010068 | CP08-434-P03-04 | TR | PB08 | 1 | 770 | 100 | 7.7 | 0.9625 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 18:36 | 2025-02-27 08:30 |  | 770 |  |  | 2
2025-01-10 | JOST25010067 | CP08-433-P01-06 | SM | SM01 | 1 | 680 | 6120 | 0.11111 | 0.013889 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-13 19:50 | 2025-02-27 08:30 |  | 680 |  |  | 2
2025-01-10 | JOST25010067 | CP08-433-P02-06 | ST-4 | PP21-110T | 1 | 680 | 300 | 2.2667 | 0.28333 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 02:18 | 2025-02-27 08:30 |  | 680 |  |  | 1
2025-01-10 | JOST25010067 | CP08-433-P03-06 | ST-4 | PP21-110T | 1 | 680 | 300 | 2.2667 | 0.28333 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 02:18 | 2025-02-27 08:30 |  | 680 |  |  | 2
2025-01-10 | JOST25010067 | CP08-433-P04-06 | TR | PB08 | 1 | 680 | 132 | 5.1515 | 0.64394 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 10:57 | 2025-02-27 08:30 |  | 680 |  |  | 3
2025-01-10 | JOST25010067 | CP08-433-P05-06 | TR | PB08 | 1 | 680 | 96 | 7.0833 | 0.88542 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 16:45 | 2025-02-27 08:30 |  | 680 |  |  | 1
2025-01-10 | JOST25010047 | CP08-292-P01-06 | ST-3 | PP25-160T | 1 | 2200 | 360 | 6.1111 | 0.76389 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 13:50 | 2025-03-03 08:30 |  | 2200 |  |  | 2
2025-01-10 | JOST25010047 | CP08-292-P02-06 | ST-3 | PP26-110T | 1 | 2200 | 360 | 6.1111 | 0.76389 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 13:50 | 2025-03-03 08:30 |  | 2200 |  |  | 3
2025-01-10 | JOST25010047 | CP08-292-P03-06 | ST-3 | PP20-110T | 1 | 2200 | 360 | 6.1111 | 0.76389 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 13:50 | 2025-03-03 08:30 |  | 2200 |  |  | 1
2025-01-10 | JOST25010047 | CP08-292-P04-06 | ST-3 | PP28-110T | 1 | 2200 | 360 | 6.1111 | 0.76389 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 13:50 | 2025-03-03 08:30 |  | 2200 |  |  | 3
2025-01-10 | JOST25010047 | CP08-292-P05-06 | ST-3 | PP24-160T | 1 | 2200 | 360 | 6.1111 | 0.76389 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 13:50 | 2025-03-03 08:30 |  | 2200 |  |  | 2
2025-01-10 | JOST25010045 | CP08-258-P01-03 | ST | SM01 | 1 | 1767 | 240 | 7.3625 | 0.92031 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 17:35 | 2025-03-10 08:30 |  | 1767 |  |  | 3
2025-01-10 | JOST25010045 | CP08-258-P02-03 | ST | PP22-060T | 1 | 1767 | 250 | 7.068 | 0.8835 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 16:42 | 2025-03-10 08:30 |  | 1767 |  |  | 1
2025-01-10 | JOST25010044 | CP08-257-P01-05 | ST-1 | SM01 | 1 | 1072 | 240 | 4.4667 | 0.55833 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 08:54 | 2025-03-10 08:30 |  | 1072 |  |  | 2
2025-01-10 | JOST25010044 | CP08-257-P02-05 | ST-3 | PP10-080T | 1 | 1072 | 360 | 2.9778 | 0.37222 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 04:26 | 2025-03-10 08:30 |  | 1072 |  |  | 3
2025-01-10 | JOST25010044 | CP08-257-P03-05 | ST-3 | PP04-060T | 1 | 1072 | 360 | 2.9778 | 0.37222 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 04:26 | 2025-03-10 08:30 |  | 1072 |  |  | 2
2025-01-10 | JOST25010044 | CP08-257-P04-05 | ST-3 | PP03-060T | 1 | 1072 | 360 | 2.9778 | 0.37222 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 04:26 | 2025-03-10 08:30 |  | 1072 |  |  | 2
2025-01-10 | JOAW25010037 | CP08-231A-P01-03 | WN | WS01 | 1 | 1600 | 900 | 1.7778 | 0.22222 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 00:50 | 2025-03-10 08:30 |  | 1600 |  |  | 2
2025-01-10 | JOAW25010037 | CP08-231A-P02-03 | WN | JIG-HAND BEND | 1 | 1600 | 120 | 13.3333 | 1.6667 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-26 11:30 | 2025-03-10 08:30 |  | 1600 |  |  | 1
2025-01-10 | JOAW25010038 | CP08-231B-P01-06 | WN | WS01 | 1 | 3200 | 720 | 4.4444 | 0.55556 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 08:50 | 2025-03-10 08:30 |  | 3200 |  |  | 2
2025-01-10 | JOAW25010038 | CP08-231B-P02-06 | WN | PP23-060T | 1 | 3200 | 330 | 9.697 | 1.2121 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-26 00:35 | 2025-03-10 08:30 |  | 3200 |  |  | 3
2025-01-10 | JOAW25010038 | CP08-231B-P03-06 | WN | JIG-HAND BEND | 1 | 3200 | 240 | 13.3333 | 1.6667 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-26 11:30 | 2025-03-10 08:30 |  | 3200 |  |  | 1
2025-01-10 | JOAW25010038 | CP08-231B-P04-06 | WN | PP23-060T | 1 | 3200 | 420 | 7.619 | 0.95238 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 18:21 | 2025-03-10 08:30 |  | 3200 |  |  | 2
2025-01-10 | JOAW25010038 | CP08-231B-P05-06 | WN | PP23 | 1 | 3200 | 240 | 13.3333 | 1.6667 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-26 11:30 | 2025-03-10 08:30 |  | 3200 |  |  | 3
2025-01-10 | JOAW25010039 | CP08-231C-P01-03 | WN | WS01 | 1 | 1600 | 900 | 1.7778 | 0.22222 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 00:50 | 2025-03-10 08:30 |  | 1600 |  |  | 1
2025-01-10 | JOAW25010039 | CP08-231C-P02-03 | WN | JIG-HAND BEND | 1 | 1600 | 420 | 3.8095 | 0.47619 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 06:56 | 2025-03-10 08:30 |  | 1600 |  |  | 3
2025-01-10 | JOAW25010040 | CP08-231D-P01-02 | WN | WS01 | 1 | 7200 | 960 | 7.5 | 0.9375 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 18:00 | 2025-03-10 08:30 |  | 7200 |  |  | 2
2025-01-10 | JOAW25010041 | CP08-231E-P01-02 | WN | WS01 | 1 | 6400 | 720 | 8.8889 | 1.1111 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 22:10 | 2025-03-10 08:30 |  | 6400 |  |  | 3
2025-01-10 | JOAW25010042 | CP08-231F-P01-02 | WN | WS01 | 1 | 6400 | 900 | 7.1111 | 0.88889 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 16:50 | 2025-03-10 08:30 |  | 6400 |  |  | 1
2025-01-10 | JOAW25010042 | CP08-231G-P01-02 | WN | WS01 | 1 | 5600 | 840 | 6.6667 | 0.83333 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 15:30 | 2025-03-10 08:30 |  | 5600 |  |  | 2
2025-01-10 | JOST25010032 | CP08-180-P01-04 | ST-3 | PP09-160T | 1 | 897 | 220 | 4.0773 | 0.50966 | 0.041667 | 0.083333 | 0.33333 | 2025-02-07 08:30 | 2025-02-08 07:44 | 2025-02-21 08:30 |  | 897 |  |  | 3
2025-01-10 | JOST25010032 | CP08-180-P02-04 | ST-3 | PP16-110T | 1 | 897 | 220 | 4.0773 | 0.50966 | 0.041667 | 0.083333 | 0.33333 | 2025-02-07 08:30 | 2025-02-08 07:44 | 2025-02-21 08:30 |  | 897 |  |  | 2
2025-01-10 | JOST25010032 | CP08-180-P03-04 | ST-3 | PP27-110T | 1 | 897 | 220 | 4.0773 | 0.50966 | 0.041667 | 0.083333 | 0.33333 | 2025-02-07 08:30 | 2025-02-08 07:44 | 2025-02-21 08:30 |  | 897 |  |  | 2
2025-01-10 | JOST25010031 | CP08-146-P01-04 | ST-1 | PP06 | 1 | 8163 | 1500 | 5.442 | 0.68025 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-22 11:50 | 2025-03-07 08:30 |  | 8163 |  |  | 2
2025-01-10 | JOST25010031 | CP08-146-P02-04 | ST-1 | PP13-060T | 1 | 8163 | 360 | 22.675 | 2.8344 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-24 15:32 | 2025-03-07 08:30 |  | 8163 |  |  | 2
2025-01-10 | JOST25010031 | CP08-146-P03-04 | ST-1 | PP11-035T | 1 | 8163 | 240 | 34.0125 | 4.2516 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-26 01:32 | 2025-03-07 08:30 |  | 8163 |  |  | 1
2025-01-10 | JOST25010030 | CP08-145-P01-06 | ST-3 | PP09-160T | 1 | 5000 | 300 | 16.6667 | 2.0833 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-19 21:30 | 2025-03-07 08:30 |  | 5000 |  |  | 3
2025-01-10 | JOST25010030 | CP08-145-P02-06 | ST-3 | PP18-150T | 1 | 5000 | 300 | 16.6667 | 2.0833 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-19 21:30 | 2025-03-07 08:30 |  | 5000 |  |  | 2
2025-01-10 | JOST25010030 | CP08-145-P03-06 | ST-3 | PP17-110T | 1 | 5000 | 300 | 16.6667 | 2.0833 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-19 21:30 | 2025-03-03 08:30 |  | 5000 |  |  | 3
2025-01-10 | JOST25010030 | CP08-145-P04-06 | ST-3 | PP16-110T | 1 | 5000 | 300 | 16.6667 | 2.0833 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-19 21:30 | 2025-03-03 08:30 |  | 5000 |  |  | 3
2025-01-10 | JOST25010030 | CP08-145-P05-06 | ST-3 | PP27-110T | 1 | 5000 | 300 | 16.6667 | 2.0833 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-19 21:30 | 2025-03-03 08:30 |  | 5000 |  |  | 3
2025-01-10 | JOST25010034 | CP08-221-P01-05 | ST-4 | PP24-160T | 1 | 1265 | 240 | 5.2708 | 0.65885 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 11:19 | 2025-03-10 08:30 |  | 1265 |  |  | 3
2025-01-10 | JOST25010034 | CP08-221-P02-05 | ST-4 | PP25-160T | 1 | 1265 | 240 | 5.2708 | 0.65885 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 11:19 | 2025-03-10 08:30 |  | 1265 |  |  | 2
2025-01-10 | JOST25010034 | CP08-221-P03-05 | ST-4 | PP20-110T | 1 | 1265 | 240 | 5.2708 | 0.65885 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 11:19 | 2025-03-10 08:30 |  | 1265 |  |  | 2
2025-01-10 | JOST25010034 | CP08-221-P04-05 | ST-4 | PP26-110T | 1 | 1265 | 240 | 5.2708 | 0.65885 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 11:19 | 2025-03-10 08:30 |  | 1265 |  |  | 2
2025-01-10 | JOST25010155 | CA01-051-P02-03 | ST-2 | PP07-016T | 1 | 46640 | 1260 | 37.0159 | 4.627 | 0.041667 | 0.083333 | 0.33333 | 2025-01-24 08:30 | 2025-01-29 10:33 | 2025-02-10 08:30 | 35563 | 11077 |  |  | 1
2025-01-10 | JOST25010132 | CT10-020-P02-06 | ST-4 | PP24-160T | 1 | 1800 | 300 | 6 | 0.75 | 0.041667 | 0.083333 | 0.33333 | 2025-01-31 08:30 | 2025-02-01 13:30 | 2025-02-04 08:30 |  | 1800 |  |  | 2
2025-01-10 | JOST25010132 | CT10-020-P03-06 | ST-4 | PP25-160T | 1 | 1800 | 300 | 6 | 0.75 | 0.041667 | 0.083333 | 0.33333 | 2025-01-31 08:30 | 2025-02-01 13:30 | 2025-02-04 08:30 |  | 1800 |  |  | 3
2025-01-10 | JOST25010132 | CT10-020-P04-06 | ST-4 | PP20-110T | 1 | 1800 | 300 | 6 | 0.75 | 0.041667 | 0.083333 | 0.33333 | 2025-01-31 08:30 | 2025-02-01 13:30 | 2025-02-04 08:30 |  | 1800 |  |  | 1
2025-01-10 | JOST25010132 | CT10-020-P05-06 | ST-4 | PP28-110T | 1 | 1800 | 300 | 6 | 0.75 | 0.041667 | 0.083333 | 0.33333 | 2025-01-31 08:30 | 2025-02-01 13:30 | 2025-02-04 08:30 |  | 1800 |  |  | 2
2025-01-10 | JOST25010133 | CT10-020-P01-06 | SM | SM01 | 1 | 1800 | 360 | 5 | 0.625 | 0.041667 | 0.083333 | 0.33333 | 2025-02-20 08:30 | 2025-02-21 10:30 | 2025-03-06 08:30 |  | 1800 |  |  | 3
2025-01-10 | JOST25010133 | CT10-020-P02-06 | ST-4 | PP24-160T | 1 | 1800 | 300 | 6 | 0.75 | 0.041667 | 0.083333 | 0.33333 | 2025-02-20 08:30 | 2025-02-21 13:30 | 2025-03-06 08:30 |  | 1800 |  |  | 1
2025-01-10 | JOST25010133 | CT10-020-P03-06 | ST-4 | PP25-160T | 1 | 1800 | 300 | 6 | 0.75 | 0.041667 | 0.083333 | 0.33333 | 2025-02-20 08:30 | 2025-02-21 13:30 | 2025-03-06 08:30 |  | 1800 |  |  | 3
2025-01-10 | JOST25010133 | CT10-020-P04-06 | ST-4 | PP20-110T | 1 | 1800 | 300 | 6 | 0.75 | 0.041667 | 0.083333 | 0.33333 | 2025-02-20 08:30 | 2025-02-21 13:30 | 2025-03-06 08:30 |  | 1800 |  |  | 2
2025-01-10 | JOST25010133 | CT10-020-P05-06 | ST-4 | PP28-110T | 1 | 1800 | 300 | 6 | 0.75 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 13:30 | 2025-02-27 08:30 |  | 1800 |  |  | 3
2025-01-10 | JOST25010134 | CT10-021-P01-04 | SM | SM01 | 1 | 1045 | 2280 | 0.45833 | 0.057292 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-13 20:52 | 2025-02-27 08:30 |  | 1045 |  |  | 1
2025-01-10 | JOST25010134 | CT10-021-P02-04 | ST-2 | PP15-080T | 1 | 1045 | 360 | 2.9028 | 0.36285 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 04:12 | 2025-02-27 08:30 |  | 1045 |  |  | 2
2025-01-10 | JOST25010134 | CT10-021-P03-04 | ST-2 | PP15-080T | 1 | 1045 | 360 | 2.9028 | 0.36285 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 04:12 | 2025-02-27 08:30 |  | 1045 |  |  | 3
2025-01-10 | JOST25010135 | CT10-025-P01-06 | ST-3 | PP09-160T | 1 | 2432 | 330 | 7.3697 | 0.92121 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 17:37 | 2025-02-21 08:30 |  | 2432 |  |  | 2
2025-01-10 | JOST25010135 | CT10-025-P02-06 | ST-3 | PP18-150T | 1 | 2432 | 330 | 7.3697 | 0.92121 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 17:37 | 2025-02-21 08:30 |  | 2432 |  |  | 2
2025-01-10 | JOST25010135 | CT10-025-P03-06 | ST-3 | PP17-110T | 1 | 2432 | 330 | 7.3697 | 0.92121 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 17:37 | 2025-02-21 08:30 |  | 2432 |  |  | 2
2025-01-10 | JOST25010135 | CT10-025-P04-06 | ST-3 | PP16-110T | 1 | 2432 | 330 | 7.3697 | 0.92121 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 17:37 | 2025-02-21 08:30 |  | 2432 |  |  | 2
2025-01-10 | JOST25010135 | CT10-025-P05-06 | ST-3 | PP27-110T | 1 | 2432 | 330 | 7.3697 | 0.92121 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 17:37 | 2025-02-21 08:30 |  | 2432 |  |  | 1
2025-01-10 | JOST25010131 | CT10-019-P01-08 | ST-3 | SM01 | 1 | 1400 | 240 | 5.8333 | 0.72917 | 0.041667 | 0.083333 | 0.33333 | 2025-02-20 08:30 | 2025-02-21 13:00 | 2025-03-06 08:30 |  | 1400 |  |  | 3
2025-01-10 | JOST25010131 | CT10-019-P02-08 | ST-3 | PP09-160T | 1 | 1400 | 240 | 5.8333 | 0.72917 | 0.041667 | 0.083333 | 0.33333 | 2025-02-20 08:30 | 2025-02-21 13:00 | 2025-03-06 08:30 |  | 1400 |  |  | 2
2025-01-10 | JOST25010131 | CT10-019-P03-08 | ST-3 | PP18-150T | 1 | 1400 | 240 | 5.8333 | 0.72917 | 0.041667 | 0.083333 | 0.33333 | 2025-02-20 08:30 | 2025-02-21 13:00 | 2025-03-06 08:30 |  | 1400 |  |  | 3
2025-01-10 | JOST25010131 | CT10-019-P04-08 | ST-3 | TP03 | 1 | 1400 | 240 | 5.8333 | 0.72917 | 0.041667 | 0.083333 | 0.33333 | 2025-02-20 08:30 | 2025-02-21 13:00 | 2025-03-06 08:30 |  | 1400 |  |  | 3
2025-01-10 | JOST25010131 | CT10-019-P05-08 | ST-3 | PP17-110T | 1 | 1400 | 240 | 5.8333 | 0.72917 | 0.041667 | 0.083333 | 0.33333 | 2025-02-20 08:30 | 2025-02-21 13:00 | 2025-03-06 08:30 |  | 1400 |  |  | 3
2025-01-10 | JOST25010131 | CT10-019-P06-08 | ST-3 | PP16-110T | 1 | 1400 | 240 | 5.8333 | 0.72917 | 0.041667 | 0.083333 | 0.33333 | 2025-02-20 08:30 | 2025-02-21 13:00 | 2025-03-06 08:30 |  | 1400 |  |  | 3
2025-01-10 | JOST25010131 | CT10-019-P07-08 | ST-3 | PP27-110T | 1 | 1400 | 240 | 5.8333 | 0.72917 | 0.041667 | 0.083333 | 0.33333 | 2025-02-20 08:30 | 2025-02-21 13:00 | 2025-03-06 08:30 |  | 1400 |  |  | 2
2025-01-10 | JOST25010129 | CT10-016-P01-06 | SM | SM01 | 1 | 968 | 5280 | 0.18333 | 0.022917 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-13 20:03 | 2025-02-27 08:30 |  | 968 |  |  | 2
2025-01-10 | JOST25010129 | CT10-016-P02-06 | ST-3 | PP17-110T | 1 | 968 | 360 | 2.6889 | 0.33611 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 03:34 | 2025-02-27 08:30 |  | 968 |  |  | 2
2025-01-10 | JOST25010129 | CT10-016-P03-06 | ST-3 | PP16-110T | 1 | 968 | 240 | 4.0333 | 0.50417 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 07:36 | 2025-02-27 08:30 |  | 968 |  |  | 3
2025-01-10 | JOST25010129 | CT10-016-P04-06 | ST-3 | PP27-110T | 1 | 968 | 240 | 4.0333 | 0.50417 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 07:36 | 2025-02-27 08:30 |  | 968 |  |  | 3
2025-01-10 | JOST25010129 | CT10-016-P05-06 | ST-3 | TP03 | 1 | 968 | 300 | 3.2267 | 0.40333 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 05:11 | 2025-02-27 08:30 |  | 968 |  |  | 1
2025-01-10 | JOST25010128 | CT10-014-P01-06 | ST-3 | PP09-160T | 1 | 2128 | 330 | 6.4485 | 0.80606 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 14:51 | 2025-02-21 08:30 | 1381 | 747 |  |  | 1
2025-01-10 | JOST25010128 | CT10-014-P02-06 | ST-3 | PP18 | 1 | 2128 | 330 | 6.4485 | 0.80606 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 14:51 | 2025-02-21 08:30 | 1381 | 747 |  |  | 3
2025-01-10 | JOST25010128 | CT10-014-P03-06 | ST-3 | PP17-110T | 1 | 2128 | 330 | 6.4485 | 0.80606 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 14:51 | 2025-02-21 08:30 | 1381 | 747 |  |  | 1
2025-01-10 | JOST25010128 | CT10-014-P04-06 | ST-3 | PP16-110T | 1 | 2128 | 330 | 6.4485 | 0.80606 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 14:51 | 2025-02-21 08:30 | 1381 | 747 |  |  | 2
2025-01-10 | JOST25010128 | CT10-014-P05-06 | ST-3 | PP27-110T | 2 | 2128 | 330 | 6.4485 | 0.80606 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 14:51 | 2025-02-21 08:30 | 1381 | 747 |  |  | 3
2025-01-10 | JOTP25010127 | CT10-009-P01-05 | ST-3 | SW01 | 1 | 300 | 60 | 5 | 0.625 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 10:30 | 2025-03-03 08:30 |  | 300 |  |  | 1
2025-01-10 | JOTP25010127 | CT10-009-P02-05 | ST-3 | SW01 | 1 | 300 | 40 | 7.5 | 0.9375 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 18:00 | 2025-03-03 08:30 |  | 300 |  |  | 2
2025-01-10 | JOTP25010127 | CT10-009-P03-05 | TR | PAINTING | 1 | 300 | 40 | 7.5 | 0.9375 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 18:00 | 2025-03-03 08:30 |  | 300 |  |  | 3
2025-01-10 | JOTP25010127 | CT10-009-P04-05 | ST-1 | PAINTING | 1 | 300 | 40 | 7.5 | 0.9375 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 18:00 | 2025-03-03 08:30 |  | 300 |  |  | 1
2025-01-10 | JOTP25010121 | CP08-594-P02-03 | ST | PP05 | 1 | 630 | 360 | 1.75 | 0.21875 | 0.041667 | 0.083333 | 0.33333 | 2025-01-13 08:30 | 2025-01-14 00:45 | 2025-01-22 08:30 |  | 630 |  |  | 3
2025-01-13 | JOTP25010119 | CP08-584-P01-04 | PB | SW09 | 1 | 225 | 60 | 3.75 | 0.46875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-20 08:30 | 2025-02-21 06:45 | 2025-03-03 08:30 |  | 225 |  |  | 2
2025-01-13 | JOTP25010119 | CP08-584-P02-04 | PB | OPT | 1 | 225 | 30 | 7.5 | 0.9375 | 0.041667 | 0.083333 | 0.33333 | 2025-02-20 08:30 | 2025-02-21 18:00 | 2025-03-03 08:30 |  | 225 |  |  | 3
2025-01-13 | JOTP25010119 | CP08-584-P03-04 | PB | OPT | 1 | 225 | 60 | 3.75 | 0.46875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-20 08:30 | 2025-02-21 06:45 | 2025-03-03 08:30 |  | 225 |  |  | 1
2025-01-13 | OST25010123 | CP08-601-P01-03 | ST | PP29 | 1 | 140 | 120 | 1.1667 | 0.14583 | 0.041667 | 0.083333 | 0.33333 | 2025-02-08 08:30 | 2025-02-08 23:00 | 2025-02-20 08:30 |  | 140 |  |  | 2
2025-01-13 | OST25010123 | CP08-601-P02-03 | ST | PP33 | 1 | 140 | 120 | 1.1667 | 0.14583 | 0.041667 | 0.083333 | 0.33333 | 2025-02-08 08:30 | 2025-02-08 23:00 | 2025-02-20 08:30 |  | 140 |  |  | 3
2025-01-13 | OST25010123 | CP08-601-P03-03 | ST | PP29 | 1 | 140 | 120 | 1.1667 | 0.14583 | 0.041667 | 0.083333 | 0.33333 | 2025-02-08 08:30 | 2025-02-08 23:00 | 2025-02-20 08:30 |  | 140 |  |  | 2
2025-01-13 | JOST25010124 | CT10-003-P01-06 | ST-3 | PP18 | 1 | 600 | 240 | 2.5 | 0.3125 | 0.041667 | 0.083333 | 0.33333 | 2025-02-07 08:30 | 2025-02-08 03:00 | 2025-02-18 08:30 |  | 600 |  |  | 2
2025-01-13 | JOST25010124 | CT10-003-P02-06 | ST-3 | PP17-110T | 1 | 600 | 240 | 2.5 | 0.3125 | 0.041667 | 0.083333 | 0.33333 | 2025-02-07 08:30 | 2025-02-08 03:00 | 2025-02-18 08:30 |  | 600 |  |  | 2
2025-01-13 | JOST25010124 | CT10-003-P03-06 | ST-3 | PP16-110T | 1 | 600 | 240 | 2.5 | 0.3125 | 0.041667 | 0.083333 | 0.33333 | 2025-02-07 08:30 | 2025-02-08 03:00 | 2025-02-18 08:30 |  | 600 |  |  | 2
2025-01-13 | JOST25010124 | CT10-003-P04-06 | ST-3 | PP27-110T | 1 | 600 | 240 | 2.5 | 0.3125 | 0.041667 | 0.083333 | 0.33333 | 2025-02-07 08:30 | 2025-02-08 03:00 | 2025-02-18 08:30 |  | 600 |  |  | 1
2025-01-13 | JOST25010124 | CT10-003-P05-06 | ST-3 | SW01 | 1 | 600 | 240 | 2.5 | 0.3125 | 0.041667 | 0.083333 | 0.33333 | 2025-02-07 08:30 | 2025-02-08 03:00 | 2025-02-18 08:30 |  | 600 |  |  | 3
2025-01-13 | JOTP25010126 | CT10-009-P01-05 | ST-3 | SW01 | 1 | 200 | 60 | 3.3333 | 0.41667 | 0.041667 | 0.083333 | 0.33333 | 2025-02-14 08:30 | 2025-02-15 05:30 | 2025-02-24 08:30 |  | 200 |  |  | 2
2025-01-13 | JOTP25010126 | CT10-009-P02-05 | ST-3 | SW01 | 1 | 200 | 40 | 5 | 0.625 | 0.041667 | 0.083333 | 0.33333 | 2025-02-14 08:30 | 2025-02-15 10:30 | 2025-02-24 08:30 |  | 200 |  |  | 3
2025-01-13 | JOTP25010126 | CT10-009-P03-05 | TR | PAINTING | 1 | 200 | 40 | 5 | 0.625 | 0.041667 | 0.083333 | 0.33333 | 2025-02-14 08:30 | 2025-02-15 10:30 | 2025-02-24 08:30 |  | 200 |  |  | 3
2025-01-13 | JOTP25010126 | CT10-009-P04-05 | ST-1 | PAINTING | 1 | 200 | 40 | 5 | 0.625 | 0.041667 | 0.083333 | 0.33333 | 2025-02-14 08:30 | 2025-02-15 10:30 | 2025-02-24 08:30 |  | 200 |  |  | 3
2025-01-13 | JOTP25010102 | CP08-565-P01-04 | TR | TM05 | 1 | 500 | 80 | 6.25 | 0.78125 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 14:15 | 2025-03-03 08:30 |  | 500 |  |  | 3
2025-01-13 | JOTP25010102 | CP08-565-P02-04 | PB | PB03 | 1 | 500 | 120 | 4.1667 | 0.52083 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 08:00 | 2025-03-03 08:30 |  | 500 |  |  | 2
2025-01-13 | JOTP25010102 | CP08-565-P03-04 | PB | PB01 | 1 | 500 | 90 | 5.5556 | 0.69444 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 12:10 | 2025-03-03 08:30 |  | 500 |  |  | 2
2025-01-13 | JOST25010101 | CP08-561-P01-04 | ST | PP25-160T | 1 | 650 | 360 | 1.8056 | 0.22569 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 00:55 | 2025-03-03 08:30 |  | 650 |  |  | 2
2025-01-13 | JOST25010101 | CP08-561-P02-04 | ST | PP26 | 1 | 650 | 300 | 2.1667 | 0.27083 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 02:00 | 2025-03-03 08:30 |  | 650 |  |  | 3
2025-01-13 | JOST25010101 | CP08-561-P03-04 | ST | PP20-110T | 1 | 650 | 300 | 2.1667 | 0.27083 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 02:00 | 2025-03-03 08:30 |  | 650 |  |  | 3
2025-01-14 | JOST25010100 | CP08-560-P01-04 | ST | PP09 | 1 | 405 | 360 | 1.125 | 0.14062 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-10 22:52 | 2025-02-24 08:30 |  | 405 |  |  | 1
2025-01-14 | JOST25010100 | CP08-560-P02-04 | ST | PP18 | 1 | 405 | 300 | 1.35 | 0.16875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-10 23:33 | 2025-02-24 08:30 |  | 405 |  |  | 1
2025-01-14 | JOST25010100 | CP08-560-P03-04 | ST | PP27-110T | 1 | 405 | 300 | 1.35 | 0.16875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-10 23:33 | 2025-02-24 08:30 |  | 405 |  |  | 3
2025-01-14 | JOST25010099 | CP08-559-P01-02 | ST | PP32 | 1 | 65052 | 1680 | 38.7214 | 4.8402 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-22 15:40 | 2025-03-03 08:30 |  | 65052 |  |  | 3
2025-01-14 | JOST25010098 | CP08-559-P01-02 | ST | PP32 | 1 | 52950 | 1680 | 31.5179 | 3.9397 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-14 18:03 | 2025-02-24 08:30 |  | 52950 |  |  | 1
2025-01-14 | JOST25010097 | CP08-558-P01-02 | ST | PP30-200T | 1 | 59259 | 1500 | 39.506 | 4.9383 | 0.041667 | 0.083333 | 0.33333 | 2025-02-14 08:30 | 2025-02-19 18:01 | 2025-02-28 08:30 |  | 59259 |  |  | 2
2025-01-14 | JOST25010096 | CP08-555-P01-04 | TR | PP17-110T | 1 | 3200 | 240 | 13.3333 | 1.6667 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-19 11:30 | 2025-03-03 08:30 |  | 3200 |  |  | 3
2025-01-14 | JOST25010096 | CP08-555-P02-04 | ST | PP16-110T | 1 | 3200 | 240 | 13.3333 | 1.6667 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-19 11:30 | 2025-03-03 08:30 |  | 3200 |  |  | 1
2025-01-14 | JOST25010096 | CP08-555-P03-04 | ST | PP27-110T | 1 | 3200 | 240 | 13.3333 | 1.6667 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-19 11:30 | 2025-03-03 08:30 |  | 3200 |  |  | 3
2025-01-14 | JOST25010094 | CP08-539-P01-11 | ST-3 | PP09-160T | 1 | 1840 | 120 | 15.3333 | 1.9167 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-23 17:30 | 2025-03-07 08:30 |  | 1840 |  |  | 2
2025-01-14 | JOST25010094 | CP08-539-P02-11 | ST-3 | PP18-150T | 1 | 1840 | 120 | 15.3333 | 1.9167 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-23 17:30 | 2025-03-07 08:30 |  | 1840 |  |  | 3
2025-01-14 | JOST25010094 | CP08-539-P03-11 | ST-3 | PP17-110T | 1 | 1840 | 120 | 15.3333 | 1.9167 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-23 17:30 | 2025-03-07 08:30 |  | 1840 |  |  | 1
2025-01-14 | JOST25010094 | CP08-539-P04-11 | ST-3 | TP03 | 1 | 1840 | 120 | 15.3333 | 1.9167 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-23 17:30 | 2025-03-07 08:30 |  | 1840 |  |  | 2
2025-01-14 | JOST25010094 | CP08-539-P05-11 | ST-3 | PP16-110T | 1 | 1840 | 120 | 15.3333 | 1.9167 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-23 17:30 | 2025-03-07 08:30 |  | 1840 |  |  | 3
2025-01-14 | JOST25010094 | CP08-539-P06-11 | ST-3 | TP03 | 1 | 1840 | 120 | 15.3333 | 1.9167 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-23 17:30 | 2025-03-07 08:30 |  | 1840 |  |  | 2
2025-01-14 | JOST25010094 | CP08-539-P07-11 | ST-3 | PP17-110T | 1 | 1840 | 120 | 15.3333 | 1.9167 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-23 17:30 | 2025-03-07 08:30 |  | 1840 |  |  | 2
2025-01-14 | JOST25010094 | CP08-539-P08-11 | ST-3 | PP16-110T | 1 | 1840 | 120 | 15.3333 | 1.9167 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-23 17:30 | 2025-03-07 08:30 |  | 1840 |  |  | 2
2025-01-14 | JOST25010094 | CP08-539-P09-11 | ST-3 | PP27-110T | 1 | 1840 | 120 | 15.3333 | 1.9167 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-23 17:30 | 2025-03-07 08:30 |  | 1840 |  |  | 2
2025-01-14 | JOST25010094 | CP08-539-P10-11 | ST-3 | SW01 | 1 | 1840 | 120 | 15.3333 | 1.9167 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-23 17:30 | 2025-03-07 08:30 |  | 1840 |  |  | 1
2025-01-14 | JOST25010147 | CO02-017-P01-04 | SM | SM01 | 1 | 3150 | 2400 | 1.3125 | 0.16406 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-10 23:26 | 2025-02-24 08:30 |  | 3150 |  |  | 3
2025-01-14 | JOST25010147 | CO02-017-P02-04 | ST-1 | PP04-060T | 1 | 3150 | 360 | 8.75 | 1.0938 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 21:45 | 2025-02-24 08:30 |  | 3150 |  |  | 2
2025-01-14 | JOST25010147 | CO02-017-P03-04 | ST-1 | PP03-060T | 1 | 3150 | 240 | 13.125 | 1.6406 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-12 10:52 | 2025-02-24 08:30 |  | 3150 |  |  | 3
2025-01-16 | JOTP25010162 | CT10-006-P02-08 | ST-2 | PP14-080T | 1 | 200 | 240 | 0.83333 | 0.10417 | 0.041667 | 0.083333 | 0.33333 | 2025-01-20 08:30 | 2025-01-20 22:00 | 2025-02-03 08:30 |  | 200 |  |  | 3
2025-01-16 | JOTP25010162 | CT10-006-P03-08 | ST-2 | PP14-080T | 1 | 200 | 240 | 0.83333 | 0.10417 | 0.041667 | 0.083333 | 0.33333 | 2025-01-20 08:30 | 2025-01-20 22:00 | 2025-02-03 08:30 |  | 200 |  |  | 3
2025-01-16 | JOTP25010162 | CT10-006-P04-08 | ST-3 | PP22-060T | 1 | 200 | 240 | 0.83333 | 0.10417 | 0.041667 | 0.083333 | 0.33333 | 2025-01-20 08:30 | 2025-01-20 22:00 | 2025-02-03 08:30 |  | 200 |  |  | 3
2025-01-16 | JOTP25010162 | CT10-006-P05-08 | TP | TP03 | 1 | 200 | 100 | 2 | 0.25 | 0.041667 | 0.083333 | 0.33333 | 2025-01-20 08:30 | 2025-01-21 01:30 | 2025-02-03 08:30 |  | 200 |  |  | 2
2025-01-16 | JOTP25010162 | CT10-006-P06-08 | TR | PB04 | 1 | 200 | 80 | 2.5 | 0.3125 | 0.041667 | 0.083333 | 0.33333 | 2025-01-20 08:30 | 2025-01-21 03:00 | 2025-02-03 08:30 |  | 200 |  |  | 2
2025-01-16 | JOTP25010162 | CT10-006-P07-08 | TR | PB03 | 1 | 200 | 240 | 0.83333 | 0.10417 | 0.041667 | 0.083333 | 0.33333 | 2025-01-20 08:30 | 2025-01-20 22:00 | 2025-02-03 08:30 |  | 200 |  |  | 2
2025-01-16 | JOST24120403 | CP08-599-P01-04 | TP | SM01 | 1 | 104 | 240 | 0.43333 | 0.054167 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-17 20:48 | 2025-03-03 08:30 |  | 104 |  |  | 3
2025-01-16 | JOST24120403 | CP08-599-P02-04 | TP | SM01 | 1 | 104 | 360 | 0.28889 | 0.036111 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-17 20:22 | 2025-03-03 08:30 |  | 104 |  |  | 3
2025-01-16 | JOST24120403 | CP08-599-P03-04 | ST | PP24 | 1 | 104 | 180 | 0.57778 | 0.072222 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-17 21:14 | 2025-03-03 08:30 |  | 104 |  |  | 1
2025-01-16 | JOAW25010001 | CD11-027-P01-06 | WN | SW08 | 1 | 5000 | 120 | 41.6667 | 5.2083 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-03-02 00:30 | 2025-03-17 08:30 |  | 5000 |  |  | 1
2025-01-16 | JOAW25010001 | CD11-027-P02-06 | WN | PP23-060T | 1 | 5000 | 300 | 16.6667 | 2.0833 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-26 21:30 | 2025-03-17 08:30 |  | 5000 |  |  | 3
2025-01-16 | JOAW25010001 | CD11-027-P05-06 | WN | TW01 | 1 | 5000 | 400 | 12.5 | 1.5625 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-26 09:00 | 2025-03-17 08:30 |  | 5000 |  |  | 1
2025-01-16 | JOAW24100349 | CA16-011-P01-03 | FM | SW05 | 1 | 60000 | 450 | 133.3333 | 16.6667 | 0.041667 | 0.083333 | 0.33333 | 2025-02-19 08:30 | 2025-03-08 11:30 | 2025-03-19 08:30 |  | 60000 |  |  | 2
2025-01-16 | JOAW24100349 | CA16-011-P02-03 | FM | OPT | 1 | 60000 | 900 | 66.6667 | 8.3333 | 0.041667 | 0.083333 | 0.33333 | 2025-02-19 08:30 | 2025-02-28 03:30 | 2025-03-19 08:30 |  | 60000 |  |  | 3
2025-01-16 | JOST24120254 | CO02-001-P04-05 | ST-3 | PP10-080T | 1 | 10240 | 300 | 34.1333 | 4.2667 | 0.041667 | 0.083333 | 0.33333 | 2025-02-06 08:30 | 2025-02-11 01:54 | 2025-02-20 08:30 |  | 10240 |  |  | 1
2025-01-16 | JOST24120255 | CO02-002-P02-04 | ST-1 | PP03-060T | 1 | 4167 | 720 | 5.7875 | 0.72344 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 12:52 | 2025-02-24 08:30 | 1932 | 2235 |  |  | 2
2025-01-16 | JOST24120255 | CO02-002-P03-04 | ST-2 | PP01-110T | 1 | 4167 | 360 | 11.575 | 1.4469 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-12 06:14 | 2025-02-24 08:30 |  | 4167 |  |  | 3
2025-01-16 | JOST24120256 | CO02-003-P01-04 | SM | SM01 | 1 | 4332 | 4560 | 0.95 | 0.11875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-10 22:21 | 2025-02-24 08:30 |  | 4332 |  |  | 1
2025-01-16 | JOST24120256 | CO02-003-P02-04 | ST-1 | PP03-060T | 1 | 4332 | 720 | 6.0167 | 0.75208 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 13:33 | 2025-02-24 08:30 |  | 4332 |  |  | 3
2025-01-17 | JOST24120256 | CO02-003-P03-04 | ST-4 | PP26-110T | 1 | 4332 | 450 | 9.6267 | 1.2033 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-12 00:23 | 2025-02-24 08:30 |  | 4332 |  |  | 2
2025-01-17 | JOST24120389 | CP08-567-P01-06 | ST | PP33 | 1 | 450 | 180 | 2.5 | 0.3125 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 03:00 | 2025-02-24 08:30 |  | 450 |  |  | 3
2025-01-17 | JOST24120389 | CP08-567-P02-06 | ST | PP29 | 1 | 450 | 180 | 2.5 | 0.3125 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 03:00 | 2025-02-24 08:30 |  | 450 |  |  | 1
2025-01-17 | JOST24120389 | CP08-567-P03-06 | ST | PP29 | 1 | 450 | 180 | 2.5 | 0.3125 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 03:00 | 2025-02-24 08:30 |  | 450 |  |  | 2
2025-01-17 | JOST24120389 | CP08-567-P04-06 | ST | PP30 | 1 | 450 | 180 | 2.5 | 0.3125 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 03:00 | 2025-02-24 08:30 |  | 450 |  |  | 3
2025-01-17 | JOST24120389 | CP08-567-P05-06 | ST | PP33 | 1 | 450 | 180 | 2.5 | 0.3125 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 03:00 | 2025-02-24 08:30 |  | 450 |  |  | 2
2025-01-17 | JOST24120388 | CP08-558-P01-02 | ST | PP30-200T | 1 | 60000 | 1500 | 40 | 5 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-15 19:30 | 2025-02-24 08:30 |  | 60000 |  |  | 2
2025-01-17 | JOST24120402 | CP08-598-P01-03 | ST | SM01 | 1 | 96 | 240 | 0.4 | 0.05 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-17 20:42 | 2025-03-03 08:30 |  | 96 |  |  | 2
2025-01-17 | JOST24120402 | CP08-598-P02-03 | ST | PP21 | 1 | 96 | 180 | 0.53333 | 0.066667 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-17 21:06 | 2025-03-03 08:30 |  | 96 |  |  | 2
2025-01-17 | JOST24120358 | CP08-504-P01-02 | ST-4 | PP29-250T | 1 | 216 | 120 | 1.8 | 0.225 | 0.041667 | 0.083333 | 0.33333 | 2025-02-07 08:30 | 2025-02-08 00:54 | 2025-02-14 08:30 |  | 216 |  |  | 1
2025-01-17 | JOTP24120349 | CP08-428A-P01-03 | TR | TM03 | 1 | 450 | 47 | 9.5745 | 1.1968 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-12 00:13 | 2025-02-24 08:30 |  | 450 |  |  | 3
2025-01-17 | JOTP24120349 | CP08-428A-P02-03 | TR | PB07 | 1 | 450 | 96 | 4.6875 | 0.58594 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 09:34 | 2025-02-24 08:30 |  | 450 |  |  | 2
2025-01-17 | JOTP24120346 | CP08-427-P02-03 | TR | PB05 | 1 | 600 | 30 | 20 | 2.5 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-13 07:30 | 2025-02-24 08:30 |  | 600 |  |  | 3
2025-01-17 | JOST24120342 | CP08-369/CP08-370-P01-05 | SM | SM01 | 1 | 1680 | 360 | 4.6667 | 0.58333 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 09:30 | 2025-02-24 08:30 |  | 1680 |  |  | 3
2025-01-17 | JOST24120342 | CP08-369/CP08-370-P02-05 | ST-3 | PP25-160T | 1 | 1680 | 300 | 5.6 | 0.7 | 0.041667 | 0.083333 | 0.33333 | 2025-02-14 08:30 | 2025-02-15 12:18 | 2025-02-28 08:30 |  | 1680 |  |  | 3
2025-01-17 | JOST24120342 | CP08-369/CP08-370-P03-05 | ST-4 | PP20-110T | 1 | 1680 | 300 | 5.6 | 0.7 | 0.041667 | 0.083333 | 0.33333 | 2025-02-14 08:30 | 2025-02-15 12:18 | 2025-02-28 08:30 |  | 1680 |  |  | 3
2025-01-17 | JOST24120342 | CP08-369/CP08-370-P04-05 | ST-3 | PP28-110T | 1 | 1680 | 300 | 5.6 | 0.7 | 0.041667 | 0.083333 | 0.33333 | 2025-02-14 08:30 | 2025-02-15 12:18 | 2025-02-28 08:30 |  | 1680 |  |  | 2
2025-01-17 | JOTP24120353 | CP08-440-P01-03 | TR | TM03 | 1 | 880 | 96 | 9.1667 | 1.1458 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 23:00 | 2025-03-03 08:30 |  | 880 |  |  | 2
2025-01-17 | JOTP24120353 | CP08-440-P02-03 | TR | PB01 | 1 | 880 | 180 | 4.8889 | 0.61111 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 10:10 | 2025-03-03 08:30 |  | 880 |  |  | 2
2025-01-17 | JOST24120363 | CP08-510-P01-05 | ST-4 | PP29-250T | 1 | 1500 | 150 | 10 | 1.25 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-19 01:30 | 2025-03-03 08:30 |  | 1500 |  |  | 1
2025-01-17 | JOST24120363 | CP08-510-P02-05 | ST-4 | PP30 | 1 | 1500 | 120 | 12.5 | 1.5625 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-19 09:00 | 2025-03-03 08:30 |  | 1500 |  |  | 2
2025-01-17 | JOST24120363 | CP08-510-P03-05 | ST-4 | PP29-250T | 1 | 1500 | 120 | 12.5 | 1.5625 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-19 09:00 | 2025-03-03 08:30 |  | 1500 |  |  | 3
2025-01-17 | JOST24120363 | CP08-510-P04-05 | ST-4 | PP30 | 1 | 1500 | 120 | 12.5 | 1.5625 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-19 09:00 | 2025-03-03 08:30 |  | 1500 |  |  | 1
2025-01-17 | JOST24120377 | CP08-554C-P01-04 | ST | PP29 | 1 | 405 | 360 | 1.125 | 0.14062 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-10 22:52 | 2025-02-24 08:30 |  | 405 |  |  | 2
2025-01-17 | JOST24120377 | CP08-554C-P02-04 | ST | PP30-200T | 1 | 405 | 360 | 1.125 | 0.14062 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-10 22:52 | 2025-02-24 08:30 |  | 405 |  |  | 3
2025-01-17 | JOST24120377 | CP08-554C-P03-04 | ST | PP21 | 1 | 405 | 240 | 1.6875 | 0.21094 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 00:34 | 2025-02-24 08:30 |  | 405 |  |  | 1
2025-01-17 | JOST24120340 | CP08-368-P01-02 | ST-3 | PP29 | 1 | 200 | 68 | 2.9412 | 0.36765 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 04:19 | 2025-02-24 08:30 |  | 200 |  |  | 3
2025-01-17 | JOST24120335 | CP08-350-P01-04 | ST-4 | PP25-160T | 1 | 4400 | 300 | 14.6667 | 1.8333 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-12 15:30 | 2025-02-24 08:30 |  | 4400 |  |  | 2
2025-01-17 | JOST24120335 | CP08-350-P02-04 | ST-3 | PP20-110T | 1 | 4400 | 300 | 14.6667 | 1.8333 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-12 15:30 | 2025-02-24 08:30 |  | 4400 |  |  | 3
2025-01-17 | JOST24120335 | CP08-350-P03-04 | ST-4 | PP28-110T | 1 | 4400 | 300 | 14.6667 | 1.8333 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-12 15:30 | 2025-02-24 08:30 |  | 4400 |  |  | 1
2025-01-17 | JOST24120325 | CP08-256-P01-02 | ST-1 | PP29 | 2 | 4186 | 240 | 17.4417 | 2.1802 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-12 23:50 | 2025-02-24 08:30 |  | 4186 |  |  | 2
2025-01-17 | JOAW24120316 | CP08-231A-P01-03 | WN | WS01 | 1 | 2000 | 900 | 2.2222 | 0.27778 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 02:10 | 2025-02-27 08:30 |  | 2000 |  |  | 3
2025-01-17 | JOAW24120316 | CP08-231A-P02-03 | WN | JIG-HAND BEND | 1 | 2000 | 120 | 16.6667 | 2.0833 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-15 21:30 | 2025-02-27 08:30 |  | 2000 |  |  | 2
2025-01-17 | JOAW24120317 | CP08-231B-P01-06 | WN | WS01 | 1 | 4000 | 720 | 5.5556 | 0.69444 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 12:10 | 2025-02-27 08:30 |  | 4000 |  |  | 2
2025-01-17 | JOAW24120317 | CP08-231B-P02-06 | WN | PP23-060T | 1 | 4000 | 330 | 12.1212 | 1.5152 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-15 07:52 | 2025-02-27 08:30 |  | 4000 |  |  | 2
2025-01-17 | JOAW24120317 | CP08-231B-P03-06 | WN | JIG-HAND BEND | 1 | 4000 | 240 | 16.6667 | 2.0833 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-15 21:30 | 2025-02-27 08:30 |  | 4000 |  |  | 1
2025-01-17 | JOAW24120317 | CP08-231B-P04-06 | WN | PP23-060T | 1 | 4000 | 420 | 9.5238 | 1.1905 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-15 00:04 | 2025-02-27 08:30 |  | 4000 |  |  | 2
2025-01-17 | JOAW24120317 | CP08-231B-P05-06 | WN | PP23 | 1 | 4000 | 240 | 16.6667 | 2.0833 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-15 21:30 | 2025-02-27 08:30 |  | 4000 |  |  | 3
2025-01-17 | JOAW24120318 | CP08-231C-P01-03 | WN | WS01 | 1 | 2000 | 900 | 2.2222 | 0.27778 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 02:10 | 2025-02-27 08:30 |  | 2000 |  |  | 1
2025-01-17 | JOAW24120318 | CP08-231C-P02-03 | WN | JIG-HAND BEND | 1 | 2000 | 420 | 4.7619 | 0.59524 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 09:47 | 2025-02-27 08:30 |  | 2000 |  |  | 2
2025-01-17 | JOAW24120319 | CP08-231D-P01-02 | WN | WS01 | 1 | 9000 | 960 | 9.375 | 1.1719 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 23:38 | 2025-02-27 08:30 |  | 9000 |  |  | 3
2025-01-17 | JOAW24120320 | CP08-231E-P01-02 | WN | WS01 | 1 | 8000 | 720 | 11.1111 | 1.3889 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-15 04:50 | 2025-02-27 08:30 |  | 8000 |  |  | 1
2025-01-17 | JOAW24120321 | CP08-231F-P01-02 | WN | WS01 | 1 | 8000 | 900 | 8.8889 | 1.1111 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 22:10 | 2025-02-27 08:30 |  | 8000 |  |  | 3
2025-01-17 | JOAW24120322 | CP08-231G-P01-02 | WN | WS01 | 1 | 7000 | 840 | 8.3333 | 1.0417 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 20:30 | 2025-02-27 08:30 |  | 7000 |  |  | 2
2025-01-17 | JOST24120306 | CP08-152-P01-05 | SM | SM01 | 1 | 1755 | 3120 | 0.5625 | 0.070312 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-10 21:11 | 2025-02-24 08:30 |  | 1755 |  |  | 3
2025-01-17 | JOST24120306 | CP08-152-P02-05 | ST-3 | PP28-110T | 1 | 1755 | 360 | 4.875 | 0.60938 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 10:08 | 2025-02-24 08:30 |  | 1755 |  |  | 1
2025-01-17 | JOST24120306 | CP08-152-P03-05 | ST-4 | PP20-110T | 1 | 1755 | 360 | 4.875 | 0.60938 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 10:08 | 2025-02-24 08:30 |  | 1755 |  |  | 2
2025-01-17 | JOST24120306 | CP08-152-P04-05 | ST-4 | PP26-110T | 1 | 1755 | 360 | 4.875 | 0.60938 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 10:08 | 2025-02-24 08:30 |  | 1755 |  |  | 3
2025-01-17 | JOST24120304 | CP08-080-P01-02 | ST-2 | PP01-110T | 1 | 1650 | 3000 | 0.55 | 0.06875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-10 21:09 | 2025-02-24 08:30 |  | 1650 |  |  | 2
2025-01-17 | JOST24120303 | CP08-079-P01-02 | ST-3 | PP01-110T | 1 | 2601 | 3000 | 0.867 | 0.10837 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-10 22:06 | 2025-02-24 08:30 |  | 2601 |  |  | 2
2025-01-17 | JOST24120323 | CP08-254-P01-05 | ST-3 | PP25-160T | 1 | 2100 | 300 | 7 | 0.875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 16:30 | 2025-03-03 08:30 |  | 2100 |  |  | 2
2025-01-17 | JOST24120323 | CP08-254-P02-05 | ST-3 | PP26-110T | 1 | 2100 | 300 | 7 | 0.875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 16:30 | 2025-03-03 08:30 |  | 2100 |  |  | 2
2025-01-17 | JOST24120323 | CP08-254-P03-05 | ST-3 | PP20-110T | 1 | 2100 | 300 | 7 | 0.875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 16:30 | 2025-03-03 08:30 |  | 2100 |  |  | 1
2025-01-17 | JOST24120323 | CP08-254-P04-05 | ST-3 | PP28-110T | 2 | 2100 | 300 | 7 | 0.875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 16:30 | 2025-03-03 08:30 |  | 2100 |  |  | 3
2025-01-17 | JOST24120327 | CP08-293-P01-06 | ST-3 | PP25-160T | 1 | 2100 | 360 | 5.8333 | 0.72917 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 13:00 | 2025-03-03 08:30 |  | 2100 |  |  | 2
2025-01-17 | JOST24120327 | CP08-293-P02-06 | ST-3 | PP26-110T | 1 | 4000 | 360 | 11.1111 | 1.3889 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-19 04:50 | 2025-03-03 08:30 |  | 4000 |  |  | 3
2025-01-17 | JOST24120327 | CP08-293-P03-06 | ST-3 | PP20-110T | 1 | 4000 | 360 | 11.1111 | 1.3889 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-19 04:50 | 2025-03-03 08:30 |  | 4000 |  |  | 3
2025-01-17 | JOST24120327 | CP08-293-P04-06 | ST-3 | PP28-110T | 1 | 4000 | 360 | 11.1111 | 1.3889 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-19 04:50 | 2025-03-03 08:30 |  | 4000 |  |  | 3
2025-01-17 | JOST24120327 | CP08-293-P05-06 | ST-3 | PP24-160T | 2 | 4000 | 360 | 11.1111 | 1.3889 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-19 04:50 | 2025-03-03 08:30 |  | 4000 |  |  | 3
2025-01-17 | JOTP24120330 | CP08-339-P01-04 | TR | SM01 | 1 | 308 | 240 | 1.2833 | 0.16042 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-17 23:21 | 2025-03-03 08:30 |  | 308 |  |  | 2
2025-01-17 | JOTP24120330 | CP08-339-P02-04 | TR | TM03 | 1 | 308 | 100 | 3.08 | 0.385 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 04:44 | 2025-03-03 08:30 |  | 308 |  |  | 2
2025-01-17 | JOTP24120330 | CP08-339-P03-04 | TR | PB01 | 1 | 308 | 51 | 6.0392 | 0.7549 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 13:37 | 2025-03-03 08:30 |  | 308 |  |  | 2
2025-01-17 | JOST24120308 | CP08-154-P01-04 | SM | SM01 | 1 | 1750 | 12600 | 0.13889 | 0.017361 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-10 19:55 | 2025-02-24 08:30 |  | 1750 |  |  | 1
2025-01-17 | JOST24120308 | CP08-154-P02-04 | ST-4 | PP16-110T | 1 | 1750 | 360 | 4.8611 | 0.60764 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 10:05 | 2025-02-24 08:30 |  | 1750 |  |  | 2
2025-01-17 | JOST24120308 | CP08-154-P03-04 | ST-4 | PP17-110T | 1 | 1750 | 180 | 9.7222 | 1.2153 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-12 00:40 | 2025-02-24 08:30 |  | 1750 |  |  | 3
2025-01-17 | JOTP24120350 | CP08-428B-P01-03 | TR | TM06 | 1 | 342 | 65 | 5.2615 | 0.65769 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-22 11:17 | 2025-03-07 08:30 |  | 342 |  |  | 1
2025-01-17 | JOTP24120350 | CP08-428B-P02-03 | TR | PB04 | 1 | 342 | 72 | 4.75 | 0.59375 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-22 09:45 | 2025-03-07 08:30 |  | 342 |  |  | 2
2025-01-17 | JOTP24120351 | CP08-428C-P01-03 | TR | TM06 | 1 | 344 | 60 | 5.7333 | 0.71667 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-22 12:42 | 2025-03-07 08:30 |  | 344 |  |  | 3
2025-01-17 | JOTP24120351 | CP08-428C-P02-03 | TR | PB04 | 1 | 344 | 95 | 3.6211 | 0.45263 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-22 06:22 | 2025-03-07 08:30 |  | 344 |  |  | 1
2025-01-17 | JOTP24120352 | CP08-428D-P01-03 | TR | TM06 | 1 | 336 | 55 | 6.1091 | 0.76364 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-22 13:50 | 2025-03-07 08:30 |  | 336 |  |  | 3
2025-01-17 | JOTP24120352 | CP08-428D-P02-03 | TR | PB07 | 1 | 336 | 70 | 4.8 | 0.6 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-22 09:54 | 2025-03-07 08:30 |  | 336 |  |  | 2
2025-01-17 | JOTP24120375 | CP08-554-P01-06 | TR | SW14 | 1 | 400 | 93 | 4.3011 | 0.53763 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 08:24 | 2025-03-14 08:30 |  | 400 |  |  | 3
2025-01-17 | JOTP24120375 | CP08-554-P02-06 | TR | SW14 | 1 | 400 | 129 | 3.1008 | 0.3876 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 04:48 | 2025-03-14 08:30 |  | 400 |  |  | 1
2025-01-17 | JOTP24120375 | CP08-554-P03-06 | TR | SW14 | 1 | 400 | 12 | 33.3333 | 4.1667 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-28 23:30 | 2025-03-14 08:30 |  | 400 |  |  | 2
2025-01-17 | JOTP24120375 | CP08-554-P04-06 | TR | PAINTING | 1 | 400 | 12 | 33.3333 | 4.1667 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-28 23:30 | 2025-03-14 08:30 |  | 400 |  |  | 3
2025-01-17 | JOTP24120375 | CP08-554-P05-06 | TR | PACK & LABEL | 1 | 400 | 12 | 33.3333 | 4.1667 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-28 23:30 | 2025-03-14 08:30 |  | 400 |  |  | 2
2025-01-17 | JOST24120347 | CP08-428-P01-09 | ST-3 | SW01 | 1 | 115 | 90 | 1.2778 | 0.15972 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-24 23:20 | 2025-03-10 08:30 |  | 115 |  |  | 2
2025-01-17 | JOST24120347 | CP08-428-P02-09 | ST-3 | SW01 | 1 | 115 | 120 | 0.95833 | 0.11979 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-24 22:22 | 2025-03-10 08:30 |  | 115 |  |  | 2
2025-01-17 | JOST24120347 | CP08-428-P03-09 | ST-3 | SW01 | 1 | 115 | 120 | 0.95833 | 0.11979 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-24 22:22 | 2025-03-10 08:30 |  | 115 |  |  | 2
2025-01-17 | JOST24120347 | CP08-428-P04-09 | ST-3 | SW01 | 1 | 115 | 90 | 1.2778 | 0.15972 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-24 23:20 | 2025-03-10 08:30 |  | 115 |  |  | 1
2025-01-17 | JOST24120347 | CP08-428-P05-09 | ST-3 | SW01 | 1 | 115 | 40 | 2.875 | 0.35938 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 04:08 | 2025-03-10 08:30 |  | 115 |  |  | 3
2025-01-17 | JOST24120347 | CP08-428-P06-09 | ST-3 | SW01 | 1 | 115 | 30 | 3.8333 | 0.47917 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 07:00 | 2025-03-10 08:30 |  | 115 |  |  | 2
2025-01-17 | JOST24120347 | CP08-428-P07-09 | ST-3 | PAINTING | 1 | 115 | 17 | 6.7647 | 0.84559 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 15:48 | 2025-03-10 08:30 |  | 115 |  |  | 3
2025-01-17 | JOST24120347 | CP08-428-P08-09 | ST-3 | CLEAN | 1 | 115 | 60 | 1.9167 | 0.23958 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 01:15 | 2025-03-10 08:30 |  | 115 |  |  | 3
2025-01-17 | JOAW24120378 | CP08-556-P03-09 | TR | PB07 | 1 | 200 | 60 | 3.3333 | 0.41667 | 0.041667 | 0.083333 | 0.33333 | 2025-02-27 08:30 | 2025-02-28 05:30 | 2025-03-24 08:30 |  | 200 |  |  | 3
2025-01-17 | JOAW24120378 | CP08-556-P04-09 | WN | SW06 | 1 | 200 | 60 | 3.3333 | 0.41667 | 0.041667 | 0.083333 | 0.33333 | 2025-02-27 08:30 | 2025-02-28 05:30 | 2025-03-24 08:30 |  | 200 |  |  | 3
2025-01-17 | JOAW24120378 | CP08-556-P05-09 | WN | OPT | 1 | 200 | 50 | 4 | 0.5 | 0.041667 | 0.083333 | 0.33333 | 2025-02-27 08:30 | 2025-02-28 07:30 | 2025-03-24 08:30 |  | 200 |  |  | 2
2025-01-17 | JOAW24120378 | CP08-556-P06-09 | WN | OPT | 1 | 200 | 50 | 4 | 0.5 | 0.041667 | 0.083333 | 0.33333 | 2025-02-27 08:30 | 2025-02-28 07:30 | 2025-03-24 08:30 |  | 200 |  |  | 2
2025-01-17 | JOAW24120378 | CP08-556-P08-09 | WN | CHECKING | 1 | 200 | 8 | 25 | 3.125 | 0.041667 | 0.083333 | 0.33333 | 2025-02-27 08:30 | 2025-03-02 22:30 | 2025-03-24 08:30 |  | 200 |  |  | 2
2025-01-17 | JOAW24120314 | CP08-231-P01-06 | WN | SW03 | 1 | 500 | 15 | 33.3333 | 4.1667 | 0.041667 | 0.083333 | 0.33333 | 2025-02-27 08:30 | 2025-03-03 23:30 | 2025-04-03 08:30 |  | 500 |  |  | 3
2025-01-17 | JOAW24120314 | CP08-231-P02-06 | WN | SW03 | 1 | 500 | 12 | 41.6667 | 5.2083 | 0.041667 | 0.083333 | 0.33333 | 2025-02-27 08:30 | 2025-03-05 00:30 | 2025-04-03 08:30 |  | 500 |  |  | 3
2025-01-17 | JOAW24120314 | CP08-231-P03-06 | WN | SW04 | 1 | 500 | 12 | 41.6667 | 5.2083 | 0.041667 | 0.083333 | 0.33333 | 2025-02-27 08:30 | 2025-03-05 00:30 | 2025-04-03 08:30 |  | 500 |  |  | 1
2025-01-17 | JOAW24120314 | CP08-231-P04-06 | WN | TW03 | 1 | 500 | 12 | 41.6667 | 5.2083 | 0.041667 | 0.083333 | 0.33333 | 2025-02-27 08:30 | 2025-03-05 00:30 | 2025-04-03 08:30 |  | 500 |  |  | 1
2025-01-20 | JOST25010174 | CP08-291-P01-02 | ST-1 | PP29 | 2 | 6000 | 240 | 25 | 3.125 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-03 22:30 | 2025-03-14 08:30 |  | 6000 |  |  | 3
2025-01-20 | JOST25010171 | CP08-087-P02-04 | ST-3 | PP21-110T | 1 | 9574 | 300 | 31.9133 | 3.9892 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-14 19:14 | 2025-03-03 08:30 |  | 9574 |  |  | 1
2025-01-20 | JOST25010171 | CP08-087-P03-04 | ST-3 | TP09 | 1 | 9574 | 120 | 79.7833 | 9.9729 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-20 18:51 | 2025-03-03 08:30 |  | 9574 |  |  | 2
2025-01-20 | JOST25010164 | CP08-012-P01-03 | ST-1 | PP14-080T | 1 | 20000 | 1800 | 11.1111 | 1.3889 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-12 04:50 | 2025-03-03 08:30 |  | 20000 |  |  | 3
2025-01-20 | JOST25010189 | CP08-502-P01-02 | ST-4 | PP24-160T | 1 | 1000 | 180 | 5.5556 | 0.69444 | 0.041667 | 0.083333 | 0.33333 | 2025-02-03 08:30 | 2025-02-04 12:10 | 2025-02-17 08:30 |  | 1000 |  |  | 1
2025-01-20 | JOTP25010188 | CP08-500-P04-07 | TR | PB07 | 1 | 960 | 60 | 16 | 2 | 0.041667 | 0.083333 | 0.33333 | 2025-02-03 08:30 | 2025-02-05 19:30 | 2025-02-17 08:30 |  | 960 |  |  | 2
2025-01-20 | JOTP25010188 | CP08-500-P05-07 | TR | PB01 | 1 | 960 | 60 | 16 | 2 | 0.041667 | 0.083333 | 0.33333 | 2025-02-03 08:30 | 2025-02-05 19:30 | 2025-02-17 08:30 |  | 960 |  |  | 3
2025-01-20 | JOTP25010188 | CP08-500-P06-07 | TR | PB03 | 1 | 960 | 60 | 16 | 2 | 0.041667 | 0.083333 | 0.33333 | 2025-02-03 08:30 | 2025-02-05 19:30 | 2025-02-17 08:30 |  | 960 |  |  | 1
2025-01-20 | JOST25010186 | CP08-496-P01-03 | 0 | STICK LABEL | 1 | 600 | 15 | 40 | 5 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-22 19:30 | 2025-03-10 08:30 |  | 600 |  |  | 3
2025-01-20 | JOST25010186 | CP08-496-P02-03 | 0 | STICK LABEL | 1 | 600 | 15 | 40 | 5 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-22 19:30 | 2025-03-10 08:30 |  | 600 |  |  | 2
2025-01-20 | JOST25010185 | CP08-496-P01-03 | 0 | STICK LABEL | 1 | 800 | 15 | 53.3333 | 6.6667 | 0.041667 | 0.083333 | 0.33333 | 2025-01-17 08:30 | 2025-01-24 11:30 | 2025-02-27 08:30 |  | 800 |  |  | 3
2025-01-20 | JOST25010185 | CP08-496-P02-03 | 0 | STICK LABEL | 1 | 800 | 15 | 53.3333 | 6.6667 | 0.041667 | 0.083333 | 0.33333 | 2025-01-17 08:30 | 2025-01-24 11:30 | 2025-02-27 08:30 |  | 800 |  |  | 1
2025-01-20 | JOTP25010184 | CP08-488-P01-05 | TR | TM02 | 1 | 105 | 80 | 1.3125 | 0.16406 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-17 23:26 | 2025-03-03 08:30 |  | 105 |  |  | 2
2025-01-20 | JOTP25010184 | CP08-488-P02-05 | WN | DEBURR | 1 | 105 | 80 | 1.3125 | 0.16406 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-17 23:26 | 2025-03-03 08:30 |  | 105 |  |  | 3
2025-01-20 | JOTP25010184 | CP08-488-P03-05 | TR | PB04 | 1 | 105 | 120 | 0.875 | 0.10938 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-17 22:08 | 2025-03-03 08:30 |  | 105 |  |  | 2
2025-01-20 | JOTP25010184 | CP08-488-P04-05 | ST-1 | PAINTING | 1 | 105 | 20 | 5.25 | 0.65625 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 11:15 | 2025-03-03 08:30 |  | 105 |  |  | 2
2025-01-20 | JOST25010176 | CP08-349-P01-04 | ST-4 | PP25-160T | 1 | 3100 | 300 | 10.3333 | 1.2917 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-02 02:30 | 2025-03-14 08:30 |  | 3100 |  |  | 2
2025-01-20 | JOST25010176 | CP08-349-P02-04 | ST-3 | PP20-110T | 1 | 3100 | 300 | 10.3333 | 1.2917 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-02 02:30 | 2025-03-14 08:30 |  | 3100 |  |  | 2
2025-01-20 | JOST25010176 | CP08-349-P03-04 | ST-4 | PP28-110T | 1 | 3100 | 300 | 10.3333 | 1.2917 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-02 02:30 | 2025-03-14 08:30 |  | 3100 |  |  | 1
2025-01-20 | JOAW25010175 | CP08-299-P01-03 | FM | FM03 | 1 | 5932 | 1800 | 3.2956 | 0.41194 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-01 05:23 | 2025-03-14 08:30 |  | 5932 |  |  | 3
2025-01-20 | JOAW25010175 | CP08-299-P02-03 | FM | VM01 | 1 | 5932 | 1000 | 5.932 | 0.7415 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-01 13:18 | 2025-03-14 08:30 |  | 5932 |  |  | 2
2025-01-20 | JOTP25010190 | CP08-505-P01-05 | TR | TM03 | 1 | 1080 | 102 | 10.5882 | 1.3235 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-23 03:16 | 2025-03-07 08:30 |  | 1080 |  |  | 3
2025-01-20 | JOTP25010190 | CP08-505-P02-05 | ST-3 | PP17-110T | 1 | 1080 | 300 | 3.6 | 0.45 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-22 06:18 | 2025-03-07 08:30 |  | 1080 |  |  | 3
2025-01-20 | JOTP25010190 | CP08-505-P03-05 | ST-2 | PP16-110T | 1 | 1080 | 300 | 3.6 | 0.45 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-22 06:18 | 2025-03-07 08:30 |  | 1080 |  |  | 3
2025-01-20 | JOTP25010190 | CP08-505-P04-05 | ST-2 | PP27-110T | 1 | 1080 | 300 | 3.6 | 0.45 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-22 06:18 | 2025-03-07 08:30 |  | 1080 |  |  | 3
2025-01-20 | JOST25010191 | CP08-516-P01-11 | ST-3 | PP09-160T | 1 | 1300 | 120 | 10.8333 | 1.3542 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-23 04:00 | 2025-03-07 08:30 |  | 1300 |  |  | 2
2025-01-20 | JOST25010191 | CP08-516-P02-11 | ST-3 | PP18-150T | 1 | 1300 | 120 | 10.8333 | 1.3542 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-23 04:00 | 2025-03-07 08:30 |  | 1300 |  |  | 2
2025-01-20 | JOST25010191 | CP08-516-P03-11 | ST-3 | PP17-110T | 1 | 1300 | 120 | 10.8333 | 1.3542 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-23 04:00 | 2025-03-07 08:30 |  | 1300 |  |  | 2
2025-01-20 | JOST25010191 | CP08-516-P04-11 | ST-3 | TP03 | 1 | 1300 | 120 | 10.8333 | 1.3542 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-23 04:00 | 2025-03-07 08:30 |  | 1300 |  |  | 3
2025-01-20 | JOST25010191 | CP08-516-P05-11 | ST-3 | PP16-110T | 1 | 1300 | 120 | 10.8333 | 1.3542 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-23 04:00 | 2025-03-07 08:30 |  | 1300 |  |  | 2
2025-01-20 | JOST25010191 | CP08-516-P06-11 | ST-3 | TP03 | 1 | 1300 | 120 | 10.8333 | 1.3542 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-23 04:00 | 2025-03-07 08:30 |  | 1300 |  |  | 2
2025-01-20 | JOST25010191 | CP08-516-P07-11 | ST-3 | PP17-110T | 1 | 1300 | 120 | 10.8333 | 1.3542 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-23 04:00 | 2025-03-07 08:30 |  | 1300 |  |  | 2
2025-01-20 | JOST25010191 | CP08-516-P08-11 | ST-3 | PP16-110T | 1 | 1300 | 120 | 10.8333 | 1.3542 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-23 04:00 | 2025-03-07 08:30 |  | 1300 |  |  | 3
2025-01-20 | JOST25010191 | CP08-516-P09-11 | ST-3 | PP27-110T | 1 | 1300 | 120 | 10.8333 | 1.3542 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-23 04:00 | 2025-03-07 08:30 |  | 1300 |  |  | 3
2025-01-20 | JOST25010191 | CP08-516-P10-11 | ST-3 | SW01 | 1 | 1300 | 120 | 10.8333 | 1.3542 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-23 04:00 | 2025-03-07 08:30 |  | 1300 |  |  | 1
2025-01-20 | JOST25010193 | CP08-518-P01-02 | ST-3 | PP01-110T | 1 | 5500 | 3000 | 1.8333 | 0.22917 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-22 01:00 | 2025-03-07 08:30 |  | 5500 |  |  | 1
2025-01-20 | JOST25010192 | CP08-517-P01-03 | ST-1 | PP10-080T | 1 | 3307 | 300 | 11.0233 | 1.3779 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-19 04:34 | 2025-03-03 08:30 |  | 3307 |  |  | 3
2025-01-20 | JOST25010192 | CP08-517-P02-03 | ST-3 | PP03-060T | 1 | 3307 | 240 | 13.7792 | 1.7224 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-19 12:50 | 2025-03-03 08:30 |  | 3307 |  |  | 1
2025-01-20 | JOST25010194 | CP08-523-P01-03 | ST-2 | PP10-080T | 1 | 4166 | 1800 | 2.3144 | 0.28931 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-01 02:27 | 2025-03-14 08:30 |  | 4166 |  |  | 2
2025-01-20 | JOST25010194 | CP08-523-P02-03 | AL | TP04 | 1 | 4166 | 300 | 13.8867 | 1.7358 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-02 13:10 | 2025-03-14 08:30 |  | 4166 |  |  | 3
2025-01-20 | JOAW25010218 | CA21-001-P01-04 | FM | FM01 | 1 | 127182 | 2400 | 52.9925 | 6.6241 | 0.041667 | 0.083333 | 0.33333 | 2025-02-12 08:30 | 2025-02-19 10:29 | 2025-03-19 08:30 | 65000 | 62182 |  |  | 1
2025-01-20 | JOST25010217 | CP16-042-P02-03 | ST-2 | PP03-060T | 1 | 2688 | 240 | 11.2 | 1.4 | 0.041667 | 0.083333 | 0.33333 | 2025-02-03 08:30 | 2025-02-05 05:06 | 2025-02-13 08:30 | 2 | 2686 |  |  | 2
2025-01-20 | JOST25010216 | CP16-030-P03-04 | ST-1 | PP05-060T | 1 | 5832 | 240 | 24.3 | 3.0375 | 0.041667 | 0.083333 | 0.33333 | 2025-02-08 08:30 | 2025-02-11 20:24 | 2025-02-20 08:30 |  | 5832 |  |  | 3
2025-01-20 | JOST25010216 | CP16-009-P01-02 | FM | FM03 | 1 | 30769 | 2400 | 12.8204 | 1.6026 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-12 09:58 | 2025-02-21 08:30 |  | 30769 |  |  | 1
2025-01-20 | JOST25010213 | CO02-021-P01-06 | SM | SM01 | 1 | 279 | 240 | 1.1625 | 0.14531 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-10 22:59 | 2025-02-24 08:30 |  | 279 |  |  | 3
2025-01-20 | JOST25010213 | CO02-021-P02-06 | ST-3 | PP27-110T | 1 | 279 | 240 | 1.1625 | 0.14531 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-10 22:59 | 2025-02-24 08:30 |  | 279 |  |  | 2
2025-01-20 | JOST25010213 | CO02-021-P03-06 | ST-3 | PP16-110T | 1 | 279 | 360 | 0.775 | 0.096875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-10 21:50 | 2025-02-24 08:30 |  | 279 |  |  | 3
2025-01-20 | JOST25010213 | CO02-021-P04-06 | ST-3 | PP17-110T | 1 | 279 | 360 | 0.775 | 0.096875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-10 21:50 | 2025-02-24 08:30 |  | 279 |  |  | 1
2025-01-20 | JOST25010213 | CO02-021-P05-06 | ST-3 | PP18-150T | 1 | 279 | 360 | 0.775 | 0.096875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-10 21:50 | 2025-02-24 08:30 |  | 279 |  |  | 2
2025-01-20 | JOAW25010210 | CJ01-003-P01-04 | ST-2 | PP07-016T | 1 | 5100 | 360 | 14.1667 | 1.7708 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-12 14:00 | 2025-03-03 08:30 |  | 5100 |  |  | 3
2025-01-20 | JOAW25010210 | CJ01-003-P02-04 | AL | BL04 | 1 | 5100 | 150 | 34 | 4.25 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-15 01:30 | 2025-03-03 08:30 |  | 5100 |  |  | 2
2025-01-20 | JOTP25010202 | CP08-585-P01-04 | PB | SW09 | 1 | 216 | 40.2 | 5.3731 | 0.67164 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 11:37 | 2025-03-03 08:30 |  | 216 |  |  | 2
2025-01-20 | JOTP25010202 | CP08-585-P02-04 | PB | OPT | 1 | 216 | 40.2 | 5.3731 | 0.67164 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 11:37 | 2025-03-03 08:30 |  | 216 |  |  | 2
2025-01-20 | JOTP25010202 | CP08-585-P03-04 | PB | OPT | 1 | 216 | 50.4 | 4.2857 | 0.53571 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 08:21 | 2025-03-03 08:30 |  | 216 |  |  | 2
2025-01-20 | JOTP25010201 | CP08-583B-P01-04 | PB | PB07 | 1 | 152 | 90 | 1.6889 | 0.21111 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-01 00:34 | 2025-03-14 08:30 |  | 152 |  |  | 1
2025-01-20 | JOTP25010201 | CP08-583B-P02-04 | PB | PB02 | 1 | 152 | 60 | 2.5333 | 0.31667 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-01 03:06 | 2025-03-14 08:30 |  | 152 |  |  | 3
2025-01-20 | JOTP25010201 | CP08-583B-P03-04 | PB | PB02 | 1 | 152 | 120 | 1.2667 | 0.15833 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-02-28 23:18 | 2025-03-14 08:30 |  | 152 |  |  | 2
2025-01-20 | JOTP25010200 | CP08-583A-P01-05 | TP | TM03 | 1 | 152 | 45 | 3.3778 | 0.42222 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-01 05:38 | 2025-03-14 08:30 |  | 152 |  |  | 3
2025-01-20 | JOTP25010200 | CP08-583A-P02-05 | PB | PB02 | 1 | 152 | 180 | 0.84444 | 0.10556 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-02-28 22:02 | 2025-03-14 08:30 |  | 152 |  |  | 3
2025-01-20 | JOTP25010200 | CP08-583A-P03-05 | PB | PB07 | 1 | 152 | 50.4 | 3.0159 | 0.37698 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-01 04:33 | 2025-03-14 08:30 |  | 152 |  |  | 3
2025-01-20 | JOTP25010200 | CP08-583A-P04-05 | PB | PB07 | 1 | 152 | 90 | 1.6889 | 0.21111 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-01 00:34 | 2025-03-14 08:30 |  | 152 |  |  | 3
2025-01-20 | JOST25010197 | CP08-559-P01-02 | ST | PP32 | 1 | 49924 | 1680 | 29.7167 | 3.7146 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-04 12:39 | 2025-03-14 08:30 |  | 49924 |  |  | 2
2025-01-21 | JOAW24120242 | CD11-026A-P01-02 | FM | FM03 | 1 | 60000 | 1200 | 50 | 6.25 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-03-03 01:30 | 2025-03-10 08:30 |  | 60000 |  |  | 2
2025-01-21 | JOAW24120244 | CD11-026B-P01-02 | WN | WS01 | 1 | 80000 | 2160 | 37.037 | 4.6296 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-03-01 10:37 | 2025-03-10 08:30 |  | 80000 |  |  | 2
2025-01-21 | JOAW24120246 | CD11-026C-P01-02 | WN | WS01 | 1 | 20000 | 2400 | 8.3333 | 1.0417 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 20:30 | 2025-03-10 08:30 |  | 20000 |  |  | 1
2025-01-21 | JOAW24120239 | CD11-026-P01-06 | WN | SW13 | 1 | 25000 | 120 | 208.3333 | 26.0417 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-03-22 20:30 | 2025-04-07 08:30 | 5410 | 19590 |  |  | 2
2025-01-21 | JOAW24120239 | CD11-026-P02-06 | WN | PP23-060T | 1 | 25000 | 540 | 46.2963 | 5.787 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-03-02 14:23 | 2025-04-07 08:30 | 5 | 24995 |  |  | 3
2025-01-21 | JOAW24120239 | CD11-026-P05-06 | WN | TW01 | 1 | 25000 | 420 | 59.5238 | 7.4405 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-03-04 06:04 | 2025-04-07 08:30 |  | 25000 |  |  | 1
2025-01-21 | JOTP25010226 | CT10-026A-P01-02 | TP | SW09 | 1 | 200 | 8 | 25 | 3.125 | 0.041667 | 0.083333 | 0.33333 | 2025-02-06 08:30 | 2025-02-09 22:30 | 2025-02-14 08:30 | 108 | 92 |  |  | 2
2025-01-21 | JOTP25010222 | CT10-026-P01-04 | TP | SW09 | 1 | 100 | 12 | 8.3333 | 1.0417 | 0.041667 | 0.083333 | 0.33333 | 2025-02-12 08:30 | 2025-02-13 20:30 | 2025-02-24 08:30 |  | 100 |  |  | 3
2025-01-21 | JOTP25010222 | CT10-026-P02-04 | TP | OPT | 1 | 100 | 6 | 16.6667 | 2.0833 | 0.041667 | 0.083333 | 0.33333 | 2025-02-12 08:30 | 2025-02-14 21:30 | 2025-02-24 08:30 |  | 100 |  |  | 1
2025-01-21 | JOTP25010222 | CT10-026-P03-04 | TP | OPT | 1 | 100 | 30 | 3.3333 | 0.41667 | 0.041667 | 0.083333 | 0.33333 | 2025-02-12 08:30 | 2025-02-13 05:30 | 2025-02-24 08:30 |  | 100 |  |  | 3
2025-01-22 | JOTP25010239 | CT10-026I-P01-02 | TP | PB01 | 1 | 600 | 90 | 6.6667 | 0.83333 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 15:30 | 2025-03-10 08:30 |  | 600 |  |  | 2
2025-01-22 | JOTP25010238 | CT10-026H-P01-03 | TP | TP02 | 1 | 432 | 120 | 3.6 | 0.45 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 06:18 | 2025-03-10 08:30 |  | 432 |  |  | 3
2025-01-22 | JOTP25010238 | CT10-026H-P02-03 | TP | PB07 | 1 | 432 | 40 | 10.8 | 1.35 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-26 03:54 | 2025-03-10 08:30 |  | 432 |  |  | 1
2025-01-22 | JOTP25010237 | CT10-026G-P01-03 | TP | PB01 | 1 | 486 | 180 | 2.7 | 0.3375 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 03:36 | 2025-03-10 08:30 |  | 486 |  |  | 2
2025-01-22 | JOTP25010237 | CT10-026G-P02-03 | TP | PB01 | 1 | 486 | 180 | 2.7 | 0.3375 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 03:36 | 2025-03-10 08:30 |  | 486 |  |  | 3
2025-01-22 | JOTP25010236 | CT10-026F-P01-03 | TP | PB02 | 1 | 280 | 90 | 3.1111 | 0.38889 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 04:50 | 2025-03-10 08:30 |  | 280 |  |  | 2
2025-01-22 | JOTP25010236 | CT10-026F-P02-03 | TP | PB01 | 1 | 280 | 180 | 1.5556 | 0.19444 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 00:10 | 2025-03-10 08:30 |  | 280 |  |  | 2
2025-01-22 | JOTP25010235 | CT10-026E-P01-02 | TP | PB01 | 1 | 460 | 18 | 25.5556 | 3.1944 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-21 00:10 | 2025-03-10 08:30 |  | 460 |  |  | 2
2025-01-22 | JOTP25010234 | CT10-026D-P01-03 | TP | TM03 | 1 | 210 | 48 | 4.375 | 0.54688 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 08:38 | 2025-03-10 08:30 |  | 210 |  |  | 1
2025-01-22 | JOTP25010234 | CT10-026D-P02-03 | TP | PB01 | 1 | 210 | 50 | 4.2 | 0.525 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 08:06 | 2025-03-10 08:30 |  | 210 |  |  | 2
2025-01-22 | JOTP25010233 | CT10-026C-P01-03 | TP | TM03 | 1 | 648 | 51 | 12.7059 | 1.5882 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-26 09:37 | 2025-03-10 08:30 |  | 648 |  |  | 3
2025-01-22 | JOTP25010233 | CT10-026C-P02-03 | TP | PB01 | 1 | 648 | 90 | 7.2 | 0.9 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 17:06 | 2025-03-10 08:30 |  | 648 |  |  | 1
2025-01-22 | JOTP25010232 | CT10-026B-P01-03 | TP | TM03 | 1 | 220 | 80 | 2.75 | 0.34375 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 03:45 | 2025-03-10 08:30 |  | 220 |  |  | 2
2025-01-22 | JOTP25010232 | CT10-026B-P02-03 | TP | PB01 | 1 | 220 | 90 | 2.4444 | 0.30556 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 02:50 | 2025-03-10 08:30 |  | 220 |  |  | 3
2025-01-22 | JOTP25010231 | CT10-026A-C-P01-14 | 0 | 0 | 1 | 220 | 0 | #DIV/0! | #DIV/0! | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | #DIV/0! | 2025-03-10 08:30 |  | 220 |  |  | 1
2025-01-22 | JOTP25010231 | CT10-026A-C-P02-14 | 0 | 0 | 1 | 220 | 0 | #DIV/0! | #DIV/0! | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | #DIV/0! | 2025-03-10 08:30 |  | 220 |  |  | 3
2025-01-22 | JOTP25010231 | CT10-026A-C-P03-14 | 0 | 0 | 1 | 220 | 0 | #DIV/0! | #DIV/0! | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | #DIV/0! | 2025-03-10 08:30 |  | 220 |  |  | 2
2025-01-22 | JOTP25010231 | CT10-026A-C-P04-14 | 0 | 0 | 1 | 220 | 0 | #DIV/0! | #DIV/0! | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | #DIV/0! | 2025-03-10 08:30 |  | 220 |  |  | 3
2025-01-22 | JOTP25010231 | CT10-026A-C-P05-14 | 0 | 0 | 1 | 220 | 0 | #DIV/0! | #DIV/0! | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | #DIV/0! | 2025-03-10 08:30 |  | 220 |  |  | 1
2025-01-22 | JOTP25010231 | CT10-026A-C-P06-14 | 0 | 0 | 1 | 220 | 0 | #DIV/0! | #DIV/0! | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | #DIV/0! | 2025-03-10 08:30 |  | 220 |  |  | 2
2025-01-22 | JOTP25010231 | CT10-026A-C-P07-14 | 0 | 0 | 1 | 220 | 0 | #DIV/0! | #DIV/0! | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | #DIV/0! | 2025-03-10 08:30 |  | 220 |  |  | 3
2025-01-22 | JOTP25010231 | CT10-026A-C-P08-14 | 0 | 0 | 1 | 220 | 0 | #DIV/0! | #DIV/0! | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | #DIV/0! | 2025-03-10 08:30 |  | 220 |  |  | 2
2025-01-22 | JOTP25010231 | CT10-026A-C-P09-14 | 0 | 0 | 1 | 220 | 0 | #DIV/0! | #DIV/0! | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | #DIV/0! | 2025-03-10 08:30 |  | 220 |  |  | 2
2025-01-22 | JOTP25010231 | CT10-026A-C-P10-14 | 0 | 0 | 1 | 220 | 0 | #DIV/0! | #DIV/0! | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | #DIV/0! | 2025-03-10 08:30 |  | 220 |  |  | 2
2025-01-22 | JOTP25010231 | CT10-026A-C-P11-14 | 0 | 0 | 1 | 220 | 0 | #DIV/0! | #DIV/0! | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | #DIV/0! | 2025-03-10 08:30 |  | 220 |  |  | 2
2025-01-22 | JOTP25010231 | CT10-026A-C-P12-14 | 0 | 0 | 1 | 220 | 0 | #DIV/0! | #DIV/0! | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | #DIV/0! | 2025-03-10 08:30 |  | 220 |  |  | 1
2025-01-22 | JOTP25010231 | CT10-026A-C-P13-14 | 0 | 0 | 1 | 220 | 0 | #DIV/0! | #DIV/0! | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | #DIV/0! | 2025-03-10 08:30 |  | 220 |  |  | 3
2025-01-22 | JOST25010244 | CC09-004-P01-04 | SM | SM01 | 1 | 14355 | 11520 | 1.2461 | 0.15576 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-24 23:14 | 2025-03-10 08:30 |  | 14355 |  |  | 2
2025-01-22 | JOST25010244 | CC09-004-P02-04 | ST-1 | PP05-060T | 1 | 14355 | 900 | 15.95 | 1.9937 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-26 19:21 | 2025-03-10 08:30 |  | 14355 |  |  | 3
2025-01-22 | JOST25010244 | CC09-004-P03-04 | ST-1 | PP13-060T | 1 | 14355 | 480 | 29.9062 | 3.7383 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-28 13:13 | 2025-03-10 08:30 |  | 14355 |  |  | 3
2025-01-22 | JOTP25010229 | CT10-026A-B-P01-03 | TP | TM03 | 1 | 200 | 72 | 2.7778 | 0.34722 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 03:50 | 2025-03-10 08:30 |  | 200 |  |  | 3
2025-01-22 | JOTP25010229 | CT10-026A-B-P02-03 | TP | PB01 | 1 | 200 | 120 | 1.6667 | 0.20833 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 00:30 | 2025-03-10 08:30 |  | 200 |  |  | 3
2025-01-22 | JOTP25010228 | CT10-026A-A-P01-07 | TP | TM03 | 1 | 216 | 48 | 4.5 | 0.5625 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 09:00 | 2025-03-10 08:30 |  | 216 |  |  | 2
2025-01-22 | JOTP25010228 | CT10-026A-A-P02-07 | TP | PB01 | 1 | 216 | 120 | 1.8 | 0.225 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 00:54 | 2025-03-10 08:30 |  | 216 |  |  | 2
2025-01-22 | JOTP25010228 | CT10-026A-A-P03-07 | TP | PB01 | 1 | 216 | 60 | 3.6 | 0.45 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 06:18 | 2025-03-10 08:30 |  | 216 |  |  | 2
2025-01-22 | JOTP25010228 | CT10-026A-A-P04-07 | TP | PB01 | 1 | 216 | 60 | 3.6 | 0.45 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 06:18 | 2025-03-10 08:30 |  | 216 |  |  | 1
2025-01-22 | JOTP25010228 | CT10-026A-A-P05-07 | TP | PB01 | 1 | 216 | 60 | 3.6 | 0.45 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 06:18 | 2025-03-10 08:30 |  | 216 |  |  | 2
2025-01-22 | JOTP25010228 | CT10-026A-A-P06-07 | TP | SW09 | 1 | 216 | 90 | 2.4 | 0.3 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 02:42 | 2025-03-10 08:30 |  | 216 |  |  | 3
2025-01-22 | JOST25010220 | CP08-384-P01-03 | ST | SM01 | 1 | 2520 | 240 | 10.5 | 1.3125 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-12 03:00 | 2025-02-20 08:30 |  | 2520 |  |  | 1
2025-01-22 | JOST25010220 | CP08-384-P02-03 | ST | PP21 | 1 | 2520 | 180 | 14 | 1.75 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-12 13:30 | 2025-02-20 08:30 |  | 2520 |  |  | 2
2025-01-22 | JOST25010170 | CP08-086-P01-02 | ST-3 | SW01 | 1 | 1031 | 90 | 11.4556 | 1.4319 | 0.041667 | 0.083333 | 0.33333 | 2025-01-31 08:30 | 2025-02-02 05:52 | 2025-02-13 08:30 | 329 | 702 |  |  | 3
2025-01-22 | JOST25010212 | CM03-038-P01-03 | ST-3 | PP02-060T | 1 | 8776 | 360 | 24.3778 | 3.0472 | 0.041667 | 0.083333 | 0.33333 | 2025-02-12 08:30 | 2025-02-15 20:38 | 2025-02-26 08:30 | 3100 | 5676 |  |  | 1
2025-01-22 | JOST25010212 | CM03-038-P02-03 | ST-3 | PP05-060T | 1 | 8776 | 240 | 36.5667 | 4.5708 | 0.041667 | 0.083333 | 0.33333 | 2025-02-12 08:30 | 2025-02-17 09:12 | 2025-02-26 08:30 |  | 8776 |  |  | 3
2025-01-22 | JOAW24120290 | CM18-001A-P01-02 | WN | WS01 | 1 | 75000 | 2160 | 34.7222 | 4.3403 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-15 03:40 | 2025-02-24 08:30 |  | 75000 |  |  | 2
2025-01-22 | JOAW24120292 | CM18-001B-P01-02 | FM | FM03 | 1 | 45000 | 1260 | 35.7143 | 4.4643 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-15 06:39 | 2025-02-24 08:30 |  | 45000 |  |  | 3
2025-01-22 | JOAW24120294 | CM18-001C-P01-02 | WN | WS01 | 1 | 15000 | 2400 | 6.25 | 0.78125 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 14:15 | 2025-02-24 08:30 |  | 15000 |  |  | 1
2025-01-22 | JOST24120258 | CO02-011-P01-06 | SM | SM01 | 1 | 1610 | 300 | 5.3667 | 0.67083 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 11:36 | 2025-02-24 08:30 |  | 1610 |  |  | 2
2025-01-22 | JOST24120258 | CO02-011-P02-06 | ST-3 | PP18-150T | 1 | 1610 | 300 | 5.3667 | 0.67083 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 11:36 | 2025-02-24 08:30 |  | 1610 |  |  | 3
2025-01-22 | JOST24120258 | CO02-011-P03-06 | ST-3 | PP17-110T | 1 | 1610 | 300 | 5.3667 | 0.67083 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 11:36 | 2025-02-24 08:30 |  | 1610 |  |  | 2
2025-01-22 | JOST24120258 | CO02-011-P04-06 | ST-3 | PP16-110T | 1 | 1610 | 300 | 5.3667 | 0.67083 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 11:36 | 2025-02-24 08:30 |  | 1610 |  |  | 2
2025-01-22 | JOST24120258 | CO02-011-P05-06 | ST-3 | PP27-110T | 1 | 1610 | 300 | 5.3667 | 0.67083 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 11:36 | 2025-02-24 08:30 |  | 1610 |  |  | 2
2025-01-22 | JOST24120260 | CO02-013-P02-04 | ST-1 | PP22-060T | 1 | 5976 | 360 | 16.6 | 2.075 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-12 21:18 | 2025-02-24 08:30 |  | 5976 |  |  | 2
2025-01-22 | JOST24120260 | CO02-013-P03-04 | ST-1 | PP10-080T | 1 | 5976 | 180 | 33.2 | 4.15 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-14 23:06 | 2025-02-24 08:30 |  | 5976 |  |  | 1
2025-01-22 | JOST24120261 | CO02-022-P01-07 | SM | SM01 | 1 | 315 | 1080 | 0.29167 | 0.036458 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-10 20:22 | 2025-02-24 08:30 |  | 315 |  |  | 3
2025-01-22 | JOST24120261 | CO02-022-P02-07 | ST-3 | PP09-160T | 1 | 315 | 240 | 1.3125 | 0.16406 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-10 23:26 | 2025-02-24 08:30 |  | 315 |  |  | 2
2025-01-22 | JOST24120261 | CO02-022-P03-07 | ST-3 | PP18-150T | 1 | 315 | 240 | 1.3125 | 0.16406 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-10 23:26 | 2025-02-24 08:30 |  | 315 |  |  | 3
2025-01-22 | JOST24120261 | CO02-022-P04-07 | ST-3 | PP17-110T | 1 | 315 | 240 | 1.3125 | 0.16406 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-10 23:26 | 2025-02-24 08:30 |  | 315 |  |  | 3
2025-01-22 | JOST24120261 | CO02-022-P05-07 | ST-3 | PP16-110T | 1 | 315 | 240 | 1.3125 | 0.16406 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-10 23:26 | 2025-02-24 08:30 |  | 315 |  |  | 3
2025-01-22 | JOST24120261 | CO02-022-P06-07 | ST-3 | PP27-110T | 1 | 315 | 240 | 1.3125 | 0.16406 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-10 23:26 | 2025-02-24 08:30 |  | 315 |  |  | 3
2025-01-22 | JOAW24120288 | CM18-001-P01-06 | WN | SW13 | 1 | 15000 | 150 | 100 | 12.5 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-03-09 07:30 | 2025-04-10 08:30 |  | 15000 |  |  | 2
2025-01-22 | JOAW24120288 | CM18-001-P02-06 | WN | PP23 | 1 | 15000 | 420 | 35.7143 | 4.4643 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-03-01 06:39 | 2025-04-10 08:30 |  | 15000 |  |  | 2
2025-01-22 | JOAW24120288 | CM18-001-P05-06 | WN | TW01 | 1 | 15000 | 450 | 33.3333 | 4.1667 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-28 23:30 | 2025-04-10 08:30 |  | 15000 |  |  | 2
2025-01-22 | JOAW24120247 | CD11-027-P01-06 | WN | SW08 | 1 | 15000 | 120 | 125 | 15.625 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-03-12 10:30 | 2025-04-07 08:30 |  | 15000 |  |  | 3
2025-01-22 | JOAW24120247 | CD11-027-P02-06 | WN | PP23-060T | 1 | 15000 | 300 | 50 | 6.25 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-03-03 01:30 | 2025-04-07 08:30 |  | 15000 |  |  | 3
2025-01-22 | JOAW24120247 | CD11-027-P05-06 | WN | TW01 | 1 | 15000 | 400 | 37.5 | 4.6875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-03-01 12:00 | 2025-04-07 08:30 |  | 15000 |  |  | 1
2025-01-23 | JOTP25010245 | CP08-490-P01-04 | TR | TM02 | 1 | 45 | 80 | 0.5625 | 0.070312 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-17 21:11 | 2025-03-03 08:30 |  | 45 |  |  | 1
2025-01-23 | JOTP25010245 | CP08-490-P02-04 | WN | DEBURR | 1 | 45 | 14 | 3.2143 | 0.40179 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 05:09 | 2025-03-03 08:30 |  | 45 |  |  | 3
2025-01-23 | JOTP25010245 | CP08-490-P03-04 | ST-1 | PAINTING | 1 | 45 | 50 | 0.9 | 0.1125 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-17 22:12 | 2025-03-03 08:30 |  | 45 |  |  | 1
2025-01-23 | JOAW24120315 | CP08-231-P01-06 | WN | SW03 | 1 | 500 | 15 | 33.3333 | 4.1667 | 0.041667 | 0.083333 | 0.33333 | 2025-03-03 08:30 | 2025-03-07 23:30 | 2025-04-07 08:30 |  | 500 |  |  | 2
2025-01-23 | JOAW24120315 | CP08-231-P02-06 | WN | SW03 | 1 | 500 | 12 | 41.6667 | 5.2083 | 0.041667 | 0.083333 | 0.33333 | 2025-03-03 08:30 | 2025-03-09 00:30 | 2025-04-07 08:30 |  | 500 |  |  | 3
2025-01-23 | JOAW24120315 | CP08-231-P03-06 | WN | SW04 | 1 | 500 | 12 | 41.6667 | 5.2083 | 0.041667 | 0.083333 | 0.33333 | 2025-03-03 08:30 | 2025-03-09 00:30 | 2025-04-07 08:30 |  | 500 |  |  | 1
2025-01-23 | JOAW24120315 | CP08-231-P04-06 | WN | TW03 | 1 | 500 | 12 | 41.6667 | 5.2083 | 0.041667 | 0.083333 | 0.33333 | 2025-03-03 08:30 | 2025-03-09 00:30 | 2025-04-07 08:30 |  | 500 |  |  | 2
2025-01-23 | JOTP25010223 | CT10-026-P01-04 | TP | SW09 | 1 | 95 | 12 | 7.9167 | 0.98958 | 0.041667 | 0.083333 | 0.33333 | 2025-03-03 08:30 | 2025-03-04 19:15 | 2025-03-17 08:30 |  | 95 |  |  | 3
2025-01-23 | JOTP25010223 | CT10-026-P02-04 | TP | OPT | 1 | 95 | 6 | 15.8333 | 1.9792 | 0.041667 | 0.083333 | 0.33333 | 2025-03-03 08:30 | 2025-03-05 19:00 | 2025-03-17 08:30 |  | 95 |  |  | 1
2025-01-23 | JOTP25010223 | CT10-026-P03-04 | TP | OPT | 1 | 95 | 30 | 3.1667 | 0.39583 | 0.041667 | 0.083333 | 0.33333 | 2025-03-03 08:30 | 2025-03-04 05:00 | 2025-03-17 08:30 |  | 95 |  |  | 3
2025-01-23 | JOTP25010053 | CP08-415A-P01-04 | TR | TM05 | 1 | 640 | 35 | 18.2857 | 2.2857 | 0.041667 | 0.083333 | 0.33333 | 2025-03-03 08:30 | 2025-03-06 02:21 | 2025-03-17 08:30 |  | 640 |  |  | 2
2025-01-23 | JOTP25010053 | CP08-415A-P02-04 | TR | PB05 | 1 | 640 | 40 | 16 | 2 | 0.041667 | 0.083333 | 0.33333 | 2025-03-03 08:30 | 2025-03-05 19:30 | 2025-03-17 08:30 |  | 640 |  |  | 3
2025-01-23 | JOTP25010053 | CP08-415A-P03-04 | WN | SW09 | 1 | 640 | 60 | 10.6667 | 1.3333 | 0.041667 | 0.083333 | 0.33333 | 2025-03-03 08:30 | 2025-03-05 03:30 | 2025-03-17 08:30 |  | 640 |  |  | 1
2025-01-23 | JOAW24100350 | CA16-011-P01-03 | FM | SW05 | 1 | 60000 | 450 | 133.3333 | 16.6667 | 0.041667 | 0.083333 | 0.33333 | 2025-03-05 08:30 | 2025-03-22 11:30 | 2025-03-21 08:30 |  | 60000 |  |  | 2
2025-01-23 | JOAW24100350 | CA16-011-P02-03 | FM | OPT | 1 | 60000 | 900 | 66.6667 | 8.3333 | 0.041667 | 0.083333 | 0.33333 | 2025-03-05 08:30 | 2025-03-14 03:30 | 2025-03-21 08:30 |  | 60000 |  |  | 3
2025-01-23 | JOST24120348 | CP08-428-P01-09 | ST-3 | SW01 | 1 | 338 | 90 | 3.7556 | 0.46944 | 0.041667 | 0.083333 | 0.33333 | 2025-03-07 08:30 | 2025-03-08 06:46 | 2025-03-21 08:30 |  | 338 |  |  | 2
2025-01-23 | JOST24120348 | CP08-428-P02-09 | ST-3 | SW01 | 1 | 338 | 120 | 2.8167 | 0.35208 | 0.041667 | 0.083333 | 0.33333 | 2025-03-07 08:30 | 2025-03-08 03:57 | 2025-03-21 08:30 |  | 338 |  |  | 2
2025-01-23 | JOST24120348 | CP08-428-P03-09 | ST-3 | SW01 | 1 | 338 | 120 | 2.8167 | 0.35208 | 0.041667 | 0.083333 | 0.33333 | 2025-03-07 08:30 | 2025-03-08 03:57 | 2025-03-21 08:30 |  | 338 |  |  | 2
2025-01-23 | JOST24120348 | CP08-428-P04-09 | ST-3 | SW01 | 1 | 338 | 90 | 3.7556 | 0.46944 | 0.041667 | 0.083333 | 0.33333 | 2025-03-07 08:30 | 2025-03-08 06:46 | 2025-03-21 08:30 |  | 338 |  |  | 2
2025-01-23 | JOST24120348 | CP08-428-P05-09 | ST-3 | SW01 | 1 | 338 | 40 | 8.45 | 1.0562 | 0.041667 | 0.083333 | 0.33333 | 2025-03-07 08:30 | 2025-03-08 20:51 | 2025-03-21 08:30 |  | 338 |  |  | 1
2025-01-23 | JOST24120348 | CP08-428-P06-09 | ST-3 | SW01 | 1 | 338 | 30 | 11.2667 | 1.4083 | 0.041667 | 0.083333 | 0.33333 | 2025-03-07 08:30 | 2025-03-09 05:18 | 2025-03-21 08:30 |  | 338 |  |  | 3
2025-01-23 | JOST24120348 | CP08-428-P07-09 | ST-3 | PAINTING | 1 | 338 | 17 | 19.8824 | 2.4853 | 0.041667 | 0.083333 | 0.33333 | 2025-03-07 08:30 | 2025-03-10 07:09 | 2025-03-21 08:30 |  | 338 |  |  | 2
2025-01-23 | JOST24120348 | CP08-428-P08-09 | ST-3 | CLEAN | 1 | 338 | 60 | 5.6333 | 0.70417 | 0.041667 | 0.083333 | 0.33333 | 2025-03-07 08:30 | 2025-03-08 12:24 | 2025-03-21 08:30 |  | 338 |  |  | 3
2025-01-23 | JOAW25010167 | CP08-068-P01-02 | FM | FM01 | 1 | 19230 | 1800 | 10.6833 | 1.3354 | 0.041667 | 0.083333 | 0.33333 | 2025-03-07 08:30 | 2025-03-09 03:33 | 2025-04-04 08:30 |  | 19230 |  |  | 3
2025-01-23 | JOAW25010169 | CP08-082-P01-02 | FM | FM01 | 1 | 238095 | 1800 | 132.275 | 16.5344 | 0.041667 | 0.083333 | 0.33333 | 2025-03-07 08:30 | 2025-03-24 08:20 | 2025-04-04 08:30 |  | 238095 |  |  | 3
2025-01-23 | JOTP25010137 | CT10-027A-P01-04 | TP | TM03 | 1 | 184 | 24 | 7.6667 | 0.95833 | 0.041667 | 0.083333 | 0.33333 | 2025-03-07 08:30 | 2025-03-08 18:30 | 2025-03-21 08:30 |  | 184 |  |  | 1
2025-01-23 | JOTP25010137 | CT10-027A-P02-04 | TP | PB02 | 1 | 184 | 180 | 1.0222 | 0.12778 | 0.041667 | 0.083333 | 0.33333 | 2025-03-07 08:30 | 2025-03-07 22:34 | 2025-03-21 08:30 |  | 184 |  |  | 2
2025-01-23 | JOTP25010137 | CT10-027A-P03-04 | TP | PB07 | 1 | 184 | 30 | 6.1333 | 0.76667 | 0.041667 | 0.083333 | 0.33333 | 2025-03-07 08:30 | 2025-03-08 13:54 | 2025-03-21 08:30 |  | 184 |  |  | 3
2025-01-23 | JOTP25010138 | CT10-027B-P01-03 | TP | TM03 | 1 | 180 | 54 | 3.3333 | 0.41667 | 0.041667 | 0.083333 | 0.33333 | 2025-03-07 08:30 | 2025-03-08 05:30 | 2025-03-21 08:30 |  | 180 |  |  | 1
2025-01-23 | JOTP25010138 | CT10-027B-P02-03 | TP | PB01 | 1 | 180 | 60 | 3 | 0.375 | 0.041667 | 0.083333 | 0.33333 | 2025-03-07 08:30 | 2025-03-08 04:30 | 2025-03-21 08:30 |  | 180 |  |  | 3
2025-01-23 | JOTP25010246 | CP08-571-P01-05 | TR | SM01 | 1 | 720 | 360 | 2 | 0.25 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 01:30 | 2025-03-10 08:30 |  | 720 |  |  | 2
2025-01-23 | JOTP25010246 | CP08-571-P02-05 | TR | TM03 | 1 | 720 | 72 | 10 | 1.25 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-26 01:30 | 2025-03-10 08:30 |  | 720 |  |  | 3
2025-01-23 | JOTP25010246 | CP08-571-P03-05 | PB | PB08 | 1 | 720 | 120 | 6 | 0.75 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 13:30 | 2025-03-10 08:30 |  | 720 |  |  | 1
2025-01-23 | JOTP25010246 | CP08-571-P04-05 | PB | PB04 | 1 | 720 | 90 | 8 | 1 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 19:30 | 2025-03-10 08:30 |  | 720 |  |  | 2
2025-01-23 | JOST25010253 | CP16-032-P01-04 | SM | SM01 | 1 | 729 | 19440 | 0.0375 | 0.0046875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-10 19:37 | 2025-02-24 08:30 |  | 729 |  |  | 3
2025-01-23 | JOST25010253 | CP16-032-P02-04 | ST-1 | PP11 | 1 | 729 | 360 | 2.025 | 0.25312 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 01:35 | 2025-02-24 08:30 |  | 729 |  |  | 2
2025-01-23 | JOST25010253 | CP16-032-P03-04 | ST-1 | PP05-060T | 1 | 729 | 240 | 3.0375 | 0.37969 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 04:37 | 2025-02-24 08:30 |  | 729 |  |  | 2
2025-01-23 | JOAW25010252 | CM17-005-P01-05 | FM | FM02 | 1 | 41584 | 2400 | 17.3267 | 2.1658 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-23 23:29 | 2025-04-02 08:30 |  | 41584 |  |  | 2
2025-01-23 | JOAW25010252 | CM17-005-P04-05 | AL | CHECK | 1 | 41584 | 270 | 154.0148 | 19.2519 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-03-13 01:33 | 2025-04-02 08:30 |  | 41584 |  |  | 2
2025-01-23 | JOST25010250 | CM10-009-P01-05 | ST-2 | PP19-110T | 1 | 32258 | 1500 | 21.5053 | 2.6882 | 0.041667 | 0.083333 | 0.33333 | 2025-03-17 08:30 | 2025-03-20 12:01 | 2025-04-21 08:30 |  | 32258 |  |  | 1
2025-01-23 | JOST25010250 | CM10-009-P02-05 | AL | TP09 | 1 | 32258 | 420 | 76.8048 | 9.6006 | 0.041667 | 0.083333 | 0.33333 | 2025-03-17 08:30 | 2025-03-27 09:55 | 2025-04-21 08:30 |  | 32258 |  |  | 3
2025-01-23 | JOST25010250 | CM10-009-P04-05 | AL | CHECKING | 1 | 32258 | 1200 | 26.8817 | 3.3602 | 0.041667 | 0.083333 | 0.33333 | 2025-03-17 08:30 | 2025-03-21 04:09 | 2025-04-21 08:30 |  | 32258 |  |  | 2
2025-01-23 | JOST25010249 | CM10-009-P01-05 | ST-2 | PP19-110T | 1 | 32258 | 1500 | 21.5053 | 2.6882 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-20 12:01 | 2025-03-07 08:30 |  | 32258 |  |  | 3
2025-01-23 | JOST25010249 | CM10-009-P02-05 | AL | TP09 | 1 | 32258 | 420 | 76.8048 | 9.6006 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-27 09:55 | 2025-03-07 08:30 |  | 32258 |  |  | 3
2025-01-23 | JOST25010249 | CM10-009-P04-05 | AL | CHECKING | 1 | 32258 | 1200 | 26.8817 | 3.3602 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-21 04:09 | 2025-03-07 08:30 |  | 32258 |  |  | 3
2025-01-23 | JOST25010248 | CM10-009-P01-05 | ST-2 | PP19-110T | 1 | 9217 | 1500 | 6.1447 | 0.76808 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 13:56 | 2025-03-07 08:30 |  | 9217 |  |  | 3
2025-01-23 | JOST25010248 | CM10-009-P02-05 | AL | TP09 | 1 | 9217 | 420 | 21.9452 | 2.7432 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-20 13:20 | 2025-03-07 08:30 |  | 9217 |  |  | 2
2025-01-23 | JOST25010248 | CM10-009-P04-05 | AL | CHECKING | 1 | 9217 | 1200 | 7.6808 | 0.9601 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 18:33 | 2025-03-07 08:30 |  | 9217 |  |  | 2
2025-01-24 | JOAW25010251 | CM17-002-P01-04 | FM | FM02 | 1 | 43697 | 3600 | 12.1381 | 1.5173 | 0.041667 | 0.083333 | 0.33333 | 2025-03-07 08:30 | 2025-03-09 07:55 | 2025-04-02 08:30 |  | 43697 |  |  | 2
2025-01-24 | JOTP25010179 | CP08-428A-P01-03 | TR | TM03 | 1 | 639 | 47 | 13.5957 | 1.6995 | 0.041667 | 0.083333 | 0.33333 | 2025-03-10 08:30 | 2025-03-12 12:17 | 2025-03-24 08:30 |  | 639 |  |  | 3
2025-01-24 | JOTP25010179 | CP08-428A-P02-03 | TR | PB07 | 1 | 639 | 96 | 6.6562 | 0.83203 | 0.041667 | 0.083333 | 0.33333 | 2025-03-10 08:30 | 2025-03-11 15:28 | 2025-03-24 08:30 |  | 639 |  |  | 3
2025-01-24 | JOTP25010180 | CP08-428B-P01-03 | TR | TM06 | 1 | 636 | 65 | 9.7846 | 1.2231 | 0.041667 | 0.083333 | 0.33333 | 2025-03-10 08:30 | 2025-03-12 00:51 | 2025-03-24 08:30 |  | 636 |  |  | 1
2025-01-24 | JOTP25010180 | CP08-428B-P02-03 | TR | PB04 | 1 | 636 | 72 | 8.8333 | 1.1042 | 0.041667 | 0.083333 | 0.33333 | 2025-03-10 08:30 | 2025-03-11 22:00 | 2025-03-24 08:30 |  | 636 |  |  | 1
2025-01-24 | JOTP25010181 | CP08-428C-P01-03 | TR | TM06 | 1 | 632 | 60 | 10.5333 | 1.3167 | 0.041667 | 0.083333 | 0.33333 | 2025-03-10 08:30 | 2025-03-12 03:06 | 2025-03-24 08:30 |  | 632 |  |  | 3
2025-01-24 | JOTP25010181 | CP08-428C-P02-03 | TR | PB04 | 1 | 632 | 95 | 6.6526 | 0.83158 | 0.041667 | 0.083333 | 0.33333 | 2025-03-10 08:30 | 2025-03-11 15:27 | 2025-03-24 08:30 |  | 632 |  |  | 1
2025-01-24 | JOTP25010182 | CP08-428D-P01-03 | TR | TM06 | 1 | 640 | 55 | 11.6364 | 1.4545 | 0.041667 | 0.083333 | 0.33333 | 2025-03-10 08:30 | 2025-03-12 06:25 | 2025-03-24 08:30 |  | 640 |  |  | 2
2025-01-24 | JOTP25010182 | CP08-428D-P02-03 | TR | PB07 | 1 | 640 | 70 | 9.1429 | 1.1429 | 0.041667 | 0.083333 | 0.33333 | 2025-03-10 08:30 | 2025-03-11 22:56 | 2025-03-24 08:30 |  | 640 |  |  | 3
2025-01-24 | JOST25010195 | CP08-544-P01-02 | ST | STICK LABEL | 1 | 1050 | 30 | 35 | 4.375 | 0.041667 | 0.083333 | 0.33333 | 2025-03-10 08:30 | 2025-03-15 04:30 | 2025-03-24 08:30 |  | 1050 |  |  | 1
2025-01-24 | JOTP25010227 | CT10-026A-P01-02 | TP | SW09 | 1 | 220 | 8 | 27.5 | 3.4375 | 0.041667 | 0.083333 | 0.33333 | 2025-03-10 08:30 | 2025-03-14 06:00 | 2025-03-21 08:30 |  | 220 |  |  | 2
2025-01-24 | JOAW25010036 | CP08-231-P01-06 | WN | SW03 | 1 | 800 | 15 | 53.3333 | 6.6667 | 0.041667 | 0.083333 | 0.33333 | 2025-03-10 08:30 | 2025-03-17 11:30 | 2025-04-14 08:30 |  | 800 |  |  | 3
2025-01-24 | JOAW25010036 | CP08-231-P02-06 | WN | SW03 | 1 | 800 | 12 | 66.6667 | 8.3333 | 0.041667 | 0.083333 | 0.33333 | 2025-03-10 08:30 | 2025-03-19 03:30 | 2025-04-14 08:30 |  | 800 |  |  | 1
2025-01-24 | JOAW25010036 | CP08-231-P03-06 | WN | SW04 | 1 | 800 | 12 | 66.6667 | 8.3333 | 0.041667 | 0.083333 | 0.33333 | 2025-03-10 08:30 | 2025-03-19 03:30 | 2025-04-14 08:30 |  | 800 |  |  | 3
2025-01-24 | JOAW25010036 | CP08-231-P04-06 | WN | TW03 | 1 | 800 | 12 | 66.6667 | 8.3333 | 0.041667 | 0.083333 | 0.33333 | 2025-03-10 08:30 | 2025-03-19 03:30 | 2025-04-14 08:30 |  | 800 |  |  | 2
2025-01-24 | JOAW24120240 | CD11-026-P01-06 | WN | SW13 | 1 | 20000 | 120 | 166.6667 | 20.8333 | 0.041667 | 0.083333 | 0.33333 | 2025-03-10 08:30 | 2025-03-31 15:30 | 2025-04-21 08:30 |  | 20000 |  |  | 3
2025-01-24 | JOAW24120240 | CD11-026-P02-06 | WN | PP23-060T | 1 | 20000 | 540 | 37.037 | 4.6296 | 0.041667 | 0.083333 | 0.33333 | 2025-03-10 08:30 | 2025-03-15 10:37 | 2025-04-21 08:30 |  | 20000 |  |  | 1
2025-01-24 | JOAW24120240 | CD11-026-P05-06 | WN | TW01 | 1 | 20000 | 420 | 47.619 | 5.9524 | 0.041667 | 0.083333 | 0.33333 | 2025-03-10 08:30 | 2025-03-16 18:21 | 2025-04-21 08:30 |  | 20000 |  |  | 2
2025-01-24 | JOAW24120164 | CA16-011-P01-03 | FM | SW05 | 1 | 60000 | 450 | 133.3333 | 16.6667 | 0.041667 | 0.083333 | 0.33333 | 2025-03-10 08:30 | 2025-03-27 11:30 | 2025-04-07 08:30 |  | 60000 |  |  | 3
2025-01-24 | JOAW24120164 | CA16-011-P02-03 | FM | OPT | 1 | 60000 | 900 | 66.6667 | 8.3333 | 0.041667 | 0.083333 | 0.33333 | 2025-03-10 08:30 | 2025-03-19 03:30 | 2025-04-07 08:30 |  | 60000 |  |  | 2
2025-01-24 | JOST24120163 | CA16-010-P01-03 | ST | PP01-110T | 1 | 79545 | 3000 | 26.515 | 3.3144 | 0.041667 | 0.083333 | 0.33333 | 2025-03-10 08:30 | 2025-03-14 03:03 | 2025-03-31 08:30 |  | 79545 |  |  | 2
2025-01-24 | JOST24120163 | CA16-010-P02-03 | ST-1 | VM01 | 1 | 79545 | 1000 | 79.545 | 9.9431 | 0.041667 | 0.083333 | 0.33333 | 2025-03-10 08:30 | 2025-03-20 18:08 | 2025-03-31 08:30 |  | 79545 |  |  | 2
2025-01-27 | JOAW25010303 | CS18-010-P01-03 | WN | SW06 | 1 | 300 | 18 | 16.6667 | 2.0833 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-15 21:30 | 2025-02-24 08:30 | 83 | 217 |  |  | 2
2025-01-27 | JOAW25010303 | CS18-010-P02-03 | WN | TW01 | 1 | 300 | 18 | 16.6667 | 2.0833 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-15 21:30 | 2025-02-24 08:30 | 83 | 217 |  |  | 1
2025-01-27 | JOAW25010298 | CS18-006-P01-03 | WN | SW06 | 1 | 350 | 15 | 23.3333 | 2.9167 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-20 17:30 | 2025-03-03 08:30 |  | 350 |  |  | 3
2025-01-27 | JOAW25010298 | CS18-006-P02-03 | WN | TW01 | 1 | 350 | 15 | 23.3333 | 2.9167 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-20 17:30 | 2025-03-03 08:30 |  | 350 |  |  | 2
2025-01-27 | JOST25010255 | CP08-499A-P01-06 | ST-4 | PP29-250T | 1 | 300 | 120 | 2.5 | 0.3125 | 0.041667 | 0.083333 | 0.33333 | 2025-01-31 08:30 | 2025-02-01 03:00 | 2025-02-14 08:30 |  | 300 |  |  | 3
2025-01-27 | JOST25010255 | CP08-499A-P02-06 | ST-4 | PP30 | 1 | 300 | 120 | 2.5 | 0.3125 | 0.041667 | 0.083333 | 0.33333 | 2025-01-31 08:30 | 2025-02-01 03:00 | 2025-02-14 08:30 |  | 300 |  |  | 3
2025-01-27 | JOST25010255 | CP08-499A-P03-06 | ST-3 | TP03 | 1 | 300 | 120 | 2.5 | 0.3125 | 0.041667 | 0.083333 | 0.33333 | 2025-01-31 08:30 | 2025-02-01 03:00 | 2025-02-14 08:30 |  | 300 |  |  | 3
2025-01-27 | JOST25010255 | CP08-499A-P04-06 | AL | TP09 | 1 | 300 | 120 | 2.5 | 0.3125 | 0.041667 | 0.083333 | 0.33333 | 2025-01-31 08:30 | 2025-02-01 03:00 | 2025-02-14 08:30 |  | 300 |  |  | 3
2025-01-27 | JOST25010255 | CP08-499A-P05-06 | TR | PB05 | 1 | 300 | 60 | 5 | 0.625 | 0.041667 | 0.083333 | 0.33333 | 2025-01-31 08:30 | 2025-02-01 10:30 | 2025-02-14 08:30 |  | 300 |  |  | 2
2025-01-27 | JOST25010256 | CP08-499-P01-02 | ST-3 | SW01 | 1 | 300 | 30 | 10 | 1.25 | 0.041667 | 0.083333 | 0.33333 | 2025-02-14 08:30 | 2025-02-16 01:30 | 2025-02-21 08:30 |  | 300 |  |  | 2
2025-01-27 | JOST25010309 | CN08-001-P01-04 | ST | PP14 | 1 | 46428 | 1200 | 38.69 | 4.8362 | 0.041667 | 0.083333 | 0.33333 | 2025-03-03 08:30 | 2025-03-08 15:34 | 2025-04-14 08:30 |  | 46428 |  |  | 2
2025-01-27 | JOST25010309 | CN08-001-P02-04 | ST | TP09 | 1 | 46428 | 480 | 96.725 | 12.0906 | 0.041667 | 0.083333 | 0.33333 | 2025-03-03 08:30 | 2025-03-15 21:40 | 2025-04-14 08:30 |  | 46428 |  |  | 1
2025-01-27 | JOST25010292 | CT10-018-P01-07 | ST-3 | PP27-110T | 1 | 210 | 120 | 1.75 | 0.21875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 00:45 | 2025-02-27 08:30 |  | 210 |  |  | 2
2025-01-27 | JOST25010292 | CT10-018-P02-07 | ST-3 | PP16-110T | 1 | 210 | 120 | 1.75 | 0.21875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 00:45 | 2025-02-27 08:30 |  | 210 |  |  | 3
2025-01-27 | JOST25010292 | CT10-018-P03-07 | ST-3 | PP17-110T | 1 | 210 | 120 | 1.75 | 0.21875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 00:45 | 2025-02-27 08:30 |  | 210 |  |  | 1
2025-01-27 | JOST25010292 | CT10-018-P04-07 | ST-3 | TP03 | 1 | 210 | 120 | 1.75 | 0.21875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 00:45 | 2025-02-27 08:30 |  | 210 |  |  | 2
2025-01-27 | JOST25010292 | CT10-018-P05-07 | ST-3 | PP18 | 1 | 210 | 120 | 1.75 | 0.21875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 00:45 | 2025-02-27 08:30 |  | 210 |  |  | 3
2025-01-27 | JOST25010292 | CT10-018-P06-07 | ST | SW01 | 1 | 210 | 120 | 1.75 | 0.21875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 00:45 | 2025-02-27 08:30 |  | 210 |  |  | 1
2025-01-27 | JOST25010291 | CT10-015-P01-05 | ST-4 | PP24-160T | 1 | 14400 | 360 | 40 | 5 | 0.041667 | 0.083333 | 0.33333 | 2025-02-14 08:30 | 2025-02-19 19:30 | 2025-02-28 08:30 |  | 14400 |  |  | 3
2025-01-27 | JOST25010291 | CT10-015-P02-05 | ST-4 | PP25-160T | 1 | 14400 | 360 | 40 | 5 | 0.041667 | 0.083333 | 0.33333 | 2025-02-14 08:30 | 2025-02-19 19:30 | 2025-02-28 08:30 |  | 14400 |  |  | 2
2025-01-27 | JOST25010291 | CT10-015-P03-05 | ST-4 | PP20-110T | 1 | 14400 | 360 | 40 | 5 | 0.041667 | 0.083333 | 0.33333 | 2025-02-14 08:30 | 2025-02-19 19:30 | 2025-02-28 08:30 |  | 14400 |  |  | 3
2025-01-27 | JOST25010291 | CT10-015-P04-05 | ST-4 | PP28-110T | 1 | 14400 | 360 | 40 | 5 | 0.041667 | 0.083333 | 0.33333 | 2025-02-14 08:30 | 2025-02-19 19:30 | 2025-02-28 08:30 |  | 14400 |  |  | 1
2025-01-27 | JOST25010290 | CT10-015-P01-05 | ST-4 | PP24-160T | 1 | 14400 | 360 | 40 | 5 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-15 19:30 | 2025-02-24 08:30 | 8412 | 5988 |  |  | 2
2025-01-27 | JOST25010290 | CT10-015-P02-05 | ST-4 | PP25-160T | 1 | 14400 | 360 | 40 | 5 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-15 19:30 | 2025-02-24 08:30 | 8412 | 5988 |  |  | 3
2025-01-27 | JOST25010290 | CT10-015-P03-05 | ST-4 | PP20-110T | 1 | 14400 | 360 | 40 | 5 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-15 19:30 | 2025-02-24 08:30 | 8412 | 5988 |  |  | 2
2025-01-27 | JOST25010290 | CT10-015-P04-05 | ST-4 | PP28-110T | 1 | 14400 | 360 | 40 | 5 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-15 19:30 | 2025-02-24 08:30 | 8412 | 5988 |  |  | 2
2025-01-27 | JOST25010288 | CT10-005-P01-07 | ST-3 | PP27-110T | 1 | 500 | 120 | 4.1667 | 0.52083 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 08:00 | 2025-02-27 08:30 |  | 500 |  |  | 2
2025-01-27 | JOST25010288 | CT10-005-P02-07 | ST-3 | PP16-110T | 1 | 500 | 120 | 4.1667 | 0.52083 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 08:00 | 2025-02-27 08:30 |  | 500 |  |  | 1
2025-01-27 | JOST25010288 | CT10-005-P03-07 | ST-3 | PP17-110T | 1 | 500 | 120 | 4.1667 | 0.52083 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 08:00 | 2025-02-27 08:30 |  | 500 |  |  | 2
2025-01-27 | JOST25010288 | CT10-005-P04-07 | ST-3 | TP03 | 1 | 500 | 120 | 4.1667 | 0.52083 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 08:00 | 2025-02-27 08:30 |  | 500 |  |  | 3
2025-01-27 | JOST25010288 | CT10-005-P05-07 | ST-3 | PP18-150T | 1 | 500 | 120 | 4.1667 | 0.52083 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 08:00 | 2025-02-27 08:30 |  | 500 |  |  | 1
2025-01-27 | JOST25010288 | CT10-005-P06-07 | ST-3 | SW01 | 1 | 500 | 120 | 4.1667 | 0.52083 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 08:00 | 2025-02-27 08:30 |  | 500 |  |  | 2
2025-01-27 | JOTP25010287 | CP08-563A-P01-03 | TR | TM05 | 1 | 760 | 60 | 12.6667 | 1.5833 | 0.041667 | 0.083333 | 0.33333 | 2025-03-03 08:30 | 2025-03-05 09:30 | 2025-03-17 08:30 |  | 760 |  |  | 3
2025-01-27 | JOTP25010287 | CP08-563A-P02-03 | PB | PB08 | 1 | 760 | 90 | 8.4444 | 1.0556 | 0.041667 | 0.083333 | 0.33333 | 2025-03-03 08:30 | 2025-03-04 20:50 | 2025-03-17 08:30 |  | 760 |  |  | 1
2025-01-27 | JOTP25010286 | CP08-563-P01-04 | PB | SW09 | 1 | 760 | 120 | 6.3333 | 0.79167 | 0.041667 | 0.083333 | 0.33333 | 2025-03-17 08:30 | 2025-03-18 14:30 | 2025-03-31 08:30 |  | 760 |  |  | 3
2025-01-27 | JOTP25010286 | CP08-563-P02-04 | PB | OPT | 1 | 760 | 36 | 21.1111 | 2.6389 | 0.041667 | 0.083333 | 0.33333 | 2025-03-17 08:30 | 2025-03-20 10:50 | 2025-03-31 08:30 |  | 760 |  |  | 2
2025-01-27 | JOTP25010286 | CP08-563-P03-04 | TP | OPT | 1 | 760 | 80 | 9.5 | 1.1875 | 0.041667 | 0.083333 | 0.33333 | 2025-03-17 08:30 | 2025-03-19 | 2025-03-31 08:30 |  | 760 |  |  | 3
2025-01-27 | JOTP25010282 | CP08-562A-P01-03 | TR | TM03 | 1 | 804 | 40 | 20.1 | 2.5125 | 0.041667 | 0.083333 | 0.33333 | 2025-03-07 08:30 | 2025-03-10 07:48 | 2025-03-21 08:30 |  | 804 |  |  | 1
2025-01-27 | JOTP25010282 | CP08-562A-P02-03 | PB | PB05 | 1 | 804 | 120 | 6.7 | 0.8375 | 0.041667 | 0.083333 | 0.33333 | 2025-03-07 08:30 | 2025-03-08 15:36 | 2025-03-21 08:30 |  | 804 |  |  | 2
2025-01-27 | JOTP25010283 | CP08-562B-P01-03 | TR | TM03 | 1 | 812 | 60 | 13.5333 | 1.6917 | 0.041667 | 0.083333 | 0.33333 | 2025-03-07 08:30 | 2025-03-09 12:06 | 2025-03-21 08:30 |  | 812 |  |  | 3
2025-01-27 | JOTP25010283 | CP08-562B-P02-03 | PB | PB04 | 1 | 812 | 100 | 8.12 | 1.015 | 0.041667 | 0.083333 | 0.33333 | 2025-03-07 08:30 | 2025-03-08 19:52 | 2025-03-21 08:30 |  | 812 |  |  | 2
2025-01-27 | JOTP25010284 | CP08-562C-P01-05 | TR | TM03 | 1 | 800 | 44 | 18.1818 | 2.2727 | 0.041667 | 0.083333 | 0.33333 | 2025-03-07 08:30 | 2025-03-10 02:03 | 2025-03-21 08:30 |  | 800 |  |  | 2
2025-01-27 | JOTP25010284 | CP08-562C-P02-05 | PB | PB04 | 1 | 800 | 120 | 6.6667 | 0.83333 | 0.041667 | 0.083333 | 0.33333 | 2025-03-07 08:30 | 2025-03-08 15:30 | 2025-03-21 08:30 |  | 800 |  |  | 2
2025-01-27 | JOTP25010284 | CP08-562C-P03-05 | PB | PB08 | 1 | 800 | 90 | 8.8889 | 1.1111 | 0.041667 | 0.083333 | 0.33333 | 2025-03-07 08:30 | 2025-03-08 22:10 | 2025-03-21 08:30 |  | 800 |  |  | 2
2025-01-27 | JOTP25010284 | CP08-562C-P04-05 | PB | PB04 | 1 | 800 | 120 | 6.6667 | 0.83333 | 0.041667 | 0.083333 | 0.33333 | 2025-03-07 08:30 | 2025-03-08 15:30 | 2025-03-21 08:30 |  | 800 |  |  | 1
2025-01-27 | JOTP25010285 | CP08-562D-P01-03 | TR | TM03 | 1 | 805 | 35 | 23 | 2.875 | 0.041667 | 0.083333 | 0.33333 | 2025-03-07 08:30 | 2025-03-10 16:30 | 2025-03-21 08:30 |  | 805 |  |  | 3
2025-01-27 | JOTP25010285 | CP08-562D-P02-03 | PB | PB07 | 1 | 805 | 100 | 8.05 | 1.0063 | 0.041667 | 0.083333 | 0.33333 | 2025-03-07 08:30 | 2025-03-08 19:39 | 2025-03-21 08:30 |  | 805 |  |  | 2
2025-01-27 | JOTP25010286 | CP08-563-P01-04 | PB | SW09 | 1 | 760 | 120 | 6.3333 | 0.79167 | 0.041667 | 0.083333 | 0.33333 | 2025-03-17 08:30 | 2025-03-18 14:30 | 2025-03-31 08:30 |  | 760 |  |  | 3
2025-01-27 | JOTP25010286 | CP08-563-P02-04 | PB | OPT | 1 | 760 | 36 | 21.1111 | 2.6389 | 0.041667 | 0.083333 | 0.33333 | 2025-03-17 08:30 | 2025-03-20 10:50 | 2025-03-31 08:30 |  | 760 |  |  | 3
2025-01-27 | JOTP25010286 | CP08-563-P03-04 | TP | OPT | 1 | 760 | 80 | 9.5 | 1.1875 | 0.041667 | 0.083333 | 0.33333 | 2025-03-17 08:30 | 2025-03-19 | 2025-03-31 08:30 |  | 760 |  |  | 3
2025-01-27 | JOTP25010281 | CP08-562-P01-05 | PB | SW14 | 1 | 802 | 120 | 6.6833 | 0.83542 | 0.041667 | 0.083333 | 0.33333 | 2025-03-21 08:30 | 2025-03-22 15:33 | 2025-04-04 08:30 |  | 802 |  |  | 3
2025-01-27 | JOTP25010281 | CP08-562-P02-05 | PB | SW14 | 1 | 802 | 17 | 47.1765 | 5.8971 | 0.041667 | 0.083333 | 0.33333 | 2025-03-21 08:30 | 2025-03-27 17:02 | 2025-04-04 08:30 |  | 802 |  |  | 2
2025-01-27 | JOTP25010281 | CP08-562-P03-05 | OPT | OPT | 1 | 802 | 50 | 16.04 | 2.005 | 0.041667 | 0.083333 | 0.33333 | 2025-03-21 08:30 | 2025-03-23 19:37 | 2025-04-04 08:30 |  | 802 |  |  | 2
2025-01-27 | JOTP25010281 | CP08-562-P04-05 | OPT | OPT | 1 | 802 | 60 | 13.3667 | 1.6708 | 0.041667 | 0.083333 | 0.33333 | 2025-03-21 08:30 | 2025-03-23 11:36 | 2025-04-04 08:30 |  | 802 |  |  | 2
2025-01-27 | JOAW25010276 | CP08-557C-P01-04 | WN | WS01 | 1 | 1000 | 900 | 1.1111 | 0.13889 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-17 22:50 | 2025-03-03 08:30 |  | 1000 |  |  | 1
2025-01-27 | JOAW25010276 | CP08-557C-P02-04 | WN | JIG BENDING | 1 | 1000 | 240 | 4.1667 | 0.52083 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 08:00 | 2025-03-03 08:30 |  | 1000 |  |  | 2
2025-01-27 | JOAW25010276 | CP08-557C-P03-04 | WN | JIG BENDING | 1 | 1000 | 240 | 4.1667 | 0.52083 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 08:00 | 2025-03-03 08:30 |  | 1000 |  |  | 3
2025-01-27 | JOAW25010277 | CP08-557D-P01-03 | WN | WS01 | 1 | 1000 | 5700 | 0.17544 | 0.02193 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-17 20:02 | 2025-03-03 08:30 |  | 1000 |  |  | 1
2025-01-27 | JOAW25010277 | CP08-557D-P02-03 | WN | JIG BENDING | 1 | 1000 | 120 | 8.3333 | 1.0417 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 20:30 | 2025-03-03 08:30 |  | 1000 |  |  | 2
2025-01-27 | JOAW25010278 | CP08-557E-P01-02 | WN | WS01 | 1 | 6000 | 4800 | 1.25 | 0.15625 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-17 23:15 | 2025-03-03 08:30 |  | 6000 |  |  | 3
2025-01-27 | JOAW25010279 | CP08-557F-P01-02 | WN | WS01 | 1 | 5000 | 900 | 5.5556 | 0.69444 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 12:10 | 2025-03-03 08:30 |  | 5000 |  |  | 1
2025-01-27 | JOAW25010275 | CP08-557-P01-09 | WN | SW04 | 1 | 1000 | 30 | 33.3333 | 4.1667 | 0.041667 | 0.083333 | 0.33333 | 2025-03-03 08:30 | 2025-03-07 23:30 | 2025-03-31 08:30 |  | 1000 |  |  | 3
2025-01-27 | JOAW25010275 | CP08-557-P02-09 | WN | PP23-060T | 1 | 1000 | 180 | 5.5556 | 0.69444 | 0.041667 | 0.083333 | 0.33333 | 2025-03-03 08:30 | 2025-03-04 12:10 | 2025-03-31 08:30 |  | 1000 |  |  | 2
2025-01-27 | JOAW25010275 | CP08-557-P03-09 | TR | SW06 | 1 | 1000 | 50 | 20 | 2.5 | 0.041667 | 0.083333 | 0.33333 | 2025-03-03 08:30 | 2025-03-06 07:30 | 2025-03-31 08:30 |  | 1000 |  |  | 3
2025-01-27 | JOAW25010275 | CP08-557-P04-09 | TR | SW05 | 1 | 1000 | 120 | 8.3333 | 1.0417 | 0.041667 | 0.083333 | 0.33333 | 2025-03-03 08:30 | 2025-03-04 20:30 | 2025-03-31 08:30 |  | 1000 |  |  | 1
2025-01-27 | JOAW25010275 | CP08-557-P05-09 | WN | TW02 | 1 | 1000 | 90 | 11.1111 | 1.3889 | 0.041667 | 0.083333 | 0.33333 | 2025-03-03 08:30 | 2025-03-05 04:50 | 2025-03-31 08:30 |  | 1000 |  |  | 2
2025-01-27 | JOAW25010275 | CP08-557-P06-09 | WN | OPT | 1 | 1000 | 90 | 11.1111 | 1.3889 | 0.041667 | 0.083333 | 0.33333 | 2025-03-03 08:30 | 2025-03-05 04:50 | 2025-03-31 08:30 |  | 1000 |  |  | 3
2025-01-27 | JOAW25010275 | CP08-557-P08-09 | AL | CHECKING | 1 | 1000 | 15 | 66.6667 | 8.3333 | 0.041667 | 0.083333 | 0.33333 | 2025-03-03 08:30 | 2025-03-12 03:30 | 2025-03-31 08:30 |  | 1000 |  |  | 2
2025-01-27 | JOTP25010272 | CP08-554A-P01-04 | TR | TM05 | 1 | 500 | 60 | 8.3333 | 1.0417 | 0.041667 | 0.083333 | 0.33333 | 2025-03-03 08:30 | 2025-03-04 20:30 | 2025-03-17 08:30 |  | 500 |  |  | 2
2025-01-27 | JOTP25010272 | CP08-554A-P02-04 | TR | 1 | 1 | 500 | 20 | 25 | 3.125 | 0.041667 | 0.083333 | 0.33333 | 2025-03-03 08:30 | 2025-03-06 22:30 | 2025-03-17 08:30 |  | 500 |  |  | 2
2025-01-27 | JOTP25010272 | CP08-554A-P03-04 | TR | PB02 | 1 | 500 | 30 | 16.6667 | 2.0833 | 0.041667 | 0.083333 | 0.33333 | 2025-03-03 08:30 | 2025-03-05 21:30 | 2025-03-17 08:30 |  | 500 |  |  | 2
2025-01-27 | JOST25010273 | CP08-554C-P01-04 | ST | PP29 | 1 | 510 | 360 | 1.4167 | 0.17708 | 0.041667 | 0.083333 | 0.33333 | 2025-03-03 08:30 | 2025-03-03 23:45 | 2025-03-17 08:30 |  | 510 |  |  | 1
2025-01-27 | JOST25010273 | CP08-554C-P02-04 | ST | PP30-200T | 1 | 510 | 360 | 1.4167 | 0.17708 | 0.041667 | 0.083333 | 0.33333 | 2025-03-03 08:30 | 2025-03-03 23:45 | 2025-03-17 08:30 |  | 510 |  |  | 3
2025-01-27 | JOST25010273 | CP08-554C-P03-04 | ST | PP21 | 1 | 510 | 240 | 2.125 | 0.26562 | 0.041667 | 0.083333 | 0.33333 | 2025-03-03 08:30 | 2025-03-04 01:52 | 2025-03-17 08:30 |  | 510 |  |  | 2
2025-01-27 | JOTP25010269 | CP08-553D-P01-03 | TR | TM06 | 1 | 480 | 100 | 4.8 | 0.6 | 0.041667 | 0.083333 | 0.33333 | 2025-02-19 08:30 | 2025-02-20 09:54 | 2025-03-03 08:30 |  | 480 |  |  | 3
2025-01-27 | JOTP25010269 | CP08-553D-P02-03 | TR | PB01 | 1 | 480 | 240 | 2 | 0.25 | 0.041667 | 0.083333 | 0.33333 | 2025-02-19 08:30 | 2025-02-20 01:30 | 2025-03-03 08:30 |  | 480 |  |  | 3
2025-01-27 | JOTP25010270 | CP08-553E-P01-03 | TR | TM06 | 1 | 480 | 200 | 2.4 | 0.3 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 02:42 | 2025-03-03 08:30 |  | 480 |  |  | 3
2025-01-27 | JOTP25010270 | CP08-553E-P02-03 | TR | PB01 | 1 | 480 | 240 | 2 | 0.25 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-18 01:30 | 2025-03-03 08:30 |  | 480 |  |  | 3
2025-01-27 | JOTP25010266 | CP08-552A-P01-04 | TR | TM06 | 1 | 684 | 120 | 5.7 | 0.7125 | 0.041667 | 0.083333 | 0.33333 | 2025-02-19 08:30 | 2025-02-20 12:36 | 2025-03-03 08:30 |  | 684 |  |  | 2
2025-01-27 | JOTP25010266 | CP08-552A-P02-04 | TR | RL1 | 1 | 684 | 30 | 22.8 | 2.85 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-16 15:54 | 2025-02-27 08:30 |  | 684 |  |  | 2
2025-01-27 | JOTP25010266 | CP08-552A-P03-04 | TR | PB02 | 1 | 684 | 30 | 22.8 | 2.85 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-16 15:54 | 2025-02-27 08:30 |  | 684 |  |  | 2
2025-01-27 | JOST25010267 | CP08-552B-P01-04 | ST | PP30-200T | 1 | 561 | 240 | 2.3375 | 0.29219 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 02:31 | 2025-02-27 08:30 |  | 561 |  |  | 3
2025-01-27 | JOST25010267 | CP08-552B-P02-04 | ST | PP29 | 1 | 561 | 120 | 4.675 | 0.58437 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 09:32 | 2025-02-27 08:30 |  | 561 |  |  | 3
2025-01-27 | JOST25010267 | CP08-552B-P03-04 | ST | PP21 | 1 | 561 | 240 | 2.3375 | 0.29219 | 0.041667 | 0.083333 | 0.33333 | 2025-02-13 08:30 | 2025-02-14 02:31 | 2025-02-27 08:30 |  | 561 |  |  | 1
2025-01-27 | JOTP25010268 | CP08-553-P01-07 | TR | SW14 | 1 | 162 | 60 | 2.7 | 0.3375 | 0.041667 | 0.083333 | 0.33333 | 2025-03-03 08:30 | 2025-03-04 03:36 | 2025-03-17 08:30 |  | 162 |  |  | 1
2025-01-27 | JOTP25010268 | CP08-553-P02-07 | TR | SW14 | 1 | 162 | 60 | 2.7 | 0.3375 | 0.041667 | 0.083333 | 0.33333 | 2025-03-03 08:30 | 2025-03-04 03:36 | 2025-03-17 08:30 |  | 162 |  |  | 3
2025-01-27 | JOTP25010268 | CP08-553-P03-07 | TR | SW14 | 1 | 162 | 60 | 2.7 | 0.3375 | 0.041667 | 0.083333 | 0.33333 | 2025-03-03 08:30 | 2025-03-04 03:36 | 2025-03-17 08:30 |  | 162 |  |  | 1
2025-01-27 | JOTP25010268 | CP08-553-P04-07 | TR | SW14 | 1 | 162 | 12 | 13.5 | 1.6875 | 0.041667 | 0.083333 | 0.33333 | 2025-03-03 08:30 | 2025-03-05 12:00 | 2025-03-17 08:30 |  | 162 |  |  | 2
2025-01-27 | JOTP25010268 | CP08-553-P05-07 | TR | PAINTING | 1 | 162 | 12 | 13.5 | 1.6875 | 0.041667 | 0.083333 | 0.33333 | 2025-03-03 08:30 | 2025-03-05 12:00 | 2025-03-17 08:30 |  | 162 |  |  | 3
2025-01-27 | JOTP25010268 | CP08-553-P06-07 | TR | PACK & LABEL | 1 | 162 | 12 | 13.5 | 1.6875 | 0.041667 | 0.083333 | 0.33333 | 2025-03-03 08:30 | 2025-03-05 12:00 | 2025-03-17 08:30 |  | 162 |  |  | 1
2025-01-27 | JOTP25010265 | CP08-552-P01-07 | TR | SW14 | 1 | 162 | 60 | 2.7 | 0.3375 | 0.041667 | 0.083333 | 0.33333 | 2025-02-27 08:30 | 2025-02-28 03:36 | 2025-03-13 08:30 |  | 162 |  |  | 2
2025-01-27 | JOTP25010265 | CP08-552-P02-07 | TR | SW14 | 1 | 162 | 60 | 2.7 | 0.3375 | 0.041667 | 0.083333 | 0.33333 | 2025-02-27 08:30 | 2025-02-28 03:36 | 2025-03-13 08:30 |  | 162 |  |  | 3
2025-01-27 | JOTP25010265 | CP08-552-P03-07 | TR | SW14 | 1 | 162 | 60 | 2.7 | 0.3375 | 0.041667 | 0.083333 | 0.33333 | 2025-02-27 08:30 | 2025-02-28 03:36 | 2025-03-13 08:30 |  | 162 |  |  | 1
2025-01-27 | JOTP25010265 | CP08-552-P04-07 | TR | SW14 | 1 | 162 | 12 | 13.5 | 1.6875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-27 08:30 | 2025-03-01 12:00 | 2025-03-13 08:30 |  | 162 |  |  | 3
2025-01-27 | JOTP25010265 | CP08-552-P05-07 | TR | PAINTING | 1 | 162 | 12 | 13.5 | 1.6875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-27 08:30 | 2025-03-01 12:00 | 2025-03-13 08:30 |  | 162 |  |  | 2
2025-01-27 | JOTP25010265 | CP08-552-P06-07 | TR | PACK & LABEL | 1 | 162 | 12 | 13.5 | 1.6875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-27 08:30 | 2025-03-01 12:00 | 2025-03-13 08:30 |  | 162 |  |  | 3
2025-01-27 | JOTP25010259 | CP08-323A-P01-04 | SM | SM01 | 1 | 45 | 240 | 0.1875 | 0.023438 | 0.041667 | 0.083333 | 0.33333 | 2025-02-14 08:30 | 2025-02-14 20:04 | 2025-02-28 08:30 |  | 45 |  |  | 1
2025-01-27 | JOTP25010259 | CP08-323A-P02-04 | TR | TM03 | 1 | 45 | 82 | 0.54878 | 0.068598 | 0.041667 | 0.083333 | 0.33333 | 2025-02-14 08:30 | 2025-02-14 21:09 | 2025-02-28 08:30 |  | 45 |  |  | 2
2025-01-27 | JOTP25010259 | CP08-323A-P03-04 | TR | PB05 | 1 | 45 | 25 | 1.8 | 0.225 | 0.041667 | 0.083333 | 0.33333 | 2025-02-14 08:30 | 2025-02-15 00:54 | 2025-02-28 08:30 |  | 45 |  |  | 3
2025-01-27 | JOST25010258 | CP08-323-P01-02 | ST-3 | PP09-160T | 1 | 45 | 120 | 0.375 | 0.046875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-02-28 20:38 | 2025-03-14 08:30 |  | 45 |  |  | 2
2025-01-27 | JOAW25010257 | CP08-300-P01-03 | FM | FM03 | 1 | 17241 | 1800 | 9.5783 | 1.1973 | 0.041667 | 0.083333 | 0.33333 | 2025-03-14 08:30 | 2025-03-16 00:14 | 2025-04-04 08:30 |  | 17241 |  |  | 2
2025-01-27 | JOAW25010257 | CP08-300-P02-03 | FM | VM01 | 1 | 17241 | 1000 | 17.241 | 2.1551 | 0.041667 | 0.083333 | 0.33333 | 2025-03-14 08:30 | 2025-03-16 23:13 | 2025-04-04 08:30 |  | 17241 |  |  | 2
2025-01-27 | JOST25010264 | CP08-483-P01-04 | SM | SM01 | 1 | 2050 | 205 | 10 | 1.25 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-12 01:30 | 2025-02-24 08:30 |  | 2050 |  |  | 2
2025-01-27 | JOST25010264 | CP08-483-P02-04 | ST-2 | PP10-080T | 1 | 2050 | 360 | 5.6944 | 0.71181 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 12:35 | 2025-02-24 08:30 |  | 2050 |  |  | 1
2025-01-27 | JOST25010264 | CP08-483-P03-04 | ST-3 | PP21-110T | 1 | 2050 | 240 | 8.5417 | 1.0677 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 21:08 | 2025-02-24 08:30 |  | 2050 |  |  | 3
2025-01-27 | JOTP25010262 | CP08-421-P01-03 | TR | TM05 | 1 | 900 | 90 | 10 | 1.25 | 0.041667 | 0.083333 | 0.33333 | 2025-03-14 08:30 | 2025-03-16 01:30 | 2025-03-28 08:30 |  | 900 |  |  | 2
2025-01-27 | JOTP25010262 | CP08-421-P02-03 | TR | PB08 | 1 | 900 | 120 | 7.5 | 0.9375 | 0.041667 | 0.083333 | 0.33333 | 2025-03-14 08:30 | 2025-03-15 18:00 | 2025-03-28 08:30 |  | 900 |  |  | 3
2025-01-27 | JOTP25010263 | CP08-422-P01-03 | TR | TM05 | 1 | 900 | 50 | 18 | 2.25 | 0.041667 | 0.083333 | 0.33333 | 2025-03-14 08:30 | 2025-03-17 01:30 | 2025-03-28 08:30 |  | 900 |  |  | 3
2025-01-27 | JOTP25010263 | CP08-422-P02-03 | TR | PB08 | 1 | 900 | 72 | 12.5 | 1.5625 | 0.041667 | 0.083333 | 0.33333 | 2025-03-14 08:30 | 2025-03-16 09:00 | 2025-03-28 08:30 |  | 900 |  |  | 3
2025-01-27 | JOST25010261 | CP08-369/CP08-370-P01-05 | SM | SM01 | 1 | 2800 | 360 | 7.7778 | 0.97222 | 0.041667 | 0.083333 | 0.33333 | 2025-03-14 08:30 | 2025-03-15 18:50 | 2025-03-28 08:30 |  | 2800 |  |  | 3
2025-01-27 | JOST25010261 | CP08-369/CP08-370-P02-05 | ST-3 | PP25-160T | 1 | 2800 | 300 | 9.3333 | 1.1667 | 0.041667 | 0.083333 | 0.33333 | 2025-03-14 08:30 | 2025-03-15 23:30 | 2025-03-28 08:30 |  | 2800 |  |  | 2
2025-01-27 | JOST25010261 | CP08-369/CP08-370-P03-05 | ST-4 | PP20-110T | 1 | 2800 | 300 | 9.3333 | 1.1667 | 0.041667 | 0.083333 | 0.33333 | 2025-03-14 08:30 | 2025-03-15 23:30 | 2025-03-28 08:30 |  | 2800 |  |  | 2
2025-01-27 | JOST25010261 | CP08-369/CP08-370-P04-05 | ST-3 | PP28-110T | 1 | 2800 | 300 | 9.3333 | 1.1667 | 0.041667 | 0.083333 | 0.33333 | 2025-03-14 08:30 | 2025-03-15 23:30 | 2025-03-28 08:30 |  | 2800 |  |  | 2
2025-01-27 | JOST25010250 | CM10-009-P01-05 | ST-2 | PP19-110T | 1 | 32258 | 1500 | 21.5053 | 2.6882 | 0.041667 | 0.083333 | 0.33333 | 2025-03-14 08:30 | 2025-03-17 12:01 | 2025-03-28 08:30 |  | 32258 |  |  | 3
2025-01-27 | JOST25010250 | CM10-009-P02-05 | AL | TP09 | 1 | 32258 | 420 | 76.8048 | 9.6006 | 0.041667 | 0.083333 | 0.33333 | 2025-03-17 08:30 | 2025-03-27 09:55 | 2025-04-21 08:30 |  | 32258 |  |  | 2
2025-01-27 | JOST25010250 | CM10-009-P04-05 | AL | CHECKING | 1 | 32258 | 1200 | 26.8817 | 3.3602 | 0.041667 | 0.083333 | 0.33333 | 2025-03-17 08:30 | 2025-03-21 04:09 | 2025-04-21 08:30 |  | 32258 |  |  | 2
2025-01-27 | JOTP25010271 | CP08-554-P01-06 | TR | SW14 | 1 | 500 | 93 | 5.3763 | 0.67204 | 0.041667 | 0.083333 | 0.33333 | 2025-03-17 08:30 | 2025-03-18 11:38 | 2025-03-31 08:30 |  | 500 |  |  | 2
2025-01-27 | JOTP25010271 | CP08-554-P02-06 | TR | SW14 | 1 | 500 | 129 | 3.876 | 0.4845 | 0.041667 | 0.083333 | 0.33333 | 2025-03-17 08:30 | 2025-03-18 07:08 | 2025-03-31 08:30 |  | 500 |  |  | 3
2025-01-27 | JOTP25010271 | CP08-554-P03-06 | TR | SW14 | 1 | 500 | 12 | 41.6667 | 5.2083 | 0.041667 | 0.083333 | 0.33333 | 2025-03-17 08:30 | 2025-03-23 00:30 | 2025-03-31 08:30 |  | 500 |  |  | 3
2025-01-27 | JOTP25010271 | CP08-554-P04-06 | TR | PAINTING | 1 | 500 | 12 | 41.6667 | 5.2083 | 0.041667 | 0.083333 | 0.33333 | 2025-03-17 08:30 | 2025-03-23 00:30 | 2025-03-31 08:30 |  | 500 |  |  | 1
2025-01-27 | JOTP25010271 | CP08-554-P05-06 | TR | PACK & LABEL | 1 | 500 | 12 | 41.6667 | 5.2083 | 0.041667 | 0.083333 | 0.33333 | 2025-03-17 08:30 | 2025-03-23 00:30 | 2025-03-31 08:30 |  | 500 |  |  | 1
2025-01-27 | JOST25010274 | CP08-555-P01-04 | TR | PP17-110T | 1 | 2600 | 240 | 10.8333 | 1.3542 | 0.041667 | 0.083333 | 0.33333 | 2025-03-21 08:30 | 2025-03-23 04:00 | 2025-04-04 08:30 |  | 2600 |  |  | 3
2025-01-27 | JOST25010274 | CP08-555-P02-04 | ST | PP16-110T | 1 | 2600 | 240 | 10.8333 | 1.3542 | 0.041667 | 0.083333 | 0.33333 | 2025-03-21 08:30 | 2025-03-23 04:00 | 2025-04-04 08:30 |  | 2600 |  |  | 1
2025-01-27 | JOST25010274 | CP08-555-P03-04 | ST | PP27-110T | 1 | 2600 | 240 | 10.8333 | 1.3542 | 0.041667 | 0.083333 | 0.33333 | 2025-03-21 08:30 | 2025-03-23 04:00 | 2025-04-04 08:30 |  | 2600 |  |  | 2
2025-01-27 | JOST25010280 | CP08-560-P01-04 | ST | PP09 | 1 | 405 | 360 | 1.125 | 0.14062 | 0.041667 | 0.083333 | 0.33333 | 2025-03-21 08:30 | 2025-03-21 22:52 | 2025-04-04 08:30 |  | 405 |  |  | 3
2025-01-27 | JOST25010280 | CP08-560-P02-04 | ST | PP18 | 1 | 405 | 300 | 1.35 | 0.16875 | 0.041667 | 0.083333 | 0.33333 | 2025-03-21 08:30 | 2025-03-21 23:33 | 2025-04-04 08:30 |  | 405 |  |  | 1
2025-01-27 | JOST25010280 | CP08-560-P03-04 | ST | PP27-110T | 1 | 405 | 300 | 1.35 | 0.16875 | 0.041667 | 0.083333 | 0.33333 | 2025-03-21 08:30 | 2025-03-21 23:33 | 2025-04-04 08:30 |  | 405 |  |  | 2
2025-01-27 | JOST25010221 | CT10-022-P01-02 | ST-1 | PP19-110T | 1 | 10204 | 1800 | 5.6689 | 0.70861 | 0.041667 | 0.083333 | 0.33333 | 2025-03-17 08:30 | 2025-03-18 12:30 | 2025-03-31 08:30 |  | 10204 |  |  | 3
2025-01-27 | JOST25010205 | CP08-604-P01-03 | PB | TM03 | 1 | 200 | 85 | 2.3529 | 0.29412 | 0.041667 | 0.083333 | 0.33333 | 2025-03-14 08:30 | 2025-03-15 02:34 | 2025-03-28 08:30 |  | 200 |  |  | 1
2025-01-27 | JOST25010205 | CP08-604-P02-03 | PB | PB01 | 1 | 200 | 180 | 1.1111 | 0.13889 | 0.041667 | 0.083333 | 0.33333 | 2025-03-14 08:30 | 2025-03-14 22:50 | 2025-03-28 08:30 |  | 200 |  |  | 3
2025-01-27 | JOST25010196 | CP08-558-P01-02 | ST | PP30-200T | 1 | 55555 | 1500 | 37.0367 | 4.6296 | 0.041667 | 0.083333 | 0.33333 | 2025-03-14 08:30 | 2025-03-19 10:37 | 2025-03-28 08:30 |  | 55555 |  |  | 2
2025-01-27 | JOTP25010199 | CP08-583-P01-04 | PB | SW09 | 1 | 152 | 90 | 1.6889 | 0.21111 | 0.041667 | 0.083333 | 0.33333 | 2025-03-14 08:30 | 2025-03-15 00:34 | 2025-03-28 08:30 |  | 152 |  |  | 3
2025-01-27 | JOTP25010199 | CP08-583-P02-04 | PB | OPT | 1 | 152 | 60 | 2.5333 | 0.31667 | 0.041667 | 0.083333 | 0.33333 | 2025-03-14 08:30 | 2025-03-15 03:06 | 2025-03-28 08:30 |  | 152 |  |  | 1
2025-01-27 | JOTP25010199 | CP08-583-P03-04 | PB | OPT | 1 | 152 | 60 | 2.5333 | 0.31667 | 0.041667 | 0.083333 | 0.33333 | 2025-03-14 08:30 | 2025-03-15 03:06 | 2025-03-28 08:30 |  | 152 |  |  | 2
2025-01-27 | JOST25010183 | CP08-456-P01-04 | ST-3 | PP25-160T | 1 | 1200 | 360 | 3.3333 | 0.41667 | 0.041667 | 0.083333 | 0.33333 | 2025-03-14 08:30 | 2025-03-15 05:30 | 2025-03-28 08:30 |  | 1200 |  |  | 3
2025-01-27 | JOST25010183 | CP08-456-P02-04 | ST-3 | PP20-110T | 1 | 1200 | 360 | 3.3333 | 0.41667 | 0.041667 | 0.083333 | 0.33333 | 2025-03-14 08:30 | 2025-03-15 05:30 | 2025-03-28 08:30 |  | 1200 |  |  | 2
2025-01-27 | JOST25010183 | CP08-456-P03-04 | ST-3 | PP28-110T | 1 | 1200 | 360 | 3.3333 | 0.41667 | 0.041667 | 0.083333 | 0.33333 | 2025-03-14 08:30 | 2025-03-15 05:30 | 2025-03-28 08:30 |  | 1200 |  |  | 2
2025-01-27 | JOST25010187 | CP08-496-P01-03 | 0 | STICK LABEL | 1 | 700 | 15 | 46.6667 | 5.8333 | 0.041667 | 0.083333 | 0.33333 | 2025-03-17 08:30 | 2025-03-23 15:30 | 2025-04-07 08:30 |  | 700 |  |  | 2
2025-01-27 | JOST25010187 | CP08-496-P02-03 | 0 | STICK LABEL | 1 | 700 | 15 | 46.6667 | 5.8333 | 0.041667 | 0.083333 | 0.33333 | 2025-03-17 08:30 | 2025-03-23 15:30 | 2025-04-07 08:30 |  | 700 |  |  | 2
2025-01-27 | JOST25010172 | CP08-256-P01-02 | ST-1 | PP29 | 1 | 4200 | 240 | 17.5 | 2.1875 | 0.041667 | 0.083333 | 0.33333 | 2025-03-14 08:30 | 2025-03-17 | 2025-03-28 08:30 |  | 4200 |  |  | 1
2025-01-27 | JOST25010173 | CP08-289-P01-06 | ST-2 | PP01-110T | 1 | 25806 | 450 | 57.3467 | 7.1683 | 0.041667 | 0.083333 | 0.33333 | 2025-03-14 08:30 | 2025-03-21 23:32 | 2025-04-18 08:30 |  | 25806 |  |  | 3
2025-01-27 | JOST25010173 | CP08-289-P02-06 | ST-2 | PP15-080T | 1 | 25806 | 450 | 57.3467 | 7.1683 | 0.041667 | 0.083333 | 0.33333 | 2025-03-14 08:30 | 2025-03-21 23:32 | 2025-04-18 08:30 |  | 25806 |  |  | 2
2025-01-27 | JOST25010173 | CP08-289-P04-06 | ST-4 | TP08 | 1 | 25806 | 360 | 71.6833 | 8.9604 | 0.041667 | 0.083333 | 0.33333 | 2025-03-14 08:30 | 2025-03-23 18:33 | 2025-04-18 08:30 |  | 25806 |  |  | 3
2025-01-27 | JOST25010173 | CP08-289-P05-06 | AL | CHECKING | 1 | 25806 | 360 | 71.6833 | 8.9604 | 0.041667 | 0.083333 | 0.33333 | 2025-03-14 08:30 | 2025-03-23 18:33 | 2025-04-18 08:30 |  | 25806 |  |  | 3
2025-02-05 | JOAW25020001 | CD11-029-P01-06 | 0 | SW08 | 1 | 3000 | 34.8 | 86.2069 | 10.7759 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-21 14:07 | 2025-03-12 08:30 |  | 3000 |  |  | 3
2025-02-05 | JOAW25020001 | CD11-029-P02-06 | 0 | LV01 | 1 | 3000 | 420 | 7.1429 | 0.89286 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 16:56 | 2025-03-12 08:30 |  | 3000 |  |  | 3
2025-02-05 | JOAW25020001 | CD11-029-P03-06 | 0 | PP05-060T | 1 | 3000 | 180 | 16.6667 | 2.0833 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-12 21:30 | 2025-03-12 08:30 |  | 3000 |  |  | 2
2025-02-05 | JOAW25020001 | CD11-029-P04-06 | 0 | OPT | 1 | 3000 | 120 | 25 | 3.125 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-13 22:30 | 2025-03-12 08:30 |  | 3000 |  |  | 2
2025-02-05 | JOAW25020001 | CD11-029A-P01-02 | 0 | WS02 | 1 | 39000 | 2700 | 14.4444 | 1.8056 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-12 14:50 | 2025-03-12 08:30 |  | 39000 |  |  | 2
2025-02-05 | JOAW25020001 | CD11-029B-P01-02 | 0 | WS02 | 1 | 81000 | 2700 | 30 | 3.75 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-14 13:30 | 2025-03-12 08:30 |  | 81000 |  |  | 1
2025-02-05 | JOST25010260 | CP08-353&CP08-354-P01-05 | SM | SM01 | 1 | 2800 | 480 | 5.8333 | 0.72917 | 0.041667 | 0.083333 | 0.33333 | 2025-03-28 08:30 | 2025-03-29 13:00 | 2025-04-11 08:30 |  | 2800 |  |  | 2
2025-02-05 | JOST25010260 | CP08-353&CP08-354-P02-05 | ST-4 | PP25-160T | 1 | 2800 | 300 | 9.3333 | 1.1667 | 0.041667 | 0.083333 | 0.33333 | 2025-03-28 08:30 | 2025-03-29 23:30 | 2025-04-11 08:30 |  | 2800 |  |  | 3
2025-02-05 | JOST25010260 | CP08-353&CP08-354-P03-05 | ST-4 | PP20-110T | 1 | 2800 | 300 | 9.3333 | 1.1667 | 0.041667 | 0.083333 | 0.33333 | 2025-03-28 08:30 | 2025-03-29 23:30 | 2025-04-11 08:30 |  | 2800 |  |  | 1
2025-02-05 | JOST25010260 | CP08-353&CP08-354-P04-05 | ST-4 | PP28-110T | 1 | 2800 | 300 | 9.3333 | 1.1667 | 0.041667 | 0.083333 | 0.33333 | 2025-03-28 08:30 | 2025-03-29 23:30 | 2025-04-11 08:30 |  | 2800 |  |  | 2
2025-02-05 | JOTP25010219 | CP08-609-P01-05 | TR | TM03 | 1 | 108 | 30 | 3.6 | 0.45 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 06:18 | 2025-02-20 08:30 |  | 108 |  |  | 3
2025-02-05 | JOTP25010219 | CP08-609-P02-05 | ST | PP31 | 1 | 108 | 120 | 0.9 | 0.1125 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-10 22:12 | 2025-02-20 08:30 |  | 108 |  |  | 1
2025-02-05 | JOTP25010219 | CP08-609-P03-05 | ST | PP31 | 1 | 108 | 120 | 0.9 | 0.1125 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-10 22:12 | 2025-02-20 08:30 |  | 108 |  |  | 3
2025-02-05 | JOTP25010219 | CP08-609-P04-05 | PB | PB07 | 1 | 108 | 60 | 1.8 | 0.225 | 0.041667 | 0.083333 | 0.33333 | 2025-02-10 08:30 | 2025-02-11 00:54 | 2025-02-20 08:30 |  | 108 |  |  | 2
2025-02-05 | JOTP25010052 | CP08-415-P01-04 | ST-3 | SW09 | 1 | 640 | 60 | 10.6667 | 1.3333 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-02 03:30 | 2025-03-14 08:30 |  | 640 |  |  | 3
2025-02-05 | JOTP25010052 | CP08-415-P02-04 | ST-1 | PAINTING | 1 | 640 | 30 | 21.3333 | 2.6667 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-03 11:30 | 2025-03-14 08:30 |  | 640 |  |  | 1
2025-02-05 | JOTP25010052 | CP08-415-P03-04 | ST-3 | CLEAN | 1 | 640 | 30 | 21.3333 | 2.6667 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-03 11:30 | 2025-03-14 08:30 |  | 640 |  |  | 2
2025-02-05 | JOAW25010149 | CD06-006-P01-04 | FM | FM02 | 1 | 12500 | 2400 | 5.2083 | 0.65104 | 0.041667 | 0.083333 | 0.33333 | 2025-03-14 08:30 | 2025-03-15 11:08 | 2025-04-18 08:30 |  | 12500 |  |  | 3
2025-02-05 | JOTP25010224 | CT10-026-P01-04 | TP | SW09 | 1 | 120 | 12 | 10 | 1.25 | 0.041667 | 0.083333 | 0.33333 | 2025-03-21 08:30 | 2025-03-23 01:30 | 2025-04-04 08:30 |  | 120 |  |  | 2
2025-02-05 | JOTP25010224 | CT10-026-P02-04 | TP | OPT | 1 | 120 | 6 | 20 | 2.5 | 0.041667 | 0.083333 | 0.33333 | 2025-03-21 08:30 | 2025-03-24 07:30 | 2025-04-04 08:30 |  | 120 |  |  | 2
2025-02-05 | JOTP25010224 | CT10-026-P03-04 | TP | OPT | 1 | 120 | 30 | 4 | 0.5 | 0.041667 | 0.083333 | 0.33333 | 2025-03-21 08:30 | 2025-03-22 07:30 | 2025-04-04 08:30 |  | 120 |  |  | 2
2025-02-05 | JOST25010177 | CP08-428-P01-09 | ST-3 | SW01 | 1 | 280 | 90 | 3.1111 | 0.38889 | 0.041667 | 0.083333 | 0.33333 | 2025-03-24 08:30 | 2025-03-25 04:50 | 2025-04-07 08:30 |  | 280 |  |  | 1
2025-02-05 | JOST25010177 | CP08-428-P02-09 | ST-3 | SW01 | 1 | 280 | 120 | 2.3333 | 0.29167 | 0.041667 | 0.083333 | 0.33333 | 2025-03-24 08:30 | 2025-03-25 02:30 | 2025-04-07 08:30 |  | 280 |  |  | 2
2025-02-05 | JOST25010177 | CP08-428-P03-09 | ST-3 | SW01 | 1 | 280 | 120 | 2.3333 | 0.29167 | 0.041667 | 0.083333 | 0.33333 | 2025-03-24 08:30 | 2025-03-25 02:30 | 2025-04-07 08:30 |  | 280 |  |  | 3
2025-02-05 | JOST25010177 | CP08-428-P04-09 | ST-3 | SW01 | 1 | 280 | 90 | 3.1111 | 0.38889 | 0.041667 | 0.083333 | 0.33333 | 2025-03-24 08:30 | 2025-03-25 04:50 | 2025-04-07 08:30 |  | 280 |  |  | 1
2025-02-05 | JOST25010177 | CP08-428-P05-09 | ST-3 | SW01 | 1 | 280 | 40 | 7 | 0.875 | 0.041667 | 0.083333 | 0.33333 | 2025-03-24 08:30 | 2025-03-25 16:30 | 2025-04-07 08:30 |  | 280 |  |  | 2
2025-02-05 | JOST25010177 | CP08-428-P06-09 | ST-3 | SW01 | 1 | 280 | 30 | 9.3333 | 1.1667 | 0.041667 | 0.083333 | 0.33333 | 2025-03-24 08:30 | 2025-03-25 23:30 | 2025-04-07 08:30 |  | 280 |  |  | 3
2025-02-05 | JOST25010177 | CP08-428-P07-09 | ST-3 | PAINTING | 1 | 280 | 17 | 16.4706 | 2.0588 | 0.041667 | 0.083333 | 0.33333 | 2025-03-24 08:30 | 2025-03-26 20:55 | 2025-04-07 08:30 |  | 280 |  |  | 1
2025-02-05 | JOST25010177 | CP08-428-P08-09 | ST-3 | CLEAN | 1 | 280 | 60 | 4.6667 | 0.58333 | 0.041667 | 0.083333 | 0.33333 | 2025-03-24 08:30 | 2025-03-25 09:30 | 2025-04-07 08:30 |  | 280 |  |  | 3
2025-02-05 | JOTP25010136 | CT10-027-P01-04 | TP | SW09 | 1 | 180 | 45 | 4 | 0.5 | 0.041667 | 0.083333 | 0.33333 | 2025-03-21 08:30 | 2025-03-22 07:30 | 2025-04-03 08:30 |  | 180 |  |  | 2
2025-02-05 | JOTP25010136 | CT10-027-P02-04 | TP | OPT | 1 | 180 | 30 | 6 | 0.75 | 0.041667 | 0.083333 | 0.33333 | 2025-03-21 08:30 | 2025-03-22 13:30 | 2025-04-03 08:30 |  | 180 |  |  | 3
2025-02-05 | JOTP25010136 | CT10-027-P03-04 | TP | OPT | 1 | 180 | 60 | 3 | 0.375 | 0.041667 | 0.083333 | 0.33333 | 2025-03-21 08:30 | 2025-03-22 04:30 | 2025-04-03 08:30 |  | 180 |  |  | 1
2025-02-05 | JOTP25010136 | CV02-066-P02-04 | ST | PP13 | 1 | 8333 | 480 | 17.3604 | 2.1701 | 0.041667 | 0.083333 | 0.33333 | 2025-02-07 08:30 | 2025-02-09 23:35 | 2025-02-13 08:30 |  | 8333 |  |  | 2
2025-02-05 | JOTP25010136 | CV02-066-P03-04 | ST | PP04 | 1 | 83333 | 360 | 231.4806 | 28.9351 | 0.041667 | 0.083333 | 0.33333 | 2025-02-07 08:30 | 2025-03-08 17:56 | 2025-02-13 08:30 |  | 83333 |  |  | 3
2025-02-12 | JOST24100368 | CV04-008-P01-05 | ST-1 | PP14-080T | 1 | 41647 | 1800 | 23.1372 | 2.8922 | 0.041667 | 0.083333 | 0.33333 | 2025-02-11 08:30 | 2025-02-14 16:55 | 2025-02-13 08:30 | 6994 | 34653 |  |  | 2
2025-02-12 | JOST24100368 | CV04-008-P02-05 | ST-2 | PP06-040T | 1 | 41647 | 360 | 115.6861 | 14.4608 | 0.041667 | 0.083333 | 0.33333 | 2025-02-11 08:30 | 2025-02-26 06:34 | 2025-02-13 08:30 | 1045 | 40602 |  |  | 2
2025-02-12 | JOST24100368 | CV04-008-P03-05 | ST-1 | PP11-035T | 1 | 41647 | 360 | 115.6861 | 14.4608 | 0.041667 | 0.083333 | 0.33333 | 2025-02-11 08:30 | 2025-02-26 06:34 | 2025-02-13 08:30 | 4 | 41643 |  |  | 2
2025-02-13 | JOTP25020006 | CP08-569-P01-05 | ST | SM01 | 1 | 240 | 180 | 1.3333 | 0.16667 | 0.041667 | 0.083333 | 0.33333 | 2025-02-18 08:30 | 2025-02-18 23:30 | 2025-02-28 08:30 |  |  |  |  | 2
2025-02-13 | JOTP25020006 | CP08-569-P02-05 | TR | TM05 | 1 | 240 | 38 | 6.3158 | 0.78947 | 0.041667 | 0.083333 | 0.33333 | 2025-02-18 08:30 | 2025-02-19 14:27 | 2025-02-28 08:30 |  |  |  |  | 1
2025-02-13 | JOTP25020006 | CP08-569-P03-05 | PB | PB03 | 1 | 240 | 75 | 3.2 | 0.4 | 0.041667 | 0.083333 | 0.33333 | 2025-02-18 08:30 | 2025-02-19 05:06 | 2025-02-28 08:30 |  |  |  |  | 3
2025-02-13 | JOTP25020006 | CP08-569-P04-05 | PB | PB03 | 1 | 240 | 75 | 3.2 | 0.4 | 0.041667 | 0.083333 | 0.33333 | 2025-02-18 08:30 | 2025-02-19 05:06 | 2025-02-28 08:30 |  |  |  |  | 2
2025-02-13 | JOTP25020005 | CP08-610-P01-07 | TR | TM03 | 1 | 165 | 30 | 5.5 | 0.6875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-18 08:30 | 2025-02-19 12:00 | 2025-02-28 08:30 |  |  |  |  | 3
2025-02-13 | JOTP25020005 | CP08-610-P02-07 | PB | PB02 | 1 | 165 | 180 | 0.91667 | 0.11458 | 0.041667 | 0.083333 | 0.33333 | 2025-02-18 08:30 | 2025-02-18 22:15 | 2025-02-28 08:30 |  |  |  |  | 3
2025-02-13 | JOTP25020005 | CP08-610-P03-07 | PB | PB03 | 1 | 165 | 180 | 0.91667 | 0.11458 | 0.041667 | 0.083333 | 0.33333 | 2025-02-18 08:30 | 2025-02-18 22:15 | 2025-02-28 08:30 |  |  |  |  | 3
2025-02-13 | JOTP25020005 | CP08-610-P04-07 | PB | PB08 | 1 | 165 | 180 | 0.91667 | 0.11458 | 0.041667 | 0.083333 | 0.33333 | 2025-02-18 08:30 | 2025-02-18 22:15 | 2025-02-28 08:30 |  |  |  |  | 3
2025-02-13 | JOTP25020005 | CP08-610-P05-07 | PB | PB04 | 1 | 165 | 180 | 0.91667 | 0.11458 | 0.041667 | 0.083333 | 0.33333 | 2025-02-18 08:30 | 2025-02-18 22:15 | 2025-02-28 08:30 |  |  |  |  | 2
2025-02-13 | JOTP25020005 | CP08-610-P06-07 | PB | PB07 | 1 | 165 | 40 | 4.125 | 0.51562 | 0.041667 | 0.083333 | 0.33333 | 2025-02-18 08:30 | 2025-02-19 07:52 | 2025-02-28 08:30 |  |  |  |  | 2
2025-02-14 | JOST25010073 | CP08-437-P01-05 | SM | SM01 | 1 | 1710 | 5400 | 0.31667 | 0.039583 | 0.041667 | 0.083333 | 0.33333 | 2025-02-14 | 2025-02-14 11:57 | 2025-02-28 08:30 |  |  |  |  | 2
2025-02-14 | JOST25010073 | CP08-437-P02-05 | ST-1 | PP03-060T | 1 | 1710 | 480 | 3.5625 | 0.44531 | 0.041667 | 0.083333 | 0.33333 | 2025-02-14 | 2025-02-14 21:41 | 2025-02-28 08:30 |  |  |  |  | 1
2025-02-14 | JOST25010073 | CP08-437-P03-05 | ST-1 | PP03-060T | 1 | 1710 | 360 | 4.75 | 0.59375 | 0.041667 | 0.083333 | 0.33333 | 2025-02-14 | 2025-02-15 01:15 | 2025-02-28 08:30 |  |  |  |  | 2
2025-02-14 | JOST25010073 | CP08-437-P04-05 | TR | PP22 | 1 | 1710 | 200 | 8.55 | 1.0688 | 0.041667 | 0.083333 | 0.33333 | 2025-02-14 | 2025-02-15 12:39 | 2025-02-28 08:30 |  |  |  |  | 3
2025-02-13 | JOST25020075 | CT10-001-P01-06 | ST-3 | PP09-160T | 1 | 6080 | 330 | 18.4242 | 2.303 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-20 02:46 | 2025-02-28 08:30 |  | 6080 | 18.4242 | 2.303 | 1
2025-02-13 | JOST25020075 | CT10-001-P02-06 | ST-3 | PP18 | 1 | 6080 | 330 | 18.4242 | 2.303 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-20 02:46 | 2025-02-28 08:30 |  | 6080 | 18.4242 | 2.303 | 2
2025-02-13 | JOST25020075 | CT10-001-P03-06 | ST-3 | PP17-110T | 1 | 6080 | 330 | 18.4242 | 2.303 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-20 02:46 | 2025-02-28 08:30 |  | 6080 | 18.4242 | 2.303 | 3
2025-02-13 | JOST25020075 | CT10-001-P04-06 | ST-3 | PP16-110T | 1 | 6080 | 330 | 18.4242 | 2.303 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-20 02:46 | 2025-02-28 08:30 |  | 6080 | 18.4242 | 2.303 | 1
2025-02-13 | JOST25020075 | CT10-001-P05-06 | ST-3 | PP27-110T | 1 | 6080 | 330 | 18.4242 | 2.303 | 0.041667 | 0.083333 | 0.33333 | 2025-02-17 08:30 | 2025-02-20 02:46 | 2025-02-28 08:30 |  | 6080 | 18.4242 | 2.303 | 3
2025-02-14 | JOST25020008 | CP08-032-P01-03 | ST-3 | PP09-160T | 1 | 804 | 300 | 2.68 | 0.335 | 0.041667 | 0.083333 | 0.33333 | 2025-02-18 08:30 | 2025-02-19 03:32 | 2025-02-28 08:30 |  | 804 |  |  | 2
2025-02-14 | JOST25020008 | CP08-032-P02-03 | ST-3 | PP16-110T | 1 | 804 | 300 | 2.68 | 0.335 | 0.041667 | 0.083333 | 0.33333 | 2025-02-18 08:30 | 2025-02-19 03:32 | 2025-02-28 08:30 |  |  |  |  | 3
2025-02-14 | JOAW25020058 | CP08-556B-P01-05 | WN | WS01 | 1 | 200 | 600 | 0.33333 | 0.041667 | 0.041667 | 0.083333 | 0.33333 | 2025-02-18 08:30 | 2025-02-18 20:30 | 2025-02-28 08:30 |  |  |  |  | 1
2025-02-14 | JOAW25020058 | CP08-556B-P02-05 | WN | JIG BENDING | 1 | 200 | 180 | 1.1111 | 0.13889 | 0.041667 | 0.083333 | 0.33333 | 2025-02-18 08:30 | 2025-02-18 22:50 | 2025-02-28 08:30 |  |  |  |  | 2
2025-02-14 | JOAW25020058 | CP08-556B-P03-05 | WN | JIG BENDING | 1 | 200 | 180 | 1.1111 | 0.13889 | 0.041667 | 0.083333 | 0.33333 | 2025-02-18 08:30 | 2025-02-18 22:50 | 2025-02-28 08:30 |  |  |  |  | 3
2025-02-14 | JOAW25020058 | CP08-556B-P04-05 | WN | PP23-060T | 1 | 200 | 120 | 1.6667 | 0.20833 | 0.041667 | 0.083333 | 0.33333 | 2025-02-18 08:30 | 2025-02-19 00:30 | 2025-02-28 08:30 |  |  |  |  | 2
2025-02-14 | JOAW25020059 | CP08-556C-P01-03 | WN | WS01 | 1 | 400 | 4800 | 0.083333 | 0.010417 | 0.041667 | 0.083333 | 0.33333 | 2025-02-18 08:30 | 2025-02-18 19:45 | 2025-02-28 08:30 |  |  |  |  | 2
2025-02-14 | JOAW25020059 | CP08-556C-P02-03 | 0 | JIG BENDING | 1 | 400 | 120 | 3.3333 | 0.41667 | 0.041667 | 0.083333 | 0.33333 | 2025-02-18 08:30 | 2025-02-19 05:30 | 2025-02-28 08:30 |  |  |  |  | 2
2025-02-14 | JOAW25020060 | CP08-556D-P01-02 | WN | WS01 | 1 | 2000 | 5700 | 0.35088 | 0.04386 | 0.041667 | 0.083333 | 0.33333 | 2025-02-18 08:30 | 2025-02-18 20:33 | 2025-02-28 08:30 |  |  |  |  | 2
2025-02-14 | JOAW25020061 | CP08-556E-P01-02 | WN | WS01 | 1 | 1000 | 600 | 1.6667 | 0.20833 | 0.041667 | 0.083333 | 0.33333 | 2025-02-18 08:30 | 2025-02-19 00:30 | 2025-02-28 08:30 |  |  |  |  | 1
2025-02-14 | JOST25020152 | CP08-602-P01-04 | ST | PP33 | 1 | 173 | 120 | 1.4417 | 0.18021 | 0.041667 | 0.083333 | 0.33333 | 2025-02-18 08:30 | 2025-02-18 23:50 | 2025-02-28 08:30 |  |  |  |  | 3
2025-02-14 | JOST25020152 | CP08-602-P02-04 | ST | PP33 | 1 | 173 | 120 | 1.4417 | 0.18021 | 0.041667 | 0.083333 | 0.33333 | 2025-02-18 08:30 | 2025-02-18 23:50 | 2025-02-28 08:30 |  |  |  |  | 2
2025-02-14 | JOST25020152 | CP08-602-P03-04 | ST | PP33 | 1 | 173 | 120 | 1.4417 | 0.18021 | 0.041667 | 0.083333 | 0.33333 | 2025-02-18 08:30 | 2025-02-18 23:50 | 2025-02-28 08:30 |  |  |  |  | 3
2025-02-14 | JOST25020010 | CP08-120-P01-04 | ST | SM01 | 1 | 90 | 240 | 0.375 | 0.046875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-18 08:30 | 2025-02-18 20:38 | 2025-02-28 08:30 |  |  |  |  | 3
2025-02-14 | JOST25020010 | CP08-120-P02-04 | ST | PP04 | 1 | 90 | 240 | 0.375 | 0.046875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-18 08:30 | 2025-02-18 20:38 | 2025-02-28 08:30 |  |  |  |  | 3
2025-02-14 | JOST25020010 | CP08-120-P03-04 | ST | PP04 | 1 | 90 | 240 | 0.375 | 0.046875 | 0.041667 | 0.083333 | 0.33333 | 2025-02-18 08:30 | 2025-02-18 20:38 | 2025-02-28 08:30 |  |  |  |  | 3
2025-02-17 | JOAW25020134 | CS18-007A-P01-04 | WN | WS01 | 1 | 600 | 900 | 0.66667 | 0.083333 | 0.041667 | 0.083333 | 0.33333 | 2025-02-19 08:30 | 2025-02-19 21:30 | 2025-03-05 08:30 |  |  |  |  | 2
2025-02-17 | JOAW25020134 | CS18-007A-P02-04 | WN | JIG BENDING | 1 | 600 | 180 | 3.3333 | 0.41667 | 0.041667 | 0.083333 | 0.33333 | 2025-02-19 08:30 | 2025-02-20 05:30 | 2025-03-05 08:30 |  |  |  |  | 2
2025-02-17 | JOAW25020134 | CS18-007A-P03-04 | WN | PP23-060T | 1 | 600 | 240 | 2.5 | 0.3125 | 0.041667 | 0.083333 | 0.33333 | 2025-02-19 08:30 | 2025-02-20 03:00 | 2025-03-05 08:30 |  |  |  |  | 2
2025-02-17 | JOAW25020135 | CS18-007B-P01-02 | WN | WS01 | 1 | 600 | 600 | 1 | 0.125 | 0.041667 | 0.083333 | 0.33333 | 2025-02-19 08:30 | 2025-02-19 22:30 | 2025-03-05 08:30 |  |  |  |  | 3
2025-02-17 | JOAW25020136 | CS18-007C-P01-02 | WN | WS01 | 1 | 800 | 720 | 1.1111 | 0.13889 | 0.041667 | 0.083333 | 0.33333 | 2025-02-19 08:30 | 2025-02-19 22:50 | 2025-03-05 08:30 |  |  |  |  | 3
2025-02-17 | JOAW25020137 | CS18-007D-P01-03 | WN | WS01 | 1 | 200 | 600 | 0.33333 | 0.041667 | 0.041667 | 0.083333 | 0.33333 | 2025-02-19 08:30 | 2025-02-19 20:30 | 2025-03-05 08:30 |  |  |  |  | 1
2025-02-17 | JOAW25020137 | CS18-007D-P02-03 | WN | JIG BENDING | 1 | 200 | 120 | 1.6667 | 0.20833 | 0.041667 | 0.083333 | 0.33333 | 2025-02-19 08:30 | 2025-02-20 00:30 | 2025-03-05 08:30 |  |  |  |  | 1
2025-02-17 | JOAW25020099 | CA25-001-P01-04 | AL | CM03 | 1 | 4250 | 72 | 59.0278 | 7.3785 | 0.041667 | 0.083333 | 0.33333 | 2025-02-20 08:30 | 2025-02-28 04:35 | 2025-03-07 08:30 |  |  |  |  | 3
2025-02-17 | JOAW25020099 | CA25-001-P02-04 | AL | BDS01 | 1 | 4250 | 600 | 7.0833 | 0.88542 | 0.041667 | 0.083333 | 0.33333 | 2025-02-20 08:30 | 2025-02-21 16:45 | 2025-03-07 08:30 |  |  |  |  | 1
2025-02-17 | JOAW25020099 | CA25-001-P03-04 | AL | ALDG | 1 | 4250 | 1200 | 3.5417 | 0.44271 | 0.041667 | 0.083333 | 0.33333 | 2025-02-20 08:30 | 2025-02-21 06:08 | 2025-03-07 08:30 |  |  |  |  | 2
2025-02-17 | JOAW25020143 | CU01-002-P01-04 | 0 | CM05 | 1 | 990 | 150 | 6.6 | 0.825 | 0.041667 | 0.083333 | 0.33333 | 2025-02-20 08:30 | 2025-02-21 15:18 | 2025-03-13 08:30 |  |  |  |  | 3
2025-02-17 | JOAW25020143 | CU01-002-P02-04 | 0 | BDS01 | 1 | 990 | 600 | 1.65 | 0.20625 | 0.041667 | 0.083333 | 0.33333 | 2025-02-20 08:30 | 2025-02-21 00:27 | 2025-03-13 08:30 |  |  |  |  | 1
2025-02-17 | JOAW25020143 | CU01-002-P03-04 | SUB CON | SUB CON | 1 | 990 | 5 DAYS | #VALUE! | #VALUE! | 0.041667 | 0.083333 | 0.33333 | 2025-02-20 08:30 | #VALUE! | 2025-03-13 08:30 |  |  |  |  | 2
2025-02-17 | JOAW25020143 | CU01-002-P04-04 | WH1 | WH1 | 1 | 990 | 1 DAY | #VALUE! | #VALUE! | 0.041667 | 0.083333 | 0.33333 | 2025-02-20 08:30 | #VALUE! | 2025-03-13 08:30 |  |  |  |  | 3
2025-02-17 | JOAW25020144 | CU01-016-P01-04 | AL | CM05 | 1 | 980 | 150 | 6.5333 | 0.81667 | 0.041667 | 0.083333 | 0.33333 | 2025-02-20 08:30 | 2025-02-21 15:06 | 2025-03-13 08:30 |  |  |  |  | 1
2025-02-17 | JOAW25020144 | CU01-016-P02-04 | AL | BDS01 | 1 | 980 | 600 | 1.6333 | 0.20417 | 0.041667 | 0.083333 | 0.33333 | 2025-02-20 08:30 | 2025-02-21 00:24 | 2025-03-13 08:30 |  |  |  |  | 3
2025-02-17 | JOAW25020144 | CU01-016-P03-04 | SUB CON | SUB CON | 1 | 980 | 5 DAYS | #VALUE! | #VALUE! | 0.041667 | 0.083333 | 0.33333 | 2025-02-20 08:30 | #VALUE! | 2025-03-13 08:30 |  |  |  |  | 2
2025-02-17 | JOST25020044 | CP08-509-P01-04 | ST-3 | PP17-110T | 1 | 6094 | 360 | 16.9278 | 2.116 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-23 22:17 | 2025-03-07 08:30 |  |  |  |  | 3
2025-02-17 | JOST25020044 | CP08-509-P02-04 | ST-3 | PP16-110T | 1 | 6094 | 360 | 16.9278 | 2.116 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-23 22:17 | 2025-03-07 08:30 |  |  |  |  | 1
2025-02-17 | JOST25020044 | CP08-509-P03-04 | ST-3 | PP27-110T | 1 | 6094 | 360 | 16.9278 | 2.116 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-23 22:17 | 2025-03-07 08:30 |  |  |  |  | 2
2025-02-17 | JOAW25020067 | CP08-572-P01-03 | FM | FM02 | 1 | 100000 | 1260 | 79.3651 | 9.9206 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-03-03 17:36 | 2025-03-13 08:30 |  |  |  |  | 3
2025-02-17 | JOTP25020073 | CP08-607 | [17 empty] | 2
2025-02-17 | JOST25020091 | CT10-015-P01-05 | ST-4 | PP24-160T | 1 | 14400 | 360 | 40 | 5 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-26 19:30 | 2025-03-13 08:30 |  |  |  |  | 2
2025-02-17 | JOST25020091 | CT10-015-P02-05 | ST-4 | PP25-160T | 1 | 14400 | 360 | 40 | 5 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-26 19:30 | 2025-03-13 08:30 |  |  |  |  | 2
2025-02-17 | JOST25020091 | CT10-015-P03-05 | ST-4 | PP20-110T | 1 | 14400 | 360 | 40 | 5 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-26 19:30 | 2025-03-13 08:30 |  |  |  |  | 2
2025-02-17 | JOST25020091 | CT10-015-P04-05 | ST-4 | PP28-110T | 1 | 14400 | 360 | 40 | 5 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-26 19:30 | 2025-03-13 08:30 |  |  |  |  | 1
2025-02-17 | JOTP25020157 | CU01-055A-P01-03 | TP | TM03 | 1 | 105 | 18 | 5.8333 | 0.72917 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 13:00 | 2025-03-06 08:30 |  |  |  |  | 3
2025-02-17 | JOTP25020157 | CU01-055A-P02-03 | PB | PB07 | 1 | 105 | 45 | 2.3333 | 0.29167 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 02:30 | 2025-03-06 08:30 |  |  |  |  | 2
2025-02-17 | JOTP25020156 | CU01-054B-P01-03 | TP | TM03 | 1 | 300 | 120 | 2.5 | 0.3125 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-22 03:00 | 2025-03-03 08:30 |  |  |  |  | 3
2025-02-17 | JOTP25020156 | CU01-054B-P02-03 | PB | PB02 | 1 | 300 | 180 | 1.6667 | 0.20833 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-22 00:30 | 2025-03-03 08:30 |  |  |  |  | 3
2025-02-17 | JOTP25020155 | CU01-054F-P01-02 | PB | SW09 | 1 | 205 | 60 | 3.4167 | 0.42708 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-22 05:45 | 2025-03-03 08:30 |  |  |  |  | 3
2025-02-17 | JOTP25020154 | CU01-054E-P01-02 | PB | SW09 | 1 | 210 | 60 | 3.5 | 0.4375 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-22 06:00 | 2025-03-03 08:30 |  |  |  |  | 3
2025-02-17 | JOAW25020153 | CC02-007-P01-04 | FM | FM02 | 1 | 23455 | 3000 | 7.8183 | 0.97729 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-22 18:57 | 2025-03-03 08:30 |  |  |  |  | 2
2025-02-17 | JOAW25020153 | CC02-007-P02-04 | 0 | 0 | 1 | 23455 | 0 | #DIV/0! | #DIV/0! | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | #DIV/0! | 2025-03-03 08:30 |  |  |  |  | 1
2025-02-17 | JOAW25020153 | CC02-007-P03-04 | 0 | 0 | 1 | 23455 | 0 | #DIV/0! | #DIV/0! | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | #DIV/0! | 2025-03-03 08:30 |  |  |  |  | 2
2025-02-17 | JOAW25020150 | CM03-001-P01-04 | FM | FM02 | 1 | 43145 | 1080 | 39.9491 | 4.9936 | 0.041667 | 0.083333 | 0.33333 | 2025-02-26 08:30 | 2025-03-03 19:21 | 2025-04-02 08:30 |  |  |  |  | 3
2025-02-17 | JOAW25020150 | CM03-001-P02-04 | ST | VM04 | 1 | 43145 | 250 | 172.58 | 21.5725 | 0.041667 | 0.083333 | 0.33333 | 2025-02-26 08:30 | 2025-03-20 09:14 | 2025-04-02 08:30 |  |  |  |  | 1
2025-02-17 | JOAW25020150 | CM03-001-P03-04 | AL | CHECKING | 1 | 43145 | 250 | 172.58 | 21.5725 | 0.041667 | 0.083333 | 0.33333 | 2025-02-26 08:30 | 2025-03-20 09:14 | 2025-04-02 08:30 |  |  |  |  | 2
2025-02-17 | JOAW25020142 | CS18-008D-P01-03 | WN | WS01 | 1 | 200 | 480 | 0.41667 | 0.052083 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-21 20:45 | 2025-03-07 08:30 |  |  |  |  | 3
2025-02-17 | JOAW25020142 | CS18-008D-P02-03 | WN | JIG BENDING | 1 | 200 | 240 | 0.83333 | 0.10417 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-21 22:00 | 2025-03-07 08:30 |  |  |  |  | 1
2025-02-17 | JOAW25020141 | CS18-008C-P01-02 | WN | WS01 | 1 | 800 | 720 | 1.1111 | 0.13889 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-21 22:50 | 2025-03-07 08:30 |  |  |  |  | 3
2025-02-17 | JOAW25020140 | CS18-008B-P01-02 | WN | WS01 | 1 | 600 | 900 | 0.66667 | 0.083333 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-21 21:30 | 2025-03-07 08:30 |  |  |  |  | 2
2025-02-17 | JOAW25020139 | CS18-008A-P01-04 | WN | WS01 | 1 | 600 | 1200 | 0.5 | 0.0625 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-21 21:00 | 2025-03-07 08:30 |  |  |  |  | 3
2025-02-17 | JOAW25020139 | CS18-008A-P02-04 | WN | JIG BENDING | 1 | 600 | 340 | 1.7647 | 0.22059 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-22 00:48 | 2025-03-07 08:30 |  |  |  |  | 1
2025-02-17 | JOAW25020139 | CS18-008A-P03-04 | WN | PP23-060T | 1 | 600 | 480 | 1.25 | 0.15625 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-21 23:15 | 2025-03-07 08:30 |  |  |  |  | 2
2025-02-17 | JOAW25020104 | CD11-002C-P01-02 | WN | WS01 | 1 | 7200 | 3000 | 2.4 | 0.3 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-22 02:42 | 2025-03-07 08:30 |  |  |  |  | 3
2025-02-17 | JOAW25020103 | CD11-002B-P01-02 | WN | WS01 | 1 | 79200 | 3000 | 26.4 | 3.3 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-25 02:42 | 2025-03-07 08:30 |  |  |  |  | 2
2025-02-17 | JOAW25020102 | CD11-002A-P01-02 | WN | WS01 | 1 | 136800 | 3000 | 45.6 | 5.7 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-27 12:18 | 2025-03-07 08:30 |  |  |  |  | 2
2025-02-17 | JOST25020097 | CT10-025-P01-06 | ST-3 | PP09-160T | 1 | 2128 | 330 | 6.4485 | 0.80606 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-22 14:51 | 2025-03-07 08:30 |  |  |  |  | 2
2025-02-17 | JOST25020097 | CT10-025-P02-06 | ST-3 | PP18-150T | 1 | 2128 | 330 | 6.4485 | 0.80606 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-22 14:51 | 2025-03-07 08:30 |  |  |  |  | 2
2025-02-17 | JOST25020097 | CT10-025-P03-06 | ST-3 | PP17-110T | 1 | 2128 | 330 | 6.4485 | 0.80606 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-22 14:51 | 2025-03-07 08:30 |  |  |  |  | 1
2025-02-17 | JOST25020097 | CT10-025-P04-06 | ST-3 | PP16-110T | 1 | 2128 | 330 | 6.4485 | 0.80606 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-22 14:51 | 2025-03-07 08:30 |  |  |  |  | 3
2025-02-17 | JOST25020097 | CT10-025-P05-06 | ST-3 | PP27-110T | 2 | 2128 | 330 | 6.4485 | 0.80606 | 0.041667 | 0.083333 | 0.33333 | 2025-02-21 08:30 | 2025-02-22 14:51 | 2025-03-07 08:30 |  |  |  |  | 2
2025-02-17 | JOST25020092 | CT10-015-P01-05 | ST-4 | PP24-160T | 1 | 14400 | 360 | 40 | 5 | 0.041667 | 0.083333 | 0.33333 | 2025-02-27 08:30 | 2025-03-04 19:30 | 2025-03-10 08:30 |  |  |  |  | 3
2025-02-17 | JOST25020092 | CT10-015-P02-05 | ST-4 | PP25-160T | 1 | 14400 | 360 | 40 | 5 | 0.041667 | 0.083333 | 0.33333 | 2025-02-27 08:30 | 2025-03-04 19:30 | 2025-03-10 08:30 |  |  |  |  | 3
2025-02-17 | JOST25020092 | CT10-015-P03-05 | ST-4 | PP20-110T | 1 | 14400 | 360 | 40 | 5 | 0.041667 | 0.083333 | 0.33333 | 2025-02-27 08:30 | 2025-03-04 19:30 | 2025-03-10 08:30 |  |  |  |  | 3
2025-02-17 | JOST25020092 | CT10-015-P04-05 | ST-4 | PP28-110T | 1 | 14400 | 360 | 40 | 5 | 0.041667 | 0.083333 | 0.33333 | 2025-02-27 08:30 | 2025-03-04 19:30 | 2025-03-10 08:30 |  |  |  |  | 3
2025-02-17 | JOST25020039 | CP08-499A-P01-06 | ST-4 | PP29-250T | 1 | 630 | 120 | 5.25 | 0.65625 | 0.041667 | 0.083333 | 0.33333 | 2025-02-22 08:30 | 2025-02-23 11:15 | 2025-03-06 08:30 |  |  |  |  | 2
2025-02-17 | JOST25020039 | CP08-499A-P02-06 | ST-4 | PP30 | 1 | 630 | 120 | 5.25 | 0.65625 | 0.041667 | 0.083333 | 0.33333 | 2025-02-22 08:30 | 2025-02-23 11:15 | 2025-03-06 08:30 |  |  |  |  | 2
2025-02-17 | JOST25020039 | CP08-499A-P03-06 | ST-3 | TP03 | 1 | 630 | 120 | 5.25 | 0.65625 | 0.041667 | 0.083333 | 0.33333 | 2025-02-22 08:30 | 2025-02-23 11:15 | 2025-03-06 08:30 |  |  |  |  | 2
2025-02-17 | JOST25020039 | CP08-499A-P04-06 | AL | TP09 | 1 | 630 | 120 | 5.25 | 0.65625 | 0.041667 | 0.083333 | 0.33333 | 2025-02-22 08:30 | 2025-02-23 11:15 | 2025-03-06 08:30 |  |  |  |  | 3
2025-02-17 | JOST25020039 | CP08-499A-P05-06 | TR | PB05 | 1 | 630 | 60 | 10.5 | 1.3125 | 0.041667 | 0.083333 | 0.33333 | 2025-02-22 08:30 | 2025-02-24 03:00 | 2025-03-06 08:30 |  |  |  |  | 2
2025-02-17 | JOST25020041 | CP08-499B-P01-04 | 0 | PP30-200T | 1 | 722 | 180 | 4.0111 | 0.50139 | 0.041667 | 0.083333 | 0.33333 | 2025-02-22 08:30 | 2025-02-23 07:32 | 2025-03-06 08:30 |  |  |  |  | 3
2025-02-17 | JOST25020041 | CP08-499B-P02-04 | 0 | PP21 | 1 | 722 | 180 | 4.0111 | 0.50139 | 0.041667 | 0.083333 | 0.33333 | 2025-02-22 08:30 | 2025-02-23 07:32 | 2025-03-06 08:30 |  |  |  |  | 1
2025-02-17 | JOST25020041 | CP08-499B-P03-04 | 0 | PP30-200T | 1 | 722 | 180 | 4.0111 | 0.50139 | 0.041667 | 0.083333 | 0.33333 | 2025-02-22 08:30 | 2025-02-23 07:32 | 2025-03-06 08:30 |  |  |  |  | 2
2025-02-17 | JOST25020076 | CT10-001-P01-06 | ST-3 | PP09-160T | 1 | 6080 | 330 | 18.4242 | 2.303 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-27 02:46 | 2025-03-07 08:30 |  |  |  |  | 3
2025-02-17 | JOST25020076 | CT10-001-P02-06 | ST-3 | PP18 | 1 | 6080 | 330 | 18.4242 | 2.303 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-27 02:46 | 2025-03-07 08:30 |  |  |  |  | 1
2025-02-17 | JOST25020076 | CT10-001-P03-06 | ST-3 | PP17-110T | 1 | 6080 | 330 | 18.4242 | 2.303 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-27 02:46 | 2025-03-07 08:30 |  |  |  |  | 3
2025-02-17 | JOST25020076 | CT10-001-P04-06 | ST-3 | PP16-110T | 1 | 6080 | 330 | 18.4242 | 2.303 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-27 02:46 | 2025-03-07 08:30 |  |  |  |  | 2
2025-02-17 | JOST25020076 | CT10-001-P05-06 | ST-3 | PP27-110T | 2 | 6080 | 330 | 18.4242 | 2.303 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-27 02:46 | 2025-03-07 08:30 |  |  |  |  | 3
2025-02-17 | JOST25020089 | CT10-014-P01-06 | ST-3 | PP09-160T | 1 | 1824 | 330 | 5.5273 | 0.69091 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 12:05 | 2025-03-07 08:30 |  | 1824 |  |  | 1
2025-02-17 | JOST25020089 | CT10-014-P02-06 | ST-3 | PP18 | 1 | 1824 | 330 | 5.5273 | 0.69091 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 12:05 | 2025-03-07 08:30 |  | 1824 |  |  | 2
2025-02-17 | JOST25020089 | CT10-014-P03-06 | ST-3 | PP17-110T | 1 | 1824 | 330 | 5.5273 | 0.69091 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 12:05 | 2025-03-07 08:30 |  | 1824 |  |  | 3
2025-02-17 | JOST25020089 | CT10-014-P04-06 | ST-3 | PP16-110T | 1 | 1824 | 330 | 5.5273 | 0.69091 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 12:05 | 2025-03-07 08:30 |  | 1824 |  |  | 2
2025-02-17 | JOST25020089 | CT10-014-P05-06 | ST-3 | PP27-110T | 2 | 1824 | 330 | 5.5273 | 0.69091 | 0.041667 | 0.083333 | 0.33333 | 2025-02-24 08:30 | 2025-02-25 12:05 | 2025-03-07 08:30 |  | 1824 |  |  | 2
2025-02-17 | JOAW25020057 | CP08-556-P01-09 | TR | SW04 | 1 | 200 | 16.7 | 11.976 | 1.497 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-02 07:26 | 2025-03-20 08:30 |  |  |  |  | 2
2025-02-17 | JOAW25020057 | CP08-556-P02-09 | WN | TW02 | 1 | 200 | 60 | 3.3333 | 0.41667 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-01 05:30 | 2025-03-20 08:30 |  |  |  |  | 2
2025-02-17 | JOAW25020057 | CP08-556-P03-09 | TR | PB07 | 1 | 200 | 60 | 3.3333 | 0.41667 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-01 05:30 | 2025-03-20 08:30 |  |  |  |  | 1
2025-02-17 | JOAW25020057 | CP08-556-P04-09 | WN | SW06 | 1 | 200 | 60 | 3.3333 | 0.41667 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-01 05:30 | 2025-03-20 08:30 |  |  |  |  | 3
2025-02-17 | JOAW25020057 | CP08-556-P05-09 | WN | OPT | 1 | 200 | 50 | 4 | 0.5 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-01 07:30 | 2025-03-20 08:30 |  |  |  |  | 2
2025-02-17 | JOAW25020057 | CP08-556-P06-09 | WN | OPT | 1 | 200 | 50 | 4 | 0.5 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-01 07:30 | 2025-03-20 08:30 |  |  |  |  | 3
2025-02-17 | JOAW25020057 | CP08-556-P07-09 | SUB CON | 0 | 1 | 200 | 0 | #DIV/0! | #DIV/0! | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | #DIV/0! | 2025-03-20 08:30 |  |  |  |  | 3
2025-02-17 | JOAW25020057 | CP08-556-P08-09 | WN | CHECKING | 1 | 200 | 8 | 25 | 3.125 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-03 22:30 | 2025-03-20 08:30 |  |  |  |  | 3
2025-02-17 | JOTP25020086 | CT10-009B-P01-06 | TR | TM03 | 1 | 1144 | 90 | 12.7111 | 1.5889 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-02 09:38 | 2025-03-14 08:30 |  |  |  |  | 3
2025-02-17 | JOTP25020086 | CT10-009B-P02-06 | ST-1 | PP31 | 1 | 1144 | 360 | 3.1778 | 0.39722 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-01 05:02 | 2025-03-14 08:30 |  |  |  |  | 2
2025-02-17 | JOTP25020086 | CT10-009B-P03-06 | ST-1 | PP31 | 1 | 1144 | 360 | 3.1778 | 0.39722 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-01 05:02 | 2025-03-14 08:30 |  |  |  |  | 3
2025-02-17 | JOTP25020086 | CT10-009B-P04-06 | ST-3 | TP03 | 1 | 1144 | 120 | 9.5333 | 1.1917 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-02 00:06 | 2025-03-14 08:30 |  |  |  |  | 1
2025-02-17 | JOTP25020086 | CT10-009B-P05-06 | TR | PB01 | 1 | 1144 | 120 | 9.5333 | 1.1917 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-02 00:06 | 2025-03-14 08:30 |  |  |  |  | 2
2025-02-17 | JOTP25020087 | CT10-009C-P01-07 | TR | TM03 | 1 | 520 | 36 | 14.4444 | 1.8056 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-02 14:50 | 2025-03-14 08:30 |  |  |  |  | 3
2025-02-17 | JOTP25020087 | CT10-009C-P02-07 | TR | PB02 | 1 | 520 | 100 | 5.2 | 0.65 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-01 11:06 | 2025-03-14 08:30 |  |  |  |  | 1
2025-02-17 | JOTP25020087 | CT10-009C-P03-07 | TR | PB03 | 1 | 520 | 100 | 5.2 | 0.65 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-01 11:06 | 2025-03-14 08:30 |  |  |  |  | 3
2025-02-17 | JOTP25020087 | CT10-009C-P04-07 | TR | PB04 | 1 | 520 | 40 | 13 | 1.625 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-02 10:30 | 2025-03-14 08:30 |  |  |  |  | 2
2025-02-17 | JOTP25020087 | CT10-009C-P05-07 | TR | PB05 | 1 | 520 | 50 | 10.4 | 1.3 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-02 02:42 | 2025-03-14 08:30 |  |  |  |  | 3
2025-02-17 | JOTP25020087 | CT10-009C-P06-07 | TR | SW09 | 0 | 520 | 35 | 14.8571 | 1.8571 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-02 16:04 | 2025-03-14 08:30 |  |  |  |  | 1
2025-02-18 | JOST25020014 | CP08-219B-P01-04 | SM | SM01 | 1 | 3588 | 9360 | 0.38333 | 0.047917 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-02-28 20:39 | 2025-03-14 08:30 |  |  |  |  | 2
2025-02-18 | JOST25020014 | CP08-219B-P02-04 | ST-2 | PP13-060T | 1 | 3588 | 600 | 5.98 | 0.7475 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-01 13:26 | 2025-03-14 08:30 |  |  |  |  | 3
2025-02-18 | JOST25020014 | CP08-219B-P03-04 | ST-1 | PP03-060T | 1 | 3588 | 360 | 9.9667 | 1.2458 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-02 01:24 | 2025-03-14 08:30 |  |  |  |  | 2
2025-02-19 | JOST25020161 | CM03-040-P01-02 | ST-4 | PP30-200T | 1 | 18116 | 1200 | 15.0967 | 1.8871 | 0.041667 | 0.083333 | 0.33333 | 2025-02-19 08:30 | 2025-02-21 16:47 | 2025-02-27 08:30 |  |  |  |  | 2
2025-02-19 | JOPRD25020163 | [18 empty] | 2
2025-02-19 | JOTP25020195 | CP08-608A-P01-03 | TR | TM03 | 1 | 99 | 60 | 1.65 | 0.20625 | 0.041667 | 0.083333 | 0.33333 | 2025-02-20 08:30 | 2025-02-21 00:27 | 2025-02-24 08:30 |  |  |  |  | 2
2025-02-19 | JOTP25020195 | CP08-608A-P02-03 | PB | PB07 | 1 | 99 | 50.4 | 1.9643 | 0.24554 | 0.041667 | 0.083333 | 0.33333 | 2025-02-20 08:30 | 2025-02-21 01:24 | 2025-02-24 08:30 |  |  |  |  | 1
2025-02-19 | JOST25020209 | CP08-600-P01-03 | ST | PP29 | 1 | 146 | 120 | 1.2167 | 0.15208 | 0.041667 | 0.083333 | 0.33333 | 2025-02-20 08:30 | 2025-02-20 23:09 | 2025-02-24 08:30 |  |  |  |  | 3
2025-02-19 | JOST25020209 | CP08-600-P02-03 | ST | PP33 | 1 | 146 | 120 | 1.2167 | 0.15208 | 0.041667 | 0.083333 | 0.33333 | 2025-02-20 08:30 | 2025-02-20 23:09 | 2025-02-24 08:30 |  |  |  |  | 2
2025-02-19 | JOST25020167 | CP08-031-P01-04 | ST-3 | PP09-160T | 1 | 906 | 240 | 3.775 | 0.47187 | 0.041667 | 0.083333 | 0.33333 | 2025-02-25 08:30 | 2025-02-26 06:50 | 2025-03-07 08:30 |  |  |  |  | 3
2025-02-19 | JOST25020167 |  | 0 | 0 | 1 | 906 | 0 | #DIV/0! | #DIV/0! | 0.041667 | 0.083333 | 0.33333 | 2025-02-25 08:30 | #DIV/0! | 2025-03-07 08:30 |  |  |  |  | 3
2025-02-19 | JOST25020167 | CP08-031-P02-04 | ST-3 | PP16-110T | 1 | 906 | 240 | 3.775 | 0.47187 | 0.041667 | 0.083333 | 0.33333 | 2025-02-25 08:30 | 2025-02-26 06:50 | 2025-03-07 08:30 |  |  |  |  | 3
2025-02-19 | JOST25020167 | CP08-031-P03-04 | ST-3 | PP27-110T | 1 | 906 | 240 | 3.775 | 0.47187 | 0.041667 | 0.083333 | 0.33333 | 2025-02-25 08:30 | 2025-02-26 06:50 | 2025-03-07 08:30 |  |  |  |  | 3
2025-02-19 | JOTP25020194 | CP08-608A-P01-03 | TR | TM03 | 1 | 99 | 60 | 1.65 | 0.20625 | 0.041667 | 0.083333 | 0.33333 | 2025-02-26 08:30 | 2025-02-27 00:27 | 2025-03-03 08:30 |  |  |  |  | 1
2025-02-19 | JOTP25020194 | CP08-608A-P02-03 | PB | PB07 | 1 | 99 | 50.4 | 1.9643 | 0.24554 | 0.041667 | 0.083333 | 0.33333 | 2025-02-26 08:30 | 2025-02-27 01:24 | 2025-03-03 08:30 |  |  |  |  | 2
2025-02-20 | JOST25020207 | CA24-002-P01-03 | ST-2 | PP19-110T | 1 | 10576 | 1800 | 5.8756 | 0.73444 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-01 13:08 | 2025-03-17 08:30 |  |  |  |  | 3
2025-02-20 | JOST25020207 | CA24-002-P02-03 | ST-1 | PP05-060T | 1 | 10576 | 240 | 44.0667 | 5.5083 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-06 07:42 | 2025-03-17 08:30 |  |  |  |  | 1
2025-02-20 | JOST25020207 | CA24-002-P03-04 | ST-2 | VM01 | 1 | 10576 | 1000 | 10.576 | 1.322 | 0.041667 | 0.083333 | 0.33333 | 2025-02-28 08:30 | 2025-03-02 03:14 | 2025-03-17 08:30 |  |  |  |  | 2
2025-02-20 | JOST25020016 | CP08-305-P01-03 | ST-2 | PP10-080T | 1 | 1041 | 1500 | 0.694 | 0.08675 | 0.041667 | 0.083333 | 0.33333 | 2025-03-03 08:30 | 2025-03-03 21:35 | 2025-03-17 08:30 |  |  |  |  | 3
2025-02-20 | JOST25020016 | CP08-305-P02-03 | AL | TP04 | 1 | 1041 | 300 | 3.47 | 0.43375 | 0.041667 | 0.083333 | 0.33333 | 2025-03-03 08:30 | 2025-03-04 05:55 | 2025-03-17 08:30 |  |  |  |  | 1
Formulas:
PLANNED_END = +[PLANNED_START]+[SETTING_HOUR]+[DAYS NEEDED 16hrs]+[BREAK_HOUR]+[NO_PRODUCTION_HOUR]

## MasterProcess
PlS check following
Some Codes nos. repeating | [7 empty] | Lock to delete column
some no output qty
some process many version
Filter RSC#/MC# Edited for #N/A, manual key in correct mc#
Nos of Operator pls check
Section Code S/A , S/T split follow process eg P01-02 = ST, P02-02 = A, Pls filter to edit
Edit & update above data when need use. while waiting finalization of NEX ERP Routing data v mc | [13 empty] | REMARK : FOR JOB CP08-516 & CP08-512 MUST RUN PP09, IF MACHINE BREAK DOWN CAN NOT RUN PRODUCTION
Assembly Part with A~F, Process Code start with A ~F follow by FG eg. CP08-428A~F, CP08-428
RSC Location =VLOOKUP(=VLOOKUP(M13,'ResourceMasterList-Prod'!C:D,2,0)
RSC# / MC# Edited =VLOOKUP(N13,'ResourceMasterList-Prod'!B:D,2,0) IF USE VLOOKUP Formula
CODE NO | GP, GC CODE |  | PROCESS | Version | Dropdown list formula | PART PROCESS CODE | Dropdown list formula | PROCESS NAME | SECTION | NOS. OF OPR | OUTPUT/ HRS | OUTPUT/ MIN | RSC Location | RSC# / MC# Edited | 1st MC | 2ND MC | 3RD MC | 4TH MC | 5TH MC | 6TH MC | 7TH MC | 8TH MC | 9TH MC | REMARKS 1 | REMARKS 2 | REMARK 3
CA01-051 |  | - | P01-03 |  | 0 | CA01-051-P01-03 |  | #REF! | ST | 1 | 26400 | 440 | SM | SM01 | SM01
CA01-051 |  | - | P02-03 |  | 0 | CA01-051-P02-03 |  | BLANKING | ST | 1 | 1260 | 21 | ST-2 | PP07-016T | PP07
CA16-001A |  | - | P01-03 |  | 0 | CA16-001A-P01-03 |  | PROGRESSIVE | ST | 1 | 3000 | 50 | ST-2 | PP19-110T | PP19 | PP14 | PP01
CA16-001A |  | - | P02-03 |  | 0 | CA16-001A-P02-03 |  | DEGREASING | ST | 1 | 1000 | 16.6667 | ST-2 | VM01 | VM01 | VM04
CA16-001A |  | - | P03-03 |  | 0 | CA16-001A-P03-03 |  |  | ST | 1 | WH1 | WH1 | WH1 | WH1 | STORE
CA16-001 | GP01-003 | - | P01-03 |  | 0 | CA16-001-P01-03 |  |  | ST | 1 | 300 | 5 | FM | SW02 | SW02
CA16-001 | GP01-003 | - | P02-03 |  | 0 | CA16-001-P02-03 |  |  | ST | 1 | 600 | 10 | FM | CHECK | CHECKING
CA16-004 | GP01-005 | - | P01-03 |  | 0 | CA16-004-P01-03 |  |  | ST | 1 | 2400 | 40 | ST-2 | PP32 | PP32
CA16-004 | GP01-005 | - | P02-03 |  | 0 | CA16-004-P02-03 |  | DEGREASING | ST | 1 | 1000 | 16.6667 | ST-2 | VM01 | VM01 | VM04
CA17-001 | GP01-007 | - | P01-01 |  | 0 | CA17-001-P01-01 |  |  | ST | 1 | 2400 | 40 | FM | FM01 | FM01
CA21-001 |  | - | P01-04 |  | 0 | CA21-001-P01-04 |  |  | ST | 1 | 2400 | 40 | FM | FM01 | FM01 | FM02
CA24-002 |  | - | P01-04 |  | 0 | CA24-002-P01-03 |  |  | ST | 1 | 1800 | 30 | ST-2 | PP19-110T | PP19 | PP12 | PP14 | PP32
CA24-002 |  | - | P02-04 |  | 0 | CA24-002-P02-03 |  |  | ST | 1 | 240 | 4 | ST-1 | PP05-060T | PP05 | PP13 | PP06
CA24-006 |  | - | P01-03 |  | 0 | CA24-006-P01-03 |  |  | ST | 1 | 480 | 8 | ST-2 | PP01-110T | PP01 | PP02 | PP19 | PP14 | PP12 |  |  |  |  | SAME DIE WITH CA24-009-P01-03,CA24-007-P01-03
CA24-006 |  | - | P02-03 |  | 0 | CA24-006-P02-03 |  |  | ST | 1 | 180 | 3 | ST-3 | PP21-110T | PP21 | PP12 | PP14 | [6 empty] | SAME DIE WITH CA24-009-P02-03,CA24-007-P02-03,CL02-008
CA24-007 |  | - | P01-03 |  | 0 | CA24-007-P01-03 |  |  | ST | 1 | 480 | 8 | ST-1 | PP19-110T | PP10 | PP12 | PP02 | PP14 | PP19 | PP12 |  |  |  |  | SHARE DIE V CA24-009,CA24-006-P01-03,CA24-008
CA24-007 |  | - | P02-03 |  | 0 | CA24-007-P02-03 |  |  | ST | 1 | 180 | 3 | ST-2 | PP21-110T | PP15 | PP21 | PP31 | PP17 | PP14 | PP12 |  |  |  |  | SHARE DIE V CA24-009,CA24-006-P02-03,CA24-008,CL02-008
CA25-001 |  | - | P01-03 |  | 0 | CA25-001-P01-04 |  |  | AL | 1 | 72 | 1.2 | AL | CM03 | CM03 | CM05
CA25-001 |  | - | P02-03 |  | 0 | CA25-001-P02-04 |  |  | AL | 1 | 600 | 10 | AL | BDS01 | BDS1
CA25-001 |  | - | P03-03 |  | 0 | CA25-001-P03-04 |  |  | AL | 1 | 1200 | 20 | AL | ALDG | DEGREASING
CA28-001 |  | - | P01-06 |  | 0 | CA28-001-P01-06 |  | CUT TO SIZE = 567.3+-0.3 | ST | 1 | 150 | 2.5 | ST-1 | PP14-080T | PP14 | PP02
CA28-001 |  | - | P02-06 |  | 0 | CA28-001-P02-06 |  | PUNCH HOLE | ST | 1 | 120 | 2 | ST-1 | PP02-060T | PP02 | PP14
CA28-001 |  | - | P03-06 |  | 0 | CA28-001-P03-06 |  | TURRET PUNCH | ST | 1 | 120 | 2 | #N/A | TM02 | TM02
CA28-001 |  | - | P04-06 |  | 0 | CA28-001-P04-06 |  | BENDING 1 | ST | 1 | 120 | 2 | TR | PB02 | PB02 | PB08
CA28-001 |  | - | P05-06 |  | 0 | CA28-001-P05-06 |  | BENDING 2 | ST | 1 | 120 | 2 | TR | PB02 | PB02 | PB08
CB07-003 |  | - | P01-05 |  | 0 | CB07-003-P01-05 |  |  | WN | 1 | 20 | 0.33333 | WN | SW13 | SW13 | SW05 | SW06
CB07-003 |  | - | P02-05 |  | 0 | CB07-003-P02-05 |  |  | WN | 1 | 50 | 0.83333 | WN | TW01 | TW01 | TW02 | TW03
CB07-003 |  | - | P03-05 |  | 0 | CB07-003-P03-05 |  | CHECKING | WN | 1 | 60 | 1 | AL | CHECKING | CHECKING
CB07-003D |  | - | P01-02 |  | 0 | CB07-003D-P01-02 |  |  | WN | 1 | 4800 | 80 | WN | WS01 | WS01 | [8 empty] | LU METAL MATERIAL EASILY RUST,ONCE MATERIAL COME, NEED RUN IN BETWEEN 2 DAY
CB07-003E |  | - | P01-02 |  | 0 | CB07-003E-P01-02 |  |  | WN | 1 | 1200 | 20 | WN | WS01 | WS01 | [8 empty] | LU METAL MATERIAL EASILY RUST,ONCE MATERIAL COME, NEED RUN IN BETWEEN 2 DAY
CB07-005 |  | - | P01-05 |  | 0 | CB07-005-P01-05 |  |  | WN | 1 | 12 | 0.2 | TR | SW13 | SW05 | SW13
CB07-005 |  | - | P02-05 |  | 0 | CB07-005-P02-05 |  |  | WN | 1 | 20 | 0.33333 | WN | TW01 | TW01
CB07-005 |  | - | P03-05 |  | 0 | CB07-005-P03-05 |  |  | WN | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CB07-005 |  | - | P04-05 |  | 0 | CB07-005-P04-05 |  |  | WN | 1 | WH1 | WH1 | WH1 | WH1 | STORE
CB07-005D |  | - | P01-02 |  | 0 | CB07-005D-P01-02 |  |  | WN | 1 | 5400 | 90 | #N/A | WS01 | WS01
CB07-005E |  | - | P01-02 |  | 0 | CB07-005E-P01-02 |  |  | WN | 1 | 900 | 15 | #N/A | WS01 | WS01
CB07-006 |  | - | P01-02 |  | 0 | CB07-006-P01-02 |  |  | ST | 1 | 1800 | 30 | ST-4 | PP30-200T | PP30
CB11-001 |  | - | P01-02 |  | 0 | CB11-001-P01-02 |  |  | ST | 1 | 3000 | 50 | ST-1 | PP10-080T | PP10 | PP02 | PP14
CB11-002 |  | - | P01-02 |  | 0 | CB11-002-P01-02 |  |  | ST | 2 | 1800 | 30 | ST-1 | PP10-080T | PP10 | PP12 | PP14
CB11-004 |  | - | P01-02 |  | 0 | CB11-004-P01-02 |  |  | ST | 1 | 1800 | 30 | ST-1 | PP10-080T | PP10 | PP02 | PP14
CB11-005 |  | - | P01-02 |  | 0 | CB11-005-P01-02 |  |  | ST | 1 | 480 | 8 | ST-3 | PP09-160T | PP09
CB11-005 |  | - | P02-02 |  | 0 | CB11-005-P02-02 |  |  | ST | 1 | 240 | 4 | ST-3 | PP21-110T | PP21
CB11-006 |  | - | P01-02 |  | 0 | CB11-006-P01-03 |  |  | S/T | 2 | 180 | 3 | ST-4 | PP30-200T | PP30
CB11-006 |  | - | P02-02 |  | 0 | CB11-006-P02-03 |  |  | S/T | 2 | 60 | 1 | TR | PB07 | PB07 | [8 empty] | NEED 2 OPT RUN
CB11-007 |  | - | P01-02 |  | 0 | CB11-007-P01-02 |  |  | ST | 1 | 480 | 8 | ST-1 | PP10-080T | PP10
CB11-007 |  | - | P02-02 |  | 0 | CB11-007-P02-02 |  |  | ST | 1 | 240 | 4 | ST-2 | PP15-080T | PP15
CC02-004 |  | - | P01-04 |  | 0 | CC02-004-P01-04 |  |  | FM | 1 | 1800 | 30 | FM | FM02 | FM01 | FM02
CC02-004 |  | - | P02-04 |  | 0 | CC02-004-P02-04 |  |  | FM | 1 | 30000 | 500 | ST | VM01 | VM01 | VM04
CC02-005 |  | - | P01-04 |  | 0 | CC02-005-P01-04 |  |  | FM | 1 | 1800 | 30 | FM | FM02 | FM02 | [9 empty] | IF NO CHOICE CAN RUN FM01
CC02-005 |  | - | P02-04 |  | 0 | CC02-005-P02-04 |  |  | FM | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CC02-005 |  | - | P03-04 |  | 0 | CC02-005-P03-04 |  |  | FM | 1 | 3000 | 50 | FM | VM01 | VM01 | VM04
CC02-006 |  | - | P01-04 |  | 0 | CC02-006-P01-04 |  |  | FM | 1 | 3000 | 50 | FM | FM02 | FM02 | FM01 | FM03
CC06-001 | GP01-002 | - | P01-04 |  | 0 | CC06-001-P01-04 |  |  | S/A | 1 | 2220 | 37 | ST-2 | PP06-040T | PP06
CC06-001 | GP01-002 | - | P02-04 |  | 0 | CC06-001-P02-04 |  |  | S/A | 1 | 600 | 10 | AL | TP08 | TP04 | TP06 | TP08
CC06-001 | GP01-002 | - | P03-04 |  | 0 | CC06-001-P03-04 |  |  | S/A | 1 | 780 | 13 | AL | DRY-1 | V1,DRY-1
CC09-001 |  | - | P01-02 |  | 0 | CC09-001-P01-03 |  |  | TR | 1 | 150 | 2.5 | TR | TM05 | TM03 | TM05 | TM06
CC09-001 |  | - | P02-02 |  | 0 | CC09-001-P02-03 |  |  | TR | 1 | 100 | 1.6667 | TR | PB08 | PB02 | PB04 | PB08
CC09-002 |  | - | P02-04 |  | 0 | CC09-002-P02-04 |  |  | TR | 1 | 120 | 2 | TR | TM06 | TM03 | TM05 | TM06
CC09-002 |  | - | P03-04 |  | 0 | CC09-002-P03-04 |  |  | TR | 1 | 100 | 1.6667 | TR | PB08 | PB02 | PB08
CC09-003 |  | - | P01-04 |  | 0 | CC09-003-P01-04 |  |  | TR | 1 | 720 | 12 | SM | SM01 | SM01
CC09-003 |  | - | P02-04 |  | 0 | CC09-003-P02-04 |  |  | TR | 1 | 300 | 5 | TR | TM03 | TM03 | TM05 | TM06
CC09-003 |  | - | P03-04 |  | 0 | CC09-003-P03-04 |  |  | TR | 1 | 180 | 3 | TR | PB02 | PB02 | PB07 | PB03 | PB08
CC09-004 |  | - | P01-04 |  | 0 | CC09-004-P01-04 |  |  | ST | 1 | 11520 | 192 | SM | SM01 | SM01
CC09-004 |  | - | P02-04 |  | 0 | CC09-004-P02-04 |  |  | ST | 1 | 900 | 15 | ST-1 | PP05-060T | PP03 | PP22 | PP05 | PP13
CC09-004 |  | - | P03-04 |  | 0 | CC09-004-P03-04 |  |  | ST | 1 | 480 | 8 | ST-1 | PP13-060T | PP04 | PP21 | PP13 | PP03 | PP05 | PP12
CC09-005 |  | - | P01-03 |  | 0 | CC09-005-P01-03 |  |  | TR | 1 | 80 | 1.3333 | TR | TM05 | TM05 | TM03 | TM06
CC09-005 |  | - | P02-03 |  | 0 | CC09-005-P02-03 |  |  | TR | 1 | 180 | 3 | TR | PB07 | PB07 | PB04 | PB05 | PB03
CD06-006 |  | - | P01-04 |  | 0 | CD06-006-P01-04 |  |  | FM | 1 | 2400 | 40 | FM | FM02 | FM02 | FM01
CD06-006 |  | - | P02-04 |  | 0 | CD06-006-P02-04 |  |  | FM | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CD06-006 |  | - | P03-04 |  | 0 | CD06-006-P03-04 |  |  | FM | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CD06-006 |  | - | P04-04 |  | 0 | CD06-006-P04-04 |  |  | FM | 1 | WH1 | WH1 | WH1 | WH1 | STORE
CD11-002 |  | - | P01-06 |  | 0 | CD11-002-P01-06 |  |  | WN | 3 | 62 | 1.0333 | WN | SW08 | SW08 | SW04 | [7 empty] | 17PCS/HOUR(0.28/MIN) IF 2 OPERATORS 1 PREPARING JIG CAN GET 34 PCS/HOUR
CD11-002 |  | - | P02-06 |  | 0 | CD11-002-P02-06 |  |  | WN | 1 | 510 | 8.5 | WN | LVL01 | LVL01 | LVL02
CD11-002 |  | - | P03-06 |  | 0 | CD11-002-P03-06 |  |  | WN | 1 | 240 | 4 | WN | PP05-060T | PP05
CD11-002 |  | - | P04-06 |  | 0 | CD11-002-P04-06 |  |  | WN | 1 | 120 | 2 | AL | CHECKING | CHECKING | [8 empty] | NO NEED CHECKING,SEND TO SUB CON FOR COATING
CD11-003 |  | - | P01-02 |  | 0 | CD11-003-P01-02 |  |  | TR | 1 | 6 | 0.1 | ST | SW12 | SW12 | SW14 | SWQ13
CD11-003A |  | - | P02-12 |  | 0 | CD11-003A-P02-12 |  |  | S/T | 1 | 120 | 2 | ST-1 | PP12 | PP03 | PP22 | PP03 | PP04 | PP23 | PP02 | PP15 | PP21 | PP12 | RUN FIRST PROCESS - ARAY METAL,2ND T6,P03-P3,P4,3RD-P3,P4,P05&P06-PB,PB4,PB3,PB2,P07-SW10 |  | 1
CD11-003A |  | - | P03-12 |  | 0 | CD11-003A-P03-12 |  |  | S/T | 1 | 120 | 2 | ST-1 | PP14-080T | PP15 | PP02 | PP03 |  |  |  |  | PP22 | PP14 | RUN P23.P31-270622 | RUN PP05 ON 290822
CD11-003A |  | - | P04-12 |  | 0 | CD11-003A-P04-12 |  |  | S/T | 1 | 46 | 0.76667 | TR | PB01 | PB01 | [8 empty] | difficult process | run 4 opr only on 190722
CD11-003A |  | - | P05-12 |  | 0 | CD11-003A-P05-12 |  |  | S/T | 1 | 46 | 0.76667 | TR | PB04 | PB04 | [8 empty] | PB4 (SHARE OPT WITH PB2 - 1 OPT) run 1 opr only on 190722
CD11-003A |  | - | P06-12 |  | 0 | CD11-003A-P06-12 |  |  | S/T |  | 46 | 0.76667 | TR | PB03 | PB03 | [8 empty] | run 1 opr only on 190722
CD11-003A |  | - | P07-12 |  | 0 | CD11-003A-P07-12 |  |  | S/T |  | 46 | 0.76667 | TR | PB02 | PB02 | [8 empty] | RUN PB1 ON 300622
CD11-003A |  | - | P08-12 |  | 0 | CD11-003A-P08-12 |  |  | S/T | 1 | 46 | 0.76667 | TR | PB07 | PB07 | [8 empty] | difficult process
CD11-003A |  | - | P09-12 |  | 0 | CD11-003A-P09-12 |  |  | S/T | 1 | 45 | 0.75 | TR | PB03 | PB03 | PB02 | PB03 | [6 empty] | PB1 (1 OPT) & PB4 (SHARE 1 OPT ONLY) | ON DATE : 15.5.24 IMPROVE PROCESS OPF TO 3 M/C RUNNING : PB02,PB04,PB01 (3 OPT RUNNING)
CD11-003A |  | - | P10-12 |  | 0 | CD11-003A-P10-12 |  |  | S/T | 1 | 45 | 0.75 | TR | PB04 | PB04 | PB04 | PB04 | [6 empty] | 1 OPT | ON 090622 - NOT RUN OPF-P03/12-PB1,P04-PB1,P05-PB1,P05-PB3,P06-PB7,P06-PB7,P07-PB7,P08-PB1,P09-PB1,P10-PB1
CD11-003A |  | - | P11-12 |  | 0 | CD11-003A-P11-12 |  |  | S/T | 1 | 45 | 0.75 | TR | PB01 | PB01 |  | PB01 | [6 empty] | 2 OPT | FROM DATE : 01.07.24 IMPROVE PROCESS OPF TO 3 M/C RUNNING PB01,PB04,PB03
CD11-003A |  | - | P01-12 |  | 0 | CD11-003A-P01-12 |  |  | S/T | 1 | 20 | 0.33333 | TR | TM03 | TM03 | TM06 | TM05 | [6 empty] | 2 OPT
CD11-003B |  | - | P01-04 |  | 0 | CD11-003B-P01-04 |  |  | TR | 1 | 5760 | 96 | TR | SM01 | SM01
CD11-003B |  | - | P02-04 |  | 0 | CD11-003B-P02-04 |  |  | TR | 1 | 240 | 4 | TR | PP31-080T | PP31 | PP02 | PP04 | [8 empty] | 4
CD11-003B |  | - | P03-04 |  | 0 | CD11-003B-P03-04 |  |  | TR | 1 | 240 | 4 | TR | PP31-080T | PP31 | PP14 | PP04 | [6 empty] | EFF-150822 BENDING PP31
CD11-003C |  | - | P01-04 |  | 0 | CD11-003C-P01-04 |  |  | TR | 1 | 100 | 1.6667 | TR | TM06 | TM03 | TM05 | TM06 | [8 empty] | 2
CD11-003C |  | - | P02-04 |  | 0 | CD11-003C-P02-04 |  |  | TR | 1 | 240 | 4 | TR | PP31-080T | [9 empty] | SAME TOOLING WITH CD11-003B | EFF FROM 08.06.23 PROCESS ONLY:TURRET PUNCH, PP31 & SW PROCESS
CD11-003C |  | - | P03-04 |  | 0 | CD11-003C-P03-04 |  |  | TR | 1 | 120 | 2 | ST | SW13 | SW09 | SW13 | SW14 | [7 empty] | RUN P02-07-PB3,P03-07-PB3,P04-07-PB4,P05-0-PB4,P06-07-PB2,P07-07-SW11 ON 110622
CD11-003D |  | - | P01-05 |  | 0 | CD11-003D-P01-05 |  |  | TR | 1 | 240 | 4 | SM | SM01 | SM01 | [10 empty] | 1
CD11-003D |  | - | P02-05 |  | 0 | CD11-003D-P02-05 |  |  | TR | 1 | 280 | 4.6667 | TR | TM06 | TM05 | TM03 | TM06 | [6 empty] | SAME TOOLING V CD11-003E
CD11-003D |  | - | P03-05 |  | 0 | CD11-003D-P03-05 |  |  | TR | 1 | 90 | 1.5 | TR | PB02 | PB02 | PB08 | [7 empty] | RUN PB3 - 040722 | EFFECTIVE - 10.12.24 - BENDING ONLY RUN AT M/C : PP31
CD11-003D |  | - | P04-05 |  | 0 | CD11-003D-P04-05 |  |  | TR | 1 | 100 | 1.6667 | TR | PB03 | PB03 | PB08 | PB02 | [6 empty] | RUN PB3 - 040722
CD11-003E |  | - | P01-05 |  | 0 | CD11-003E-P01-05 |  |  | TR | 1 | 23760 | 396 | SM | SM01 | SM01 | [10 empty] | 1
CD11-003E |  | - | P02-05 |  | 0 | CD11-003E-P02-05 |  |  | TR | 1 | 180 | 3 | TR | TM06 | TM03 | TM05 | TM06 | [6 empty] | SAME TOOLING V CD11-003D
CD11-003E |  | - | P03-05 |  | 0 | CD11-003E-P03-05 |  |  | TR | 1 | 90 | 1.5 | TR | PB02 | PB02 | PB08 | [7 empty] | RUN PB3 - 040722
CD11-003E |  | - | P04-05 |  | 0 | CD11-003E-P04-05 |  |  | TR | 1 | 100 | 1.6667 | TR | PB03 | PB03 | PB08 | PB02 | [6 empty] | RUN PB3 - 040722
CD11-003H |  | - | P01-03 |  | 0 |  |  |  | TR | 1 |  | 0 | TR | TM05 | TM05 | TM03 | TM06 | [6 empty] | FROM D11-003A |  | 1
CD11-003H |  | - | P01-02 |  | 0 | CD11-003H-P01-02 |  |  | TR | 1 | 360 | 6 | ST-3 | PP31-080T | PP31 | PP05 | PP22 | P13 | [5 empty] | P5-RUN ON 050922 | (EFF FROM 14/1/22 CHANGE TO DIE RUN) | 1 | SHARE DIE V CD11-003K
CD11-003G |  | - | P01-06 |  | 0 | CD11-003G-P01-06 |  |  | TR | 1 | 120 | 2 | TR | TM06 | TM03 | TM05 | TM06
CD11-003G |  | - | P02-06 |  | 0 | CD11-003G-P02-06 |  |  | TR | 1 | 60 | 1 | TR | PB05 | PB05
CD11-003G |  | - | P03-06 |  | 0 | CD11-003G-P03-06 |  |  | TR | 1 | 80 | 1.3333 | ST | SW13 | SW09 | SW06 | SW13 | SW14 | SW04
CD11-003G |  | - | P04-06 |  | 0 | CD11-003G-P04-06 |  |  | TR | 1 | 60 | 1 | #N/A | MIG | MIG
CD11-003G |  | - | P05-06 |  | 0 | CD11-003G-P05-06 |  |  | TR | 1 | 60 | 1 | #N/A | OPT CLEANNING | OPT CLEANNING | [8 empty] | CLEANING
CD11-003I |  | - | P01-03 |  | 0 | CD11-003I-P01-03 |  |  | S/T | 1 | 360 | 6 | ST-3 | PP31-080T | PP22 | PP31 | [9 empty] | 1
CD11-003I |  | - | P02-03 |  | 0 | CD11-003I-P02-03 |  |  | S/T | 1 | 120 | 2 | ST | SW13 | SW09 | SW13 | SW04 | [6 empty] | EFF - 24/3/22
CD11-003J |  | - | P01-03 |  | 0 | CD11-003J-P01-03 |  |  | TR | 1 | 75 | 1.25 | TR | TM06 | TM05 | TM06 | TM03 | [8 empty] | 1
CD11-003J |  | - | P02-03 |  | 0 | CD11-003J-P02-03 |  |  | TR | 1 | 60 | 1 | TR | PB01 | PB01 | PB07 | [7 empty] | RUN PB1 ON 290622
CD11-003K |  |  | P01-04 |  | 0 | CD11-003K-P01-04 |  |  | TR | 1 | 240 | 4 |  | SM01 | SM01 | [10 empty] | 2
CD11-003K |  | - | P02-04 |  | 0 | CD11-003K-P02-04 |  |  | TR | 1 | 240 | 4 | TR | PP11-035T | PP11
CD11-003K |  | - | P03-04 |  | 0 | CD11-003K-P03-04 |  |  | TR | 1 | 360 | 6 | ST-3 | PP31-080T | PP05 | PP31 | PP22 | [6 empty] | P5-RUN ON 050922 | SHARE DIE V CD11-003H
CD11-003L |  |  | P01-04 |  |  | CD11-003L-P01-04 |  |  | TR | 1 | 240 | 4 | ST | SM01 | SM01 | [10 empty] | 1
CD11-003L |  | - | P02-04 |  | 0 | CD11-003L-P02-04 |  |  | TR | 1 | 200 | 3.3333 | TR | TM03 | TM03 | TM05 | TM06
CD11-003L |  | - | P03-04 |  | 0 | CD11-003L-P03-04 |  |  | TR | 1 | 60 | 1 | TR | PB01 | PB01 | PB05
CD11-004 |  | - | P01-02 |  | 0 | CD11-004-P01-02 |  |  | TR | 1 | 60 | 1 | TR | SW09 | SW09 | SW05
CD11-004A |  | - | P01-03 |  | 0 | CD11-004A-P01-03 |  |  | TR | 1 | 120 | 2 | TR | TM05 | TM05 | TM03 | TM06
CD11-004A |  | - | P02-03 |  | 0 | CD11-004A-P02-03 |  |  | TR | 1 | 60 | 1 | TR | PB07 | PB07 | PB05 | [7 empty] | RUN PB7 ON 170622 - 60/HOUR
CD11-004B |  | - | P01-03 |  | 0 | CD11-004B-P01-03 |  |  | TR | 1 | 120 | 2 | TR | TM05 | TM05 | TM03 | TM06
CD11-004B |  | - | P02-03 |  | 0 | CD11-004B-P02-03 |  |  | TR | 1 | 180 | 3 | TR | PB04 | PB04 | [8 empty] | RUN PB4 ON 180822
CD11-005 |  | - | P02-05 |  | 0 | CD11-005-P02-05 |  |  | TR | 1 | 600 | 10 | TR | PP31-080T | PP31 | PP22 | PP22 | PP12 | [6 empty] | EFF -080722,NO MORE HAND BENDING
CD11-005 |  | - | P03-05 |  | 0 | CD11-005-P03-05 |  |  | TR | 1 | 360 | 6 | TR | PP31-080T | PP31 | PP22 | PP03 | PP12 | [5 empty] | RUN PB7
CD11-005 |  | - | P04-05 |  | 0 | CD11-005-P04-05 |  |  | TR | 1 | 240 | 4 | ST-1 | PP31-080T | PP31 | PP22 | PP05 | PP12 | [5 empty] | STAMPING CCANOT RUN - RUN PB3 | EFF -080722,NO MORE HAND BENDING
CD11-007 |  | - | P01-07 |  | 0 | CD11-007-P01-07 |  |  | WN | 1 | 3000 | 50 | WN | WS01 | WS01 | WS02 | [7 empty] | (20~24PCS/MINUTES)/1440PCS/HOUR
CD12-001 |  | - | P02-07 |  | 0 | CD12-001-P02-07 |  |  | ? | 1 | 34 | 0.56667 | WN | SW04 | SW04 | SW03 | SW9/SW10(BORROW)
CD12-002 |  | - | P03-07 |  | 0 | CD12-002-P03-07 |  |  | ? | 1 | 120 | 2 | WN | TW02 | TW02 | TW01 | TW03
CD12-003 |  | - | P04-07 |  | 0 | CD12-003-P04-07 |  |  | ? | 1 | 120 | 2 | WN | LVL01 | LVL01 | LVL02
CD12-004 |  | - | P05-07 |  | 0 | CD12-004-P05-07 |  |  | ? | 1 | 120 | 2 | AL | CHECKING | CHECKING | CHECKING3
CD12-005 |  | - | P06-07 |  | 0 | CD12-005-P06-07 |  |  | ? | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CD12-006 |  | - | P07-07 |  | 0 | CD12-006-P07-07 |  |  | ? | 1 | WH1 | WH1 | WH1 | WH1 | STORE | STORE3 | [7 empty] | *COATING BACK,CHECKING & PANTING=50/MIN
GC02-027 | GC02-027 | - | P01-01 |  | 0 | GC02-027-P01-02 |  |  | TR | 1 | 15 | 0.25 | TR | TM05 | TM05 | TM03 | TM06
CD11-008 |  | - | P01-07 |  | 0 | CD11-008-P01-07 |  |  | WN | 2 | 15 | 0.25 | WN | SW13 | SW13 | SW08
CD11-008 |  | - | P02-07 |  | 0 | CD11-008-P02-07 |  |  | WN | 1 | 120 | 2 | WN | LVL02 | LVL02
CD11-008 |  | - | P03-07 |  | 0 | CD11-008-P03-07 |  |  | WN | 1 | 120 | 2 | ST-3 | PP02-060T | PP02 | PP21
CD11-008 |  | - | P04-07 |  | 0 | CD11-008-P04-07 |  |  | WN | 1 | 200 | 3.3333 | ST-1 | PP21-110T | PP05 | PP31 | PP21
CD11-008 |  | - | P05-07 |  | 0 | CD11-008-P05-07 |  |  | WN | 1 | ED COATING BLACK | ED COATING BLACK | SUB CON | SUB CON | ED COATING BLACK | [8 empty] | ED COATING BLACK
CD11-008 |  | - | P06-07 |  | 0 | CD11-008-P06-07 |  |  | WN | 1 |  | 0 | AL | OPT WHITE MARKING | MARKING WHITE | [8 empty] | MARKING WHITE
CD11-008A |  | - | P01-02 |  | 0 | CD11-008A-P01-02 |  |  | WN | 1 | 960 | 16 | WN | WS02 | WS02 | WS01
CD11-008B |  | - | P01-02 |  | 0 | CD11-008B-P01-02 |  |  | WN | 1 | 960 | 16 | WN | WS02 | WS02 | WS01
CD11-008C |  | - | P01-02 |  | 0 | CD11-008C-P01-02 |  |  | WN | 1 | 960 | 16 | WN | WS02 | WS02 | WS01
CE03-002 |  | - | P01-03 |  | 0 | CE03-002-P01-03 |  |  | ST | 1 | 105 | 1.75 | ST-3 | PP09-160T | PP09 | PP03
CE03-002 |  | - | P02-03 |  | 0 | CE03-002-P02-03 |  |  | ST | 1 | 105 | 1.75 | ST-3 | PP18-150T | PP18 | PP03 | PP27
CE03-005 |  | - | P01-04 |  | 0 | CE03-005-P01-04 |  |  | S/A | 1 | 1500 | 25 | ST-2 | PP06-040T | PP06 | PP03
CE03-005 |  | - | P02-04 |  | 0 | CE03-005-P02-04 |  |  | S/A | 1 | 360 | 6 | AL | TP06 | TP06 | TP02
CE03-005 |  | - | P03-04 |  | 0 | CE03-005-P03-04 |  |  | S/A | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CE03-005 |  | - | P04-04 |  | 0 | CE03-005-P04-04 |  |  | S/A | 1 | WH1 | WH1 | WH1 | WH1 | STORE | STORE3
CE03-009 |  | - | P01-02 |  | 0 | CE03-009-P01-02 |  |  | AL | 1 | 240 | 4 | AL | CM03 | CM03
CE03-009 |  | - | P02-02 |  | 0 | CE03-009-P02-02 |  |  | AL | 1 | 1800 | 30 | #N/A | #N/A | V1,DRY1 | V1,DRY3
CE03-019 |  | - | P01-03 |  | 0 | CE03-019-P01-03 |  |  | FM | 1 | 1800 | 30 | FM | FM01 | FM01
CE03-019 |  | - | P02-03 |  | 0 | CE03-019-P02-03 |  |  | FM | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CE03-020 |  | - | P01-02 |  | 0 | CE03-020-P01-02 |  |  | ST | 1 | 1200 | 20 | ST-1 | PP14-080T | PP14
CE03-022 |  | - | P01-03 |  | 0 | CE03-022-P01-03 |  |  | FM | 1 | 2400 | 40 | FM | FM01 | FM01
CE03-022 |  | - | P02-03 |  | 0 | CE03-022-P02-03 |  |  | SC | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CE03-024 |  | - | P01-03 |  | 0 | CE03-024-P01-03 |  |  | ST | 1 | 720 | 12 | ST-1 | PP10-080T | PP10
CE03-024 |  | - | P02-03 |  | 0 | CE03-024-P02-03 |  |  | ST | 1 | 360 | 6 | ST-1 | PP13-060T | PP13
CE03-026 |  | - | P01-03 |  | 0 | CE03-026-P01-03 |  |  | ST | 1 | 1800 | 30 | ST-1 | PP02-060T | PP02
CE03-026 |  | - | P02-03 |  | 0 | CE03-026-P02-03 |  |  | AL | 1 | 300 | 9 | AL | TP06 | TP06
CE03-027 |  | - | P01-02 |  | 0 | CE03-027-P01-02 |  |  | FM | 1 | 1800 | 30 | FM | FM02 | FM02 | FM01 | [7 empty] | SHARE CAM WITH CE03-029
CE03-028 |  | - | P01-04 |  | 0 | CE03-028-P01-04 |  |  | ST | 1 | 1500 | 25 | ST-1 | PP02-060T | PP02
CE03-028 |  | - | P02-04 |  | 0 | CE03-028-P02-04 |  |  | AL | 1 | 300 | 9 | #N/A | TP06
CE03-028 |  | - | P03-04 |  | 0 | CE03-028-P03-04 |  |  | SC | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CE03-029 |  | - | P01-02 |  | 0 | CE03-029-P01-02 |  |  | FM | 1 | 1800 | 30 | FM | FM02 | FM02 | FM01 | [7 empty] | SHARE CAM WITH CE03-027
CE03-030 |  | - | P01-05 |  | 0 | CE03-030-P01-05 |  |  | FM | 1 | 2700 | 45 | FM | FM01 | FM01
CE03-030 |  | - | P02-05 |  | 0 | CE03-030-P02-05 |  |  | FM | 1 | 270 | 4.5 | ST-1 | PP11-035T | PP11 | [8 empty] | PROCESS P02,NEED TOGETHER RUN WITH FORMING WHEN RUNNING
CE03-030 |  | - | P03-05 |  | 0 | CE03-030-P03-05 |  |  | FM | 1 | 180 | 3 | AL | TP06 | TP06
CE03-030 |  | - | P04-05 |  | 0 | CE03-030-P04-05 |  |  | FM | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CE03-032 |  | - | P01-03 |  | 0 | CE03-032-P01-03 |  |  | ST | 1 | 240 | 4 | SM | SM01 | SM01
CE03-032 |  | - | P02-03 |  | 0 | CE03-032-P02-03 |  |  | ST | 1 | 360 | 6 | ST-1 | PP10-080T | PP10
CE03-032 |  | - | P03-03 |  | 0 | CE03-032-P03-03 |  |  | ST | 1 | 360 | 6 | ST-1 | PP10-080T | PP10
CE03-033 |  | - | P01-02 |  | 0 | CE03-033-P01-02 |  |  | ST | 1 | 1800 | 30 | ST-2 | PP06-040T | PP06 | PP03
CE03-040 |  | - | P01-02 |  | 0 | CE03-040-P01-02 |  |  | ST | 1 | 90 | 1.5 | TR | SW05 | SW05
CE03-040A |  | - | P01-04 |  | 0 | CE03-040A-P01-04 |  | SLITTING | ST | 1 | 240 | 4 | ST-1 | SM01 | SM01
CE03-040A |  | - | P02-04 |  | 0 |  |  |  | ST | 1 | 360 | 6 | ST-1
CE03-040B |  | - | P01-03 |  | 0 | CE03-040B-P01-03 |  | FORMING | FM | 1 | 3000 | 50 | FM | FM02 | FM02
CF03-007 |  | - | P01-04 |  | 0 | CF03-007-P01-04 |  |  | ST | 1 | 900 | 15 | ST-1 | PP02-060T | PP02 | PP14
CF03-007 |  | - | P02-04 |  | 0 | CF03-007-P02-04 |  |  | ST | 1 | 360 | 6 | ST-1 | PP06-040T | PP06 | PP03 | PP12
CF03-007 |  | - | P03-04 |  | 0 | CF03-007-P03-04 |  |  | ST | 1 | 240 | 4 | ST-1 | PP04-060T | PP04 | PP03 | PP06 | PP12
CH04-001 |  | - | P01-06 |  | 0 | CH04-001-P01-06 |  |  | ST | 1 | 360 | 6 | ST-1 | PP13-060T | PP10 | PP03 | PP17 | PP13
CH04-001 |  | - | P02-06 |  | 0 | CH04-001-P02-06 |  |  | ST | 1 | 360 | 6 | ST-1 | PP03-060T | PP04 | PP03 | PP16
CH04-001 |  | - | P03-06 |  | 0 | CH04-001-P03-06 |  |  | ST | 1 | 360 | 6 | ST-1 | PP04-060T | PP03 | PP27 | PP05 | PP13 | PP04
CH04-001 |  | - | P04-06 |  | 0 | CH04-001-P04-06 |  |  | ST | 1 | 360 | 6 | WN | SW01 | SW01 | SW09
CH04-001 |  | - | P05-06 |  | 0 | CH04-001-P05-06 |  |  | ST | 1 | 180 | 3 | ST-1 | OPT PAINTING | OPT PAINTING
CH04-002 |  | - | P01-07 |  | 0 | CH04-002-P01-07 |  |  | ST | 1 | 300 | 5 | ST-3 | PP25 | PP21 | PP03 | PP24 | PP28 | PP18 | PP25 | PP24 | PP24
CH04-002 |  | - | P02-07 |  | 0 | CH04-002-P02-07 |  |  | ST | 1 | 300 | 5 | ST-3 | PP26-110T | PP17 | PP03 | PP26 | PP20 | PP17 | PP26 | PP25 | PP25
CH04-002 |  | - | P03-07 |  | 0 | CH04-002-P03-07 |  |  | ST | 1 | 300 | 5 | ST-3 | PP20 | PP16 | PP03 | PP20 | PP26 | PP16 | PP20 | PP20 | PP26
CH04-002 |  | - | P04-07 |  | 0 | CH04-002-P04-07 |  |  | ST | 1 | 300 | 5 | ST-3 | PP28-110T | PP27 | PP03 | PP28 | PP25 | PP27 | PP28 | PP28 | PP28
CH04-002 |  | - | P05-07 |  | 0 | CH04-002-P05-07 |  |  | ST | 1 | 300 | 5 | ST-3 | SW01 | SW01 | SW09 |  |  |  | SW01
CH04-002 |  | - | P06-07 |  | 0 | CH04-002-P06-07 |  |  | ST | 2 | 120 | 2 | ST-1 | OPT PAINTING | OPT PAINTING |  |  |  | PAINTING
CJ01-001 |  | - | P01-04 |  | 0 | CJ01-001-P01-04 |  |  | ST | 1 | 240 | 4 | ST-2 | RV01 | RV01
CJ01-001 |  | - | P02-04 |  | 0 | CJ01-001-P02-04 |  |  | ST | 1 | 240 | 4 | #N/A | OPT | OPT
CJ01-001 |  | - | P03-04 |  | 0 | CJ01-001-P03-04 |  |  | ST | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CJ01-001A |  | - | P01-03 |  | 0 | CJ01-001A-P01-03 |  |  | ST | 1 | 360 | 6 | ST-1 | PP05-060T | PP05 | PP03 | PP04 | PP13
CJ01-001A |  | - | P02-03 |  | 0 | CJ01-001A-P02-03 |  |  | ST | 1 | 360 | 6 | ST-1 | PP04-060T | PP02 | PP03 | PP04 | PP22
CJ01-002 |  | - | P01-04 |  | 0 | CJ01-002-P01-04 |  |  | ST | 1 | 180 | 3 | ST-2 | RV01 | RV01
CJ01-002 |  | - | P02-04 |  | 0 | CJ01-002-P02-04 |  |  | ST | 1 | 180 | 3 | #N/A | OPT | OPT
CJ01-002 |  | - | P03-04 |  | 0 | CJ01-002-P03-04 |  |  | ST | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CJ01-002A |  | - | P01-03 |  | 0 | CJ01-002A-P01-03 |  |  | ST | 1 | 480 | 8 | ST-1 | PP05-060T | PP02 | PP03 | PP13 | PP21 | PP05
CJ01-002A |  | - | P02-03 |  | 0 | CJ01-002A-P02-03 |  |  | ST | 1 | 540 | 9 | ST-1 | PP23 | PP10 |  | PP10 | PP05 | PP23 | PP12
CJ01-003 |  | - | P01-04 |  | 0 | CJ01-003-P01-04 |  |  | S/A | 1 | 360 | 6 | ST-2 | PP07-016T | PP07 | PP03
CJ01-003 |  | - | P02-04 |  | 0 | CJ01-003-P02-04 |  |  | S/A | 1 | 150 | 2.5 | AL | BL04 | BL03 | BL04
CJ01-004 |  | - | P01-05 |  | 0 | CJ01-004-P01-05 |  |  | AL | 1 | 3960 | 66 | WN | WS01 | WS01
CJ01-004 |  | - | P02-05 |  | 0 | CJ01-004-P02-05 |  |  | AL | 1 | 240 | 4 | AL | BL03 | BL04 | BL03
CJ01-004 |  | - | P03-05 |  | 0 | CJ01-004-P03-05 |  |  | AL | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CJ01-004 |  | - | P04-05 |  | 0 | CJ01-004-P04-05 |  |  | AL | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CJ01-004 |  | - | P05-05 |  | 0 | CJ01-004-P05-05 |  |  | AL | 1 | WH1 | WH1 | WH1 | WH1 | STORE
CK01-005 |  | - | P01-02 |  | 0 | CK01-005-P01-02 |  |  | ST | 1 | 1800 | 30 | ST-1 | PP02-060T | PP02 | PP03 | PP14 | PP12
CK02-004 |  | - | P01-06 |  | 0 | CK02-004-P01-06 |  |  | S/A | 1 | 90 | 1.5 | ST | CT02 | CT02
CK02-004 |  | - | P02-06 |  | 0 | CK02-004-P02-06 |  |  | S/A | 1 | 132 | 2.2 | AL | BL04 | BL04 | BL03
CK02-004 |  | - | P03-06 |  | 0 | CK02-004-P03-06 |  |  | S/A | 1 | 132 | 2.2 | AL | BL04 | BL04 | BL03
CK02-004 |  | - | P04-06 |  | 0 | CK02-004-P04-06 |  |  | S/A | 1 | 150 | 2.5 | ST-3 | PP21-110T | PP21 | PP03 | PP21 | PP10
CK02-004 |  | - | P05-06 |  | 0 | CK02-004-P05-06 |  |  | S/A | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CJ01-004A |  | - | P01-02 |  | 0 | CJ01-004A-P01-02 |  |  | S/A | 1 | 300 | 5 | ST-2 | PP07-016T | PP07 | PP03
CJ01-004A |  | - | P02-02 |  | 0 | CJ01-004A-P02-02 |  |  | S/A | 1 | 420 | 7 | MT | ML02 | ML02 | ML03
CK12-001/CO02-017 | GP01-012 | - | P01-04 |  | 0 | CO02-017-P01-04 |  |  | ST | 1 | 2400 | 40 | SM | SM01 | SM01
CK12-001/CO02-017 | GP01-012 | - | P02-04 |  | 0 | CO02-017-P02-04 |  |  | ST | 1 | 360 | 6 | ST-1 | PP04-060T | PP05 | PP03 | PP13 | PP04 | [5 empty] | SETTING PP04,PP03 MUST AT THE SAME TIME
CK12-001/CO02-017 | GP01-012 | - | P03-04 |  | 0 | CO02-017-P03-04 |  |  | ST | 1 | 240 | 4 | ST-1 | PP03-060T | PP05 | PP03 | PP04 | PP03 | PP10
CK12-002 | GP01-013 | - | P01-05 |  | 0 | CK12-002-P01-05 |  |  | ST | 1 | 792 | 13.2 | SM | SM01 | SM01 |  | SM1
CK12-002 | GP01-013 | - | P02-05 |  | 0 | CK12-002-P02-05 |  |  | ? | 1 | 480 | 8 | ST-1 | PP05-060T | PP05 | [8 empty] | 60T
CK12-002 | GP01-013 | - | P03-05 |  | 0 | CK12-002-P03-05 |  |  | ? | 1 | 360 | 6 | ST-2 | PP06-040T | PP06 | PP05 | [7 empty] | 40T
CK12-002 | GP01-013 | - | P04-05 |  | 0 | CK12-002-P04-05 |  |  | ? | 1 | 240 | 4 | ST-1 | PP04-060T | PP04 | PP11 | [7 empty] | 60T
CK13-001 |  | - | P01-04 |  | 0 | CK13-001-P01-04 |  |  | ST | 1 | 808 | 13.4667 | SM | SM01 | SM01
CK13-001 |  | - | P02-04 |  | 0 | CK13-001-P02-04 |  |  | ST | 1 | 840 | 14 | ST-2 | PP15-080T | PP15
CK13-001 |  | - | P03-04 |  | 0 | CK13-001-P03-04 |  |  | ST | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CK13-001 |  | - | P04-04 |  | 0 | CK13-001-P04-04 |  |  | ST | 1 | STD | STD | #N/A | #N/A
CK14-001 |  | - | P01-02 |  | 0 | CK14-001-P01-02 |  |  | FM | 1 | 1200 | 20 | FM | FM02 | FM02
CL02-001 |  | - | P01-02 |  | 0 | CL02-001-P01-02 |  |  | S/A | 1 |  | 0 | #N/A | #N/A
CL02-001 |  | - | P02-02 |  | 0 | CL02-001-P02-02 |  |  | S/A | 1 | 300 | 5 | AL | TP02 | TP02
CL02-002 |  | - | P01-05 |  | 0 | CL02-002-P01-05 |  |  | ST | 1 | 720 | 12 | ST-2 | PP15-080T | PP15 | PP03 | PP04 | PP13 | [5 empty] | SAME DIE WITH CL02-003-P01,CU01-056-P02-03
CL02-002 |  | - | P02-05 |  | 0 | CL02-002-P02-05 |  |  | ST | 1 | 300 | 5 | ST-1 | PP04-060T | PP03 | PP04
CL02-002 |  | - | P03-05 |  | 0 | CL02-002-P03-05 |  |  | ST | 1 | 120 | 2 | MT | ML02 | DR04 | DR04 | ML02
CL02-002 |  | - | P04-05 |  | 0 | CL02-002-P04-05 |  |  | ST | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CL02-003 |  | - | P01-05 |  | 0 | CL02-003-P01-05 |  |  | ST | 1 | 720 | 12 | ST-1 | PP15-080T | PP04 | PP15 | [7 empty] | SAME DIE WITH CL02-002-P01-05,CU01-056-P02-03
CL02-003 |  | - | P02-05 |  | 0 | CL02-003-P02-05 |  |  | ST | 1 | 360 | 6 | ST-2 | PP04-060T | PP06 | PP15 | PP04 | PP02 | PP14
CL02-003 |  | - | P03-05 |  | 0 | CL02-003-P03-05 |  |  | ST | 1 | 360 | 6 | ST-1 | PP11-035T | PP11 | PP06 |  | PP03
CL02-003 |  | - | P04-05 |  | 0 | CL02-003-P04-05 |  |  | ST | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CL02-005 |  | - | P01-04 |  | 0 | CL02-005-P01-04 |  |  | ST | 1 | 240 | 4 | SM | SM01 | SM01
CL02-005 |  | - | P02-04 |  | 0 | CL02-005-P02-04 |  |  | ST | 1 | 300 | 5 | ST-2 | PP15-080T | PP15
CL02-005 |  | - | P03-04 |  | 0 | CL02-005-P03-04 |  |  | ST | 1 | 120 | 2 | MT | ML02 | ML02
CL02-005 |  | - | P04-04 |  | 0 | CL02-005-P04-04 |  |  | ST | 1 | 300 | 5 | ST-3 | PP17-110T | PP17
CL02-006 |  | - | P01-04 |  | 0 | CL02-006-P01-04 |  |  | ST | 1 | 240 | 4 | ST | CT02 | CT02
CL02-006 |  | - | P02-04 |  | 0 | CL02-006-P02-04 |  |  | ST | 1 | 240 | 4 | ST-2 | MANUAL WORK | OPERATOR
CL02-006 |  | - | P03-04 |  | 0 | CL02-006-P03-04 |  |  | ST | 1 | 360 | 6 | ST-2 | PP06-040T | PP06
CL02-008 |  | - | P01-07 |  | 0 | CL02-008-P01-07 |  |  | ST | 1 | 180 | 3 | ST | CT02 | CT02
CL02-008 |  | - | P02-07 |  | 0 | CL02-008-P02-07 |  |  | ST | 1 | 240 | 4 | #N/A | OPT | OPT
CL02-008 |  | - | P03-07 |  | 0 | CL02-008-P03-07 |  |  | ST | 1 | 360 | 6 | ST-3 | PP22-060T | PP22 | [8 empty] | SAME DIE V CL02-008-P03 & P04 NEED RUN SAME MACHINE
CL02-008 |  | - | P04-07 |  | 0 | CL02-008-P04-07 |  |  | ST | 1 | 360 | 6 | ST-3 | PP22-060T | PP22 | [8 empty] | SAME DIE V CL02-008-P03 & P04 NEED RUN SAME MACHINE
CL02-008 |  | - | P05-07 |  | 0 | CL02-008-P05-07 |  |  | ST | 1 | 90 | 1.5 | MT | M-1 | M-1
CL02-008 |  | - | P06-07 |  | 0 | CL02-008-P06-07 |  |  | ST | 1 | 200 | 3.3333 | ST-3 | PP03-060T | PP03 | PP12 | [7 empty] | SHARE DIE V CA24-009,CA24-006-P02-03,CA24-008,CL02-008
CM03-001 |  | - | P01-04 |  | 0 | CM03-001-P01-04 |  |  | F/S | 1 | 1080 | 18 | FM | FM02 | FM02 | FM03
CM03-001 |  | - | P02-04 |  | 0 | CM03-001-P02-04 |  |  | F/S | 1 | 250 | 4.1667 | ST | VM04 | VM01 | VM04
CM03-001 |  | - | P03-04 |  | 0 | CM03-001-P03-04 |  |  | F/S | 1 | 250 | 4.1667 | AL | CHECKING | CHECKING | CHECKING3
CM03-001 |  | - |  |  | 0
CM03-001 |  | - |  |  | 0
CM03-004 |  | - | P01-05 |  | 0 | CM03-004-P01-05 |  |  | F/S | 1 | 1080 | 18 | FM | FM02 | FM02 | FM03
CM03-004 |  | - | P02-05 |  | 0 | CM03-004-P02-05 |  |  | F/S | 1 | 540 | 9 | WN | DEBURR | DEBURR
CM03-004 |  | - | P03-05 |  | 0 | CM03-004-P03-05 |  |  | F/S | 1 | 540 | 9 | AL | CHECKING | CHECKING | [8 empty] | 15K '11'21
CM03-004 |  | - | P04-05 |  | 0 | CM03-004-P04-05 |  |  | F/S | 1 | 540 | 9 | ST-4 | REWORK | REWORK
CM03-004 |  | - | P05-05 |  | 0 | CM03-004-P05-05 |  |  | F/S | 1 | 540 | 9 | AL | CHECK | CHECKING
CM03-007 |  | - | P01-02 |  | 0 | CM03-007-P01-02 |  |  | FM | 1 | 2400 | 40 | FM | FM01 | FM01 | FM02
CM03-025 |  | - | P01-03 |  | 0 | CM03-025-P01-03 |  |  | ST | 1 | 360 | 6 | ST-3 | PP22-060T | PP22 | PP03
CM03-025 |  | - | P02-03 |  | 0 | CM03-025-P02-03 |  |  | ST | 1 | 240 | 4 | ST-3 | PP04-060T | PP22 | PP03 | PP04
CM03-026 |  | - | P01-02 |  | 0 | CM03-026-P01-02 |  |  | ST | 1 | 1800 | 30 | ST-2 | PP19-110T | PP19 | PP32 | [7 empty] | SHARE DIE V CM03-027,CM03-039
CM03-027 |  | - | P01-05 |  | 0 | CM03-027-P01-05 |  |  | ST | 1 | 1800 | 30 | ST-2 | PP19-110T | PP19 | PP32 | [7 empty] | SAME DIE WITH CM03-026,CM03-039
CM03-027 |  | - | P02-05 |  | 0 | CM03-027-P02-05 |  |  | ST | 1 | 3000 | 50 | ST | VM01 | VM01 | VM04
CM03-027 |  | - | P03-05 |  | 0 | CM03-027-P03-05 |  |  | ST | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CM03-027 |  | - | P04-05 |  | 0 | CM03-027-P04-05 |  |  | ST | 1 | 600 | 10 | AL | CHECKING | CHECKING
CM03-028 |  | - | P01-03 |  | 0 | CM03-028-P01-03 |  |  | ST | 1 | 480 | 8 | ST-1 | PP05-060T | PP05 | PP03 |  | PP02
CM03-028 |  | - | P02-03 |  | 0 | CM03-028-P02-03 |  |  | ST | 1 | 180 | 3 | ST-1 | PP15-080T | PP05 | PP03 | PP15 | PP02
CM03-030 |  | - | P01-02 |  | 0 | CM03-030-P01-03 |  |  | ST | 1 | 480 | 8 | ST-1 | PP13-060T | PP10 | PP03 | PP05 | PP13 | PP15 | PP02 | PP04 | PP22
CM03-030 |  | - | P02-02 |  | 0 | CM03-030-P02-03 |  |  | ST | 1 | 240 | 4 | ST-2 | PP03-060T | PP15 | PP22 | PP05 | PP03 | PP02
CM03-031 |  | - | P01-03 |  | 0 | CM03-031-P01-03 |  |  | ST | 1 | 1200 | 20 | ST-1 | PP02-060T | PP03 | PP14 | PP05 | PP04 | PP13 | PP10 | PP02 |  |  | IF RUN COIL P01-03 (20 PCS/MIN) IF RUN SHEET P01-03 (6PCS/MIN)
CM03-031 |  | - | P02-03 |  | 0 | CM03-031-P02-03 |  |  | ST | 1 | 240 | 4 | ST-1 | PP03-060T | PP10 | PP15 | PP05 | PP03 | PP04 | PP22
CM03-032 |  | - | P01-02 |  | 0 | CM03-032-P01-02 |  |  | ST | 1 | 480 | 8 | #N/A | #N/A
CM03-032 |  | - | P02-02 |  | 0 | CM03-032-P02-02 |  |  | ST | 1 | 240 | 4 | #N/A | #N/A
CM03-033 |  | - | P01-03 |  | 0 | CM03-033-P01-03 |  |  | ST | 1 | 480 | 8 | ST-3 | PP13-060T | PP17 | PP04 | PP13
CM03-033 |  | - | P02-03 |  | 0 | CM03-033-P02-03 |  |  | ST | 1 | 240 | 4 | ST-1 | PP04-060T | PP03 | PP04 | PP12 | PP05
CM03-034 |  | - | P01-05 |  | 0 | CM03-034-P01-05 |  |  | TR | 1 | 81 | 1.35 | TR | TM05 | TM05 | TM03 | TM06
CM03-034 |  | - | P02-05 |  | 0 | CM03-034-P02-05 |  |  | TR | 1 | 50 | 0.83333 | WN | DEBURR | DEBURR
CM03-034 |  | - | P03-05 |  | 0 | CM03-034-P03-05 |  |  | TR | 1 | 300 | 5 | TR | APPLY OIL | APPLY OIL
CM03-034 |  | - | P04-05 |  | 0 | CM03-034-P04-05 |  |  | TR | 1 | 200 | 3.3333 | TR | PB04 | PB04 | PB02 | PB08
CM03-035 |  | - | P01-05 |  | 0 | CM03-035-P01-05 |  |  | TR | 1 | 200 | 3.3333 | TR | TM05 | TM05 | TM03 | TM06
CM03-035 |  | - | P02-05 |  | 0 | CM03-035-P02-05 |  |  | TR | 1 | 200 | 3.3333 | WN | DEBURR | DEBURR
CM03-035 |  | - | P03-05 |  | 0 | CM03-035-P03-05 |  |  | TR | 1 | 300 | 5 | TR | APPLY OIL | APPLY OIL
CM03-035 |  | - | P04-05 |  | 0 | CM03-035-P04-05 |  |  | TR | 1 | 200 | 3.3333 | TR | PB04 | PB04 | PB02
CM03-037 |  | - | P01-03 |  | 0 | CM03-037-P01-03 |  |  | ST | 1 | 360 | 6 | ST-3 | PP04-060T | PP17 | PP04 | PP21 | PP03
CM03-037 |  | - | P02-03 |  | 0 | CM03-037-P02-03 |  |  | ST | 1 | 360 | 6 | ST-3 | PP03-060T | PP21 | PP05 | PP17 | PP16 | PP03 | PP15 | PP04
CM03-038 |  | - | P01-03 |  | 0 | CM03-038-P01-03 |  |  | ST | 1 | 360 | 6 | ST-3 | PP02-060T | PP22 | PP13 | P02 | PP05
CM03-038 |  | - | P02-03 |  | 0 | CM03-038-P02-03 |  |  | ST | 1 | 240 | 4 | ST-3 | PP05-060T | PP22 | PP04 | P02 | PP05 | PP31
CM03-040 |  | - | P01-02 |  | 0 | CM03-040-P01-02 |  |  | ST | 1 | 1200 | 20 | ST-4 | PP30-200T | PP30
CM03-041 |  | - | P01-02 |  | 0 | CM03-041-P01-02 |  |  | ST | 1 | 1000 | 16.6667 | ST-4 | PP30-200T | PP30
CM04-001 |  | - | P01-03 |  | 0 | CM04-001-P01-03 |  |  | ST | 1 | 480 | 8 | ST-3 | PP21-110T | PP21
CM04-001 |  | - | P02-03 |  | 0 | CM04-001-P02-03 |  |  | ST | 1 | 180 | 3 | ST-1 | PP11-035T | PP11
CM04-001 |  | - | P03-03 |  | 0 | CM04-001-P03-03 |  |  | ST | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CM06-007 |  | - | P01-04 |  | 0 | CM06-007-P01-04 |  |  | ST | 1 | 2100 | 35 | ST-1 | PP02-060T | PP02 | PP14 | PP12 | [6 empty] | SHARE DIE V CM06-011
CM10-008 |  | - | P01-01 |  | 0 | CM10-008-P01-01 |  |  | ST | 1 | 1800 | 30 | ST-1 | PP14-080T | PP14 | PP19 | PP02
CM10-009 |  | - | P01-05 |  | 0 | CM10-009-P01-05 |  |  | S/A | 1 | 1500 | 25 | ST-2 | PP19-110T | PP19
CM10-009 |  | - | P02-05 |  | 0 | CM10-009-P02-05 |  |  | S/A | 1 | 420 | 7 | AL | TP09 | TP09
CM10-009 |  | - | P03-05 |  | 0 | CM10-009-P03-05 |  |  | S/A | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CM10-009 |  | - | P04-05 |  | 0 | CM10-009-P04-05 |  |  | S/A | 1 | 1200 | 20 | AL | CHECKING | CHECKING
CM10-011 |  | - | P01-05 |  | 0 | CM10-011-P01-05 |  |  | ST | 1 | 112 | 1.8667 | SM | SM01 | SM01
CM10-011 |  | - | P02-05 |  | 0 | CM10-011-P02-05 |  |  | ST | 1 | 480 | 8 | ST-1 | PP03-060T | PP03 | PP04 | PP13
CM10-011 |  | - | P03-05 |  | 0 | CM10-011-P03-05 |  |  | ST | 1 | 360 | 6 | ST-1 | PP13-060T | PP13 | PP10
CM10-011 |  | - | P04-05 |  | 0 | CM10-011-P04-05 |  |  | ST | 1 | 360 | 6 | ST-1 | PP03-060T | PP03 | PP04
CM10-012 | GC02-016 | - | P01-04 |  | 0 | CM10-012-P01-04 |  |  | S/A | 1 | 720 | 12 | ST-3 | PP13-060T | PP13 | PP15 | PP03 | PP05 | PP04 | PP22 | PP12 | PP21 | PP02
CM10-012 | GC02-016 | - | P02-04 |  | 0 | CM10-012-P02-04 |  |  | S/A | 1 | 420 | 7 | AL | TP06 | TP06 | TP02
CM10-013 | GC02-017 | - | P01-04 |  | 0 | CM10-013-P01-04 |  | SLITTING | ST | 1 | 47520 | 792 | SM | SM01 | SM01
CM10-013 | GC02-017 | - | P02-04 |  | 0 | CM10-013-P02-04 |  | BLANKING | ST | 1 | 900 | 15 | ST-3 | PP11-035T | PP22 | PP11 | PP03 | PP04
CM10-013 | GC02-017 | - | P03-04 |  | 0 | CM10-013-P03-04 |  | BENDING | ST | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CM10-013 | GC02-017 | - | P04-04 | [5 empty] | ST | 1 | STORE | STORE | #N/A | #N/A
CM10-015 |  | - | P01-02 |  | 0 | CM10-015-P01-02 |  |  | FM | 1 | 3000 | 50 | FM | FM03 | FM01 | FM03
CM18-001 |  | - | P01-06 |  | 0 | CM18-001-P01-06 |  |  | WN | 2 | 150 | 2.5 | WN | SW13 | SW03 | SW05 | SW13 | SW04
CM18-001 | BENDING | - | P02-06 |  | 0 | CM18-001-P02-06 |  |  | WN | 1 | 420 | 7 | WN | PP23 | PP22 | PP23
CM18-001 |  | - | P03-06 |  | 0 | CM18-001-P03-06 |  |  | WN | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CM18-001 |  | - | P04-06 |  | 0 | CM18-001-P04-06 |  |  | WN | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CM18-001 |  | - | P05-06 |  | 0 | CM18-001-P05-06 |  |  | WN | 1 | 450 | 7.5 | WN | TW01 | TW01 | [8 empty] | FROM 29.07.24 450PCS/HR INSTEAD OF 360 PCS.HR
CM18-001A |  | - | P01-02 |  | 0 | CM18-001A-P01-02 |  |  | WN | 1 | 2160 | 36 | WN | WS01 | WS01
CM18-001B |  | - | P01-02 |  | 0 | CM18-001B-P01-02 |  |  | FM | 1 | 1260 | 21 | FM | FM03 | FM03 | FM01 | [7 empty] | Almost same cam die with CP20-001A,CP20-002A | SETTING 3 HOUR | LU METAL MATERIAL EASILY RUST,ONCE MATERIAL COME, NEED RUN IN BETWEEN 2 DAY
CM18-001C |  | - | P01-02 |  | 0 | CM18-001C-P01-02 |  |  | WN | 1 | 2400 | 40 | WN | WS01 | WS01
CO02-001 |  | - | P01-05 |  | 0 | CO02-001-P01-05 |  | SLITTING | ST | 1 | 7680 | 128 | SM | SM01 | SM01
CO02-001 |  | - | P02-05 |  | 0 | CO02-001-P02-05 |  | BLANKING | ST | 1 | 960 | 16 | ST-1 | PP03-060T | PP03 | PP13 | PP10 | PP05 | PP2 ONLY RUN THIS,BECAUSE PP13 BREAK DOWN | PP04 |  |  |  | SHARE DIE V CO02-002-P01,CO02-003-P01 | NO RUN FOR ONE PIECE FLOW
CO02-001 |  | - | P03-05 |  | 0 | CO02-001-P03-05 |  |  | ST | 1 | 300 | 5 | ST-1 | PP04-060T | PP04 | PP05 | PP22 | PP15 | PP13 | PP03
CO02-001 |  | - | P04-05 |  | 0 | CO02-001-P04-05 |  |  | ST | 1 | 300 | 5 | ST-3 | PP10-080T | PP22 | PP04 | PP05 | PP10
CO02-002 | GP01-037 | - | P01-04 |  | 0 | CO02-002-P01-04 |  |  | ST | 1 | 10560 | 176 | SM | SM01 | SM01
CO02-002 | GP01-037 | - | P02-04 |  | 0 | CO02-002-P02-04 |  |  | ST | 1 | 720 | 12 | ST-1 | PP03-060T | PP03 | PP15 | PP10 | PP13 | PP02 | PP04 |  |  |  | SHARE DIE V CO02-001-P01,CO02-003-P01
CO02-002 | GP01-037 | - | P03-04 |  | 0 | CO02-002-P03-04 |  |  | ST | 1 | 360 | 6 | ST-2 | PP01-110T | PP01 | PP26 | PP28 | PP20
CO02-003 | GP01-038 | - | P01-04 |  | 0 | CO02-003-P01-04 |  |  | ST | 1 | 4560 | 76 | SM | SM01 | SM01
CO02-003 | GP01-038 | - | P02-04 |  | 0 | CO02-003-P02-04 |  |  | ST | 1 | 720 | 12 | ST-1 | PP03-060T | PP03 | PP13 | PP10 | PP02 | PP04 |  |  |  |  | SHARE DIE V CO02-001-P01,CO02-002-P01
CO02-003 | GP01-038 | - | P03-04 |  | 0 | CO02-003-P03-04 |  |  | ST | 1 | 450 | 7.5 | ST-4 | PP26-110T | PP26 | PP20 | PP01 | PP09 | [5 empty] | FROM DATE : 29.07.24 (360PCS TO 450 PCS)
CO02-004 |  | - | P01-03 |  | 0 | CO02-004-P01-03 |  |  | ST | 1 | 9360 | 156 | SM | SM01 | SM01
CO02-004 |  | - | P02-03 |  | 0 | CO02-004-P02-03 |  |  | ST | 1 | 300 | 5 | ST-1 | PP05-060T | PP05 | PP22
CO02-004 |  | - | P03-03 |  | 0 | CO02-004-P03-03 |  |  | ST | 1 | 360 | 6 | ST-1 | PP03-060T | PP03 | PP22
CO02-005 |  | - | P01-03 |  | 0 | CO02-005-P01-03 |  |  | ST | 1 | 11040 | 184 | SM | SM01 | SM01
CO02-005 |  | - | P02-03 |  | 0 | CO02-005-P02-03 |  |  | ST | 1 | 300 | 5 | ST-1 | PP05-060T | PP05
CO02-005 |  | - | P03-03 |  | 0 | CO02-005-P03-03 |  |  | ST | 1 | 360 | 6 | ST-1 | PP03-060T | PP03 | PP22
CO02-007 |  | - | P01-04 |  | 0 | CO02-007-P01-04 |  |  | ST | 1 | 9360 | 156 | SM | SM01 | SM01
CO02-007 |  | - | P02-04 |  | 0 | CO02-007-P02-04 |  |  | ST | 1 | 360 | 6 | ST-3 | PP22-060T | PP05 | PP13 | PP05 | PP22
CO02-007 |  | - | P03-04 |  | 0 | CO02-007-P03-04 |  |  | ST | 1 | 360 | 6 | ST-1 | PP05-060T | PP22 | PP04 | PP05 | PP13 | PP22 |  |  |  |  | SHARE DIE V -O02-007-P03-04,O2-008-P03-04,O02-012-P03-04,P08-186-P04-05,CP08-219B-P03-04,CP08-481-P03-04
CO02-008 |  | - | P01-04 |  | 0 | CO02-008-P01-04 |  |  | ST | 1 | 500 | 8.3333 | SM | SM01 | SM01
CO02-008 |  | - | P02-04 |  | 0 | CO02-008-P02-04 |  |  | ST | 1 | 360 | 6 | ST-1 | PP22-060T | PP04 | PP13 | PP05 | PP15 | PP03 | PP22
CO02-008 |  | - | P03-04 |  | 0 | CO02-008-P03-04 |  |  | ST | 1 | 360 | 6 | ST-1 | PP05-060T | PP05 | PP04 | PP13 | PP22 | [5 empty] | SHARE DIE V -O02-007-P03-04,O2-008-P03-04,O02-012-P03-04,P08-186-P04-05,CP08-219B-P03-04,CP08-481-P03-04
CO02-009 |  | - | P01-03 |  | 0 | CO02-009-P01-03 |  |  | ST | 1 | 1274 | 21.2333 | SM | SM01 | SM01 | [8 empty] | SLITTING 2 TIMES
CO02-009 |  | - | P02-03 |  | 0 | CO02-009-P02-03 |  |  | ST | 1 | 240 | 4 | ST-1 | PP10-080T | PP10 | PP21
CO02-010 |  | - | P01-07 |  | 0 | CO02-010-P01-07 |  |  | ST | 1 | 240 | 4 | SM | SM01 | SM01 | [8 empty] | 2 TIMES SLITTING
CO02-010 |  | - | P02-07 |  | 0 | CO02-010-P02-07 |  |  | ST | 1 | 240 | 4 | ST-2 | PP09-160T | PP15 | PP09 | PP19 | [6 empty] | SAME V CO02-022
CO02-010 |  | - | P03-07 |  | 0 | CO02-010-P03-07 |  |  | ST | 1 | 240 | 4 | ST-2 | PP18-150T | PP15 | PP18 | PP18
CO02-010 |  | - | P04-07 |  | 0 | CO02-010-P04-07 |  |  | ST | 1 | 240 | 4 | ST-4 | PP17-110T | PP26 | PP27 | PP17
CO02-010 |  | - | P05-07 |  | 0 | CO02-010-P05-07 |  |  | ST | 1 | 240 | 4 | ST-4 | PP16-110T | PP20 | PP17 | PP16
CO02-010 |  | - | P06-07 |  | 0 | CO02-010-P06-07 |  |  | ST | 1 | 240 | 4 | ST-4 | PP27-110T | PP28 | PP16 | PP27
CO02-011 |  | - | P01-06 |  | 0 | CO02-011-P01-06 |  |  | ST | 1 | 300 | 5 | SM | SM01 | SM01
CO02-011 |  | - | P02-06 |  | 0 | CO02-011-P02-06 |  |  | ST | 1 | 300 | 5 | ST-3 | PP18-150T | PP18 | PP25 | PP24 | PP18 | PP27
CO02-011 |  | - | P03-06 |  | 0 | CO02-011-P03-06 |  |  | ST | 1 | 300 | 5 | ST-3 | PP17-110T | PP17 | PP26 | PP26 | PP17 | PP16
CO02-011 |  | - | P04-06 |  | 0 | CO02-011-P04-06 |  |  | ST | 1 | 300 | 5 | ST-3 | PP16-110T | PP16 | PP20 | PP20 | PP16 | PP17
CO02-011 |  | - | P05-06 |  | 0 | CO02-011-P05-06 |  |  | ST | 1 | 300 | 5 | ST-3 | PP27-110T | PP27 | PP28 | PP28 | PP20 | PP18
CO02-012 |  | - | P01-04 |  | 0 | CO02-012-P01-04 |  |  | ST | 1 | 9360 | 156 | SM | SM01 | SM01
CO02-012 |  | - | P02-04 |  | 0 | CO02-012-P02-04 |  |  | ST | 1 | 480 | 8 | ST-1 | PP22-060T | PP22 | PP02 | PP10 | PP05 | PP04 | PP03
CO02-012 |  | - | P03-04 |  | 0 | CO02-012-P03-04 |  |  | ST | 1 | 360 | 6 | ST-3 | PP05-060T | PP05 | PP03 | PP13 | PP22 | [5 empty] | SHARE DIE V O2-007-P03-04,O02-008-P03-04,O02-012-P03-04,CP08-186-P04-05
CO02-013 |  | - | P01-04 |  | 0 | CO02-013-P01-04 |  |  | ST | 1 | 5040 | 84 | SM | SM01 | SM01
CO02-013 |  | - | P02-04 |  | 0 | CO02-013-P02-04 |  |  | ST | 1 | 360 | 6 | ST-1 | PP22-060T | PP02 | PP22 | PP10 | PP03 | PP15 | PP14 | PP31
CO02-013 |  | - | P03-04 |  | 0 | CO02-013-P03-04 |  |  | ST | 1 | 180 | 3 | ST-1 | PP10-080T | PP10 | PP21 | PP22
CO02-016 | GP01-013 | - | P01-05 |  | 0 | CO02-016-P01-05 |  |  | ST | 1 | 7920 | 132 | SM | SM01 | SM01
CO02-016 | GP01-013 | - | P02-05 |  | 0 | CO02-016-P02-05 |  |  | ST | 1 | 480 | 8 | ST-1 | PP04-060T | PP04 |  | PP15 | PP22 | PP13 | PP02 |  |  |  | 1ST & 2ND PROCESS NEED RUN SAME MACHINE
CO02-016 | GP01-013 | - | P03-05 |  | 0 | CO02-016-P03-05 |  |  | ST | 1 | 360 | 6 | ST-1 | PP04-060T | PP04 | PP14 | PP15 | PP22 | PP13 | PP02 |  |  |  | 1ST & 2ND PROCESS NEED RUN SAME MACHINE
CO02-016 | GP01-013 | - | P04-05 |  | 0 | CO02-016-P04-05 |  |  | ST | 1 | 240 | 4 | ST-1 | PP11-035T | PP13 | PP11 |  | PP06 | PP04
CO02-021 |  | - | P01-06 |  | 0 | CO02-021-P01-06 |  |  | ST | 1 | 240 | 4 | SM | SM01 | SM01
CO02-021 |  | - | P02-06 |  | 0 | CO02-021-P02-06 |  |  | ST | 1 | 240 | 4 | ST-3 | PP27-110T | PP27 | PP09
CO02-021 |  | - | P03-06 |  | 0 | CO02-021-P03-06 |  |  | ST | 1 | 360 | 6 | ST-3 | PP16-110T | PP16 | PP16
CO02-021 |  | - | P04-06 |  | 0 | CO02-021-P04-06 |  |  | ST | 1 | 360 | 6 | ST-3 | PP17-110T | PP17 | PP17
CO02-021 |  | - | P05-06 |  | 0 | CO02-021-P05-06 |  |  | ST | 1 | 360 | 6 | ST-3 | PP18-150T | PP18 | PP18
CO02-022 |  | - | P01-07 |  | 0 | CO02-022-P01-07 |  |  | ST | 1 | 1080 | 18 | SM | SM01 | SM01 | [8 empty] | SLITING 2 TIMES
CO02-022 |  | - | P02-07 |  | 0 | CO02-022-P02-07 |  |  | ST | 1 | 240 | 4 | ST-3 | PP09-160T | PP09 | [8 empty] | SAME V CO02-010
CO02-022 |  | - | P03-07 |  | 0 | CO02-022-P03-07 |  |  | ST | 1 | 240 | 4 | ST-3 | PP18-150T | PP18
CO02-022 |  | - | P04-07 |  | 0 | CO02-022-P04-07 |  |  | ST | 1 | 240 | 4 | ST-3 | PP17-110T | PP17
CO02-022 |  | - | P05-07 |  | 0 | CO02-022-P05-07 |  |  | ST | 1 | 240 | 4 | ST-3 | PP16-110T | PP16
CO02-022 |  | - | P06-07 |  | 0 | CO02-022-P06-07 |  |  | ST | 1 | 240 | 4 | ST-3 | PP27-110T | PP27
CO02-023 |  | - | P01-03 |  | 0 | CO02-023-P01-03 |  |  | ST | 1 | 6120 | 102 | SM | SM01 | SM01
CO02-023 |  | - | P02-03 |  | 0 | CO02-023-P02-03 |  |  | ST | 1 | 600 | 10 | ST-4 | PP28-110T | PP28 | PP19
CP07-042 |  | - | P01-05 |  | 0 | CP07-042-P01-05 |  |  | ST | 1 | 360 | 6 | PP05 | PP05-060T | PP05
CP07-042 |  | - | P02-05 |  | 0 | CP07-042-P02-05 |  |  | ST | 1 | 360 | 6 | PP03 | PP03-060T | PP03 | PP13 | PP02
CP07-042 |  | - | P03-05 |  | 0 | CP07-042-P03-05 |  | GRINDER | ST | 1 | 60 | 1 | M02 | OPT | OPT
CP07-042 |  | - | P04-05 |  | 0 | CP07-042-P04-05 |  |  | ST | 1 | 360 | 6 | PP05 | PP05-060T | PP05 | PP03
CP07-053 |  | - |  |  | 0 | CP07-053- |  |  | ? | 1 |  | 0 | #N/A | #N/A
CP07-053 |  | - |  |  | 0 | CP07-053- |  |  | ? | 1 |  | 0 | #N/A | #N/A
CP07-053 |  | - |  |  | 0 | CP07-053- |  |  | ? | 1 |  | 0 | #N/A | #N/A
CP08-054 |  | - | P01-03 |  | 0 | CP08-054-P01-03 |  |  | ST | 1 | 14400 | 240 | SM | SM01 | SM01
CP08-054 |  | - | P02-03 |  | 0 | CP08-054-P02-03 |  |  | ST | 1 | 420 | 7 | ST-1 | PP03-060T | PP03
CP08-054 |  | - | P03-03 |  | 0 | CP08-054-P03-03 |  |  | ST | 1 | 360 | 6 | ST-1 | PP04-060T | PP04
CP08-039 |  | - | P01 |  | 0 | CP08-039-P01 |  |  | AL | 1 |  | 0 | ST | ASSY | ASSEMBLY
CP07-039B |  | - | P01 |  | 0 | CP07-039B-P01 |  |  | AL | 1 | 60 | 1 | MT | BS01 | BS01
CP07-039B |  | - | P02 |  | 0 | CP07-039B-P02 |  |  | AL | 1 | 170 | 2.8333 | AL | BL04 | BL03 | BL04
CP07-039B |  | - |  |  | 0 | CP07-039B- |  |  | AL | 1 |  | 0 | MT | LM03 | LM03
CP07-054 |  | - | P01-0 |  | 0 | CP07-054-P01-0 |  |  | ST | 1 | 450 | 7.5 | ST-1 | PP03-060T | PP03
CP07-054 |  | - | P02-0 |  | 0 | CP07-054-P02-0 |  |  | ST | 1 | 288 | 4.8 | ST-1 | PP03-060T | PP03
CP07-054 |  | - | P03- |  | 0 | CP07-054-P03- |  |  | ST | 1 |  | 0 | #N/A | #N/A
CP07-054 |  | - | P04 |  | 0 | CP07-054-P04 |  |  | ST | 1 |  | 0 | #N/A | #N/A
CP07-054B |  | - | P01- |  | 0 | CP07-054B-P01- |  |  | AL | 1 | 50 | 0.83333 | MT | BS01 | BS01
CP07-054B |  | - | P02 |  | 0 | CP07-054B-P02 |  |  | AL | 1 | 70 | 1.1667 | AL | BL04 | BL04 | BL03
CP07-054B |  | - | P03- |  | 0 | CP07-054B-P03- |  |  | AL | 1 | 2400 | 40 | ST-2 | SORT | SORTING
CP07-054B |  | - | P04 |  | 0 | CP07-054B-P04 |  |  | AL | 1 | 240 | 4 | #N/A | #N/A
CP07-057 |  | - | P01-04 |  | 0 | CP07-057-P01-04 |  |  | ? | 1 |  | 0 | SM | SM01 | SM01
CP07-057 |  | - | P02-04 |  | 0 | CP07-057-P02-04 |  |  | ? | 1 |  | 0 | ST-1 | PP03-060T | PP03
CP07-057 |  | - | P03-04 |  | 0 | CP07-057-P03-04 |  |  | ? | 1 |  | 0 | MT | DR04 | DR04
CP07-057 |  | - | P04-04 |  | 0 | CP07-057-P04-04 |  |  | ? | 1 |  | 0 | ST-1 | PP05-060T | PP05
CP07-057B |  | - | P01 |  | 0 | CP07-057B-P01 |  |  | AL | 1 | 40 | 0.66667 | MT | BS01 | BS01
CP07-057B |  | - | P02 |  | 0 | CP07-057B-P02 |  |  | AL | 1 | 100 | 1.6667 | AL | GD01 | GD01
CP07-057B |  | - | P03 |  | 0 | CP07-057B-P03 |  |  | AL | 1 | 20 | 0.33333 | AL | BL03 | BL03 | BL04
CP07-057B |  | - | P04 |  | 0 | CP07-057B-P04 |  |  | AL | 1 | 70 | 1.1667 | #N/A | #N/A
CP08-012 | GP01-021 | - | P01-03 |  | 0 | CP08-012-P01-03 |  |  | ST | 1 | 1800 | 30 | ST-1 | PP14-080T | PP12 | PP14 | PP10
CP08-024 |  | - | P01-03 |  | 0 | CP08-024-P01-03 |  |  | ST | 1 | 240 | 4 | SM | SM01 | SM01
CP08-024 |  | - | P02-03 |  | 0 | CP08-024-P02-03 |  |  | ST | 1 | 300 | 5 | ST-1 | PP05-060T | PP05 | PP22
CP08-024 |  | - | P03-03 |  | 0 | CP08-024-P03-03 |  |  | ST | 1 | 180 | 3 | ST-1 | PP05-060T | PP05 | PP13
CP08-025 |  | - | P01-04 |  | 0 | CP08-025-P01-04 |  |  | ST | 1 | 5040 | 84 | SM | SM01 | SM01
CP08-025 |  | - | P02-04 |  | 0 | CP08-025-P02-04 |  |  | ST | 1 | 360 | 6 | ST-1 | PP04-060T | PP04 | PP02
CP08-025 |  | - | P03-04 |  | 0 | CP08-025-P03-04 |  |  | ST | 1 | 270 | 4.5 | ST-1 | PP10-080T | PP10 | PP02 | [7 empty] | THIS PROCESS CAN NOT RUN 60T
CP08-026 |  | - | P01-04 |  | 0 | CP08-026-P01-04 |  |  | ST | 1 | 240 | 4 | SM | SM01 | SM01
CP08-026 |  | - | P02-04 |  | 0 | CP08-026-P02-04 |  |  | ST | 1 | 360 | 6 | ST-1 | PP10-080T | PP10 | PP21 | PP15 | PP13 | PP04
CP08-026 |  | - | P03-04 |  | 0 | CP08-026-P03-04 |  |  | ST | 1 | 180 | 3 | ST-1 | PP03-060T | PP03 | PP17 | PP15 | PP10
CP08-027 |  | - | P01-03 |  | 0 | CP08-027-P01-03 |  |  | ST | 1 | 2640 | 44 | SM | SM01 | SM01
CP08-027 |  | - | P02-03 |  | 0 | CP08-027-P02-03 |  |  | ST | 1 | 420 | 7 | ST-1 | PP04-060T | PP04 | PP13
CP08-027 |  | - | P03-03 |  | 0 | CP08-027-P03-03 |  |  | ST | 1 | 360 | 6 | ST-1 | PP03-060T | PP03 | PP05
CP08-029 |  | - | P01-05 |  | 0 | CP08-029-P01-05 |  |  | ST | 1 | 240 | 4 | ST-3 | PP09-160T | PP09 | PP01 | PP09 | [6 empty] | RUN ON 260822 - P9,P9,P17,P16,P27 - 2 PCS/MIN - 3 OPT | SHARE DIE V CP08-030,CP08-031,CP08-032,CP08-178,CP08-179,CP08-180,CP08-181
CP08-029 |  | - | P02-05 |  | 0 | CP08-029-P02-05 |  |  | ST | 1 | 240 | 4 | ST-3 | PP17-110T | PP17 |  | PP18 | [7 empty] | SHARE DIE V CP08-030,CP08-031,CP08-032,CP08-178,CP08-179,CP08-180,CP08-181
CP08-029 |  | - | P03-05 |  | 0 | CP08-029-P03-05 |  |  | ST | 1 | 240 | 4 | ST-3 | PP16-110T | PP16 |  | PP16 | [7 empty] | SHARE DIE V CP08-030,CP08-031,CP08-032,CP08-178,CP08-179,CP08-180,CP08-181
CP08-029 |  | - | P04-05 |  | 0 | CP08-029-P04-05 |  |  | ST | 1 | 240 | 4 | ST-3 | PP27-110T | PP27 |  | PP27 | [7 empty] | SHARE DIE V CP08-030,CP08-031,CP08-032,CP08-178,CP08-179,CP08-180,CP08-181
CP08-029 |  | - | P05-05 |  | 0 | CP08-029-P05-05 |  |  | ST | 1 | 240 | 4 | ST-3 | STORE | [10 empty] | SHARE DIE V CP08-030,CP08-031,CP08-032,CP08-178,CP08-179,CP08-180,CP08-181
CP08-030 |  | - | P01-03 |  | 0 | CP08-030-P01-03 |  |  | ST | 1 | 300 | 5 | ST-3 | PP09-160T | PP09 |  | PP09 | [6 empty] | SHARE DIE V CP08-029,CP08-031,CP08-032,CP08-178,CP08-179,CP08-180,CP08-181
CP08-030 |  | - | P02-03 |  | 0 | CP08-030-P02-03 |  |  | ST | 1 | 300 | 5 | ST-3 | PP16-110T | PP16 | PP18 | PP17 | [6 empty] | SHARE DIE V CP08-029,CP08-031,CP08-032,CP08-178,CP08-179,CP08-180,CP08-181
CP08-030 |  | - | P03-03 |  | 0 | CP08-030-P03-03 |  |  | WH | 1 | 300 | 5 | ST-3 | STORE |  | PP21 | [7 empty] | SHARE DIE V CP08-029,CP08-031,CP08-032,CP08-178,CP08-179,CP08-180,CP08-181
CP08-031 |  | - | P01-04 |  | 0 | CP08-031-P01-04 |  |  | ST | 1 | 240 | 4 | ST-3 | PP09-160T | PP09 | PP01 | PP09 | [6 empty] | SHARE DIE V CP08-029,CP08-030,CP08-032,CP08-178,CP08-179,CP08-180,CP08-181
CP08-031 |  | - |  |  | 0 |  |  |  | ST | 1 | 240 | 4 | ST-3 | [10 empty] | SHARE DIE V CP08-029,CP08-030,CP08-032,CP08-178,CP08-179,CP08-180,CP08-181
CP08-031 |  | - | P02-04 |  | 0 | CP08-031-P02-04 |  |  | ST | 1 | 240 | 4 | ST-3 | PP16-110T | PP16 | PP16 | PP17 | [6 empty] | SHARE DIE V CP08-029,CP08-030,CP08-032,CP08-178,CP08-179,CP08-180,CP08-181
CP08-031 |  |  | P03-04 |  |  | CP08-031-P03-04 |  |  | ST | 1 | 240 | 4 | ST-3 | PP27-110T | PP27 | PP27 | PP27
CP08-032 |  | - | P01-03 |  | 0 | CP08-032-P01-03 |  |  | ST | 1 | 300 | 5 | ST-3 | PP09-160T | PP09 | [8 empty] | SHARE DIE V CP08-029,CP08-030,CP08-031,CP08-032,CP08-178,CP08-179,CP08-180,CP08-181
CP08-032 |  | - | P02-03 |  | 0 | CP08-032-P02-03 |  |  | ST | 1 | 300 | 5 | ST-3 | PP16-110T | PP16 | PP21 | [7 empty] | SHARE DIE V CP08-029,CP08-030,CP08-031,CP08-032,CP08-178,CP08-179,CP08-180,CP08-181
CP08-035 |  | - | P01-04 |  | 0 | CP08-035-P01-04 |  |  | ST | 1 | 240 | 4 | SM | SM01 | SM01
CP08-035 |  | - | P02-04 |  | 0 | CP08-035-P02-04 |  |  | ST | 1 | 240 | 4 | ST-3 | PP09-160T | PP09
CP08-035 |  | - | P03-04 |  | 0 | CP08-035-P03-04 |  |  | ST | 1 | 240 | 4 | ST-3 | PP18-150T | PP18
CP08-035 |  | - | P04-04 |  | 0 | CP08-035-P04-04 |  |  | ST | 1 | 240 | 4 | ST-3 | PP16-110T | PP16
CP08-036 |  | - | P01-04 |  | 0 | CP08-036-P01-04 |  |  | ST | 1 | 7920 | 132 | SM | SM01 | SM01
CP08-036 |  | - | P02-04 |  | 0 | CP08-036-P02-04 |  |  | ST | 1 | 480 | 8 | ST-1 | PP10-080T | PP03 | PP15 | PP04 | PP22 | PP10
CP08-036 |  | - | P03-04 |  | 0 | CP08-036-P03-04 |  |  | ST | 1 | 360 | 6 | ST-1 | PP10-080T | PP10 | PP05 | PP12 | [6 empty] | SHARE DIE V CP08-037-P03-04,CP08-038-P03-04
CP08-037 |  | - | P01-04 |  | 0 | CP08-037-P01-04 |  |  | ST | 1 | 11520 | 192 | SM | SM01 | SM01
CP08-037 |  | - | P02-04 |  | 0 | CP08-037-P02-04 |  |  | ST | 1 | 480 | 8 | ST-1 | PP02-060T | PP10 | PP22 | PP15 | PP05 | PP19 | PP02 | PP12 | PP03
CP08-037 |  | - | P03-04 |  | 0 | CP08-037-P03-04 |  |  | ST | 1 | 360 | 6 | ST-1 | PP05-060T | PP10 | PP03 | PP05 | PP12 | [5 empty] | SHARE DIE V CP08-036-P03-04,CP08-038-P03-04
CP08-038 |  | - | P01-04 |  | 0 | CP08-038-P01-04 |  |  | ST | 1 | 14760 | 246 | SM | SM01 | SM01
CP08-038 |  | - | P02-04 |  | 0 | CP08-038-P02-04 |  |  | ST | 1 | 480 | 8 | ST-1 | PP03-060T | PP03 | PP22 | PP04
CP08-038 |  | - | P03-04 |  | 0 | CP08-038-P03-04 |  |  | ST | 1 | 360 | 6 | ST-1 | PP10-080T | PP10 | PP05 | [7 empty] | CP08-036-P03-04,CP08-037-P03-04
CP08-046 | GP01-006 | - | P01-04 |  | 0 | CP08-046-P01-04 |  |  | ST | 1 | 2100 | 35 | ST-1 | PP10-080T | PP10 | PP19 | PP14 | PP03 | PP02
CP08-046 | GP01-006 | - | P02-04 |  | 0 | CP08-046-P02-04 |  |  | ST | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CP08-046 | GP01-006 | - | P03-04 |  | 0 | CP08-046-P03-04 |  |  | ST | 1 | 1800 | 30 | AL | CHECKING | CHECKING
CP08-052 |  | - | P01-03 |  | 0 | CP08-052-P01-03 |  |  | ST | 1 | 12960 | 216 | SM | SM01 | SM01
CP08-052 |  | - | P02-03 |  | 0 | CP08-052-P02-03 |  |  | ST | 1 | 600 | 10 | ST-2 | PP15-080T | PP15 | PP04 | PP10 | PP05 | PP13 | PP03
CP08-053 |  | - | P01-03 |  | 0 | CP08-053-P01-03 |  |  | ST | 1 | 21960 | 366 | SM | SM01 | SM01
CP08-053 |  | - | P02-03 |  | 0 | CP08-053-P02-03 |  |  | ST | 1 | 600 | 10 | ST-1 | PP03-060T | PP13 | PP05 | PP22 | PP15 | PP12 | PP03
CP08-054 |  | - | P01-03 |  | 0 | CP08-054-P01-03 |  |  | ST | 1 | 14400 | 240 | #N/A | #N/A
CP08-054 |  | - | P02-03 |  | 0 | CP08-054-P02-03 |  |  | ST | 1 | 420 | 7 | #N/A | #N/A
CP08-054 |  | - | P03-03 |  | 0 | CP08-054-P03-03 |  |  | ST | 1 | 360 | 6 | #N/A | #N/A
CP08-055 |  | - | P01-03 |  | 0 | CP08-055-P01-03 |  |  | ST | 1 | 10800 | 180 | SM | SM01 | SM01
CP08-055 |  | - | P02-03 |  | 0 | CP08-055-P02-03 |  |  | ST | 1 | 420 | 7 | ST-2 | PP15-080T | PP15
CP08-055 |  | - | P03-03 |  | 0 | CP08-055-P03-03 |  |  | ST | 1 | 360 | 6 | ST-2 | PP15-080T | PP15
CP08-056 |  | - | P01-06 |  | 0 | CP08-056-P01-06 |  |  | ST | 1 | 420 | 7 | ST-4 | PP09-160T | PP24 | PP09
CP08-056 |  | - | P02-06 |  | 0 | CP08-056-P02-06 |  |  | ST | 1 | 420 | 7 | ST-4 | PP18-150T | PP25 | PP18
CP08-056 |  | - | P03-06 |  | 0 | CP08-056-P03-06 |  |  | ST | 1 | 420 | 7 | ST-4 | PP17-110T | PP26 | PP17 | PP21
CP08-056 |  | - | P04-06 |  | 0 | CP08-056-P04-06 |  |  | ST | 1 | 420 | 7 | ST-4 | PP16-110T | PP20 | PP16 | PP17
CP08-056 |  | - | P05-06 |  | 0 | CP08-056-P05-06 |  |  | ST | 1 | 420 | 7 | ST-4 | PP27-110T | PP28 | PP27 | PP16
CP08-068 |  | - | P01-02 |  | 0 | CP08-068-P01-02 |  |  | FM | 1 | 1800 | 30 | FM | FM01 | FM03 | FM01 | [7 empty] | Almost same cam die with CP08-082,CP08-071
CP08-071 |  | - | P01-03 |  | 0 | CP08-071-P01-03 |  |  | ST | 1 | 1200 | 20 | ST-1 | FM03 | FM03 | PP11 | PP06 | PP02 | [5 empty] | EFF FROM 08.06.23 CHANGE RUN TO FORMING MACHINE, 1 PROCESS ONLY
CP08-071 |  | - | P02-03 |  | 0 |  |  |  | ST | 1 | 180 | 3 | ST-1 |  | PP11 | PP06 | [7 empty] | SAME CAM WITH CP08-068,CP08-082
CP08-079 |  | - | P01-02 |  | 0 | CP08-079-P01-02 |  |  | ST | 1 | 3000 | 50 | ST-3 | PP01-110T | PP01 | PP09 | PP30 | [6 empty] | SHARE DIE V CP08-520,CP08-575
CP08-080 |  | - | P01-02 |  | 0 | CP08-080-P01-02 |  |  | ST | 1 | 3000 | 50 | ST-2 | PP01-110T | PP01 | PP09 | PP30 | [6 empty] | SHARE DIE V CP08-519,CP08-518
CP08-082 | GP01-026 | - | P01-02 |  | 0 | CP08-082-P01-02 |  |  | FM | 1 | 1800 | 30 | FM | FM01 | FM01 | FM03 | [7 empty] | Almost same cam die with CP08-068,CP08-071 | SETTING TIME AROUND 4 HOURS
CP08-085 |  | - | P01-02 |  | 0 | CP08-085-P01-02 |  |  | ST | 2 | 90 | 1.5 | ST-3 | SW01 | SW01 | SW04 | SW09
CP08-085A |  | - | P01-04 |  | 0 | CP08-085A-P01-04 |  |  | S/T | 1 | 90 | 1.5 | ST-3 | PP32 | PP09 | PP32
CP08-085A |  | - | P02-04 |  | 0 | CP08-085A-P02-04 |  |  | S/T | 1 | 90 | 1.5 | ST-3 | TP07 | TP07
CP08-085A |  | - | P03-04 |  | 0 | CP08-085A-P03-04 |  |  | S/T | 1 | 90 | 1.5 | TR | PB07 | PB01 | PB05 | PB07
CP08-086 |  | - | P01-02 |  | 0 | CP08-086-P01-02 |  |  | ST | 2 | 90 | 1.5 | ST-3 | SW01 | SW01 | SW04 | SW09
CP08-086A |  | - | P01-04 |  | 0 | CP08-086A-P01-04 |  |  | S/T | 1 | 90 | 1.5 | ST-3 | PP32 | PP09 | PP32
CP08-086A |  | - | P02-04 |  | 0 | CP08-086A-P02-04 |  |  | S/T | 1 | 90 | 1.5 | ST-3 | TP07 | TP07
CP08-086A |  | - | P03-04 |  | 0 | CP08-086A-P03-04 |  |  | S/T | 1 | 90 | 1.5 | TR | PB07 | PB01 | PB05 | PB07
CP08-087 | GP01-027 | - | P01-04 |  | 0 | CP08-087-P01-04 |  |  | ST | 1 | 600 | 10 | ST-1 | PP10-080T | PP10 | PP19 | PP21 | PP12
CP08-087 |  | - | P02-04 |  | 0 | CP08-087-P02-04 |  |  | ST | 1 | 300 | 5 | ST-3 | PP21-110T | PP04 | PP21 | PP10 | PP14 | PP15
CP08-087 |  | - | P03-04 |  | 0 | CP08-087-P03-04 |  |  | ST | 1 | 120 | 2 | ST-3 | TP09 | TP03 | TP09 | [7 empty] | EFF- 120722
CP08-102 |  | - | P01-02 |  | 0 | CP08-102-P01-02 |  |  | ST | 1 | 1800 | 30 | ST-2 | PP01-110T | PP01 | PP32 | PP24 | PP30
CP08-145 |  | - | P01-06 |  | 0 | CP08-145-P01-06 |  |  | ST | 1 | 300 | 5 | ST-3 | PP09-160T | PP09 | PP21
CP08-145 |  | - | P02-06 |  | 0 | CP08-145-P02-06 |  |  | ST | 1 | 300 | 5 | ST-3 | PP18-150T | PP18
CP08-145 |  | - | P03-06 |  | 0 | CP08-145-P03-06 |  |  | ST | 1 | 300 | 5 | ST-3 | PP17-110T | PP17
CP08-145 |  | - | P04-06 |  | 0 | CP08-145-P04-06 |  |  | ST | 1 | 300 | 5 | ST-3 | PP16-110T | PP16
CP08-145 |  | - | P05-06 |  | 0 | CP08-145-P05-06 |  |  | ST | 1 | 300 | 5 | ST-3 | PP27-110T | PP27
CP08-146 |  | - | P01-04 |  | 0 | CP08-146-P01-04 |  |  | ST | 1 | 1500 | 25 | ST-1 | PP06 | PP02 | PP06 | PP05
CP08-146 |  | - | P02-04 |  | 0 | CP08-146-P02-04 |  |  | ST | 1 | 360 | 6 | ST-1 | PP13-060T | PP13 | PP04 | PP22 | PP11 | PP06
CP08-146 |  | - | P03-04 |  | 0 | CP08-146-P03-04 |  |  | ST | 1 | 240 | 4 | ST-1 | PP11-035T | PP11 | PP06 | [7 empty] | NEED OLD OPERATOR,MORE SKILL
CP08-150 |  | - | P01-04 |  | 0 | CP08-150-P01-04 |  |  | ST | 1 | 240 | 4 | SM | SM01 | SM01
CP08-150 |  | - | P02-04 |  | 0 | CP08-150-P02-04 |  |  | ST | 1 | 480 | 8 | ST-1 | PP05-060T | PP05 | PP21 | PP04 | PP02 | PP15
CP08-150 |  | - | P03-04 |  | 0 | CP08-150-P03-04 |  |  | ST | 1 | 240 | 4 | ST-1 | PP10-080T | PP10 | PP21 | PP12
CP08-152 |  | - | P01-05 |  | 0 | CP08-152-P01-05 |  |  | ST | 1 | 3120 | 52 | SM | SM01 | SM01
CP08-152 |  | - | P02-05 |  | 0 | CP08-152-P02-05 |  |  | ST | 1 | 360 | 6 | ST-3 | PP28-110T | PP21 | PP01 | PP17 | PP25 | PP28
CP08-152 |  | - | P03-05 |  | 0 | CP08-152-P03-05 |  |  | ST | 1 | 360 | 6 | ST-4 | PP20-110T | PP20 | PP18 | PP20 |  | PP25 |  |  |  |  | SHARE DIE V CP08-153
CP08-152 |  | - | P04-05 |  | 0 | CP08-152-P04-05 |  |  | ST | 1 | 360 | 6 | ST-4 | PP26-110T | PP26 | PP09 | PP26 |  | PP26 |  |  |  |  | SHARE DIE V CP08-153
CP08-153 |  | - | P01-05 |  | 0 | CP08-153-P01-05 |  |  | ST | 1 | 360 | 6 | SM | SM01 | SM01
CP08-153 |  | - | P02-05 |  | 0 | CP08-153-P02-05 |  |  | ST | 1 | 480 | 8 | ST-4 | PP25-160T | PP25 | PP26 | PP09
CP08-153 |  | - | P03-05 |  | 0 | CP08-153-P03-05 |  |  | ST | 1 | 480 | 8 | ST-4 | PP20-110T | PP20 |  | PP18 | [6 empty] | SHARE DIE V CP08-152
CP08-153 |  | - | P04-05 |  | 0 | CP08-153-P04-05 |  |  | ST | 1 | 480 | 8 | ST-4 | PP26-110T | PP26 |  | PP26 | [6 empty] | SHARE DIE V CP08-152
CP08-154 |  | - | P01-04 |  | 0 | CP08-154-P01-04 |  |  | ST | 1 | 12600 | 210 | SM | SM01 | SM01
CP08-154 |  | - | P02-04 |  | 0 | CP08-154-P02-04 |  |  | ST | 1 | 360 | 6 | ST-4 | PP16-110T | PP20 | PP28 | PP20 | PP26 | PP28 | PP17 | PP16 | PP17 | PP15 | SHARE DIE V CP08-155
CP08-154 |  | - | P03-04 |  | 0 | CP08-154-P03-04 |  |  | ST | 1 | 180 | 3 | ST-4 | PP17-110T | PP28 | PP21 | PP26 |  | PP26 | PP21 | PP27 | PP18 | PP21 | SHARE DIE V CP08-155
CP08-155 |  | - | P01-04 |  | 0 | CP08-155-P01-04 |  |  | ST | 1 | 600 | 10 | SM | SM01 | SM01
CP08-155 |  | - | P02-04 |  | 0 | CP08-155-P02-04 |  |  | ST | 1 | 360 | 6 | ST-3 | PP16-110T | PP21 | PP20 | PP25 | PP26 | PP18 | PP16 | PP17 | PP20 | PP17 | PP16 | SHARE DIE V CP08-154
CP08-155 |  | - | P03-04 |  | 0 | CP08-155-P03-04 |  |  | ST | 1 | 180 | 3 | ST-4 | PP17-110T | PP28 | PP15 |  | PP26 | PP27 | PP17 | PP27 | PP20 | PP21 | PP27 | SHARE DIE V CP08-154
CP08-158 |  | - | P01-06 |  | 0 | CP08-158-P01-06 |  |  | ST | 1 | 240 | 4 | ST-3 | PP09-160T | PP18 | PP09 | PP09
CP08-158 |  | - | P02-06 |  | 0 | CP08-158-P02-06 |  |  | ST | 1 | 240 | 4 | ST-3 | PP18-150T | PP21 | PP18 | PP18
CP08-158 |  | - | P03-06 |  | 0 | CP08-158-P03-06 |  |  | ST | 1 | 240 | 4 | ST-3 | PP17-110T | PP17 | PP17 | PP21
CP08-158 |  | - | P04-06 |  | 0 | CP08-158-P04-06 |  |  | ST | 1 | 240 | 4 | ST-3 | PP16-110T | PP16 | PP16 | PP16
CP08-158 |  | - | P05-06 |  | 0 | CP08-158-P05-06 |  |  | ST | 2 | 240 | 4 | ST-3 | PP27-110T | PP27 | PP27 | PP27
CP08-178 |  | - | P01-05 |  | 0 | CP08-178-P01-05 |  |  | ST | 1 | 240 | 4 | ST-3 | PP09-160T | PP09 | PP01 | PP09 | [6 empty] | SHARE DIE V CP08-029,CP08-030,CP08-031,CP08-179,CP08-180,CP08-181
CP08-178 |  | - | P02-05 |  | 0 | CP08-178-P02-05 |  |  | ST | 1 | 240 | 4 | ST-3 | PP18-150T | PP18 |  | PP17 | [6 empty] | SHARE DIE V CP08-029,CP08-030,CP08-031,CP08-179,CP08-180,CP08-181
CP08-178 |  | - | P03-05 |  | 0 | CP08-178-P03-05 |  |  | ST | 1 | 240 | 4 | ST-3 | PP16-110T | PP16 | PP17 | PP16 | [6 empty] | SHARE DIE V CP08-029,CP08-030,CP08-031,CP08-179,CP08-180,CP08-181
CP08-178 |  | - | P04-05 |  | 0 | CP08-178-P04-05 |  |  | ST | 1 | 240 | 4 | ST-3 | PP27-110T | PP27 |  | PP27
CP08-179 |  | - | P01-03 |  | 0 | CP08-179-P01-03 |  |  | ST | 1 | 200 | 3.3333 | ST-3 | PP09-160T | PP09 | PP18 | [7 empty] | SHARE DIE V CP08-029,CP08-030,CP08-031,CP08-180,CP08-181
CP08-179 |  | - | P02-03 |  | 0 | CP08-179-P02-03 |  |  | ST | 1 | 200 | 3.3333 | ST-3 | PP16-110T | PP16 | PP21 | [7 empty] | SHARE DIE V CP08-029,CP08-030,CP08-031,CP08-180,CP08-181
CP08-180 |  | - | P01-04 |  | 0 | CP08-180-P01-04 |  |  | ST | 1 | 220 | 3.6667 | ST-3 | PP09-160T | PP09 | [8 empty] | SHARE DIE V CP08-029,CP08-030,CP08-031,CCP08-032,P08-181
CP08-180 |  | - | P02-04 |  | 0 | CP08-180-P02-04 |  |  | ST | 1 | 220 | 3.6667 | ST-3 | PP16-110T | PP16 | [8 empty] | SHARE DIE V CP08-029,CP08-030,CP08-031,CP08-032CP08-181
CP08-180 |  | - | P03-04 |  | 0 | CP08-180-P03-04 |  |  | ST | 1 | 220 | 3.6667 | ST-3 | PP27-110T | PP27
CP08-181 |  | - | P01-03 |  | 0 | CP08-181-P01-03 |  |  | ST | 1 | 240 | 4 | ST-3 | PP09-160T | PP09 | PP01 | [7 empty] | SHARE DIE V CP08-029,CP08-030,CP08-031,CP08-032CP08-180
CP08-181 |  | - | P02-03 |  | 0 | CP08-181-P02-03 |  |  | ST | 1 | 240 | 4 | ST-3 | PP16-110T | PP16 | PP18 | [7 empty] | SHARE DIE V CP08-029,CP08-030,CP08-031,CP08-032,CP08-180
CP08-184 |  | - | P01-01 |  | 0 | CP08-184-P01-01 |  |  | TR | 1 | 200 | 3.3333 | TR | TM03 | TM03 | TM05 | TM06
CP08-184 |  | - | P01-03 |  | 0 | CP08-184-P01-03 |  |  | ST | 1 | 240 | 4 | SM | SM01 | SM01
CP08-184 |  | - | P02-03 |  | 0 | CP08-184-P02-03 |  |  | ST | 1 | 480 | 8 | ST-2 | PP15-080T | PP15 | PP03 | PP13
CP08-185 |  | - | P01-02 |  | 0 | CP08-185-P01-02 |  |  | ST | 2 | 90 | 1.5 | ST-3 | SW01 | SW01 | SW04 | SW09
CP08-185A |  | - | P01-04 |  | 0 | CP08-185A-P01-04 |  |  | S/T | 1 | 90 | 1.5 | ST-3 | PP32 | PP09 | PP32
CP08-185A |  | - | P02-04 |  | 0 | CP08-185A-P02-04 |  |  | S/T | 1 | 90 | 1.5 | ST-3 | TP07 | TP07
CP08-185A |  | - | P03-04 |  | 0 | CP08-185A-P03-04 |  |  | S/T | 1 | 90 | 1.5 | TR | PB07 | PB07 | PB01 | PB05
CP08-186 |  | - | P01-05 |  | 0 | CP08-186-P01-05 |  |  | ST | 1 | 2160 | 36 | SM | SM01 | SM01
CP08-186 |  | - | P02-05 |  | 0 | CP08-186-P02-05 |  |  | ST | 1 | 360 | 6 | ST-1 | PP15-080T | PP05 | PP03 | PP02 | PP21 | PP19 | PP13 | PP15 | PP22 |  | SHARE DIE V CP08-437-P02-05
CP08-186 |  | - | P03-05 |  | 0 | CP08-186-P03-05 |  |  | ST | 1 | 360 | 6 | ST-3 | PP22-060T | PP22 | PP02 | PP10 | PP05 | PP15 | PP19
CP08-186 |  | - | P04-05 |  | 0 | CP08-186-P04-05 |  |  | ST | 1 | 420 | 7 | ST-1 | PP05-060T | PP05 | PP22 | PP03 | PP06 | PP04 | PP15 |  |  |  | SHARE DIE V -O02-007-P03-04,O2-008-P03-04,O02-012-P03-04,P08-186-P04-05,CP08-219B-P03-04,CP08-481-P03-04
CP08-190C |  | - | P01-07 |  | 0 | CP08-190C-P01-07 |  |  | T/S | 1 | 15 | 0.25 | #N/A | TM06 | TM06 | TM03 | TM05
CP08-190C |  | - | P02-07 |  | 0 | CP08-190C-P02-07 |  |  | T/S | 1 | 240 | 4 | #N/A | PB03 | PB03 | PB02 | PB08
CP08-190C |  | - | P03-07 |  | 0 | CP08-190C-P03-07 |  |  | T/S | 1 | 120 | 2 | #N/A | PB01 | PB01
CP08-190C |  | - | P04-07 |  | 0 | CP08-190C-P04-07 |  |  | T/S | 1 | 120 | 2 | #N/A | PB01 | PB01
CP08-190C |  | - | P05-07 |  | 0 | CP08-190C-P05-07 |  |  | T/S | 1 | 120 | 2 | #N/A | PB03 | PB03 | PB02 | PB08
CP08-190C |  | - | P06-07 |  | 0 | CP08-190C-P06-07 |  |  | T/S | 1 | 60 | 1 | #N/A | SW09 | SW09 | SW01
CP08-195 |  | - | P01-04 |  | 0 | CP08-195-P01-04 |  |  | TR | 1 | 240 | 4 | SM | SM01 | SM01
CP08-195 |  | - | P02-04 |  | 0 | CP08-195-P02-04 |  |  | TR | 1 | 43 | 0.71667 | TR | TM05 | TM03 | TM05 | TM06
CP08-195 |  | - | P03-04 |  | 0 | CP08-195-P03-04 |  |  | TR | 1 | 120 | 2 | TR | PB02 | PB02 | PB07 | PB05 | [6 empty] | RUN PB2-090622
CP08-196 |  | - | P01-05 |  | 0 | CP08-196-P01-05 |  |  | ST | 1 | 2400 | 40 | SM | SM01 | SM01
CP08-196 |  | - | P02-05 |  | 0 | CP08-196-P02-05 |  |  | ST | 1 | 360 | 6 | ST-2 | PP01-110T | PP01 | PP26 |  | PP24 | PP01
CP08-196 |  | - | P03-05 |  | 0 | CP08-196-P03-05 |  |  | ST | 1 | 360 | 6 | ST-4 | PP25-160T | PP25 | PP26 | PP01 | PP20 | PP25
CP08-196 |  | - | P04-05 |  | 0 | CP08-196-P04-05 |  |  | ST | 1 | 360 | 6 | ST-4 | PP20-110T | PP20 |  | PP01 | PP28 | PP26
CP08-198 |  | - | P01-07 |  | 0 | CP08-198-P01-07 |  |  | ST | 1 | 240 | 4 | SM | SM01 | SM01
CP08-198 |  | - | P02-07 |  | 0 | CP08-198-P02-07 |  |  | ST | 1 | 240 | 4 | ST-4 | PP24-160T | PP20 | PP24 | PP25
CP08-198 |  | - | P03-07 |  | 0 | CP08-198-P03-07 |  |  | ST | 1 | 240 | 4 | ST-4 | PP25-160T | PP25 |  | PP26
CP08-198 |  | - | P04-07 |  | 0 | CP08-198-P04-07 |  |  | ST | 1 | 240 | 4 | ST-4 | PP20-110T | PP25 | PP20 | PP20
CP08-198 |  | - | P05-07 |  | 0 | CP08-198-P05-07 |  |  | ST | 1 | 240 | 4 | ST-4 | PP28-110T | PP20 | PP28 | PP28
CP08-198 |  | - | P06-07 |  | 0 | CP08-198-P06-07 |  |  | ST | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CP08-198 |  | - | P07-07 |  | 0 | CP08-198-P07-07 |  |  | ST | 1 | STORE | STORE | #N/A | #N/A
CP08-213 |  | - | P01-04 |  | 0 | CP08-213-P01-04 |  |  | TR | 1 | 240 | 4 | SM | SM01 | SM01
CP08-213 |  | - | P02-04 |  | 0 | CP08-213-P02-04 |  |  | TR | 1 | 64 | 1.0667 | TR | TM06 | TM06
CP08-213 |  | - | P03-04 |  | 0 | CP08-213-P03-04 |  |  | TR | 1 | 50 | 0.83333 | TR | PB01 | PB01 | PB04 | PB07 | [6 empty] | PB4 - 180722 | PB7-RUN 170822
CP08-216 |  | - | P01-05 |  | 0 | CP08-216-P01-05 |  |  | ST | 1 | 20 | 0.33333 | ST-3 | SW01 | SW01
CP08-216 |  | - | P02-05 |  | 0 | CP08-216-P02-05 |  |  | ST | 1 | 40 | 0.66667 | ST-3 | SW01 | SW01
CP08-216 |  | - | P03-05 |  | 0 | CP08-216-P03-05 |  |  | ST | 1 | 30 | 0.5 | TR | CLEAN | CLEANING
CP08-216 |  | - | P04-05 |  | 0 | CP08-216-P04-05 |  |  | ST | 1 | 30 | 0.5 | TR | CLEAN | CLEANING
CP08-216 |  | - | P05-05 |  | 0 | CP08-216-P05-05 |  |  | ST | 1 | 30 | 0.5 | ST-1 | PAINTING | PAINTING
CP08-216A |  | - | P01-07 |  | 0 | CP08-216A-P01-07 |  |  | TR | 1 | 60 | 1 | TR | TM02 | TM02 | TM03
CP08-216A |  | - | P02-07 |  | 0 | CP08-216A-P02-07 |  |  | TR | 1 | 30 | 0.5 | ST-2 | MANUAL WORK | OPERATOR
CP08-216A |  | - | P03-07 |  | 0 | CP08-216A-P03-07 |  |  | TR | 1 | 108 | 1.8 | AL | TP02 | TP02 | TP03
CP08-216A |  | - | P04-07 |  | 0 | CP08-216A-P04-07 |  |  | TR | 1 | 180 | 3 | TR | PB04 | PB04
CP08-216A |  | - | P05-07 |  | 0 | CP08-216A-P05-07 |  |  | TR | 1 | 216 | 3.6 | TR | PB02 | PB02 | PB03 | PB04
CP08-216A |  | - | P06-07 |  | 0 | CP08-216A-P06-07 |  |  | TR | 1 | 110 | 1.8333 | TR | PB04 | PB04 | [8 empty] | RUN PB3,PB4
CP08-216A |  | - | P07-07 |  | 0 | CP08-216A-P07-07 |  |  | TR | 1 | 180 | 3 | TR | PB02 | PB02 | PB3,PB4/PB4,PB2
CP08-216C |  | - | P01-06 |  | 0 | CP08-216C-P01-06 |  |  | ST | 1 | 1440 | 24 | SM | SM01 | SM01
CP08-216C |  | - | P02-06 |  | 0 | CP08-216C-P02-06 |  |  | ST | 1 | 300 | 5 | ST-1 | PP05-060T | PP05
CP08-216C |  | - | P03-06 |  | 0 | CP08-216C-P03-06 |  |  | ST | 1 | 300 | 5 | ST-1 | PP03-060T | PP03
CP08-216C |  | - | P04-06 |  | 0 | CP08-216C-P04-06 |  |  | ST | 1 | 300 | 5 | ST-1 | PP04-060T | PP04
CP08-216C |  | - | P05-06 |  | 0 | CP08-216C-P05-06 |  |  | ST | 1 | 300 | 5 | ST-1 | PP10-080T | PP10
CP08-216C |  | - | P06-06 |  | 0 | CP08-216C-P06-06 |  |  | ST | 1 | 60 | 1 | ST-3 | SW01 | SW01
CP08-216D |  | - | P01-08 |  | 0 | CP08-216D-P01-08 |  |  | T/S | 1 | 72 | 1.2 | SM | SM01 | SM01
CP08-216D |  | - | P02-08 |  | 0 | CP08-216D-P02-08 |  |  | T/S | 1 | 30 | 0.5 | TR | TM03 | TM03
CP08-216D |  | - | P03-08 |  | 0 | CP08-216D-P03-08 |  |  | T/S | 1 | 100 | 1.6667 | TR | PB03 | PB03
CP08-216D |  | - | P04-08 |  | 0 | CP08-216D-P04-08 |  |  | T/S | 1 | 50 | 0.83333 | TR | PB04 | PB04 | PB2,PB3,SW5
CP08-216D |  | - | P05-08 |  | 0 | CP08-216D-P05-08 |  |  | T/S | 1 | 100 | 1.6667 | TR | PB03 | PB03 | PB04
CP08-216D |  | - | P06-08 |  | 0 | CP08-216D-P06-08 |  |  | T/S | 1 | 140 | 2.3333 | TR | PB03 | PB03 | PB05
CP08-216D |  | - | P07-08 |  | 0 | CP08-216D-P07-08 |  |  | T/S | 1 | 140 | 2.3333 | TR | PB03 | PB03 | [8 empty] | RUN PB2,PB3,PB4
CP08-216D |  | - | P08-08 |  | 0 | CP08-216D-P08-08 |  |  | T/S | 1 | 60 | 1 | TR | SW05 | SW05 | SW10
CP08-218 |  | - | P01-06 |  | 0 | CP08-218-P01-06 |  |  | ST | 1 | 1680 | 28 | SM | SM01 | SM01
CP08-218 |  | - | P02-06 |  | 0 | CP08-218-P02-06 |  |  | ST | 1 | 240 | 4 | ST-4 | PP25-160T | PP24 |  | PP24 | PP24 | PP25
CP08-218 |  | - | P03-06 |  | 0 | CP08-218-P03-06 |  |  | ST | 1 | 240 | 4 | ST-4 | PP28-110T | PP25 |  | PP25 | PP25 | PP28
CP08-218 |  | - | P04-06 |  | 0 | CP08-218-P04-06 |  |  | ST | 1 | 240 | 4 | ST-4 | PP20-110T | PP26 | PP20 | PP26 | PP20 | PP20
CP08-218 |  | - | P05-06 |  | 0 | CP08-218-P05-06 |  |  | ST | 1 | 240 | 4 | ST-4 | PP26-110T | PP20 | PP28 | PP28 | PP28 | PP26
CP08-219 |  | - | P01-04 |  | 0 | CP08-219-P01-04 |  |  | ST | 1 | 30 | 0.5 | ST-3 | SW01 | SW01 | SW9
CP08-219 |  | - | P02-04 |  | 0 | CP08-219-P02-04 |  |  | ST | 1 | 30 | 0.5 | ST-1 | PAINTING | PAINTING
CP08-219 |  | - | P03-04 |  | 0 | CP08-219-P03-04 |  |  | ST | 1 | 30 | 0.5 | ST-1 | PAINTING | PAINTING
CP08-219A |  | - | P01-05 |  | 0 | CP08-219A-P01-05 |  |  | ST | 1 | 1710 | 28.5 | SM | SM01 | SM01 | [8 empty] | SM1X2
CP08-219A |  | - | P02-05 |  | 0 | CP08-219A-P02-05 |  |  | ST | 1 | 360 | 6 | ST-2 | PP15-080T | PP15 | PP25 | PP24 | PP17 | PP10
CP08-219A |  | - | P03-05 |  | 0 | CP08-219A-P03-05 |  |  | ST | 1 | 240 | 4 | ST-3 | TP03 | TP03 | TP03
CP08-219A |  | - | P04-05 |  | 0 | CP08-219A-P04-05 |  |  | ST | 1 | 240 | 4 | ST-2 | PP15-080T | PP15 | PP24 | PP28 | PP21 | PP01 | PP10
CP08-219B |  | - | P01-04 |  | 0 | CP08-219B-P01-04 |  |  | ST | 1 | 9360 | 156 | SM | SM01 | SM01 | [9 empty] | SHARE PART WITH CT10-009A,CT10-013C,CP08-216B
CP08-219B |  | - | P02-04 |  | 0 | CP08-219B-P02-04 |  |  | ST | 1 | 600 | 10 | ST-2 | PP13-060T | PP19 | PP02 | PP13 | PP04 | PP03 | PP22 | PP14 |  |  |  | NO RUN OPF
CP08-219B |  | - | P03-04 |  | 0 | CP08-219B-P03-04 |  |  | ST | 1 | 360 | 6 | ST-1 | PP03-060T | PP10 | PP22 | PP03 | PP15 | PP04 | PP05 | PP14 |  |  |  | SHARE DIE V -O02-007-P03-04,O2-008-P03-04,O02-012-P03-04,P08-186-P04-05,CP08-219B-P03-04,CP08-481-P03-04
CP08-219C | GC02-015 | - | P01-07 |  | 0 | CP08-219C-P01-07 |  |  | ST | 1 | 1440 | 24 | SM | SM01 | SM01
CP08-219C |  | - | P02-07 |  | 0 | CP08-219C-P02-07 |  |  | ST | 1 | 300 | 5 | ST-1 | PP13-060T | PP05 | PP13 | PP18 | PP21
CP08-219C |  | - | P03-07 |  | 0 | CP08-219C-P03-07 |  |  | ST | 1 | 300 | 5 | ST-1 | PP03-060T | PP03 | PP17
CP08-219C |  | - | P04-07 |  | 0 | CP08-219C-P04-07 |  |  | ST | 1 | 300 | 5 | ST-1 | PP04-060T | PP04 |  | PP16
CP08-219C |  | - | P05-07 |  | 0 | CP08-219C-P05-07 |  |  | ST | 1 | 300 | 5 | ST-1 | PP10-080T | PP10 | PP13 | PP27 | PP21
CP08-219C |  | - | P06-07 |  | 0 | CP08-219C-P06-07 |  |  | ST | 1 | 60 | 1 | ST-3 | SW01 | SW01 | SW09
CP08-219D |  | - | P01-06 |  | 0 | CP08-219D-P01-06 |  |  | T/S | 1 | 30 | 0.5 | TR | TM03 | TM03
CP08-219D |  | - | P02-06 |  | 0 | CP08-219D-P02-06 |  |  | T/S | 1 | 100 | 1.6667 | TR | PB08 | PB03 | PB02 | PB08 | [6 empty] | ON 050522 RUN PB3
CP08-219D |  | - | P03-06 |  | 0 | CP08-219D-P03-06 |  |  | ST | 1 | 240 | 4 | ST-3 | PP21-110T | PP21 | PP15 | PP17 | PP31
CP08-219D |  | - | P04-06 |  | 0 | CP08-219D-P04-06 |  |  | T/S | 1 | 60 | 1 | TR | PB05 | PB05 | PB01 | [7 empty] | PB2,PB3,SW5 | RUN,PB3,PB4
CP08-219D |  | - | P05-06 |  | 0 | CP08-219D-P05-06 |  |  | T/S | 1 | 60 | 1 | TR | SW09 | SW09 | SW01 | [7 empty] | ON 130522-RUN PB5 | PB3,PB4 (FOR PROCESS 5 ~7)-CAPACITY - 60/HRS
CP08-221 |  | - | P01-05 |  | 0 | CP08-221-P01-05 |  |  | ST | 1 | 240 | 4 | ST-4 | PP24-160T | PP24
CP08-221 |  | - | P02-05 |  | 0 | CP08-221-P02-05 |  |  | ST | 1 | 240 | 4 | ST-4 | PP25-160T | PP25
CP08-221 |  | - | P03-05 |  | 0 | CP08-221-P03-05 |  |  | ST | 1 | 240 | 4 | ST-4 | PP20-110T | PP20
CP08-221 |  | - | P04-05 |  | 0 | CP08-221-P04-05 |  |  | ST | 1 | 240 | 4 | ST-4 | PP26-110T | PP26
CP08-224 |  |  | P01-05 |  |  | CP08-224-P01-05 |  |  | TR | 1 | 240 | 4 | TR | SM01 | SM01
CP08-224 |  | - | P02-05 |  | 0 | CP08-224-P02-05 |  |  | TR | 1 | 40 | 0.66667 | TR | TM05 | TM05 | TM06 | TM03
CP08-224 |  | - | P03-05 |  | 0 | CP08-224-P03-05 |  |  | ? | 1 | 80 | 1.3333 | TR | PB03 | PB03 | PB02 | PB03 | [6 empty] | RUN PB2,PB5 ON 140722 | RUN PB2,PB7 RUN PB3,PB4
CP08-224 |  | - | P04-05 |  | 0 | CP08-224-P04-05 |  |  | ? | 1 | 80 | 1.3333 | TR | PB04 | PB04 | PB04 | PB07
CP08-225 |  | - | P01-05 |  | 0 | CP08-225-P01-05 |  |  | TR | 1 | 120 | 2 | SM | SM01 | SM01
CP08-225 |  | - | P02-05 |  | 0 | CP08-225-P02-05 |  |  | TR | 1 | 120 | 2 | TR | TM03 | TM03 | TM05 | TM06
CP08-225 |  | - | P03-05 |  | 0 | CP08-225-P03-05 |  |  | TR | 1 | 50 | 0.83333 | TR | PB07 | PB07 | PB05 | PB04
CP08-225 |  | - | P04-05 |  | 0 | CP08-225-P04-05 |  |  | TR | 1 | 50 | 0.83333 | TR | PB02 | PB02 |  | PB03 | [6 empty] | RUN PB4,PB2-090622 | RUN PB4,PB3-ON 050822
CP08-226 |  | - | P01-05 |  | 0 | CP08-226-P01-05 |  |  | TR | 1 | 240 | 4 | SM | SM01 | SM01
CP08-226 |  | - | P02-05 |  | 0 | CP08-226-P02-05 |  |  | TR | 1 | 30 | 0.5 | TR | TM03 | TM03 | TM05 | TM06 | TM02
CP08-226 |  | - | P03-05 |  | 0 | CP08-226-P03-05 |  |  | TR | 1 | 20 | 0.33333 | WN | DEBURR | DEBURR
CP08-226 |  | - | P04-05 |  | 0 | CP08-226-P04-05 |  |  | TR | 1 | 100 | 1.6667 | TR | PB08 | PB02 | PB03 | PB07 | PB05 | PB08 |  |  |  |  | RUN PB5 - 140722 | RUN PB7 ON 070622
CP08-230 |  | - | P01-04 |  | 0 | CP08-230-P01-04 |  |  | T/S | 1 | 90 | 1.5 | TR | TM06 | TM05 | TM03 | TM06
CP08-230 |  | - | P02-04 |  | 0 | CP08-230-P02-04 |  |  | T/S | 1 | 80 | 1.3333 | TR | PB01 | PB07 | PB04 | PB05 | PB01 | [5 empty] | PB1-030822
CP08-230 |  | - | P03-04 |  | 0 | CP08-230-P03-04 |  |  | T/S | 1 | 180 | 3 | ST-3 | PP09-160T | PP09 | [8 empty] | ONLY STAMPING MACHINE CAN RUN P9,P18-070722
CP08-231 | GC02-009 | - | P01-06 |  | 0 | CP08-231-P01-06 |  |  | AWN | 1 | 15 | 0.25 | WN | SW03 | SW03
CP08-231 | GC02-009 | - | P02-06 |  | 0 | CP08-231-P02-06 |  |  | AWN | 1 | 12 | 0.2 | WN | SW03 | SW03
CP08-231 | GC02-009 | - | P03-06 |  |  | CP08-231-P03-06 |  |  | AWN |  | 12 | 0.2 | WN | SW04 | SW06 | SW04
CP08-231 | GC02-009 | - | P04-06 |  |  | CP08-231-P04-06 |  |  | AWN |  | 12 | 0.2 | WN | TW03 | TW03 | TW01
CP08-231 | GC02-009 | - | P05-06 |  |  | CP08-231-P05-06 |  |  | SUB-CON
CP08-231A | GC02-009A | - | P01-03 |  | 0 | CP08-231A-P01-03 |  |  | WN | 1 | 900 | 15 | WN | WS01 | WS01
CP08-231A | GC02-009A | - | P02-03 |  | 0 | CP08-231A-P02-03 |  |  | WN | 1 | 120 | 2 | WN | JIG-HAND BEND | JIG-HAND BEND
CP08-231B | GC02-009B | - | P01-06 |  | 0 | CP08-231B-P01-06 |  |  | WN | 1 | 720 | 12 | WN | WS01 | WS01
CP08-231B | GC02-009B | - | P02-06 |  | 0 | CP08-231B-P02-06 |  |  | WN | 1 | 330 | 5.5 | WN | PP23-060T | PP23 | PP15
CP08-231B | GC02-009B | - | P03-06 |  | 0 | CP08-231B-P03-06 |  |  | WN | 1 | 240 | 4 | WN | JIG-HAND BEND | JIG-HAND BEND
CP08-231B | GC02-009B | - | P04-06 |  | 0 | CP08-231B-P04-06 |  |  | WN | 1 | 420 | 7 | WN | PP23-060T | PP23 | PP15
CP08-231C | GC02-009C | - | P01-03 |  | 0 | CP08-231C-P01-03 |  |  | WN | 1 | 900 | 15 | WN | WS01 | WS01
CP08-231C | GC02-009C | - | P02-03 |  | 0 | CP08-231C-P02-03 |  |  | WN | 1 | 420 | 7 | WN | JIG-HAND BEND | JIG-HAND BEND
CP08-231D | GC02-009D | - | P01-02 |  | 0 | CP08-231D-P01-02 |  |  | WN | 1 | 960 | 16 | WN | WS01 | WS01
CP08-231E | GC02-009E | - | P01-02 |  | 0 | CP08-231E-P01-02 |  |  | WN | 1 | 720 | 12 | WN | WS01 | WS01
CP08-231F | GC02-009F | - | P01-02 |  | 0 | CP08-231F-P01-02 |  |  | WN | 1 | 900 | 15 | WN | WS01 | WS01
CP08-231G | GC02-009G | - | P01-02 |  | 0 | CP08-231G-P01-02 |  |  | WN | 1 | 840 | 14 | WN | WS01 | WS01
CP08-234 |  | - | P01-04 |  | 0 | CP08-234-P01-04 |  |  | TR | 1 | 18 | 0.3 | TR | TM05 | TM05 | TM03 | TM06
CP08-234 |  | - | P02-04 |  | 0 | CP08-234-P02-04 |  |  | TR | 1 | 13 | 0.21667 | #N/A | #N/A | PB6,PB1,PB3
CP08-234 |  | - | P03-04 |  | 0 | CP08-234-P03-04 |  |  | TR | 1 | 40 | 0.66667 | TR | PB02 | PB02
CP08-234 |  | - | P04-04 |  | 0 | CP08-234-P04-04 |  |  | TR | 1 | 33 | 0.55 | TR | PB03 | PB03
CP08-236 |  | - | P01-03 |  | 0 | CP08-236-P01-03 |  |  | TR | 1 | 25 | 0.41667 | TR | TM05 | TM05 | TM03 | TM06
CP08-236 |  | - | P02-03 |  | 0 | CP08-236-P02-03 |  |  | TR | 1 | 28 | 0.46667 | #N/A | #N/A | PB6,PB1,PB3
CP08-236 |  | - | P03-03 |  | 0 | CP08-236-P03-03 |  |  | TR | 1 | 28 | 0.46667 | TR | PB02 | PB02
CP08-245 |  | - | P01-07 |  | 0 | CP08-245-P01-07 |  |  | TR | 1 | 78 | 1.3 | SM | SM01 | SM01
CP08-245 |  | - | P02-07 |  | 0 | CP08-245-P02-07 |  |  | TR | 1 | 6 | 0.1 | TR | TM03 | TM03 | TM06,TM02
CP08-245 |  | - | P03-07 |  | 0 | CP08-245-P03-07 |  |  | TR | 1 | 120 | 2 | ST-3 | TP07 | TP07 | TP02
CP08-245 |  | - | P04-07 |  | 0 | CP08-245-P04-07 |  |  | TR | 1 | 60 | 1 | TR | PB03 | PB03 | PB07 | PB03 | [6 empty] | RUN T3,T2,TP2,PB2,PB4,PB3,PB02
CP08-245 |  | - | P05-07 |  | 0 | CP08-245-P05-07 |  |  | TR | 1 | 40 | 0.66667 | #N/A | PB02 | PB02 | PB02 | PB07 | [6 empty] | RUN PB03,PB07 - 04.12.24
CP08-245 |  | - | P06-07 |  | 0 | CP08-245-P06-07 |  |  | TR | 1 | 60 | 1 | TR | PB03 | PB03 | PB02 | PB07 | [6 empty] | RUN ON 23.12.24 PB02,TP07,PB05
CP08-254 |  | - | P01-05 |  | 0 | CP08-254-P01-05 |  |  | ST | 1 | 300 | 5 | ST-3 | PP25-160T | PP18 | PP25 | PP09 | PP24
CP08-254 |  | - | P02-05 |  | 0 | CP08-254-P02-05 |  |  | ST | 1 | 300 | 5 | ST-3 | PP26-110T | PP17 | PP26 | PP25 | PP25 | [5 empty] | SAME DIE V CP08-255 & CP08-458
CP08-254 |  | - | P03-05 |  | 0 | CP08-254-P03-05 |  |  | ST | 1 | 300 | 5 | ST-3 | PP20-110T | PP16 | PP20 | PP26 | PP26 | [5 empty] | SAME DIE V CP08-255 & CP08-458
CP08-254 |  | - | P04-05 |  | 0 | CP08-254-P04-05 |  |  | ST | 2 | 300 | 5 | ST-3 | PP28-110T | PP27 | PP28 | PP20 | PP28 | [5 empty] | SAME DIE V CP08-255 & CP08-458
CP08-255 |  | - | P01-05 |  | 0 | CP08-255-P01-05 |  |  | ST | 1 | 300 | 5 | ST-4 | PP25-160T | PP25 | PP09 | PP24 | [6 empty] | SAME DIE V CP08-255 & CP08-458
CP08-255 |  | - | P02-05 |  | 0 | CP08-255-P02-05 |  |  | ST | 1 | 300 | 5 | ST-4 | PP26-110T | PP26 | PP17 | PP25 | [6 empty] | SAME DIE V CP08-254 & CP08-458
CP08-255 |  | - | P03-05 |  | 0 | CP08-255-P03-05 |  |  | ST | 1 | 300 | 5 | ST-4 | PP20-110T | PP20 | PP16 | PP26 | [6 empty] | SAME DIE V CP08-254 & CP08-458
CP08-255 |  | - | P04-05 |  | 0 | CP08-255-P04-05 |  |  | ST | 2 | 300 | 5 | ST-4 | PP28-110T | PP28 | PP27 | PP20 | [6 empty] | SAME DIE V CP08-254 & CP08-458
CP08-256 |  | - | P01-02 |  | 0 | CP08-256-P01-02 |  |  | ST | 2 | 240 | 4 | ST-1 | PP29 | PP29 | PP30 | PP33 |  | PP04 | PP29 |  |  |  | SAME DIE V CP08-254 & CP08-458 | SAME KAKI WITH CP08-291
CP08-257 |  |  | P01-05 |  |  | CP08-257-P01-05 |  |  | ST | 1 | 240 | 4 | ST-1 | SM01 | SM01
CP08-257 |  | - | P02-05 |  | 0 | CP08-257-P02-05 |  |  | ST | 1 | 360 | 6 | ST-3 | PP10-080T | PP17 | PP10 | PP18 | PP18 | PP10 |  | PP10 | PP10 |  | OPF RUN
CP08-257 |  | - | P03-05 |  | 0 | CP08-257-P03-05 |  |  | ST | 1 | 360 | 6 | ST-3 | PP04-060T | PP16 | PP13 | PP04 | PP17 | PP04 |  | PP04 | PP13
CP08-257 |  | - | P04-05 |  | 0 | CP08-257-P04-05 |  |  | ST | 1 | 360 | 6 | ST-3 | PP03-060T | PP27 | PP04 | PP13 | PP05 | PP03 | PP15 | PP05 | PP03
CP08-258 |  | - | P01-03 |  | 0 | CP08-258-P01-03 |  |  | ST | 1 | 240 | 4 | ST | SM01 | SM01
CP08-258 |  | - | P02-03 |  | 0 | CP08-258-P02-03 |  |  | ST | 1 | 250 | 4.1667 | ST | PP22-060T | PP22
CP08-259 |  | - | P01-04 |  | 0 | CP08-259-P01-04 |  | SLITTING | ST | 1 | 120 | 2 | SM | SM01 | SM01
CP08-259 |  | - | P02-04 |  | 0 | CP08-259-P02-04 |  | BLANKING | ST | 1 | 360 | 6 | ST-1 | PP10-080T | PP10 | PP14 | [7 empty] | NO RUN OPF
CP08-259 |  | - | P03-04 |  | 0 | CP08-259-P03-04 |  | BENDING | ST | 1 | 240 | 4 | ST-1 | PP04-060T | PP05 | PP04 | PP13 | PP02 | PP10
CP08-265 |  | - | P01-04 |  | 0 | CP08-265-P01-04 |  |  | ST | 1 | 1200 | 20 | ST-1 | PP02-060T | PP02 | PP14 | PP10 | [6 empty] | NOT RUN OPF
CP08-265 |  | - | P02-04 |  | 0 | CP08-265-P02-04 |  |  | ST | 1 | 120 | 2 | ST-1 | PP11-035T | PP11 | PP03 | PP06 | PP22 | [5 empty] | NOT RUN OPF
CP08-265 |  | - | P03-04 |  | 0 | CP08-265-P03-04 |  |  | ST | 1 | 240 | 4 | ST-2 | PP06-040T | PP06 | PP22 | PP11 | PP05 | [5 empty] | NOT RUN OPF
CP08-285 |  | - | P01-01 |  | 0 | CP08-285-P01-01 |  |  | TR | 1 | 60 | 1 | ST | SW09 | SW09 | SW01
CP08-285A |  | - | P01-05 |  | 0 | CP08-285A-P01-05 |  |  | TR | 1 | 27 | 0.45 | TR | TM05 | TM05 | TM03 | TM06
CP08-285A |  | - | P02-05 |  | 0 | CP08-285A-P02-05 |  |  | TR | 1 | 90 | 1.5 | TR | PB02 | PB02 | PB03
CP08-285A |  | - | P03-05 |  | 0 | CP08-285A-P03-05 |  |  | TR | 1 | 65 | 1.0833 | TR | PB04 | PB04
CP08-285A |  | - | P04-05 |  | 0 | CP08-285A-P04-05 |  |  | TR | 1 | 85 | 1.4167 | TR | PB03 | PB04
CP08-285B |  | - | P01-03 |  | 0 | CP08-285B-P01-03 |  |  | TR | 1 | 160 | 2.6667 | TR | TM05 | TM05 | TM03 | TM06
CP08-285B |  | - | P02-03 |  | 0 | CP08-285B-P02-03 |  |  | TR | 1 | 90 | 1.5 | TR | PB04 | PB04
CP08-289 |  | - | P01-06 |  | 0 | CP08-289-P01-06 |  |  | ST | 1 | 450 | 7.5 | ST-2 | PP01-110T | PP01 | PP19 | PP32
CP08-289 |  | - | P02-06 |  | 0 | CP08-289-P02-06 |  |  | ST | 1 | 450 | 7.5 | ST-2 | PP15-080T | PP15
CP08-289 |  | - | P03-06 |  | 0 | CP08-289-P03-06 |  |  | ST | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CP08-289 |  | - | P04-06 |  | 0 | CP08-289-P04-06 |  |  | ST | 1 | 360 | 6 | ST-4 | TP08 | TP08
CP08-289 |  | - | P05-06 |  | 0 | CP08-289-P05-06 |  |  | ST | 1 | 360 | 6 | AL | CHECKING | CHECKING | [9 empty] | REWORK : VISUAL : 360 PCS/HOUR
CP08-291 |  | - |  |  | 0 |  |  |  | ST | 1 | 240 | 4 | ST-1 | SM01 | SM01 | [8 empty] | NO MORE SLITTING PROCESS
CP08-291 |  | - | P01-02 |  | 0 | CP08-291-P01-02 |  |  | ST | 2 | 240 | 4 | ST-1 | PP29 | PP29 | [8 empty] | SAME KAKI WITH CP08-256
CP08-291 |  | - |  |  | 0 |  |  |  | ST | 1 | 240 | 4 | ST-1 | [10 empty] | NO MORE THIS PROCESS
CP08-291 |  | - |  |  | 0 |  |  |  | ST | 1 | 240 | 4 | ST-1 | [10 empty] | NO MORE THIS PROCESS
CP08-292 |  | - | P01-06 |  | 0 | CP08-292-P01-06 |  |  | ST | 1 | 360 | 6 | ST-3 | PP25-160T | PP18 | PP25 | PP24
CP08-292 |  | - | P02-06 |  | 0 | CP08-292-P02-06 |  |  | ST | 1 | 360 | 6 | ST-3 | PP26-110T | PP17 | PP26 | PP26
CP08-292 |  | - | P03-06 |  | 0 | CP08-292-P03-06 |  |  | ST | 1 | 360 | 6 | ST-3 | PP20-110T | PP16 | PP20 | PP20
CP08-292 |  | - | P04-06 |  | 0 | CP08-292-P04-06 |  |  | ST | 1 | 360 | 6 | ST-3 | PP28-110T | PP27 | PP28 | PP25
CP08-292 |  | - | P05-06 |  | 0 | CP08-292-P05-06 |  |  | ST | 2 | 360 | 6 | ST-3 | PP24-160T | PP09 | PP24
CP08-293 |  | - | P01-06 |  | 0 | CP08-293-P01-06 |  |  | ST | 1 | 360 | 6 | ST-3 | PP25-160T | PP18 | PP25
CP08-293 |  | - | P02-06 |  | 0 | CP08-293-P02-06 |  |  | ST | 1 | 360 | 6 | ST-3 | PP26-110T | PP17 | PP26
CP08-293 |  | - | P03-06 |  | 0 | CP08-293-P03-06 |  |  | ST | 1 | 360 | 6 | ST-3 | PP20-110T | PP16 | PP20
CP08-293 |  | - | P04-06 |  | 0 | CP08-293-P04-06 |  |  | ST | 1 | 360 | 6 | ST-3 | PP28-110T | PP27 | PP28
CP08-293 |  | - | P05-06 |  | 0 | CP08-293-P05-06 |  |  | ST | 2 | 360 | 6 | ST-3 | PP24-160T | PP09 | PP24
CP08-295 |  | - | P01-02 |  | 0 | CP08-295-P01-02 |  |  | FM | 1 | 2400 | 40 | FM | FM02 | FM03 | FM01 | FM02
CP08-296 |  | - | P01-02 |  | 0 | CP08-296-P01-02 |  |  | FM | 1 | 2400 | 40 | FM | FM02 | FM02 | FM01 | FM03 | [6 empty] | SHARE DIE V CP08-297,CP08-298,CP08-302
CP08-297 |  | - | P01-02 |  | 0 | CP08-297-P01-02 |  | FORMIMG | FM | 1 | 2400 | 40 | FM | FM02 | FM03 | FM02 | FM01 | [6 empty] | SHARE DIE V CP08-296,CP08-298,CP08-302
CP08-298 |  | - | P01-03 |  | 0 | CP08-298-P01-03 |  |  | FM | 1 | 2400 | 40 | FM | FM02 | FM03 | FM01 | FM02 | [6 empty] | SHARE DIE V CP08-296,CP08-297,CP08-302
CP08-299 |  | - | P01-03 |  | 0 | CP08-299-P01-03 |  |  | FM | 1 | 1800 | 30 | FM | FM03 | FM03 | FM02 | [7 empty] | SHARE CAM V CP08-300,CP08-299
CP08-300 |  | - | P01-03 |  | 0 | CP08-300-P01-03 |  |  | FM | 1 | 1800 | 30 | FM | FM03 | FM03 | FM02 | FM01 | [6 empty] | SHARE CAM V CP08-299,CP08-300
CP08-301 |  | - | P01-05 |  | 0 | CP08-301-P01-05 |  |  | ST | 1 | 300 | 5 | ST-1 | PP10-080T | PP10 | PP10 | PP10 |  | PP10
CP08-301 |  | - | P02-05 |  | 0 | CP08-301-P02-05 |  |  | ST | 1 | 300 | 5 | ST-1 | PP04-060T | PP04 | PP04 | PP05 |  | PP04
CP08-301 |  | - | P03-05 |  | 0 | CP08-301-P03-05 |  |  | ST | 1 | 300 | 5 | ST-1 | PP03-060T | PP13 | PP03 | PP13 | PP05 | PP03
CP08-301 |  | - | P04-05 |  | 0 | CP08-301-P04-05 |  |  | ST | 1 | 300 | 5 | ST-1 | PP13-060T | PP05 | PP13 | PP03 |  | PP05
CP08-302 | GP01-025 | - | P01-02 |  | 0 | CP08-302-P01-02 |  |  | FM | 1 | 2400 | 40 | FM | FM01 | FM03 | FM01 | [7 empty] | SHARE DIE V CP08-296,CP08-297,CP08-298
CP08-304 |  | - | P01-03 |  | 0 | CP08-304-P01-03 |  |  | S/A | 1 | 1500 | 25 | ST-2 | PP10-080T | PP19 | PP14 | PP10 | PP01 | PP12 |  |  |  |  | SHARE DIE V CP08-576,CP08-305
CP08-304 |  | - | P02-03 |  | 0 | CP08-304-P02-03 |  |  | S/A | 1 | 300 | 5 | AL | TP04 | TP04 | TP02 | TP06
CP08-305 |  | - | P01-03 |  | 0 | CP08-305-P01-03 |  |  | S/A | 1 | 1500 | 25 | ST-2 | PP10-080T | PP19 | PP10 | PP01 | PP12 | [5 empty] | SHARE DIE V CP08-576,CP08-304
CP08-305 |  | - | P02-03 |  | 0 | CP08-305-P02-03 |  |  | S/A | 1 | 300 | 5 | AL | TP04 | TP06 | TP02 | TP04 | [6 empty] | SAME JIG WITH CP08-514,CP08-515,CP08-576,CP08-304
CP08-307 |  | - | P01-02 |  | 0 | CP08-307-P01-02 |  |  | S/A | 1 | 3000 | 50 | ST-3 | PP01-110T | PP09 | PP01 | [7 empty] | SHARE DIE V CP08-518,CP08-519,CP08-080
CP08-310 | GP01-035 | - | P01-06 |  | 0 | CP08-310-P01-06 |  |  | ST | 1 | 4080 | 68 | ST | SM01 | SM01 | [8 empty] | NO MORE RUN AT ALW - TP6,TP2 , RUN BY STAMPING TP3 OR TP8/TP7-210322
CP08-310 | GP01-035 | - | P02-06 |  | 0 | CP08-310-P02-06 |  |  | ST | 1 | 360 | 6 | ST | PP21-110T | PP17 | PP21 | PP15 | PP12
CP08-310 | GP01-035 | - | P03-06 |  | 0 | CP08-310-P03-06 |  |  | ST | 1 | 120 | 2 | ST | TP03 | TP07 | TP09 | TP03
CP08-310 | GP01-035 |  | P04-06 |  |  | CP08-310-P04-06 |  |  | ST | 1 | 300 | 5 | ST | TP09 | TP07 | TP09
CP08-310 | GP01-035 |  | P05-06 |  |  | CP08-310-P05-06 |  |  | ST | 1 | 240 | 4 | ST | PP21-110T | PP21 | PP17 |  | PP12
CP08-311 | GC02-013 | - | P01-04 |  | 0 | CP08-311-P01-04 |  |  | TR | 1 | 25 | 0.41667 | TR | TM06 | TM06 | TM03 | TM05 | [6 empty] | CP08-311 RUN TOGETHER V CP08-320
CP08-311 | GC02-013 | - | P02-04 |  | 0 | CP08-311-P02-04 |  |  | TR | 1 | 60 | 1 | TR | PB05 | PB05 | PB01 | [7 empty] | RUN PB5,PB2*RUN ON 270522
CP08-311 | GC02-013 | - | P03-04 |  | 0 | CP08-311-P03-04 |  |  | TR | 1 | 30 | 0.5 | TR | PB02 | PB02 | PB03 | PB01 | [6 empty] | NET ORANGE. RUN PB1,PB3,PB2
CP08-312 |  | - | P01-03 |  | 0 | CP08-312-P01-03 |  |  | TR | 1 | 30 | 0.5 | TR | TM06 | TM05 | TM03 | TM06
CP08-312 |  | - | P02-03 |  | 0 | CP08-312-P02-03 |  |  | TR | 1 | 45 | 0.75 | TR | PB05 | PB05 | [8 empty] | NET ORANGE
CP08-313 |  | - | P01-05 |  | 0 | CP08-313-P01-05 |  |  | TR | 1 | 25 | 0.41667 | TR | TM06 | TM03 | TM05 | TM06
CP08-313 |  | - | P02-05 |  | 0 | CP08-313-P02-05 |  |  | TR | 1 | 45 | 0.75 | TR | PB05 | PB01 | PB07 | PB05 | [6 empty] | RUN PB1,PB3,PB2 ON 140222
CP08-313 |  | - | P03-05 |  | 0 | CP08-313-P03-05 |  |  | TR | 1 | 45 | 0.75 | TR | PB05 | PB02 | PB03 | PB01 | PB05 | [5 empty] | NET ORANGE. RUN PB1,PB3 | RUN PB5,PB2 - 210622
CP08-313 |  | - | P04-05 |  | 0 | CP08-313-P04-05 |  |  | TR | 1 | 44 | 0.73333 | TR | PB02 | PB03 | PB02 | PB07 | [6 empty] | SHARE TOOLING 'R' WITH CP08-405 RUN PB7,PB2 ON 230522
CP08-314 |  | - | P01-03 |  | 0 | CP08-314-P01-03 |  |  | TR | 1 | 45 | 0.75 | TR | TM03 | TM03 | TM05 | TM06
CP08-314 |  | - | P02-03 |  | 0 | CP08-314-P02-03 |  |  | TR | 1 | 61 | 1.0167 | TR | PB07 | PB07 | PB05 | PB01 | [6 empty] | NET ORANGE. RUN PB4,PB6,PB7 | IF RUN PB7 NEED SEPARATE RUN BENDING - 2 BENDING-1ST BEN-50PCS/HRS,2ND BENDING - 100PCS/HRS RUN PB5-30/HOUR ON 010922
CP08-315 |  | - | P01-04 |  | 0 | CP08-315-P01-04 |  |  | TR | 1 | 18 | 0.3 | TR | TM06 | TM05 | TM03 | TM06 | [7 empty] | RUN PB1,PB4-310522
CP08-315 |  | - | P02-04 |  | 0 | CP08-315-P02-04 |  |  | TR | 1 | 90 | 1.5 | TR | PB02 | PB03 | PB02 | [7 empty] | NET ORANGE. RUN PB2(2 OPT),PB5(1 OPT) | RUN PB7,PB2,PB3
CP08-315 |  | - | P03-04 |  | 0 | CP08-315-P03-04 |  |  | TR | 1 | 30 | 0.5 | TR | PB05 | PB07 | PB05 | [7 empty] | 2 OPT. RUN PB5(1 OPT),-30/HRS,PB2(2 OPT)-80/HRS-ON 240622OPT.
CP08-316 |  | - | P01-06 |  | 0 | CP08-316-P01-06 |  |  | T/S | 1 | 90 | 1.5 | TR | TM06 | TM03 | TM05 | TM06
CP08-316 |  | - | P02-06 |  | 0 | CP08-316-P02-06 |  |  | T/S | 1 | 240 | 4 | ST-3 | PP31 | PP22 | PP21 | PP10 | PP31 | PP23
CP08-316 |  | - | P03-06 |  | 0 | CP08-316-P03-06 |  |  | T/S | 1 | 240 | 4 | ST-3 | PP31 | PP22 | PP04 | PP03 | PP31 | PP23
CP08-316 |  | - | P04-06 |  | 0 | CP08-316-P04-06 |  |  | T/S | 1 | 240 | 4 | AL | TP03 | TP03 | TP09 | [7 empty] | BOX
CP08-316 |  | - | P05-06 |  | 0 | CP08-316-P05-06 |  |  | T/S | 1 | 60 | 1 | TR | PB07 | PB04 | PB01 | PB05 | PB07
CP08-317 |  | - | P01-03 |  | 0 | CP08-317-P01-03 |  |  | TR | 1 | 45 | 0.75 | TR | TM06 | TM05 | TM03 | TM06
CP08-317 |  | - | P02-03 |  | 0 | CP08-317-P02-03 |  |  | TR | 1 | 80 | 1.3333 | TR | PB07 | PB07 | PB05 | PB03 | PB04 | [5 empty] | RUN PB1,PB4-310522
CP08-318 |  | - | P01-03 |  | 0 | CP08-318-P01-03 |  |  | TR | 1 | 40 | 0.66667 | TR | TM05 | TM05 | TM03 | TM06
CP08-318 |  | - | P02-03 |  | 0 | CP08-318-P02-03 |  |  | TR | 1 | 50 | 0.83333 | TR | PB05 | PB05 | PB01 | PB07 | [6 empty] | NET RED WORDING. RUN PB5-060622
CP08-319 |  | - | P01-02 |  | 0 | CP08-319-P01-02 |  |  | ST | 1 | 120 | 2 | ST-3 | PP29 | PP09 | PP29 | PP30
CP08-319A |  | - | P01-03 |  | 0 | CP08-319A-P01-03 |  |  | TR | 1 | 40 | 0.66667 | TR | TM03 | TM03
CP08-319A |  | - | P02-03 |  | 0 | CP08-319A-P02-03 |  |  | TR | 1 | 60 | 1 | TR | PB08 | PB08 | PB03 | PB01 | PB02 | [5 empty] | PB5
CP08-320 | GC02-013 | - |  |  | 0 |  |  |  | TR | 1 | 50 | 0.83333 | TR | TM05 | TM05 | TM03 | TM02 | [6 empty] | CP08-320 RUN TOGETHER WITH CP08-311
CP08-320 | GC02-013 | - | P01-02 |  | 0 | CP08-320-P01-02 |  |  | TR | 1 | 100 | 1.6667 | TR | PB03 | PB03 | PB02 | [7 empty] | RUN PB3 ON 180722
CP08-322 |  | - | P01-04 |  | 0 | CP08-322-P01-04 |  |  | TR | 1 | 20 | 0.33333 | TR | TM06 | TM03 | TM05 | TM06
CP08-322 |  | - | P02-04 |  | 0 | CP08-322-P02-04 |  |  | TR | 1 | 60 | 1 | TR | PB05 | PB05 | PB07
CP08-322 |  | - | P03-04 |  | 0 | CP08-322-P03-04 |  |  | TR | 1 | 60 | 1 | TR | PB02 | PB02 | PB03 | [7 empty] | RUN PB5,PB3/PB2 | FOR BENDING PROCESS SAME TOOLING V CP08-404
CP08-323 |  | - | P01-02 |  | 0 | CP08-323-P01-02 |  |  | ST | 1 | 120 | 2 | ST-3 | PP09-160T | PP09 | PP29
CP08-323A |  | - | P01-04 |  | 0 | CP08-323A-P01-04 |  |  | TR | 1 | 240 | 4 | SM | SM01 | SM01
CP08-323A |  | - | P02-04 |  | 0 | CP08-323A-P02-04 |  |  | TR | 1 | 82 | 1.3667 | TR | TM03 | TM03 | TM05 | TM06
CP08-323A |  | - | P03-04 |  | 0 | CP08-323A-P03-04 |  |  | TR | 1 | 25 | 0.41667 | TR | PB05 | PB05 | PB01 | PB02 | PB03 | [5 empty] | RUN PB4,PB1-260522 | RUN PB4,PB4 ON 190722
CP08-339 |  |  | P01-04 |  |  | CP08-339-P01-04 |  |  | ST | 1 | 240 | 4 | TR | SM01 | SM01
CP08-339 |  | - | P02-04 |  | 0 | CP08-339-P02-04 |  |  | TR | 1 | 100 | 1.6667 | TR | TM03 | TM03
CP08-339 |  | - | P03-04 |  | 0 | CP08-339-P03-04 |  |  | TR | 1 | 51 | 0.85 | TR | PB01 | PB01 | PB05 | PB04 | [6 empty] | PB4 RUN ON 020722
CP08-324 |  | - | P01-05 |  | 0 | CP08-324-P01-05 |  |  | ST | 1 | 6240 | 104 | SM | SM01 | SM01 | [8 empty] | 2 TIMES SLIT
CP08-324 |  | - | P02-05 |  | 0 | CP08-324-P02-05 |  |  | ST | 1 | 360 | 6 | ST-1 | PP22-060T | PP22 | PP13 | PP02 | PP10 | PP14 | PP05 |  |  | PP05 | NO RUN ONE PIECE FLOW
CP08-324 |  | - | P03-05 |  | 0 | CP08-324-P03-05 |  |  | ST | 1 | 240 | 4 | ST-2 | PP02-060T | PP02 | PP19 | PP03 | PP13 | PP15 | PP04 | PP05 |  | PP05
CP08-324 |  | - | P04-05 |  | 0 | CP08-324-P04-05 |  |  | ST | 1 | 240 | 4 | ST-1 | PP05-060T | PP05 | PP03 | PP05 | PP22 | PP13 | PP14 | PP02 |  | PP22
CP08-342 |  | - | P01-03 |  | 0 | CP08-342-P01-03 |  |  | TR | 1 | 80 | 1.3333 | TR | TM06 | TM05 | TM03 | TM06
CP08-342 |  | - | P02-03 |  | 0 | CP08-342-P02-03 |  |  | TR | 1 | 40 | 0.66667 | TR | PB04 | PB04 | PB07 | [7 empty] | SAME TOOLING V CP08-344
CP08-343 |  | - | P01-04 |  | 0 | CP08-343-P01-04 |  |  | TR | 1 | 75 | 1.25 | TR | TM03 | TM03
CP08-343 |  | - | P02-04 |  | 0 | CP08-343-P02-04 |  |  | TR | 1 | 100 | 1.6667 | TR | PB01 | PB01 | PB04 | PB02 | PB07 | [5 empty] | RUN PB1,PB1-050622
CP08-343 |  | - | P03-04 |  | 0 | CP08-343-P03-04 |  |  | TR | 1 | 100 | 1.6667 | TR | PB01 | PB01 |  | PB02 | PB07
CP08-344 |  | - | P01-03 |  | 0 | CP08-344-P01-03 |  |  | TR | 1 | 50 | 0.83333 | TR | TM06 | TM06 | TM03 | TM05
CP08-344 |  | - | P02-03 |  | 0 | CP08-344-P02-03 |  |  | TR | 1 | 120 | 2 | TR | PB04 | PB04 | PB05 | PB07 | [6 empty] | SAME TOOLING V CP08-342
CP08-345 | GP01-016 | - | P01-03 |  | 0 | CP08-345-P01-03 |  |  | ST | 1 | 720 | 12 | SM | SM01 | SM01
CP08-345 | GP01-016 | - | P02-03 |  | 0 | CP08-345-P02-03 |  |  | ST | 1 | 300 | 5 | ST-3 | PP05-060T | PP05 | PP21 | PP25 | PP15 | PP10 | PP03
CP08-349 |  | - | P01-04 |  | 0 | CP08-349-P01-04 |  |  | ST | 1 | 300 | 5 | ST-4 | PP25-160T | PP25 | PP20 | PP24 | PP28 |  | PP26 | PP25
CP08-349 |  | - | P02-04 |  | 0 | CP08-349-P02-04 |  |  | ST | 1 | 300 | 5 | ST-3 | PP20-110T | PP21 | PP28 | PP28 | PP20 | PP25 | PP20 | PP20 |  |  | SHARE DIE V CP08-350,CP08-456,CP08-457
CP08-349 |  | - | P03-04 |  | 0 | CP08-349-P03-04 |  |  | ST | 1 | 300 | 5 | ST-4 | PP28-110T | PP26 | PP28 | PP20 |  |  | PP28 | PP26 |  |  | SHARE DIE V CP08-350
CP08-350 |  | - | P01-04 |  | 0 | CP08-350-P01-04 |  |  | ST | 1 | 300 | 5 | ST-4 | PP25-160T | PP25 | PP20 | PP25 | PP18 |  |  | PP25 | PP25 |  |  | NOT RUN ONE PIECE FLOW PROCESS
CP08-350 |  | - | P02-04 |  | 0 | CP08-350-P02-04 |  |  | ST | 1 | 300 | 5 | ST-3 | PP20-110T | PP21 | PP20 | PP20 | PP28 | PP16 | PP27 | PP20 | PP28 |  | SHARE DIE V CP08-349,CP08-456
CP08-350 |  | - | P03-04 |  | 0 | CP08-350-P03-04 |  |  | ST | 1 | 300 | 5 | ST-4 | PP28-110T | PP26 | PP28 | PP17 |  |  |  | PP28 | PP26 |  | SHARE DIE V CP08-349
CP08-351 |  | - | P01-04 |  | 0 | CP08-351-P01-04 |  |  | ST | 1 | 12240 | 204 | SM | SM01 | SM01
CP08-351 |  | - | P02-04 |  | 0 | CP08-351-P02-04 |  |  | ST | 1 | 360 | 6 | ST-4 | PP25-160T | PP25 | PP26 | PP21 |  |  | PP18
CP08-351 |  | - | P03-04 |  | 0 | CP08-351-P03-04 |  |  | ST | 1 | 360 | 6 | ST-4 | PP28-110T | PP20 | PP28 | PP17 | PP27 | PP21 | PP09 |  |  |  | SHARE DIE V CP08-352-P03-04
CP08-352 |  | - | P01-04 |  | 0 | CP08-352-P01-04 |  |  | ST | 1 | 12240 | 204 | SM | SM01 | SM01
CP08-352 |  | - | P02-04 |  | 0 | CP08-352-P02-04 |  |  | ST | 1 | 360 | 6 | ST-4 | PP26-110T | PP18 | PP21 | PP17 | PP26 | PP20 | PP27 | PP25 | PP26 | PP25
CP08-352 |  | - | P03-04 |  | 0 | CP08-352-P03-04 |  |  | ST | 1 | 360 | 6 | ST-4 | PP28-110T | PP27 | PP28 | PP17 | PP16 | PP21 | PP20 | PP27 | PP21 | PP28 | SHARE DIE V CP08-351-P03-04
CP08-353/CP08-354 |  | - | P01-05 |  | 0 | CP08-353&CP08-354-P01-05 |  |  | ST | 1 | 480 | 8 | SM | SM01 | SM01 | [8 empty] | GC02-029
CP08-353/CP08-354 |  | - | P02-05 |  | 0 | CP08-353&CP08-354-P02-05 |  |  | ST | 1 | 300 | 5 | ST-4 | PP25-160T | PP26 | PP25 | PP18 | PP21 | PP25 | PP17 |  |  |  | note : only take job - GP01-029, for CP08-353&CP08-354 only for store purpose | SHARE DIE WITH CP08-369.CP08-370
CP08-353/CP08-354 |  | - | P03-05 |  | 0 | CP08-353&CP08-354-P03-05 |  |  | ST | 1 | 300 | 5 | ST-4 | PP20-110T | PP20 |  | PP16 | PP20 | PP20 | PP16
CP08-353/CP08-354 |  | - | P04-05 |  | 0 | CP08-353&CP08-354-P04-05 |  |  | ST | 1 | 300 | 5 | ST-4 | PP28-110T | PP28 | PP26 | PP17 |  | PP28 | PP27
CP08-357 CP08-395 | GC02-010 | - | P01-04 |  | 0 | CP08-357-P01-04 |  |  | ST | 1 | 3240 | 54 | SM | SM01 | SM01
CP08-357 CP08-395 | GC02-010 | - | P02-04 |  | 0 | CP08-357-P02-04 |  |  | ? | 1 | 360 | 6 | ST-3 | PP21-110T | PP21 | PP28 | PP24 |  |  | PP10
CP08-357 CP08-395 | GC02-010 | - | P03-04 |  | 0 | CP08-357-P03-04 |  |  | ? | 1 | 360 | 6 | ST-3 | PP21-110T | PP21 | PP28 | PP25 | PP19 | PP15 | PP10
CP08-358 |  | - | P01-04 |  | 0 | CP08-358-P01-04 |  |  | ST | 1 | 5280 | 88 | SM | SM01 | SM01
CP08-358 |  | - | P02-04 |  | 0 | CP08-358-P02-04 |  |  | ST | 1 | 480 | 8 | ST-3 | PP20-110T | PP17 | PP28 | PP15 | PP21 | PP20 | PP20 | PP28 | PP26
CP08-358 |  | - | P03-04 |  | 0 | CP08-358-P03-04 |  |  | ST | 1 | 240 | 4 | ST-1 | PP28-110T | PP14 | PP28 | PP15 | PP20 | PP17 | PP28 | PP20 | PP01
CP08-368 |  | - | P01-02 |  | 0 | CP08-368-P01-02 |  |  | ST | 1 | 68 | 1.1333 | ST-3 | PP29 | PP18 | PP29 | PP09 | PP30
CP08-368A |  | - | P01-04 |  | 0 | CP08-368A-P01-04 |  |  | ? | 1 | 2400 | 40 | SM | SM01 | SM01
CP08-368A |  | - | P02-04 |  | 0 | CP08-368A-P02-04 |  |  | ? | 1 | 300 | 5 | ST-3 | PP17-110T | PP16 | PP17 | PP21 | PP15 | PP21
CP08-368A |  | - | P03-04 |  | 0 | CP08-368A-P03-04 |  |  | ? | 1 | 300 | 5 | ST-3 | PP18-150T | PP27 | PP18 | PP21 | PP21 | PP15 | PP16
CP08-369/CP08-370 | GC02-030 | - | P01-05 |  | 0 | CP08-369/CP08-370-P01-05 |  |  | ST | 1 | 360 | 6 | SM | SM01 | SM01
CP08-369/CP08-370 | GC02-030 | - | P02-05 |  | 0 | CP08-369/CP08-370-P02-05 |  |  | ST | 1 | 300 | 5 | ST-3 | PP25-160T | PP21 | PP25 | PP26 | PP18 | PP24 | PP28 | PP25 | PP25 | PP17 | SHARE DIE WITH CP08-353.CP08-354
CP08-369/CP08-370 | GC02-030 | - | P03-05 |  | 0 | CP08-369/CP08-370-P03-05 |  |  | ST | 1 | 300 | 5 | ST-4 | PP20-110T | PP20 | PP16 | PP17 | PP25 |  |  | PP20 | PP28 | PP16
CP08-369/CP08-370 | GC02-030 | - | P04-05 |  | 0 | CP08-369/CP08-370-P04-05 |  |  | ST | 1 | 300 | 5 | ST-3 | PP28-110T | PP21 | PP28 | PP26 | PP27 |  |  | PP28 | PP26 | PP27
CP08-373 |  | - | P01-06 |  | 0 | CP08-373-P01-06 |  | SLITTING | ST | 1 | 240 | 4 | SM | SM01 | SM01
CP08-373 |  | - | P02-06 |  | 0 | CP08-373-P02-06 |  | SLITTING | ST | 1 | 360 | 6 | ST-4 | PP25-160T | PP25
CP08-373 |  | - | P03-06 |  | 0 | CP08-373-P03-06 |  | BLANKING | ST | 1 | 360 | 6 | ST-4 | PP20-110T | PP20
CP08-373 |  | - | P04-06 |  | 0 | CP08-373-P04-06 |  | BENDING | ST | 1 | 360 | 6 | ST-4 | PP28-110T | PP28
CP08-384 |  | - | P01-02 |  | 0 | CP08-384-P01-02 |  |  | ST | 1 | 180 | 3 | ST-3 | PP01-110T | PP21 | PP01 | PP15
CP08-385 |  | - | P01-05 |  | 0 | CP08-385-P01-05 |  |  | T/S | 1 | 90 | 1.5 | TR | TM03 | TM03 | TM05 | TM06
CP08-385 |  | - | P02-05 |  | 0 | CP08-385-P02-05 |  |  | T/S | 1 | 240 | 4 | ST-3 | PP31 | PP21 | PP03 | PP23 | PP15 | PP11 | PP31
CP08-385 |  | - | P03-05 |  | 0 | CP08-385-P03-05 |  |  | T/S | 1 | 240 | 4 | ST-3 | PP31 | PP21 | PP03 | PP23 | PP15 | PP32 | PP31
CP08-385 |  | - | P04-05 |  | 0 | CP08-385-P04-05 |  |  | T/S | 1 | 60 | 1 | TR | PB01 | PB01 | PB04 | PB05 | [6 empty] | RUN PB4-230822
CP08-398 |  | - | P01-03 |  | 0 | CP08-398-P01-03 |  |  | W | 1 | 18 | 0.3 | WN | SW06 | SW06
CP08-398 |  | - | P02-03 |  | 0 | CP08-398-P02-03 |  |  | W | 1 | 18 | 0.3 | WN | TW01 | TW01
CP08-398A |  | - | P01-04 |  | 0 | CP08-398A-P01-04 |  |  | W | 1 | 1500 | 25 | WN | WS01 | WS01
CP08-398A |  | - | P02-04 |  | 0 | CP08-398A-P02-04 |  |  | W | 1 | 120 | 2 | #N/A | JIG-HAND BEND | JIG-HAND BEND
CP08-398A |  | - | P03-04 |  | 0 | CP08-398A-P03-04 |  |  | W | 1 | 180 | 3 | WN | PP23-060T | PP23
CP08-398B |  | - | P01-02 |  | 0 | CP08-398B-P01-02 |  |  | W | 1 | 600 | 10 | WN | WS01 | WS01
CP08-398C |  | - | P01-02 |  | 0 | CP08-398C-P01-02 |  |  | W | 1 | 1200 | 20 | WN | WS01 | WS01
CP08-399 |  | - | P01-03 |  | 0 | CP08-399-P01-03 |  |  | W | 1 | 18 | 0.3 | WN | SW06 | SW06
CP08-399 |  | - | P02-03 |  | 0 | CP08-399-P02-03 |  |  | W | 1 | 18 | 0.3 | WN | TW01 | TW01
CP08-399A |  | - | P01-05 |  | 0 | CP08-399A-P01-05 |  |  | W | 1 | 720 | 12 | ALW | WS01 | WS01
CP08-399A |  | - | P02-05 |  | 0 | CP08-399A-P02-05 |  |  | W | 1 | 240 | 4 | ALW | JIG-HAND BEND | JIG-HAND BEND
CP08-399A |  | - | P03-05 |  | 0 | CP08-399A-P03-05 |  |  | W | 1 | 240 | 4 | ALW | JIG-HAND BEND | JIG-HAND BEND
CP08-399A |  | - | P04-05 |  | 0 | CP08-399A-P04-05 |  |  | W | 1 | 240 | 4 | ALW | PP23-060T | PP23
CP08-399B |  | - | P01-01 |  | 0 | CP08-399B-P01-02 |  |  | W | 1 | 480 | 8 | ALW | WS01 | WS01
CP08-399C |  | - | P01-01 |  | 0 | CP08-399C-P01-02 |  |  | W | 1 | 1200 | 20 | ALW | WS01 | WS01
CP08-399D |  | - | P01-04 |  | 0 | CP08-399D-P01-04 |  |  | W | 1 | 600 | 10 | ALW | WS01 | WS01
CP08-399D |  | - | P02-04 |  | 0 | CP08-399D-P02-04 |  |  | W | 1 | 360 | 6 | ALW | PP23-060T | PP23
CP08-399D |  | - | P03-04 |  | 0 | CP08-399D-P03-04 |  |  | W | 1 | 420 | 7 | ALW | JIG-HAND BEND | JIG-HAND BEND
CP08-400 | GC02-011 | - | P01-04 |  | 0 | CP08-400-P01-04 |  |  | ST | 1 | 360 | 6 | ST-4 | PP24-160T | PP24 | PP25
CP08-400 | GC02-011 | - | P02-04 |  | 0 | CP08-400-P02-04 |  |  | ST | 1 | 360 | 6 | ST-4 | PP25-160T | PP25 | PP24
CP08-400 | GC02-011 | - | P03-04 |  | 0 | CP08-400-P03-04 |  |  | ST | 2 | 360 | 6 | ST-4 | PP28-110T | PP28 | PP26
CP08-403 |  | - | P01-04 |  | 0 | CP08-403-P01-04 |  |  | TR | 1 | 60 | 1 | TR | TM06 | TM06 | TM05-40/MIN | TM03
CP08-403 |  | - | P02-04 |  | 0 | CP08-403-P02-04 |  |  | TR | 1 | 60 | 1 | TR | PB01 | PB01 | PB05 | [7 empty] | EFF 010422-NO MORE PROCESS SM1
CP08-403 |  | - | P03-04 |  | 0 | CP08-403-P03-04 |  |  | TR | 1 | 80 | 3 | TR | PP31 | [9 empty] | RUN PB1,PB3,PB4
CP08-403 |  | - |  |  | 0
CP08-404 |  | - | P01-04 |  | 0 | CP08-404-P01-03 |  |  | ST | 1 | 50 | 0.83333 | TR | PP29 | PP29
CP08-404 |  | - | P02-04 |  | 0 | CP08-404-P02-03 |  |  | ST | 2 | 60 | 1 | TR | PP33 | PP33 | [8 empty] | RUN PB1,PB3. RUN PB5,PB3-250522 | RUN PB1,PB3/PB2
CP08-404 |  | - | P03-04 |  | 0 | [18 empty] | EFF-180422 | FOR BENDING PROCESS SAME TOOLING V CP08-322
CP08-405 |  | - | P01-04 |  | 0 | CP08-405-P01-04 |  |  | TR | 1 | 30 | 0.5 | TR | TM05 | TM03 | TM05 | TM06
CP08-405 |  | - | P02-04 |  | 0 | CP08-405-P02-04 |  |  | TR | 1 | 35 | 0.58333 | TR | PB05 | PB07 | PB01 | PB05 | [6 empty] | SHARE TOOLING 'R' WITH CP08-313,CP08-311
CP08-405 |  | - | P03-04 |  | 0 | CP08-405-P03-04 |  |  | TR | 1 | 35 | 0.58333 | TR | PB02 | PB03 | PB02 | [7 empty] | SAME TOOLING V CP08-420 | RUN PB7,PB2(40PCS/HOUR) - ON 250522. RUN PB5, PB2
CP08-406 |  | - | P01-06 |  | 0 | CP08-406-P01-06 |  |  | T/S | 1 | 30 | 0.5 | TR | TM05 | TM03 | TM05 | TM06 | [6 empty] | SHARE TOOLING W CP08-500,CP08-406
CP08-406 |  | - | P02-06 |  | 0 | CP08-406-P02-06 |  |  | T/S | 1 | 120 | 2 | ST-4 | PP31 | PP24 | PP23 | PP31 | PP21 | PP15
CP08-406 |  | - | P03-06 |  | 0 | CP08-406-P03-06 |  |  | T/S | 1 | 120 | 2 | ST-4 | PP31 | PP28 | PP23 | PP31 | PP21 | PP10 | PP15
CP08-406 |  | - | P04-06 |  | 0 | CP08-406-P04-06 |  |  | T/S | 1 | 60 | 1 | TR | PB07 | PB07 | PB05 | [7 empty] | PB5,PB3 | PB1,PB2
CP08-406 |  | - | P05-06 |  | 0 | CP08-406-P05-06 |  |  | T/S | 1 | 60 | 1 | TR | PB03 | PB03 | PB08 | [7 empty] | PB1,PB3,PB2 RUN PB7,PB2-120622 | EFF-140422,RUN PB1,PB4(1 opt),PB3(opt)
CP08-407 |  | - | P01-07 |  | 0 |  |  |  | T/S | 1 | 18 | 0.3 | TR | TM03 | TM03
CP08-407 |  | - | P02-07 |  | 0 |  |  |  | T/S | 1 | 120 | 2 | ST-4 | PP31 | PP28 | PP21 | PP12 | PP04 | PP05 | PP31
CP08-407 |  | - | P03-07 |  | 0 |  |  |  | T/S | 1 | 120 | 2 | ST-1 | PP31 | PP14 | PP21 | PP31 | PP05 | PP24 | PP31 | PP05
CP08-407 |  | - | P04-07 |  | 0 |  |  |  | T/S | 1 | 50 | 0.83333 | TR | PB02 | PB02 | PB03 | PB08
CP08-407 |  | - | P05-07 |  | 0 |  |  |  | T/S | 1 | 50 | 0.83333 | TR | PB07 | PB05 | PB07 | RUN PB2,PB5,SW5 (PB2,SW5-1 OPT,PB5-1 OPT) | RUN PB1,PB2,PB3,PB7,SW5 | PB2,PB1,PB3,PB4 |  |  |  |  | RUN PB1,PB2,PB3,PB7,SW5 | PB2,PB5,SW5(PB2,SW5-1 OPT,PB5-1OPT)
CP08-407 |  | - | P06-07 |  | 0 |  |  |  | T/S |  | 50 | 0.83333 | TR | SW09 | SW09 | SW05 | SW14 | [7 empty] | EFF-240422 RUN PB2,PB7,SW5 (2 OPRT)
CP08-408 |  | - | P01-05 |  | 0 | CP08-408-P01-05 |  |  | T/S | 1 | 20 | 0.33333 | TR | TM06 | TM05 | TM03
CP08-408 |  | - | P02-05 |  | 0 | CP08-408-P02-05 |  |  | T/S | 1 | 120 | 2 | ST-2 | PP31 | PP15 | PP21 | PP31 | [6 empty] | NET - ORANGE
CP08-408 |  | - | P03-05 |  | 0 | CP08-408-P03-05 |  |  | T/S | 1 | 32 | 0.53333 | TR | PB05 | PB05 | PB01 | [7 empty] | *IF RUN PB1,PB3,PB2 (NEED 3 MACHINE) IF RUN PB5,PB2 (NEED 2 MACHINE ONLY - 280322) | PB7,PB3,PB2
CP08-408 |  | - | P04-05 |  | 0 | CP08-408-P04-05 |  |  | T/S | 1 | 32 | 0.53333 | TR | PB02 | PB02 | PB1,PB3,PB2 | [7 empty] | RUN PB1,PB3,PB4 RUN PB1,PB3,PB2 | RUN PB5,PB2 ON 040822
CP08-415A |  | - | P01-04 |  | 0 | CP08-415A-P01-04 |  |  | T/S | 1 | 35 | 0.58333 | TR | TM05 | TM06 | TM03 | TM05
CP08-415A |  | - | P02-04 |  | 0 | CP08-415A-P02-04 |  |  | T/S | 1 | 40 | 0.66667 | TR | PB05 | PB2 | PB3,PB4 | PB05 | [6 empty] | PB4,PB3,PB1 RUN PB2,PB3,PB4 | EFF-5/4-RUN PB5,SW9
CP08-415A |  | - | P03-04 |  | 0 | CP08-415A-P03-04 |  |  | T/S | 1 | 60 | 1 | WN | SW09 | SW04 | SW06 | SW01 | SW09
CP08-415 |  | - | P01-04 |  | 0 | CP08-415-P01-04 |  |  | ST | 1 | 60 | 1 | ST-3 | SW09 | SW01 | SW09
CP08-415 |  | - | P02-04 |  | 0 | CP08-415-P02-04 |  |  | ST | 1 | 30 | 0.5 | ST-1 | PAINTING | PAINTING
CP08-415 |  | - | P03-04 |  | 0 | CP08-415-P03-04 |  |  | ST | 1 | 30 | 0.5 | ST-3 | CLEAN | CLEANING
CP08-416 |  | - | P01-03 |  | 0 | CP08-416-P01-03 |  |  | TR | 1 | 70 | 1.1667 | TR | TM05 | TM05 | TM03 | TM06 | [6 empty] | RUN PB4 ON 270622
CP08-416 |  | - | P02-03 |  | 0 | CP08-416-P02-03 |  |  | TR | 1 | 40 | 0.66667 | TR | PB04 | PB04 | [8 empty] | RUN PB6
CP08-417 |  | - | P01-04 |  | 0 | CP08-417-P01-04 |  |  | TR | 1 | 48 | 0.8 | SM | SM01 | SM01
CP08-417 |  | - | P02-04 |  | 0 | CP08-417-P02-04 |  |  | TR | 1 | 150 | 2.5 | TR | TM05 | TM05 | TM03 | TM06
CP08-417 |  | - | P03-04 |  | 0 | CP08-417-P03-04 |  |  | TR | 1 | 120 | 2 | TR | PB08 | PB04 | PB05 | PB01 | PB08
CP08-418 |  | - | P01-03 |  | 0 | CP08-418-P01-03 |  |  | TR | 1 | 30 | 0.5 | TR | TM05 | TM05 | TM03 | TM06
CP08-418 |  | - | P02-03 |  | 0 | CP08-418-P02-03 |  |  | TR | 1 | 40 | 0.66667 | TR | PB05 | PB05 | PB07 | PB01 | [6 empty] | RUN PB7-070622
CP08-419 |  | - | P01-03 |  | 0 | CP08-419-P01-03 |  |  | TR | 1 | 72 | 1.2 | TR | TM03 | TM03 | TM05 | TM06 | TM02
CP08-419 |  | - | P02-03 |  | 0 | CP08-419-P02-03 |  |  | TR | 1 | 108 | 1.8 | TR | PB07 | PB07 | PB05 | PB01 | PB04 | [5 empty] | EFF,010422-NO MORE PROCESS SM1 | RUN PB7 RUN PB4-090622
CP08-420 |  | - | P01-03 |  | 0 | CP08-420-P01-03 |  |  | TR | 1 | 40 | 0.66667 | TR | TM05 | TM05 | TM03 | TM06 | TM02 | [5 empty] | SAME TOOLING V CP08-419
CP08-420 |  | - | P02-03 |  | 0 | CP08-420-P02-03 |  |  | TR | 1 | 80 | 1.3333 | TR | PB04 | PB04 | PB03 | PB02 | PB07 | [5 empty] | EFF,010422-NO MORE PROCESS SM1 | PB3,PB2-RUN ON 090622
|  | - |  |  | 0 |  |  |  | TR | 1 | [6 empty] | PB4-2/3,3/3(1 TIME RUN) | PB07 | [5 empty] | SAME TOOLING V CP08-405 | RUN PB4-2/3,3/3(1 TIME RUN)
CP08-421 |  | - | P01-03 |  | 0 | CP08-421-P01-03 |  |  | TR | 1 | 90 | 1.5 | TR | TM05 | TM05 | TM03 | TM06 | TM02
CP08-421 |  | - | P02-03 |  | 0 | CP08-421-P02-03 |  |  | TR | 1 | 120 | 2 | TR | PB08 | PB04 | PB02 | PB03 | PB08 | [5 empty] | PB1-RUN ON 240522
CP08-422 |  | - | P01-03 |  | 0 | CP08-422-P01-03 |  |  | TR | 1 | 50 | 0.83333 | TR | TM05 | TM05 | TM03 | TM06 | TM02
CP08-422 |  | - | P02-03 |  | 0 | CP08-422-P02-03 |  |  | TR | 1 | 72 | 1.2 | TR | PB08 | PB02 | PB03 | PB08 | [6 empty] | PB4 | PB1, RUN PB3 ON 180722
CP08-423 |  | - | P01-02 |  | 0 | CP08-423-P01-02 |  |  | TR | 1 | 40 | 0.66667 | TR | TM03 | TM03 | TM05 | TM06
CP08-424 |  | - | P01-03 |  | 0 | CP08-424-P01-03 |  |  | TR | 1 | 36 | 0.6 | TR | TM05 | TM03 | TM05 | TM06
CP08-424 |  | - | P02-03 |  | 0 | CP08-424-P02-03 |  |  | TR | 1 | 90 | 1.5 | TR | PB08 | PB02 | PB03 | PB04 | PB08 | [5 empty] | PB1 | RUN PB3 ON 090622, RUN PB7-ON160722
CP08-425 |  | - | P01-03 |  | 0 | CP08-425-P01-03 |  |  | TR | 1 | 60 | 1 | TR | TM03 | TM03 | TM05 | TM06 | [6 empty] | SAME TOOLING V CP08-426
CP08-425 |  | - | P02-03 |  | 0 | CP08-425-P02-03 |  |  | TR | 1 | 120 | 2 | TR | PB08 | PB08 | PB07 | PB02 | PB03 | PB01 |  |  |  |  | RUN PB4 | PB6
CP08-426 |  | - | P01-02 |  | 0 | CP08-426-P01-02 |  |  | TR | 1 | 60 | 1 | TR | TM03 | TM03 | TM05 | TM06 | [6 empty] | SAME TOOLING V CP08-425
CP08-427 |  | - | P01-03 |  | 0 | CP08-427-P01-03 |  |  | TR | 1 | 28 | 0.46667 | TR | TM06 | TM05 | TM03 | TM06
CP08-427 |  | - | P02-03 |  | 0 | CP08-427-P02-03 |  |  | TR | 2 | 30 | 0.5 | TR | PB05 | PB05 | PB07 | [7 empty] | NET ORANGE. PB7-RUN ON 090622. NEED RUN 2 OPT | RUN PB5
CP08-428A |  | - | P01-03 |  | 0 | CP08-428A-P01-03 |  |  | T/S | 1 | 47 | 0.78333 | TR | TM03 | TM03
CP08-428A |  | - | P02-03 |  | 0 | CP08-428A-P02-03 |  |  | T/S | 1 | 96 | 1.6 | TR | PB07 | PB01 | PB07 | PB05
CP08-428B |  | - | P01-03 |  | 0 | CP08-428B-P01-03 |  |  | TR | 1 | 65 | 1.0833 | TR | TM06 | TM06 | TM03 | TM05
CP08-428B |  | - | P02-03 |  | 0 | CP08-428B-P02-03 |  |  | TR | 1 | 72 | 1.2 | TR | PB04 | PB01 | PB05 | PB04 | PB07 | [5 empty] | PB4 ON 080722
CP08-428C |  | - | P01-03 |  | 0 | CP08-428C-P01-03 |  |  | TR | 1 | 60 | 1 | TR | TM06 | TM06 | TM03 | TM05
CP08-428C |  | - | P02-03 |  | 0 | CP08-428C-P02-03 |  |  | TR | 1 | 95 | 1.5833 | TR | PB04 | PB04 | PB01 | PB05 | PB07
CP08-428D |  | - | P01-03 |  | 0 | CP08-428D-P01-03 |  |  | TR | 1 | 55 | 0.91667 | TR | TM06 | TM06 | TM03 | TM05
CP08-428D |  | - | P02-03 |  | 0 | CP08-428D-P02-03 |  |  | TR | 1 | 70 | 1.1667 | TR | PB07 | PB01 | PB05 | PB07
CP08-428E |  | - | P01-04 |  | 0 | CP08-428E-P01-04 |  |  | S/T | 1 | 1904 | 31.7333 | SM | SM01 | SM01
CP08-428E |  | - | P02-04 |  | 0 | CP08-428E-P02-04 |  |  | S/T | 1 | 350 | 5.8333 | ST-1 | PP31 | PP10 | PP13 | PP31
CP08-428E |  | - | P03-04 |  | 0 | CP08-428E-P03-04 |  |  | S/T | 1 | 300 | 5 | TR | PB04 | PB03 | PB02 | PB04 | PB08
CP08-428 |  | - | P01-09 |  | 0 | CP08-428-P01-09 |  |  | ST | 1 | 90 | 1.5 | ST-3 | SW01 | SW01 | [8 empty] | NORMALLY RUN P01-09,P02-09,P03-09,P04-09 THEN RUN CP08-429-P01-06,P02-06,P03-06,THEN ONLY CONTINUE RUN CP08-428-P05-09,P06-09
CP08-428 |  | - | P02-09 |  | 0 | CP08-428-P02-09 |  |  | ST | 1 | 120 | 2 | ST-3 | SW01 | SW01 | [8 empty] | RUN NUT FIRST,EG:CP08-428-P01-09,P02-09,P03-09,P04-09,THAN RUN CP08-429-P01-06,P02-06,P03-06,P04-06,P05-06
CP08-428 |  | - | P03-09 |  | 0 | CP08-428-P03-09 |  |  | ST | 1 | 120 | 2 | ST-3 | SW01 | SW01
CP08-428 |  | - | P04-09 |  | 0 | CP08-428-P04-09 |  |  | ST | 1 | 90 | 1.5 | ST-3 | SW01 | SW01
CP08-428 |  | - | P05-09 |  | 0 | CP08-428-P05-09 |  |  | ST | 1 | 40 | 0.66667 | ST-3 | SW01 | SW01 | [8 empty] | P05-09 - ASSY PROCESS | P05 & P06 PROCESS FOR SW PROCESS TOGETHER RUN
CP08-428 |  | - | P06-09 |  | 0 | CP08-428-P06-09 |  |  | ST | 2 | 30 | 0.5 | ST-3 | SW01 | SW01
CP08-428 |  | - | P07-09 |  | 0 | CP08-428-P07-09 |  |  | ST | 2 | 17 | 0.28333 | ST-3 | PAINTING | PAINTING
CP08-428 |  | - | P08-09 |  | 0 | CP08-428-P08-09 |  |  | ST | 2 | 60 | 1 | ST-3 | CLEAN | CLEANING
CP08-429A |  | - | P01-03 |  | 0 | CP08-429A-P01-03 |  |  | T/S | 1 | 30 | 0.5 | TR | TM03 | TM03 | TM05 | TM06
CP08-429A |  | - | P02-03 |  | 0 | CP08-429A-P02-03 |  |  | T/S | 1 | 120 | 2 | TR | PB05 | PB07 | PB01 | PB05
CP08-429B |  | - | P01-03 |  | 0 | CP08-429B-P01-03 |  |  | T/S | 1 | 60 | 1 | TR | TM03 | TM03 | TM05
CP08-429B |  | - | P02-03 |  | 0 | CP08-429B-P02-03 |  |  | T/S | 1 | 120 | 2 | TR | PB04 | PB04 | PB07 | PB05 | [6 empty] | RUN PB5
CP08-429C |  | - | P01-03 |  | 0 | CP08-429C-P01-03 |  |  | T/S | 1 | 50 | 0.83333 | TR | TM03 | TM03 | TM05
CP08-429C |  | - | P02-03 |  | 0 | CP08-429C-P02-03 |  |  | T/S | 1 | 120 | 2 | TR | PB04 | PB04 | PB05 | PB07
CP08-429D |  | - | P01-03 |  | 0 | CP08-429D-P01-03 |  |  | T/S | 1 | 35 | 0.58333 | TR | TM03 | TM03 | TM05
CP08-429D |  | - | P02-02 |  | 0 | CP08-429D-P02-03 |  |  | T/S | 1 | 120 | 2 | TR | PB05 | PB01 | PB05 | PB07
CP08-429 |  | - | P01-06 |  | 0 | CP08-429-P01-06 |  |  | ST | 1 | 120 | 2 | ST-3 | SW01 | SW01
CP08-429 |  | - | P02-06 |  | 0 | CP08-429-P02-06 |  |  | ST | 1 | 120 | 2 | ST-3 | SW01 | SW01
CP08-429 |  | - | P03-06 |  | 0 | CP08-429-P03-06 |  |  | ST | 1 | 30 | 0.5 | ST-3 | SW01 | SW01 | [8 empty] | P03-06 ASSY PROCESS
CP08-429 |  | - | P04-06 |  | 0 | CP08-429-P04-06 |  |  | ST | 2 | 30 | 0.5 | ST-1 | PAINTING | PAINTING
CP08-429 |  | - | P05-06 |  | 0 | CP08-429-P05-06 |  |  | ST | 1 | 60 | 1 | TR | CLEAN | CLEANING
CP08-430 |  | - | P01-03 |  | 0 | CP08-430-P01-03 |  |  | T/S | 1 | 80 | 1.3333 | TR | TM03 | [9 empty] | ONLY CAN RUN TM03,GOT TAPPING PROCESS
CP08-430 |  | - | P02-03 |  | 0 | CP08-430-P02-03 |  |  | T/S | 1 | 60 | 1 | TR | PB05 | PB04 | PB05 | PB01 | [6 empty] | EFF 010422 NO MORE PROCESS SM1
CP08-431 |  | - | P01-06 |  | 0 | CP08-431-P01-06 |  |  | S/T | 1 | 600 | 10 | SM | SM01 | SM01 | [8 empty] | 2 TIMES SLITTING
CP08-431 |  | - | P02-06 |  | 0 | CP08-431-P02-06 |  |  | S/T | 1 | 300 | 5 | ST-4 | PP21-110T | PP28 | PP16 | PP26 | PP21
CP08-431 |  | - | P03-06 |  | 0 | CP08-431-P03-06 |  |  | S/T | 1 | 300 | 5 | ST-4 | PP21-110T | PP28 | PP27 | PP26 | PP21 | PP16 |  |  |  |  | SHARE DIE V CP08-432,CP08-431
CP08-431 |  | - | P04-06 |  | 0 | CP08-431-P04-06 |  |  | S/T | 1 | 111 | 1.85 | TR | PB02 | PB02 | PB03 | PB04 | PB02 | PB08 | PB03 | PB05 |  |  | IF RUN PB05: P04-06 & P05-06 ONE SHORT RUN
CP08-431 |  | - | P05-06 |  | 0 | CP08-431-P05-06 |  |  | S/T | 1 | 110 | 1.8333 | TR | PB03 | PB03 | PB04 |  |  | PB08 | PB03 | PB05 |  |  | IF RUN PB05: P04-06 & P05-06 ONE SHORT RUN
CP08-432 |  | - | P01-03 |  | 0 | CP08-432-P01-04 |  |  | S/T | 1 | 600 | 10 | SM | SM01 | SM01
CP08-432 |  | - | P02-03 |  | 0 | CP08-432-P02-04 |  |  | S/T | 1 | 300 | 5 | ST-4 | PP21-110T | PP28 | PP21 | PP16 | PP17 | [5 empty] | SHARE DIE V CP08-431,CP08-432
CP08-432 |  | - | P03-03 |  | 0 | CP08-432-P03-04 |  |  | S/T | 1 | 150 | 2.5 | TR | PB08 | PB08 | PB02 | PB04 | PB07 | PB03
CP08-433 |  | - | P01-06 |  | 0 | CP08-433-P01-06 |  |  | S/T | 1 | 6120 | 102 | SM | SM01 | SM01
CP08-433 |  | - | P02-06 |  | 0 | CP08-433-P02-06 |  |  | S/T | 1 | 300 | 5 | ST-4 | PP21-110T | PP28 | PP17 | PP21 | PP15 | PP16 | PP26 |  |  |  | SHARE DIE V CP08-434,CP08-433
CP08-433 |  | - | P03-06 |  | 0 | CP08-433-P03-06 |  |  | S/T | 1 | 300 | 5 | ST-4 | PP21-110T | PP28 | PP21 | PP20 | PP15 | PP17 | PP26
CP08-433 |  | - | P04-06 |  | 0 | CP08-433-P04-06 |  |  | S/T | 1 | 132 | 2.2 | TR | PB08 | PB03 | PB04 | PB08 | PB07
CP08-433 |  | - | P05-06 |  | 0 | CP08-433-P05-06 |  |  | S/T | 1 | 96 | 1.6 | TR | PB08 | PB08 | PB07 | PB04 | PB07 | PB05 |  |  |  |  | RUN PB7-P04-05,P05-05-ON070622 RUN PB3,PB4 RUN PB3,PB4 ON 170822 RUN PB4-P04-05,-100pPCS/HOUR,PB04-P05-05-140PCS/HOUR ON 010722-90PCS/HRS
CP08-434 |  | - | P01-04 |  | 0 | CP08-434-P01-04 |  |  | S/T | 1 | 5040 | 84 | SM | SM01 | SM01
CP08-434 |  | - | P02-04 |  | 0 | CP08-434-P02-04 |  |  | S/T | 1 | 300 | 5 | ST-4 | PP21-110T | PP28 | PP21 | PP27 | PP26 | PP01 | PP17 |  |  |  | SHARE DIE V CP08-433,CP08-434
CP08-434 |  | - | P03-04 |  | 0 | CP08-434-P03-04 |  |  | S/T | 1 | 100 | 1.6667 | TR | PB08 | PB03 | PB02 | PB03 | [6 empty] | RUN PB2/PB3
CP08-435 &CP08-436 | GC02-012 | - | P01-02 |  | 0 | CP08-435 &CP08-436-P01-02 |  |  | TR | 1 | 80 | 1.3333 | TR | TM06 | TM05 | TM03 | TM06
CP08-435 |  | - | P01-03 |  | 0 | CP08-435-P01-03 |  |  | PB | 1 | 160 | 2.6667 | TR | PB04 | PB04 | PB02 | PB01 | PB07 | PB03 |  |  |  |  | RUN PB1,PB3 ON 270622 PB2,PB3
CP08-435 |  | - | P02-03 |  | 0 | CP08-435-P02-03 |  |  | PB | 1 | 120 | 2 | TR | PB03 | PB03 | PB02 | PB08
CP08-436 |  | - | P01-02 |  | 0 | CP08-436-P01-02 |  |  | PB | 1 | 114 | 1.9 | TR | PB04 | PB04 | PB03 | PB02 | PB01 | PB07 |  |  |  |  | RUN PB6 RUN PB1,PB2 ON 050622, RUN PB4 RUN PB1 ON 270622
CP08-437 |  | - | P01-05 |  | 0 | CP08-437-P01-05 |  |  | S/T | 1 | 5400 | 90 | SM | SM01 | SM01
CP08-437 |  | - | P02-05 |  | 0 | CP08-437-P02-05 |  |  | S/T | 1 | 480 | 8 | ST-1 | PP03-060T | PP03 | PP05 | PP10 | PP13 | PP04 | PP02 |  |  |  | SHARE DIE V CP08-186 - P02-04
CP08-437 |  | - | P03-05 |  | 0 | CP08-437-P03-05 |  |  | S/T | 1 | 360 | 6 | ST-1 | PP03-060T | PP03 | PP02 | PP04 | PP13 | PP03 | PP22
CP08-437 |  | - | P04-05 |  | 0 | CP08-437-P04-05 |  |  | S/T | 1 | 200 | 3.3333 | TR | PP22 | PP22
CP08-437 |  | - |  |  | 0 |  |  |  | S/T | 1 | 480 | 8 | TR
CP08-438 |  | - | P01-04 |  | 0 | CP08-438-P01-04 |  |  | TR | 1 | 22 | 0.36667 | TR | TM06 | TM06 | TM03 | TM05 | [6 empty] | SAME TOOLING V CP08-439
CP08-438 |  | - | P02-04 |  | 0 | CP08-438-P02-04 |  |  | TR | 2 | 18 | 0.3 | TR | PB07 | PB07 | PB07 | PB05 | [6 empty] | NET ORANGE. PB5, RUN PB7,PB2-ON 080722
CP08-438 |  | - | P03-04 |  | 0 | CP08-438-P03-04 |  |  | TR | 2 | 18 | 0.3 | TR | PB03 | PB03 | PB02 | PB03 | [6 empty] | PB2. 4 OPTS , RUN PB5,PB3/PB2=28PCS/HR
CP08-439 |  | - | P01-06 |  | 0 | CP08-439-P01-06 |  |  | TR | 1 | 18 | 0.3 | TR | TM06 | TM06 | TM05 | TM03 | [6 empty] | SAME TOOLING V CP08-438
CP08-439 |  | - | P02-06 |  | 0 | CP08-439-P02-06 |  |  | TR | 1 | 18 | 0.3 | TR | TM02 | TM02 | [8 empty] | RUN PB7,PB2,PB3
CP08-439 |  | - | P03-06 |  | 0 | CP08-439-P03-06 |  |  | TR | 1 | 18 | 0.3 | TR | PB05 | PB01 | PB03 | PB05 | PB07 | [5 empty] | PB5,PB3,PB2
CP08-439 |  | - | P04-06 |  | 0 | CP08-439-P04-06 |  |  | TR | 1 | 18 | 0.3 | TR | PB02 | PB02 |  | PB02 | PB02 | [5 empty] | RUN PB5-(2 OPT),PB2,PB3-(2 OPT) ON 290822
CP08-439 |  | - | P05-06 |  | 0 | CP08-439-P05-06 |  |  | TR | 2 | 18 | 0.3 | TR | PB03 | PB03 | PB02 |  | PB03 | [5 empty] | NET ORANGE
CP08-440 |  | - | P01-03 |  | 0 | CP08-440-P01-03 |  |  | TR | 1 | 96 | 1.6 | TR | TM03 | TM03 | TM05 | TM06 | TM02
CP08-440 |  | - | P02-03 |  | 0 | CP08-440-P02-03 |  |  | TR | 1 | 180 | 3 | TR | PB01 | PB01 | PB04 | PB04 | PB02 | [5 empty] | RUN PB1 ON 070622
CP08-441 |  | - | P01-02 |  | 0 | CP08-441-P01-03 |  |  | TR | 1 | 75 | 1.25 | #N/A | TM03 | TM03 | TM05 | TM06
CP08-441 |  | - | P02-02 |  | 0 | CP08-441-P02-03 |  |  | TR | 1 | 50 | 0.83333 | #N/A | PB01 | PB01 | PB05 | PB07
CP08-442 |  | - | P01-04 |  | 0 | CP08-442-P01-04 |  |  | TR | 1 | 90 | 4 | TR | SM01 | SM1 | [8 empty] | NEED SM1 PROCESS
CP08-442 |  | - | P02-04 |  | 0 | CP08-442-P02-04 |  |  | TR | 1 | 180 | 1.5 | TR | TM05 | TM05 | TM03 | TM06
CP08-443 |  | - | P01-04 |  | 0 | CP08-443-P01-04 |  |  | TR | 1 | 240 | 4 | SM | SM01 | SM01 | [8 empty] | W1219-L610
CP08-443 |  | - | P02-04 |  | 0 | CP08-443-P02-04 |  |  | TR | 1 | 120 | 2 | TR | TM05 | TM05 | TM06 | TM03
CP08-443 |  | - | P03-04 |  | 0 | CP08-443-P03-04 |  |  | TR | 1 | 90 | 1.5 | TR | PB04 | PB04 | PB08 | PB02
CP08-447 |  | - | P01-04 |  | 0 | CP08-447-P01-04 |  |  | TR | 1 | 50 | 0.83333 | TR | TM06 | TM03 | TM05 | TM06
CP08-447 |  | - | P02-04 |  | 0 | CP08-447-P02-04 |  |  | TR | 1 | 70 | 1.1667 | TR | PB04 | PB04 | PB03 | PB03 | PB05 | [5 empty] | RUN PB1,PB1 ON 270622
CP08-447 |  | - | P03-04 |  | 0 | CP08-447-P03-04 |  |  | TR | 1 | 70 | 1.1667 | TR | PB04 | PB04 | PB01 | PB03 | PB05 | [5 empty] | RUN PB3,PB6, RUN PB4,PB7 | RUN PB05 CAN TOGETHER RUN 2 PROCESS
CP08-448 |  | - | P01-03 |  | 0 | CP08-448-P01-03 |  |  | TR | 1 | 45 | 0.75 | TR | TM03 | TM03
CP08-448 |  | - | P02-03 |  | 0 | CP08-448-P02-03 |  |  | TR | 1 | 100 | 1.6667 | TR | PB04 | PB04 | PB08
CP08-449 | GP01-014 | - | P01-02 |  | 0 | CP08-449-P01-02 |  |  | TR | 1 | 280 | 4.6667 | TR | TM06 | TM03 | TM05 | TM06
CP08-450 | GP01-015 | - | P01-04 |  | 0 | CP08-450-P01-04 |  |  | TR | 1 | 180 | 3 | SM | SM01 | SM01
CP08-450 | GP01-015 | - | P02-04 |  | 0 | CP08-450-P02-04 |  |  | TR | 1 | 140 | 2.3333 | TR | TM06 | TM03 | TM05 | TM06
CP08-450 | GP01-015 | - | P03-04 |  | 0 | CP08-450-P03-04 |  |  | TR | 1 | 60 | 1 | TR | PB04 | PB04 | PB05
CP08-451 |  | - | P01-03 |  | 0 | CP08-451-P01-03 |  |  | TR | 1 | 168 | 2.8 | TR | TM05 | TM05 | TM03 | TM06
CP08-451 |  | - | P02-03 |  | 0 | CP08-451-P02-03 |  |  | TR | 1 | 40 | 0.66667 | TR | PB04 | PB04
CP08-452 |  | - | P01-03 |  | 0 | CP08-452-P01-03 |  |  | TR | 1 | 180 | 3 | TR | TM05 | TM03 | TM05 | TM06
CP08-452 |  | - | P02-03 |  | 0 | CP08-452-P02-03 |  |  | TR | 1 | 80 | 1.3333 | TR | PB04 | PB04
CP08-453A |  | - | P01-03 |  | 0 | CP08-453A-P01-03 |  |  | TR | 1 | 160 | 2.6667 | TR | TM05 | TM05 | TM03 | TM06
CP08-453A |  | - | P02-03 |  | 0 | CP08-453A-P02-03 |  |  | TR | 1 | 160 | 2.6667 | TR | PB04 | PB04 | PB03
CP08-453 |  | - | P01-03 |  | 0 | CP08-453-P01-03 |  |  | ST | 1 | 45 | 0.75 | ST-3 | SW01 | SW01
CP08-453 |  | - | P02-03 |  | 0 | CP08-453-P02-03 |  |  | ST | 1 | 90 | 1.5 | ST-2 | MANUAL WORK | OPERATOR
CP08-454 |  | - | P01-03 |  | 0 | CP08-454-P01-03 |  |  | TR | 1 | 110 | 1.8333 | TR | TM06 | TM05 | TM03 | TM06
CP08-454 |  | - | P02-03 |  | 0 | CP08-454-P02-03 |  |  | TR | 1 | 60 | 1 | TR | PB01 | PB01 | PB04 | PB05 | PB07 | [5 empty] | RUN PB4 ON 250922, RUN PB2,PB4
CP08-455 |  | - | P01-03 |  | 0 | CP08-455-P01-03 |  |  | ST | 1 | 45 | 0.75 | ST-3 | SW01 | SW01 | SW09
CP08-455 |  | - | P02-03 |  | 0 | CP08-455-P02-03 |  |  | ST | 1 | 90 | 1.5 | ST-1 | PAINTING | PAINTING
CP08-455A |  | - | P01-04 |  | 0 | CP08-455A-P01-04 |  |  | TR | 1 | 240 | 4 | SM | SM01 | SM01
CP08-455A |  | - | P02-04 |  | 0 | CP08-455A-P02-04 |  |  | TR | 1 | 240 | 4 | TR | TM06 | TM06 | TM03 | TM05
CP08-455A |  | - | P03-04 |  | 0 | CP08-455A-P03-04 |  |  | TR | 1 | 200 | 3.3333 | TR | PB04 | PB04
CP08-456 |  | - | P01-04 |  | 0 | CP08-456-P01-04 |  |  | ST | 1 | 360 | 6 | ST-3 | PP25-160T | PP18 | PP25 |  |  |  | PP25 | PP25 | PP28 | PP25 |  | PP26
CP08-456 |  | - | P02-04 |  | 0 | CP08-456-P02-04 |  |  | ST | 1 | 360 | 6 | ST-3 | PP20-110T | PP16 | PP26 | PP25 | PP24 | PP18 | PP28 | PP20 | PP20 | PP20 | SHARE V CP08-349,CP08-350,CP08-456,CP08-457 | PP20
CP08-456 |  | - | P03-04 |  | 0 | CP08-456-P03-04 |  |  | ST | 1 | 360 | 6 | ST-3 | PP28-110T | PP17 | PP20 | PP16 | PP28 | PP26 | PP20 | PP28 | PP26 | PP26 |  | PP28
CP08-457 |  | - | P01-04 |  | 0 | CP08-457-P01-04 |  |  | ST | 1 | 360 | 6 | ST-3 | PP25-160T | PP17 | PP25 | PP18 | PP25
CP08-457 |  | - | P02-04 |  | 0 | CP08-457-P02-04 |  |  | ST | 1 | 360 | 6 | ST-3 | PP20-110T | PP16 | PP20 | PP21 | PP20 | [5 empty] | SHARE V CP08-349,CP08-350,CP08-456,CP08-457
CP08-457 |  | - | P03-04 |  | 0 | CP08-457-P03-04 |  |  | ST | 1 | 360 | 6 | ST-3 | PP28-110T | PP27 | PP28 | PP21 | PP26
CP08-458 |  | - | P01-05 |  | 0 | CP08-458-P01-05 |  |  | ST | 1 | 300 | 5 | ST-3 | PP25-160T | PP18 | PP25 | PP24 | [6 empty] | SAME DIE WITH CP08-254 & CP08-255
CP08-458 |  | - | P02-05 |  | 0 | CP08-458-P02-05 |  |  | ST | 1 | 300 | 5 | ST-3 | PP26-110T | PP17 | PP26 | PP25 | [6 empty] | SAME DIE WITH CP08-254 & CP08-255
CP08-458 |  | - | P03-05 |  | 0 | CP08-458-P03-05 |  |  | ST | 1 | 300 | 5 | ST-3 | PP20-110T | PP16 | PP20 | [7 empty] | SAME DIE WITH CP08-254 & CP08-255
CP08-458 |  | - | P04-05 |  | 0 | CP08-458-P04-05 |  |  | ST | 2 | 300 | 5 | ST-3 | PP28-110T | PP27 | PP28 | [7 empty] | SAME DIE WITH CP08-254 & CP08-255
CP08-481 |  | - | P01-04 |  | 0 | CP08-481-P01-04 |  |  | ST | 1 | 240 | 4 | SM | SM01 | SM01
CP08-481 |  | - | P02-04 |  | 0 | CP08-481-P02-04 |  |  | ST | 1 | 300 | 5 | ST-1 | PP22 | PP04 | PP03 | PP19 | PP22
CP08-481 |  | - | P03-04 |  | 0 | CP08-481-P03-04 |  |  | ST | 1 | 300 | 5 | ST-1 | PP22 | PP03 | PP04 | PP13 | PP22 | PP05 |  |  |  |  | EFF 4/4/22 STAMPING RUN | SHARE DIE V -O02-007-P03-04,O2-008-P03-04,O02-012-P03-04,P08-186-P04-05,CP08-219B-P03-04,CP08-481-P03-04
CP08-482 |  | - | P01-04 |  | 0 | CP08-482-P01-04 |  |  | ST | 1 | 6300 | 105 | SM | SM01 | SM01 | [8 empty] | 2 TIMES SLITTING
CP08-482 |  | - | P02-04 |  | 0 | CP08-482-P02-04 |  |  | ST | 1 | 360 | 6 | ST-3 | PP10-080T | PP27 | PP17 | PP10 | PP20 | PP21 |  | PP20 |  |  | SHARE DIE V CP08-482,CP08-483
CP08-482 |  | - | P03-04 |  | 0 | CP08-482-P03-04 |  |  | ST | 1 | 240 | 4 | ST-3 | PP21-110T | PP16 | PP17 | PP10 | PP15 | PP21 | PP19 | PP28 |  |  | SHARE DIE V CP08-483,CP08-483
CP08-483 |  | - | P01-04 |  | 0 | CP08-483-P01-04 |  |  | ST | 1 | 205 | 3.4167 | SM | SM01 | SM01 | [8 empty] | 2 TIMES SLITTING
CP08-483 |  | - | P02-04 |  | 0 | CP08-483-P02-04 |  |  | ST | 1 | 360 | 6 | ST-2 | PP10-080T | PP19 | PP27 | PP17 | PP01 | PP16 | PP15 | PP20 | PP21 | PP14 | SHARE DIE V CP08-483,CP08-482
CP08-483 |  | - | P03-04 |  | 0 | CP08-483-P03-04 |  |  | ST | 1 | 240 | 4 | ST-3 | PP21-110T | PP21 | PP16 | PP17 | PP27 | PP26 | PP15 | PP28 | PP21 |  | SHARE DIE V CP08-483,CP08-482
CP08-488 |  | - | P01-05 |  | 0 | CP08-488-P01-05 |  |  | TR | 1 | 80 | 1.3333 | TR | TM02 | TM02
CP08-488 |  | - | P02-05 |  | 0 | CP08-488-P02-05 |  |  | TR | 1 | 80 | 1.3333 | WN | DEBURR | DEBURR
CP08-488 |  | - | P03-05 |  | 0 | CP08-488-P03-05 |  |  | TR | 1 | 120 | 2 | TR | PB04 | PB04 | PB03 | PB02 | PB08
CP08-488 |  | - | P04-05 |  | 0 | CP08-488-P04-05 |  |  | TR | 1 | 20 | 0.33333 | ST-1 | PAINTING | PAINTING
CP08-489 |  | - | P01-05 |  | 0 | CP08-489-P01-05 |  |  | TR | 1 | 80 | 1.3333 | TR | TM02 | TM02 | TM03 | TM05 | TM06
CP08-489 |  | - | P02-05 |  | 0 | CP08-489-P02-05 |  |  | TR | 1 | 15 | 0.25 | WN | DEBURR | DEBURR
CP08-489 |  | - | P03-05 |  | 0 | CP08-489-P03-05 |  |  | TR | 1 | 120 | 2 | TR | PB04 | PB04 | PB02 | PB03 | PB08
CP08-489 |  | - | P04-05 |  | 0 | CP08-489-P04-05 |  |  | TR | 1 | 15 | 0.25 | ST-1 | PAINTING | PAINTING
CP08-490 |  | - | P01-04 |  | 0 | CP08-490-P01-04 |  |  | TR | 1 | 80 | 1.3333 | TR | TM02 | TM02
CP08-490 |  | - | P02-04 |  | 0 | CP08-490-P02-04 |  |  | TR | 1 | 14 | 0.23333 | WN | DEBURR | DEBURR
CP08-490 |  | - | P03-04 |  | 0 | CP08-490-P03-04 |  |  | TR | 1 | 50 | 0.83333 | ST-1 | PAINTING | PAINTING
CP08-494 |  | - | P01-04 |  | 0 | CP08-494-P01-04 |  | SLIT TO SIZE | ST | 1 | 11040 | 184 | SM | SM01 | SM01 | [8 empty] | SAME DIE WITH CP08-566
CP08-494 |  | - | P02-04 |  | 0 | CP08-494-P02-04 |  | TRIMMING | ST | 1 | 360 | 6 | ST-3 | PP03-060T | PP21 | PP05 | PP22 | PP13 | PP02 | PP14 | PP12 |  | PP04 | SAME DIE WITH CP08-566
CP08-494 |  | - | P03-04 |  | 0 | CP08-494-P03-04 |  | BENDING | ST | 1 | 360 | 6 | ST-3 | PP04-060T | PP21 | PP04 | PP05 | PP22 | PP13 | PP10 | PP14 | PP02 | PP03 | SAME DIE WITH CP08-566
CP08-496 |  | - | P01-03 |  | 0 | CP08-496-P01-03 |  |  | ST | 1 | 15 | 0.25 | #N/A | STICK LABEL | STICK LABEL
CP08-496 |  | - | P02-03 |  | 0 | CP08-496-P02-03 |  |  | ST | 0 | 15 | 0.25 | #N/A | STICK LABEL | STICK LABEL
CP08-497 |  |  | P01-04 |  |  | CP08-497-P01-04 |  |  | TR | 1 | 240 | 4 | ST | SM01 | SM01
CP08-497 |  | - | P02-04 |  | 0 | CP08-497-P02-04 |  |  | TR | 1 | 210 | 3.5 | TR | TM05 | TM05 | TM03
CP08-497 |  | - | P03-04 |  | 0 | CP08-497-P03-04 |  |  | TR | 1 | 60 | 1 | TR | PB04 | PB04 | PB05
CP08-496A | GC02-032 | - | P01-05 |  | 0 | CP08-496A-P01-05 |  |  | ST | 1 | 240 | 4 | ST-4 | PP18-150T | PP26 | PP18 | PP25 | PP24
CP08-496A | GC02-032 | - | P02-05 |  | 0 | CP08-496A-P02-05 |  |  | ST | 1 | 240 | 4 | ST-4 | PP17-110T | PP20 | PP17 | PP26 | PP25
CP08-496A | GC02-032 | - | P03-05 |  | 0 | CP08-496A-P03-05 |  |  | ST | 1 | 240 | 4 | ST-4 | PP16-110T | PP25 | PP16 | PP20
CP08-496A | GC02-032 | - | P04-05 |  | 0 | CP08-496A-P04-05 |  |  | ST | 1 | 240 | 4 | ST-4 | PP27-110T | PP28 | PP27 | PP28
CP08-495 |  | - | P01-02 |  | 0 | CP08-495-P01-02 |  |  | ST | 1 | 360 | 6 | ST-1 | PP05-060T | PP05 | SM1 | PP16 | PP03 | PP04
CP08-495 |  | - | P02-02 |  | 0 | CP08-495-P02-02 |  |  | ST | 1 | 360 | 6 | ST-1 | PP04-060T | PP04 |  | PP17
CP08-496 |  | - | P01-02 |  | 0 |  |  |  | ST | 1 | 30 | 0.5 | ST | STICK LABEL | STICK LABEL
CP08-496 |  | - | P02-02 |  | 0 |  |  |  | ST | 1 | 30 | 0.5 | ST | STICK LABEL | STICK LABEL
CP08-544A |  | - | P02-04 |  | 0 | CP08-544A-P02-04 |  |  | ? | 1 | 360 | 6 | ST-4 | PP26-110T | PP26
CP08-545A |  | - | P03-04 |  | 0 | CP08-545A-P03-04 |  |  | ? | 1 | 360 | 6 | ST-4 | PP20-110T | PP20
CP08-545A |  | - | P04-04 |  | 0 | CP08-545A-P04-04 |  |  | ? | 1 | 360 | 6 | ST-4 | PP28-110T | PP28
CP08-498 |  | - | P01-04 |  | 0 | CP08-498-P01-04 |  |  | S/T | 1 | 240 | 4 | SM | SM01 | SM01
CP08-498 |  | - | P02-04 |  | 0 | CP08-498-P02-04 |  |  | S/T | 1 | 360 | 6 | ST-1 | PP13 | PP21 | PP15 | PP22 | PP02 | PP05 | PP13 | PP04 |  |  | P01-STAMPING PROCESS,EFFECTIVE-11/2/22
CP08-499 |  | - | P01-02 |  | 0 | CP08-499-P01-02 |  |  | ST | 2 | 30 | 0.5 | ST-3 | SW01 | SW01 | SW09
CP08-499A |  | - | P01-06 |  | 0 | CP08-499A-P01-06 |  |  | T/S | 1 | 120 | 2 | ST-4 | PP29-250T | PP29 | PP29 | PP29
CP08-499A |  | - | P02-06 |  | 0 | CP08-499A-P02-06 |  |  | T/S | 1 | 120 | 2 | ST-4 | PP30 | PP29 | PP33 | PP30
CP08-499A |  | - | P03-06 |  | 0 | CP08-499A-P03-06 |  |  | T/S | 1 | 120 | 2 | ST-3 | TP03 | TP03 | TP07 | [7 empty] | P01-STAMPING PROCESS EFFECTIVE - 19/2/22
CP08-499A |  | - | P04-06 |  | 0 | CP08-499A-P04-06 |  |  | T/S | 1 | 120 | 2 | AL | TP09 | TP09 | TP07 | [7 empty] | RUN TP3,TP7, GOT TAPPING-TP7(M4) PROCESS
CP08-499A |  | - | P05-06 |  | 0 | CP08-499A-P05-06 |  |  | T/S | 1 | 60 | 1 | TR | PB05 | PB05 | PB01 | [7 empty] | RUN PB7, RUN PB5 ON 220822
CP08-499B |  | - | P01-05 |  | 0 |  |  |  | TR | 1 | 80 | 1.3333 | TR | TM06 | TM03 | TM05 | TM06 | PP30
CP08-499B |  | - | P02-05 |  | 0 |  |  |  | TR | 1 | 102 | 1.7 | TR | PB04 | PB04 | PB01 | PB04 | PP21 | [5 empty] | RUN PB4,PB3,PB2-150622
CP08-499B |  | - | P03-05 |  | 0 |  |  |  | TR | 1 | 102 | 1.7 | TR | PB03 | PB03 | PB04 | PB01 | PP30 | [5 empty] | RUN PB4,PB1,PB3
CP08-499B |  | - | P04-05 |  | 0 |  |  |  | TR | 1 | 102 | 1.7 | TR | PB02 | PB02 | PB03 | PB07 | [6 empty] | RUN PB7,PB2,PB3 ON 140722 (2 opt)
CP08-499C |  | - | P01-03 |  | 0 | CP08-499C-P01-03 |  |  | TR | 1 | 90 | 1.5 | TR | TM06 | TM03 | TM05 | TM06
CP08-499C |  | - | P02-03 |  | 0 | CP08-499C-P02-03 |  |  | TR | 1 | 97 | 1.6167 | TR | PB07 | PB01 | PB07 | PB04 | PB05
CP08-500 |  | - | P01-07 |  | 0 | CP08-500-P01-07 |  |  | T/S | 1 | 30 | 0.5 | TR | TM03 | TM03 | [8 empty] | SHARE TOOLING W CP08-406,CP08-500
CP08-500 |  | - | P02-07 |  | 0 | CP08-500-P02-07 |  |  | T/S | 1 | 240 | 4 | TR | PP31 | PP31
CP08-500 |  | - | P03-07 |  | 0 | CP08-500-P03-07 |  |  | T/S | 1 | 120 | 2 | TR | PP31 | PP31 | PP28
CP08-500 |  | - | P04-07 |  | 0 | CP08-500-P04-07 |  |  | T/S | 1 | 60 | 1 | TR | PB07 | PB07 | [8 empty] | EFF-130422-RUN - PB4(1 OPT),PB1(1 OPT),PB3,PB7(1 OPR),TOTAL NEED 3 OPERATOR | M/C NO : PB01 MACHINE BREAK DOWN NEED RUN AT M/C :PB07,PB08,PB04,PB03
CP08-500 |  | - | P05-07 |  | 0 | CP08-500-P05-07 |  |  | T/S |  | 60 | 1 | TR | PB01 | PB01 | [8 empty] | RUN PB4(1 OPT),PB1,PB3,PB2 (2 OPT)
CP08-500 |  | - | P06-07 |  | 0 | CP08-500-P06-07 |  |  | T/S | 1 | 60 | 1 | TR | PB03 | PB03 | PB02 | [7 empty] | RUN PB7,PB1,PB3 ON 220722 (3 OPT)
CP08-501 |  | - | P01-04 |  | 0 | CP08-501-P01-04 |  |  | ST | 1 | 240 | 4 | SM | SM01 | SM01
CP08-501 |  | - | P02-04 |  | 0 | CP08-501-P02-04 |  |  | ST | 1 | 420 | 7 | ST-1 | PP22 | PP04 | PP10 | PP02 | PP03 | PP22
CP08-501 |  | - | P03-04 |  | 0 | CP08-501-P03-04 |  |  | ST | 1 | 360 | 6 | ST-1 | PP22 | PP03 | PP21 | PP04 | PP03 | PP22
CP08-502 |  | - | P01-02 |  | 0 | CP08-502-P01-02 |  | BENDING MULTI | T/S | 1 | 180 | 3 | ST-4 | PP24-160T | PP24 | PP09 | PP30 | [6 empty] | SHARE DIE WITH CP08-599 | NEED SM01
CP08-503 |  | - | P01-04 |  | 0 | CP08-503-P01-04 |  |  | TR | 1 | 60 | 1 | TR | TM05 | TM05 | TM03 | TM06 | [6 empty] | OPF
CP08-503 |  | - | P02-04 |  | 0 | CP08-503-P02-04 |  |  | TR | 1 | 120 | 2 | TR | PB04 | PB04 | PB05
CP08-503 |  | - | P03-04 |  | 0 | CP08-503-P03-04 |  |  | TR | 1 | 120 | 2 | TR | PB03 | PB03 | PB03 | [7 empty] | RUN PB4,PB3 ON 020822
CP08-504A |  | - | P01-04 |  | 0 | CP08-504A-P01-04 |  |  | ST | 1 | 2222 | 37.0333 | SM | SM01 | SM01
CP08-504A |  | - | P02-04 |  | 0 | CP08-504A-P02-04 |  |  | ST | 1 | 300 | 5 | ST-4 | PP24-160T | PP24 | PP18 | PP01 | PP25 | PP30 | PP09 | PP01
CP08-504A |  | - | P03-04 |  | 0 | CP08-504A-P03-04 |  |  | ST | 1 | 300 | 5 | ST-4 | PP24-160T | PP24 | PP17 | PP01 | PP26 | PP30 | PP21
CP08-504 |  | - | P01-02 |  | 0 | CP08-504-P01-02 |  |  | ST | 1 | 120 | 2 | ST-4 | PP29-250T | PP29 | PP18 | PP09 | PP30 | PP19
CP08-505 |  | - | P01-05 |  | 0 | CP08-505-P01-05 |  |  | T/S | 1 | 102 | 1.7 | TR | TM03 | TM05 | TM03 | TM06
CP08-505 |  | - | P02-05 |  | 0 | CP08-505-P02-05 |  |  | T/S | 1 | 300 | 5 | ST-3 | PP17-110T | PP21 | PP17 | PP20 | PP16
CP08-505 |  | - | P03-05 |  | 0 | CP08-505-P03-05 |  |  | T/S | 1 | 300 | 5 | ST-2 | PP16-110T | PP15 | PP16 | PP25 | PP17
CP08-505 |  | - | P04-05 |  | 0 | CP08-505-P04-05 |  |  | T/S | 1 | 300 | 5 | ST-2 | PP27-110T | PP15 | PP27 | PP28 | PP21
CP08-506 |  | - | P02-09 |  | 0 | CP08-506-P02-09 |  |  | ST | 1 | 240 | 4 | ST-4 | PP24-160T | PP24 |  |  | PP24 | [5 empty] | SHARE V CP08-507,CP08-508
CP08-506 |  | - | P03-09 |  | 0 | CP08-506-P03-09 |  |  | ST | 1 | 240 | 4 | ST-4 | PP25-160T | PP25 | PP26 |  | PP25 | [5 empty] | SHARE V CP08-507,CP08-508
CP08-506 |  | - | P04-09 |  | 0 | CP08-506-P04-09 |  |  | ST | 1 | 240 | 4 | ST-4 | PP26-110T | PP26 | PP20 |  | PP26 | [5 empty] | SHARE V CP08-507,CP08-508
CP08-506 |  | - | P05-09 |  | 0 | CP08-506-P05-09 |  |  | ST | 1 | 240 | 4 | ST-4 | PP28-110T | PP25 |  |  | PP28 | [5 empty] | SHARE V CP08-507,CP08-508
CP08-506 |  | - | P06-09 |  | 0 | CP08-506-P06-09 |  |  | ST | 1 | 240 | 4 | ST-4 | PP24-160T | PP26 | PP24 | PP20 | PP26 | [5 empty] | SHARE V CP08-507,CP08-508
CP08-506 |  | - | P07-09 |  | 0 | CP08-506-P07-09 |  |  | ST | 1 | 240 | 4 | ST-4 | PP25-160T | PP25 | PP28 |  | PP25 | [5 empty] | SHARE V CP08-507,CP08-508
CP08-506 |  | - | P08-09 |  | 0 | CP08-506-P08-09 |  |  | ST | 2 | 240 | 4 | ST-4 | PP26-110T | PP24 | PP26 |  | PP24 | [5 empty] | SHARE V CP08-507,CP08-508
CP08-507 |  | - | P01-08 |  | 0 | CP08-507-P01-08 |  |  | ST | 1 | 240 | 4 | ST-4 | PP24-160T | PP24 |  | PP24 | [6 empty] | SHARE V CP08-506,CP08-508
CP08-507 |  | - | P02-08 |  | 0 | CP08-507-P02-08 |  |  | ST | 1 | 240 | 4 | ST-4 | PP25-160T | PP25 |  | PP25 | [6 empty] | SHARE V CP08-506,CP08-508
CP08-507 |  | - | P03-08 |  | 0 | CP08-507-P03-08 |  |  | ST | 1 | 240 | 4 | ST-4 | PP26-110T | PP26 |  | PP26 | [6 empty] | SHARE V CP08-506,CP08-508
CP08-507 |  | - | P04-08 |  | 0 | CP08-507-P04-08 |  |  | ST | 1 | 240 | 4 | ST-4 | PP28-110T | PP28 |  | PP28 | [6 empty] | SHARE V CP08-506,CP08-508
CP08-507 |  | - | P05-08 |  | 0 | CP08-507-P05-08 |  |  | ST | 1 | 240 | 4 | ST-4 | PP24-160T | PP26 | PP20 | PP26 | [6 empty] | SHARE V CP08-506,CP08-508
CP08-507 |  | - | P06-08 |  | 0 | CP08-507-P06-08 |  |  | ST | 1 | 240 | 4 | ST-4 | PP25-160T | PP25 | PP28 | PP25 | [6 empty] | SHARE V CP08-506,CP08-508
CP08-507 |  | - | P07-08 |  | 0 | CP08-507-P07-08 |  |  | ST | 2 | 240 | 4 | ST-4 | PP26-110T | PP24 |  | PP24 | [6 empty] | SHARE V CP08-506,CP08-508
CP08-508 |  | - | P02-09 |  | 0 | CP08-508-P02-09 |  |  | ST | 1 | 240 | 4 | ST-4 | PP24-160T | PP24 |  |  |  | PP24 |  |  |  |  | SHARE V CP08-506,CP08-507
CP08-508 |  | - | P03-09 |  | 0 | CP08-508-P03-09 |  |  | ST | 1 | 240 | 4 | ST-4 | PP25-160T | PP25 | PP26 |  |  | PP25 |  |  |  |  | SHARE V CP08-506,CP08-507
CP08-508 |  | - | P04-09 |  | 0 | CP08-508-P04-09 |  |  | ST | 1 | 240 | 4 | ST-4 | PP26-110T | PP26 | PP20 |  |  | PP26 |  |  |  |  | SHARE V CP08-506,CP08-507
CP08-508 |  | - | P05-09 |  | 0 | CP08-508-P05-09 |  |  | ST | 1 | 240 | 4 | ST-4 | PP28-110T | PP28 |  |  |  | PP28 |  |  |  |  | SHARE V CP08-506,CP08-507
CP08-508 |  | - | P06-09 |  | 0 | CP08-508-P06-09 |  |  | ST | 1 | 240 | 4 | ST-4 | PP24-160T | PP26 | PP20 | PP24 | PP24 | PP26 |  |  |  |  | SHARE V CP08-506,CP08-507
CP08-508 |  | - | P07-09 |  | 0 | CP08-508-P07-09 |  |  | ST | 1 | 240 | 4 | ST-4 | PP25-160T | PP25 | PP28 | PP25 | PP25 | PP25 |  |  |  |  | SHARE V CP08-506,CP08-507
CP08-508 |  | - | P08-09 |  | 0 | CP08-508-P08-09 |  |  | ST | 2 | 240 | 4 | ST-4 | PP26-110T | PP24 | PP24 | PP28 | PP26 | PP24 |  |  |  |  | SHARE V CP08-506,CP08-507
CP08-509 |  | - | P01-04 |  | 0 | CP08-509-P01-04 |  |  | ST | 1 | 360 | 6 | ST-3 | PP17-110T | PP17 | PP25 | PP18 | PP24 | PP26 | PP18
CP08-509 |  | - | P02-04 |  | 0 | CP08-509-P02-04 |  |  | ST | 1 | 360 | 6 | ST-3 | PP16-110T | PP16 | PP26 | PP28 | PP20 |  | PP21
CP08-509 |  | - | P03-04 |  | 0 | CP08-509-P03-04 |  |  | ST | 1 | 360 | 6 | ST-3 | PP27-110T | PP27 | PP20 | PP17 | PP28 |  | PP17
CP08-510 |  | - | P01-05 |  | 0 | CP08-510-P01-05 |  |  | ST | 1 | 150 | 2.5 | ST-4 | PP29-250T | PP29 | PP30
CP08-510 |  | - | P02-05 |  | 0 | CP08-510-P02-05 |  |  | ST | 1 | 120 | 2 | ST-4 | PP30 | PP29 | PP30 | PP33
CP08-510 |  | - | P03-05 |  | 0 | CP08-510-P03-05 |  |  | ST | 1 | 120 | 2 | ST-4 | PP29-250T | PP29 | PP30
CP08-510 |  | - | P04-05 |  | 0 | CP08-510-P04-05 |  |  | ST | 2 | 120 | 2 | ST-4 | PP30 | PP29 | PP30 | PP33
CP08-511 |  | - | P01-05 |  | 0 | CP08-511-P01-05 |  |  | ST | 1 | 240 | 4 | SM | SM01 | SM01
CP08-511 |  | - | P02-05 |  | 0 | CP08-511-P02-05 |  |  | ST | 1 | 240 | 4 | ST-3 | PP17-110T | PP17 | PP24 | PP16
CP08-511 |  | - | P03-05 |  | 0 | CP08-511-P03-05 |  |  | ST | 1 | 240 | 4 | ST-3 | PP16-110T | PP16 | PP25 | PP26 | PP18
CP08-511 |  | - | P04-05 |  | 0 | CP08-511-P04-05 |  |  | ST | 1 | 240 | 4 | ST-3 | PP27-110T | PP27 | PP28 | PP21
CP08-512 |  | - | P01-07 |  | 0 | CP08-512-P01-07 |  |  | ST | 1 | 300 | 5 | ST-3 | PP09-160T | PP09 |  | PP09
CP08-512 |  | - | P02-07 |  | 0 | CP08-512-P02-07 |  |  | ST | 1 | 300 | 5 | ST-3 | PP18-150T | PP16 | PP18 | PP18
CP08-512 |  | - | P03-07 |  | 0 | CP08-512-P03-07 |  |  | ST | 1 | 300 | 5 | ST-3 | PP21-110T | PP21 |  | PP21
CP08-512 |  | - | P04-07 |  | 0 | CP08-512-P04-07 |  |  | ST | 1 | 300 | 5 | ST-3 | PP17-110T | PP17 |  | PP17
CP08-512 |  | - | P05-07 |  | 0 | CP08-512-P05-07 |  |  | ST | 1 | 300 | 5 | ST-3 | PP16-110T | PP16 |  | PP16
CP08-512 |  | - | P06-07 |  | 0 | CP08-512-P06-07 |  |  | ST | 1 | 300 | 5 | ST-3 | PP27-110T | PP27 |  | PP27
CP08-513 |  | - | P01-07 |  | 0 | CP08-513-P01-07 |  |  | ST | 1 | 1680 | 28 | SM | SM01 | SM01
CP08-513 |  | - | P02-07 |  | 0 | CP08-513-P02-07 |  |  | ST | 1 | 360 | 6 | ST-4 | PP25-160T | PP25 | PP27 | PP17 | PP24 | PP24 | PP25 | PP26
CP08-513 |  | - | P03-07 |  | 0 | CP08-513-P03-07 |  |  | ST | 1 | 360 | 6 | ST-4 | PP20-110T | PP20 | PP26 | PP16 |  | PP25 | PP26 | PP20
CP08-513 |  | - | P04-07 |  | 0 | CP08-513-P04-07 |  |  | ST | 1 | 360 | 6 | ST-4 | PP28-110T | PP28 | PP17 | PP27 | PP20 | PP26 | PP20 | PP28
CP08-513 |  | - | P05-07 |  | 0 | CP08-513-P05-07 |  |  | ST | 1 | 240 | 4 | ST-3 | TP03 | TP03 | TP08 | TP09 |  | TP09 |  | TP03
CP08-514 |  | - | P01-03 |  | 0 | CP08-514-P01-03 |  |  | S/A | 1 | 1800 | 30 | ST-2 | PP10-080T | PP01 | PP19 | PP10 | PP14
CP08-514 |  | - | P02-03 |  | 0 | CP08-514-P02-03 |  |  | S/A | 1 | 300 | 5 | AL | TP04 | TP04 | TP02 | [7 empty] | SAME JIG WITH CP08-305,CP08-515
CP08-515 |  | - | P01-03 |  | 0 | CP08-515-P01-03 |  |  | S/A | 1 | 1800 | 30 | ST-2 | PP10-080T | PP19 | PP10 | PP01 | PP12
CP08-515 |  | - | P02-03 |  | 0 | CP08-515-P02-03 |  |  | S/A | 1 | 300 | 5 | AL | TP04 | TP04 | TP02 | [7 empty] | SAME JIG WITH CP08-305,CP08-514
CP08-516 | GP01-010 | - | P01-11 |  | 0 | CP08-516-P01-11 |  |  | ST | 1 | 120 | 2 | ST-3 | PP09-160T | PP09 | PP24
CP08-516 | GP01-010 | - | P02-11 |  | 0 | CP08-516-P02-11 |  |  | ST | 1 | 120 | 2 | ST-3 | PP18-150T | PP18 | PP18
CP08-516 | GP01-010 | - | P03-11 |  | 0 | CP08-516-P03-11 |  |  | ST | 1 | 120 | 2 | ST-3 | PP17-110T | PP17 | PP17
CP08-516 | GP01-010 | - | P04-11 |  | 0 | CP08-516-P04-11 |  |  | ST | 1 | 120 | 2 | ST-3 | TP03 | TP03 | TP03 | [7 empty] | WOOD BIN - 50 PCS
CP08-516 | GP01-010 | - | P05-11 |  | 0 | CP08-516-P05-11 |  |  | ST | 0 | 120 | 2 | ST-3 | PP16-110T | PP16 | PP16
CP08-516 | GP01-010 | - | P06-11 |  | 0 | CP08-516-P06-11 |  |  | ST | 1 | 120 | 2 | ST-3 | TP03 | TP03 | TP09
CP08-516 | GP01-010 | - | P07-11 |  | 0 | CP08-516-P07-11 |  |  | ST | 1 | 120 | 2 | ST-3 | PP17-110T | PP17 | PP16
CP08-516 | GP01-010 | - | P08-11 |  | 0 | CP08-516-P08-11 |  |  | ST | 1 | 120 | 2 | ST-3 | PP16-110T | PP16 | PP17
CP08-516 | GP01-010 | - | P09-11 |  | 0 | CP08-516-P09-11 |  |  | ST | 1 | 120 | 2 | ST-3 | PP27-110T | PP27 | PP28
CP08-516 | GP01-010 | - | P10-11 |  | 0 | CP08-516-P10-11 |  |  | ST | 1 | 120 | 2 | ST-3 | SW01 | SW01
CP08-517 | GP01-034 | - | P01-03 |  | 0 | CP08-517-P01-03 |  |  | ST | 1 | 300 | 5 | ST-1 | PP10-080T | PP10 | PP19
CP08-517 | GP01-034 | - | P02-03 |  | 0 | CP08-517-P02-03 |  |  | ST | 1 | 240 | 4 | ST-3 | PP03-060T | PP22 | PP04 | PP03 | PP13 | PP02
CP08-518 |  | - | P01-02 |  | 0 | CP08-518-P01-02 |  |  | ST | 1 | 3000 | 50 | ST-3 | PP01-110T | PP01 | PP09 | PP28 | PP30 | [5 empty] | SAME DIE WITH CP08-519,CP08-080,CP08-307
CP08-519 |  | - | P01-02 |  | 0 | CP08-519-P01-02 |  |  | ST | 1 | 3000 | 50 | ST-3 | PP01-110T | PP09 | PP01 | PP30 | PP24 | [5 empty] | SAME DIE WITH CP08-518
CP08-520 |  | - | P01-02 |  | 0 | CP08-520-P01-02 |  |  | ST | 1 | 3000 | 50 | ST-3 | PP01-110T | PP09 | PP01 | PP30 | [6 empty] | SHARE DIE V CP08-079
CP08-521 |  | - | P01-02 |  | 0 | CP08-521-P01-02 |  |  | ST | 1 | 3000 | 50 | ST-2 | PP01-110T | PP01 | PP09 | PP30 | PP24
CP08-522 |  | - | P01-02 |  | 0 | CP08-522-P01-02 |  |  | ST | 1 | 3000 | 50 | ST-3 | PP01-110T | PP01 | PP09 | PP30 | PP24
CP08-523 |  | - | P01-03 |  | 0 | CP08-523-P01-03 |  |  | S/A | 1 | 1800 | 30 | ST-2 | PP10-080T | PP19 | PP10 | PP09
CP08-523 |  | - | P02-03 |  | 0 | CP08-523-P02-03 |  |  | S/A | 1 | 300 | 5 | AL | TP04 | TP02 | TP04 | [7 empty] | TP6???-NEED MODIFY JIG???-7/12/21
CP08-524 |  | - | P01-05 |  | 0 | CP08-524-P01-05 |  |  | T/S | 1 | 20 | 0.33333 | TR | TM05 | TM03,20/HRS | TM05 | TM06,15/HRS
CP08-524 |  | - | P02-05 |  | 0 | CP08-524-P02-05 |  |  | T/S | 1 | 120 | 2 | ST-3 | PP31 | PP21 | PP15 | PP28 | PP10 | PP31 |  |  |  |  | NET - ORANGE
CP08-524 |  | - | P03-05 |  | 0 | CP08-524-P03-05 |  |  | T/S | 1 | 35 | 0.58333 | TR | PB05 | PB05 |  | PB01
CP08-524 |  | - | P04-05 |  | 0 | CP08-524-P04-05 |  |  | T/S | 1 | 35 | 0.58333 | TR | PB02 | PB02 | PB03 | PB08 | [6 empty] | RUN PB5,PB2-ON 270622, PB7,PB2 RUN PB5,PB3-290522
CP08-539 |  | - | P01-11 |  | 0 | CP08-539-P01-11 |  |  | ST | 1 | 120 | 2 | ST-3 | PP09-160T | PP09 | PP01 | PP24 | [6 empty] | PROCESS : P01 TO P05 - 4 OPTS RUN
CP08-539 |  | - | P02-11 |  | 0 | CP08-539-P02-11 |  |  | ST | 1 | 120 | 2 | ST-3 | PP18-150T | PP18 | [8 empty] | PROCESS : P06 TO P10 - 5 OPTS RUN
CP08-539 |  | - | P03-11 |  | 0 | CP08-539-P03-11 |  |  | ST | 1 | 120 | 2 | ST-3 | PP17-110T | PP17
CP08-539 |  | - | P04-11 |  | 0 | CP08-539-P04-11 |  |  | ST | 1 | 120 | 2 | ST-3 | TP03 | TP03
CP08-539 |  | - | P05-11 |  | 0 | CP08-539-P05-11 |  |  | ST | 0 | 120 |  | ST-3 | PP16-110T | PP16
CP08-539 |  | - | P06-11 |  | 0 | CP08-539-P06-11 |  |  | ST | 1 | 120 | 2 | ST-3 | TP03 | TP03
CP08-539 |  | - | P07-11 |  | 0 | CP08-539-P07-11 |  |  | ST | 1 | 120 | 2 | ST-3 | PP17-110T | PP17
CP08-539 |  | - | P08-11 |  | 0 | CP08-539-P08-11 |  |  | ST | 1 | 120 | 2 | ST-3 | PP16-110T | PP16
CP08-539 |  | - | P09-11 |  | 0 | CP08-539-P09-11 |  |  | ST | 1 | 120 | 2 | ST-3 | PP27-110T | PP27
CP08-539 |  | - | P10-11 |  | 0 | CP08-539-P10-11 |  |  | ST | 1 | 120 | 2 | ST-3 | SW01 | SW01 | SW09
CP08-540 |  | - | P01-03 |  | 0 | CP08-540-P01-03 |  |  | TR | 1 | 70 | 1.1667 | TR | TM06 | TM03 | TM05 | TM06
CP08-540 |  | - | P02-03 |  | 0 | CP08-540-P02-03 |  |  | TR | 1 | 60 | 1 | TR | PB01 | PB01 | PB02 | PB05 | PB07
CP08-541 |  | - | P01-06 | ver.03 | 0 | CP08-541-P01-06 |  |  | TR | 1 | 60 | 1 | TR | TM06 | TM03 | TM05 | TM06
CP08-541 |  | - | P02-06 |  | 0 | CP08-541-P02-06 |  |  | TR | 1 | 120 | 2 | TR | PB03 | PB03 | PB02 | TOGETGHER RUN WITH PROCESS NO P02 & P03-06(PB04) | [6 empty] | EFF-180522-NO MORE SLIT PROCESS -W1219-L1100 | ON 210723 ACCORDING MOMEN,BENDING ONLY 3 PROCESS RUN AT PB03,PB07,PB04 OR PB03,PB04,PB01
CP08-541 |  | - | P03-06 |  | 0 | CP08-541-P03-06 |  |  | TR | 1 | 120 | 2 | TR | PB03 | PB04 | PB03 | [7 empty] | EFF-310522
CP08-541 |  | - | P04-06 |  | 0 | CP08-541-P04-06 |  |  | TR | 1 | 72 | 1.2 | TR | PB04 | PB04 | PB01 | [7 empty] | RUN PB2,PB3,PB1,PB4 - 190922, IF RUN PB1 NO NEED RUN PROCESS PB4
CP08-541 |  | - | P05-06 |  | 0 | CP08-541-P05-06 |  |  | TR | 1 | 90 | 1.5 | TR | PB01 | PB01 | PB04
CP08-542 |  | - | P01-04 |  | 0 | CP08-542-P01-04 |  |  | ST | 1 | 5760 | 96 | SM | SM01 | SM01 | [8 empty] | t0.8XW67XL1219=36PCS,1 MATERIAL = 16 PCS PART
CP08-542 |  | - | P02-04 |  | 0 | CP08-542-P02-04 |  |  | ST | 1 | 360 | 6 | ST-1 | PP05-060T | PP05 | PP13 | PP10 | PP31 | PP04
CP08-542 |  | - | P03-04 |  | 0 | CP08-542-P03-04 |  |  | ST | 1 | 240 | 4 | ST-1 | PP05-060T | PP05 | PP10 | PP02 | PP31 | PP13
CP08-543 |  | - | P01-03 | ver.02 | 0 | CP08-543-P01-03 |  |  | TR | 1 | 110 | 1.8333 | TR | TM03 | TM05 | TM03 | TM06
CP08-543 | EFF-180522-NO MORE SLIT PROCESS-W880-L1219 | - | P02-03 |  | 0 | CP08-543-P02-03 |  |  | TR | 1 | 60 | 1 | TR | PB01 | PB01 | PB07 | PB04
CP08-544 |  | - | P01-02 |  | 0 | CP08-544-P01-02 |  |  | ST | 1 | 30 | 0.5 | ST | STICK LABEL | STICK LABEL
CP08-545 |  | - | P01-02 |  | 0 | CP08-545-P01-02 |  |  | ST | 1 | 18 | 0.3 | ST | STICK LABEL | STICK LABEL
CP08-547 |  | - | P01-02 |  | 0 | CP08-547-P01-02 |  |  | ? | 1 | 18 | 0.3 | #N/A | OPT | OPT
CP08-548 |  | - | P01-03 |  | 0 | CP08-548-P01-03 |  |  | ? | 1 | 30 | 0.5 | #N/A | LABEL
CP08-548 |  |  | P02-03 |  | 0 | CP08-548-P02-03 |  |  |  |  | 30 | 0.5 | #N/A | LABEL
CP15-001 |  | - | P01-03 |  | 0 | CP15-001-P01-03 |  |  | ST | 1 | 360 | 6 | ST-1 | PP10-080T | PP03 | PP10 | PP05 | PP19
CP15-001 |  | - | P02-03 |  | 0 | CP15-001-P02-03 |  |  | ST | 1 | 360 | 6 | ST-1 | PP10-080T | PP10 | PP05 | PP12
CP15-002 |  | - | P01-04 |  | 0 | CP15-002-P01-04 |  |  | S/A | 1 | 360 | 6 | PP02 | PP02-060T | PP12 | PP01
CP15-002 |  | - | P02-04 |  | 0 | CP15-002-P02-04 |  |  | S/A | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CP15-002 |  | - | P03-04 |  | 0 | CP15-002-P03-04 |  |  | S/A | 1 | 360 | 6 | #N/A | TP02 | TP02
CP15-003 |  | - | P01-04 |  | 0 | CP15-003-P01-04 |  |  | ST | 1 | 300 | 5 | ST-1 | PP04-060T | PP13 | PP02 | PP10 | PP04 | PP03
CP15-003 |  | - | P02-04 |  | 0 | CP15-003-P02-04 |  |  | ST | 1 | 240 | 4 | ST-1 | PP04-060T | PP05 | PP22
CP15-003 |  | - | P03-04 |  | 0 | CP15-003-P03-04 |  |  | ST | 1 | 360 | 6 | ST-1 | PP13 | PP15 | PP04 | PP13
CP15-004 |  | - | P01-02 |  | 0 | CP15-004-P01-02 |  |  | ST | 1 | 300 | 5 | ST-1 | PP13 | PP13
CP15-004B |  | - | P01-05 |  | 0 | CP15-004B-P01-05 |  |  | SUB CON | 1 |  | 0 | #N/A | #N/A
CP15-004B |  | - | P02-05 |  | 0 | CP15-004B-P02-05 |  |  | SUB CON | 1 |  | 0 | #N/A | #N/A
CP15-004B |  | - | P03-05 |  | 0 | CP15-004B-P03-05 |  |  | SUB CON | 1 |  | 0 | #N/A | #N/A
CP15-005 |  | - | P04-05 |  |  | CP15-004B-P04-05 |  |  | ST | 1 | 240 | 4 |  | PP04-060T | PP04
CP15-005 |  | - | P01-06 |  | 0 | CP15-005-P01-06 |  |  | A/S/A | 1 | 108 | 1.8 | AL | CM05 | CM05 | CM03
CP15-005 |  | - | P02-06 |  | 0 | CP15-005-P02-06 |  |  | A/S/A | 1 | 120 | 2 | AL | DIESEL DEBURR | DIESEL DEBURR
CP15-005 |  | - | P03-06 |  | 0 | CP15-005-P03-06 |  |  | A/S/A | 1 | 120 | 2 | ST-1 | PP04-060T | PP04
CP15-005 |  | - | P04-06 |  | 0 | CP15-005-P04-06 |  |  | A/S/A | 1 | 240 | 4 | AL | BL03 | BL03 | BL04
CP15-005 |  | - | P05-06 |  | 0 | CP15-005-P05-06 |  |  | A/S/A | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CP15-006 |  | - | P01-04 |  | 0 | CP15-006-P01-04 |  |  | AL | 1 | 120 | 2 | AL | CM05 | CM05
CP15-006 |  | - | P02-04 |  | 0 | CP15-006-P02-04 |  |  | AL | 1 | 600 | 10 | AL | BDS01 | BDS01
CP15-006 |  | - | P03-04 |  |  | CP15-006-P03-04 |  |  | AL | 1 | 1260 | 21 | AL | VM01 | VM01 | [8 empty] | VM01 + DRY1
CP16-010 | GP01-007 | - | P01-02 |  | 0 | CP16-010-P01-02 |  |  | FM | 1 | 2400 | 40 | FM | FM01 | FM01 | FM02 | FM03 | [7 empty] | SETTING : 4 HRS
CP16-022 |  | - | P01-04 |  | 0 | CP16-022-P01-04 |  |  | TR | 1 | 300 | 5 | SM | SM01 | SM01
CP16-022 |  | - | P02-04 |  | 0 | CP16-022-P02-04 |  |  | TR | 1 | 80 | 1.3333 | TR | TM06 | TM02 | TM03 | TM05 | TM06 | [5 empty] | IF RUN T2-51/HRS
CP16-022 |  | - | P03-04 |  | 0 | CP16-022-P03-04 |  |  | TR | 1 | 50 | 0.83333 | TR | PB07 | PB07 | PB01 | PB5
CP16-027 |  | - | P01-03 |  | 0 | CP16-027-P01-03 |  |  | ST | 1 | 120 | 2 | #N/A | SM01 | SM01
CP16-027 |  | - | P02-03 |  | 0 | CP16-027-P02-03 |  |  | ST | 1 | 300 | 5 | #N/A | PP22 | PP22 | PP03 | PP04 | PP05
CP16-030 |  | - | P01-04 |  | 0 | CP16-030-P01-04 |  |  | ST | 1 | 4320 | 72 | SM | SM01 | SM01 |  |  | SM01
CP16-030 |  | - | P02-04 |  | 0 | CP16-030-P02-04 |  |  | ST | 1 | 420 | 7 | ST-1 | PP11 | PP13 | PP11 | PP04 | PP11 | PP02
CP16-030 |  | - | P03-04 |  | 0 | CP16-030-P03-04 |  |  | ST | 1 | 240 | 4 | ST-1 | PP05-060T | PP05 | PP04 | PP15 | PP05
CP16-031 |  | - | P01-04 |  | 0 | CP16-031-P01-04 |  |  | ST | 1 | 29160 | 486 | SM | SM01 | SM01
CP16-031 |  | - | P02-04 |  | 0 | CP16-031-P02-04 |  |  | ST | 1 | 720 | 12 | ST-1 | PP11 | PP13 | PP11 | PP04 | PP05
CP16-031 |  | - | P03-04 |  | 0 | CP16-031-P03-04 |  |  | ST | 1 | 240 | 4 | ST-1 | PP05-060T | PP05 | PP04 | PP15 | PP02
CP16-032 |  | - | P01-04 |  | 0 | CP16-032-P01-04 |  |  | ST | 1 | 19440 | 324 | SM | SM01 | SM01
CP16-032 |  | - | P02-04 |  | 0 | CP16-032-P02-04 |  |  | ST | 1 | 360 | 6 | ST-1 | PP11 | PP13 | PP11 | PP04 | PP05
CP16-032 |  | - | P03-04 |  | 0 | CP16-032-P03-04 |  |  | ST | 1 | 240 | 4 | ST-1 | PP05-060T | PP05 | PP02 | PP15
CP16-042 | GP01-029 | - | P01-03 |  | 0 | CP16-042-P01-03 |  |  | ST | 1 | 300 | 5 | ST-2 | PP15 | PP19 | PP22 | PP21 | PP02 | PP17 | PP28 | PP31 | PP03 | PP14 | PP15
CP16-042 | GP01-029 | - | P02-03 |  | 0 | CP16-042-P02-03 |  |  | ST | 1 | 240 | 4 | ST-2 | PP03-060T | PP15 | PP22 | PP21 | PP17 | PP05 | PP28 | PP03 | PP14
CP16-043 | GP01-030 | - | P01-04 |  | 0 | CP16-043-P01-04 |  |  | ST | 1 | 600 | 10 | SM | SM01 | SM01
CP16-043 | GP01-030 | - | P02-04 |  | 0 | CP16-043-P02-04 |  |  | ST | 1 | 360 | 6 | ST-1 | PP05-060T | PP03 | PP05 | PP21 | PP22 | PP15 | PP02
CP16-043 | GP01-030 | - | P03-04 |  | 0 | CP16-043-P03-04 |  |  | ST | 1 | 240 | 4 | ST-1 | PP02-060T | PP02 | PP15 | PP21 | PP03 | PP05
CP17-001 |  | - | P01 |  | 0 | CP17-001-P01 |  |  | ST | 1 | 120 | 2 | #N/A | #N/A
CP17-001A |  | - | P01-02 |  | 0 | CP17-001A-P01-02 |  |  | ST | 1 | 3600 | 60 | #N/A | #N/A
CP17-002 |  | - | P01 |  | 0 | CP17-002-P01 |  |  | ? | 1 |  | 0 | #N/A | #N/A
CP17-002A |  | - | P01-02 |  | 0 | CP17-002A-P01-02 |  |  | ST | 1 | 3600 | 60 | #N/A | #N/A
CP17-001B |  | - | P01-03 |  | 0 | CP17-001B-P01-03 |  |  | AL | 1 | 84 | 1.4 | #N/A | #N/A
CP17-001B |  | - | P02-03 |  | 0 | CP17-001B-P02-03 |  |  | AL | 1 | 300 | 5 | #N/A | #N/A
CP17-001B |  | - | P03-03 |  | 0 | CP17-001B-P03-03 |  |  | AL | 1 | 60000 | 1000 | #N/A | #N/A
CP20-001A,CD11-026A |  | - | P01-02 |  | 0 | CD11-026A-P01-02 |  |  | FM | 1 | 1200 | 20 | FM | FM03 | FM01 | FM03 | [7 empty] | ALMOST SAME DIE WITH CM18-001B,CP20-002A | LU METAL MATERIAL EASILY RUSTY,ONCE MAT COME,NEED RUN IN BETWEEN 2 DAYS
CP20-001B,CD11-026B |  | - | P01-02 |  | 0 | CD11-026B-P01-02 |  |  | WN | 1 | 2160 | 36 | WN | WS01 | WS01
CP20-001C,CD11-026C |  | - | P01-02 |  | 0 | CD11-026C-P01-02 |  |  | WN | 1 | 2400 | 40 | WN | WS01 | WS01
CP20-001,CD11-026 |  | - | P01-06 |  | 0 | CD11-026-P01-06 |  |  | WN | 2 | 120 | 2 | WN | SW13 | SW05-80PCS/HR | SW08 | SW05 | SW03 | SW13
CP20-001,CD11-026 |  | - | P02-06 |  | 0 | CD11-026-P02-06 |  |  | WN | 1 | 540 | 9 | WN | PP23-060T | PP23
CP20-001,CD11-026 |  | - | P03-05 |  | 0 | CD11-026-P03-06 |  |  | SUB CON | 1 | 5 DAYS | #VALUE!
CP20-001,CD11-026 |  |  | P04-06 |  |  | CD11-026-P04-06 |  |  | SUB CON |  | 5 DAYS | #VALUE!
CP20-001,CD11-026 |  |  | P05-06 |  |  | CD11-026-P05-06 |  |  | WN | 1 | 420 | 7 | WN | TW01 | TW01 | TW02 | TW03
CP20-002B,CD11-027B |  |  | P01-02 |  |  | CD11-027B-P01-02 |  |  | WN | 1 | 2160 | 36 | WN | WS01 | WS01
CP20-002C,CD11-027C |  |  | P01-02 |  |  | CD11-027C-P01-02 |  |  | WN | 1 | 2160 | 36 | WN | WS01 | WS01
CR02-002 |  | - | P01-04 |  | 0 | CR02-002-P01-04 |  |  | AL | 1 | 90 | 1.5 | WN | WS01 | WS01
CR02-002 |  | - | P02-04 |  | 0 | CR02-002-P02-04 |  |  | AL | 1 | 420 | 7 | AL | BDS01 | BDS01
CR02-002 |  | - | P03-04 |  | 0 | CR02-002-P03-04 |  |  | AL | 1 | 480 | 8 | ST-1 | PP03-060T | PP03 | PP02
CS05-008 |  | - | P01-02 |  | 0 | CS05-008-P01-02 |  |  | ST | 1 | 1200 | 20 | ST-1 | PP10-080T | PP10 | PP12
CS05-015 |  | - | P01-05 |  | 0 | CS05-015-P01-05 |  |  | ST | 1 | 1500 | 25 | ST-1 | PP02-060T | PP14 | PP02
CS05-015 |  | - | P02-05 |  | 0 | CS05-015-P02-05 |  |  | ST | 1 | 360 | 6 | AL | TP06 | TP06
CS05-015 |  | - | P03-05 |  | 0 | CS05-015-P03-05 |  |  | ST | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CS05-015 |  | - | P04-05 |  | 0 | CS05-015-P04-05 |  |  | ST | 1 | WH1 | WH1 | WH1 | WH1 | STORE
CS05-019 |  | - | P01-02 |  | 0 | CS05-019-P01-02 |  |  | ST | 1 | 1800 | 30 | #N/A | #N/A
CS18-001 |  | - | P01-04 |  | 0 | CS18-001-P01-04 |  |  | WN | 1 | 90 | 1.5 | WN | SW03 | SW03
CS18-001 |  | - | P02-04 |  | 0 | CS18-001-P02-04 |  |  | WN | 1 | 90 | 1.5 | WN | TW01 | TW01
CS18-001 |  | - | P03-04 |  | 0 | CS18-001-P03-04 |  |  | WN | 1 | 120 | 2 | WN | LVL01 | LVL01
CS18-001A |  | - | P01-03 |  | 0 | CS18-001A-P01-03 |  |  | WN | 1 | 1500 | 25 | WN | WS01 | WS01
CS18-001A |  | - | P02-03 |  | 0 | CS18-001A-P02-03 |  |  | WN | 1 | 300 | 5 | WN | PP23-060T | PP23 | [10 empty] | 1
CS18-001B |  | - | P01-03 |  | 0 | CS18-001B-P01-03 |  |  | WN | 1 | 1500 | 25 | WN | WS01 | WS01 | [10 empty] | 1
CS18-001B |  | - | P02-03 |  | 0 | CS18-001B-P02-03 |  |  | WN | 1 | 300 | 5 | WN | PP23-060T | PP23 | [10 empty] | 1
CS18-001C |  | - | P01-02 |  | 0 | CS18-001C-P01-02 |  |  | WN | 1 | 1500 | 25 | WN | WS01 | WS01 | [10 empty] | 1
CS18-006 |  | - | P01-03 |  | 0 | CS18-006-P01-03 |  |  | WN | 1 | 15 | 0.25 | WN | SW06 | SW06 | [10 empty] | 8
CS18-006 |  | - | P02-03 |  | 0 | CS18-006-P02-03 |  |  | WN | 1 | 15 | 0.25 | WN | TW01 | TW01 | TW02 | TW03
CS18-006A |  | - | P01-04 |  | 0 | CS18-006A-P01-04 |  |  | WN | 1 | 600 | 10 | WN | WS01 | WS01
CS18-006A |  | - | P02-04 |  | 0 | CS18-006A-P02-04 |  |  | WN | 1 | 120 | 2 | WN | JIG BENDING | JIG BENDING
CS18-006A |  | - | P03-04 |  | 0 | CS18-006A-P03-04 |  |  | WN | 1 | 240 | 4 | WN | PP23-060T | PP23 | PP31
CS18-006B |  | - | P01-02 |  | 0 | CS18-006B-P01-02 |  |  | WN | 1 | 600 | 10 | WN | WS01 | WS01
CS18-006C |  | - | P01-02 |  | 0 | CS18-006C-P01-02 |  |  | WN | 1 | 600 | 10 | WN | WS01 | WS01
CS18-006D |  | - | P01-05 |  | 0 | CS18-006D-P01-05 |  |  | WN | 1 | 420 | 7 | WN | WS01 | WS01
CS18-006D |  | - | P02-05 |  | 0 | CS18-006D-P02-05 |  |  | WN | 1 | 120 | 2 | WN | JIG BENDING | JIG BENDING
CS18-006D |  | - | P03-05 |  | 0 | CS18-006D-P03-05 |  |  | WN | 1 | 120 | 2 | WN | JIG BENDING | JIG BENDING
CS18-006D |  | - | P04-05 |  | 0 | CS18-006D-P04-05 |  |  | WN | 1 | 240 | 4 | WN | PP23-060T | PP23
CS18-007 |  | - | P01-03 |  | 0 | CS18-007-P01-03 |  |  | WN | 1 | 18 | 0.3 | WN | SW06 | SW06
CS18-007 |  | - | P02-03 |  | 0 | CS18-007-P02-03 |  |  | WN | 1 | 18 | 0.3 | WN | TW01 | TW01 | TW02 | TW03
CS18-007A |  | - | P01-04 |  | 0 | CS18-007A-P01-04 |  |  | WN | 1 | 900 | 15 | WN | WS01 | WS01
CS18-007A |  | - | P02-04 |  | 0 | CS18-007A-P02-04 |  |  | WN | 1 | 180 | 3 | WN | JIG BENDING | JIG BENDING
CS18-007A |  | - | P03-04 |  | 0 | CS18-007A-P03-04 |  |  | WN | 1 | 240 | 4 | WN | PP23-060T | PP23 | PP05
CS18-007B |  | - | P01-02 |  | 0 | CS18-007B-P01-02 |  |  | WN | 1 | 600 | 10 | WN | WS01 | WS01
CS18-007C |  | - | P01-02 |  | 0 | CS18-007C-P01-02 |  |  | WN | 1 | 720 | 12 | WN | WS01 | WS01
CS18-007D |  | - | P01-03 |  | 0 | CS18-007D-P01-03 |  |  | WN | 1 | 600 | 10 | WN | WS01 | WS01
CS18-007D |  | - | P02-03 |  | 0 | CS18-007D-P02-03 |  |  | WN | 1 | 120 | 2 | WN | JIG BENDING | JIG BENDING
CS18-008 |  | - | P01-03 |  | 0 | CS18-008-P01-03 |  |  | WN | 1 | 18 | 0.3 | WN | SW06 | SW06
CS18-008 |  | - | P02-03 |  | 0 | CS18-008-P02-03 |  |  | WN | 1 | 18 | 0.3 | WN | TW01 | TW01 | TW02 | TW03
CS18-008A |  | - | P01-04 |  | 0 | CS18-008A-P01-04 |  |  | WN | 1 | 1200 | 20 | WN | WS01 | WS01
CS18-008A |  | - | P02-04 |  | 0 | CS18-008A-P02-04 |  |  | WN | 1 | 340 | 5.6667 | WN | JIG BENDING | JIG BENDING
CS18-008A |  | - | P03-04 |  | 0 | CS18-008A-P03-04 |  |  | WN | 1 | 480 | 8 | WN | PP23-060T | PP23 | PP05
CS18-008B |  | - | P01-02 |  | 0 | CS18-008B-P01-02 |  |  | WN | 1 | 900 | 15 | WN | WS01 | WS01
CS18-008C |  | - | P01-02 |  | 0 | CS18-008C-P01-02 |  |  | WN | 1 | 720 | 12 | WN | WS01 | WS01
CS18-008D |  | - | P01-03 |  | 0 | CS18-008D-P01-03 |  |  | WN | 1 | 480 | 8 | WN | WS01 | WS01
CS18-008D |  | - | P02-03 |  | 0 | CS18-008D-P02-03 |  |  | WN | 1 | 240 | 4 | WN | JIG BENDING | JIG BENDING
CS18-009 |  | - | P01-03 |  | 0 | CS18-009-P01-03 |  |  | WN | 1 | 18 | 0.3 | WN | SW06 | SW06
CS18-009 |  | - | P02-03 |  | 0 | CS18-009-P02-03 |  |  | WN | 1 | 18 | 0.3 | WN | TW02 | TW02 | TW01 | TW03
CS18-009A |  | - | P01-04 |  | 0 | CS18-009A-P01-04 |  |  | WN | 1 | 1500 | 25 | WN | WS01 | WS01
CS18-009A |  | - | P02-04 |  | 0 | CS18-009A-P02-04 |  |  | WN | 1 | 120 | 2 | WN | JIG BENDING | JIG BENDING
CS18-009A |  | - | P03-04 |  | 0 | CS18-009A-P03-04 |  |  | WN | 1 | 180 | 3 | WN | PP23-060T | PP23 | PP31
CS18-009B |  | - | P01-02 |  | 0 | CS18-009B-P01-02 |  |  | WN | 1 | 900 | 15 | WN | WS01 | WS01
CS18-009C |  | - | P01-02 |  | 0 | CS18-009C-P01-02 |  |  | WN | 1 | 2700 | 45 | WN | WS01 | WS01
CS18-010 |  | - | P01-03 |  | 0 | CS18-010-P01-03 |  |  | WN | 1 | 18 | 0.3 | WN | SW06 | SW06
CS18-010 |  | - | P02-03 |  | 0 | CS18-010-P02-03 |  |  | WN | 1 | 18 | 0.3 | WN | TW01 | TW01 | TW02 | TW03
CS18-010A |  | - | P01-05 |  | 0 | CS18-010A-P01-05 |  |  | WN | 1 | 720 | 12 | WN | WS01 | WS01
CS18-010A |  | - | P02-05 |  | 0 | CS18-010A-P02-05 |  |  | WN | 1 | 240 | 4 | #N/A | JIG BENDING | JIG BENDING
CS18-010A |  | - | P03-05 |  | 0 | CS18-010A-P03-05 |  |  | WN | 1 | 240 | 4 | #N/A | JIG BENDING | JIG BENDING
CS18-010A |  | - | P04-05 |  | 0 | CS18-010A-P04-05 |  |  | WN | 1 | 240 | 4 | WN | PP23-060T | PP23
CS18-010B |  | - | P01-02 |  | 0 | CS18-010B-P01-02 |  |  | WN | 1 | 480 | 8 | WN | WS01 | WS01
CS18-010C |  | - | P01-02 |  | 0 | CS18-010C-P01-02 |  |  | WN | 1 | 1200 | 20 | WN | WS01 | WS01
CS18-010D |  | - | P01-04 |  | 0 | CS18-010D-P01-04 |  |  | WN | 1 | 600 | 10 | WN | WS01 | WS01
CS18-010D |  | - | P02-04 |  | 0 | CS18-010D-P02-04 |  |  | WN | 1 | 360 | 6 | WN | PP23-060T | PP23
CS18-010D |  | - | P03-04 |  | 0 | CS18-010D-P03-04 |  |  | WN | 1 | 420 | 7 | #N/A | JIG BENDING | JIG BENDING
CS18-017,CP08-557 |  | - | P01-09 |  | 0 | CP08-557-P01-09 |  | 5-SPOT WELD | WN | 1 | 30 | 0.5 | WN | SW04 | SW05 | SW04 | SW13 | SW01
CS18-017,CP08-557 |  | - | P02-09 |  | 0 | CP08-557-P02-09 |  | CUT TO SIZE | WN | 1 | 180 | 3 | WN | PP23-060T | PP23
CS18-017,CP08-557 |  | - | P03-09 |  | 0 | CP08-557-P03-09 |  | 8-SPOT WELD | WN | 1 | 50 | 0.83333 | TR | SW06 | SW06
CS18-017,CP08-557 |  | - | P04-09 |  | 0 | CP08-557-P04-09 |  | 3-SPOT WELD | WN | 1 | 120 | 2 | TR | SW05 | SW05 | SW04 | SW06 | SW13 | SW01
CS18-017,CP08-557 |  | - | P05-09 |  | 0 | CP08-557-P05-09 |  | TRIMMING,HAND CUTTING | WN | 1 | 90 | 1.5 | WN | TW02 | TW01 | TW02 | TW03
CS18-017,CP08-557 |  | - |  |  | 0 |  |  |  | WN |  |  |  | WN
CS18-017,CP08-557 |  |  | P07-09 |  |  | CP08-557-P07-09 |  | ED COATING [BLACK] | SUB-CON
CS18-017,CP08-557 |  | - | P08-09 |  | 0 | CP08-557-P08-09 |  | CHECKING | WN | 1 | 15 | 0.25 | AL | CHECKING | CHECKING | [8 empty] | 4 NOS OF JIG CHECKING
CS18-017C,CP08-557C |  | - | P01-04 |  | 0 | CP08-557C-P01-04 |  |  | WN | 1 | 900 | 15 | WN | WS01 | WS01
CS18-017C,CP08-557C |  | - | P02-04 |  | 0 | CP08-557C-P02-04 |  |  | WN | 1 | 240 | 4 | WN | JIG BENDING | JIG BENDING
CS18-017C,CP08-557C |  | - | P03-04 |  | 0 | CP08-557C-P03-04 |  |  | WN | 1 | 240 | 4 | WN | JIG BENDING | JIG BENDING
CP08-557D |  | - | P01-03 |  | 0 | CP08-557D-P01-03 |  |  | WN | 1 | 5700 | 95 | WN | WS01 | WS01
CP08-557D |  | - | P02-03 |  | 0 | CP08-557D-P02-03 |  |  | WN | 1 | 120 | 2 | WN | JIG BENDING | JIG BENDING
|  | - |  |  | 0
CS18-017E,CP08-557E |  | - | P01-02 |  | 0 | CP08-557E-P01-02 |  |  | WN | 1 | 4800 | 80 | WN | WS01 | WS01
CS18-017F,CP08-557F |  | - | P01-02 |  | 0 | CP08-557F-P01-02 |  |  | WN | 1 | 900 | 15 | WN | WS01 | WS01
CP08-556 |  | - | P01-09 |  | 0 | CP08-556-P01-09 |  | 16-SPOT WELD | WN | 1 | 16.7 | 0.27833 | TR | SW04 | SW05 | SW04 | SW06 | SW01 | SW16
CP08-556 |  | - | P02-09 |  | 0 | CP08-556-P02-09 |  | CUTTING | WN | 1 | 60 | 1 | WN | TW02 | TW02 | TW01 | TW03
CP08-556 |  | - | P03-09 |  | 0 | CP08-556-P03-09 |  | BENDING (TP) | WN | 1 | 60 | 1 | TR | PB07 | PB07 | PB01 | PB02
CP08-556 |  | - | P04-09 |  | 0 | CP08-556-P04-09 |  | 2-SPOT WELD | WN | 1 | 60 | 1 | WN | SW06 | SW06 | SW04 | SW05 |  | SW16
CP08-556 |  | - | P05-09 |  | 0 | CP08-556-P05-09 |  | HAND CUTTING | WN | 1 | 50 | 0.83333 | WN | OPT | OPT
CP08-556 |  | - | P06-09 |  | 0 | CP08-556-P06-09 |  | DEBURR | WN | 1 | 50 | 0.83333 | WN | OPT | OPT
CP08-556 |  | - | P07-09 |  | 0 | CP08-556-P07-09 |  | ED COATING [BLACK] | WN | 1 |  | 0 | SUB CON
CP08-556 |  |  | P08-09 |  |  | CP08-556-P08-09 |  | CHECKING | WN | 1 | 8 | 0.13333 | WN | CHECKING | CHECKING | [8 empty] | 1 NO OF CHECKING JIG
CP08-556B |  | - | P01-05 |  | 0 | CP08-556B-P01-05 |  |  | WN | 1 | 600 | 10 | WN | WS01 | WS01
CP08-556B |  | - | P02-05 |  | 0 | CP08-556B-P02-05 |  |  | WN | 1 | 180 | 3 | WN | JIG BENDING | JIG BENDING
CP08-556B |  | - | P03-05 |  | 0 | CP08-556B-P03-05 |  |  | WN | 1 | 180 | 3 | WN | JIG BENDING | JIG BENDING
CP08-556B |  | - | P04-05 |  | 0 | CP08-556B-P04-05 |  |  | WN | 1 | 120 | 2 | WN | PP23-060T | PP23
CP08-556C |  | - | P01-03 |  | 0 | CP08-556C-P01-03 |  |  | WN | 1 | 4800 | 80 | WN | WS01 | WS01
CP08-556C |  | - | P02-03 |  | 0 | CP08-556C-P02-03 |  |  | WN | 1 | 120 | 2 | #N/A | JIG BENDING | JIG BENDING
|  | - |  |  | 0
CP08-556D |  | - | P01-02 |  | 0 | CP08-556D-P01-02 |  |  | WN | 1 | 5700 | 95 | WN | WS01 | WS01
CP08-556E |  | - | P01-02 |  | 0 | CP08-556E-P01-02 |  |  | WN | 1 | 600 | 10 | WN | WS01 | WS01
CS23-002 |  | - | P01-01 |  | 0 | CS23-002-P01-01 |  |  | FM | 1 | 2400 | 40 | FM | FM01 | FM01
CS23-004 | GP01-008 | - | P01-02 |  | 0 | CS23-004-P01-02 |  |  | FM | 1 | 2400 | 40 | FM | FM03 | FM03 | FM02
CS23-005 |  | - | P01-02 |  | 0 | CS23-005-P01-02 |  |  | FM | 1 | 3600 | 60 | FM | FM01 | FM01
CS26-002 |  | - |  |  | 0 | CS26-002- |  |  | FM | 1 |  | 0 | FM | FM02 | FM02
CT10-001 |  | - | P01-06 |  | 0 | CT10-001-P01-06 |  |  | ST | 1 | 330 | 5.5 | ST-3 | PP09-160T | PP09 | PP24
CT10-001 |  | - | P02-06 |  | 0 | CT10-001-P02-06 |  |  | ST | 1 | 330 | 5.5 | ST-3 | PP18 | PP18 | PP25
CT10-001 |  | - | P03-06 |  | 0 | CT10-001-P03-06 |  |  | ST | 1 | 330 | 5.5 | ST-3 | PP17-110T | PP17 | PP26 | [7 empty] | 6 OPT
CT10-001 |  | - | P04-06 |  | 0 | CT10-001-P04-06 |  |  | ST | 1 | 330 | 5.5 | ST-3 | PP16-110T | PP16 | PP20
CT10-001 |  | - | P05-06 |  | 0 | CT10-001-P05-06 |  |  | ST | 2 | 330 | 5.5 | ST-3 | PP27-110T | PP27 | PP28
CT10-003 |  | - | P01-06 |  | 0 | CT10-003-P01-06 |  |  | ST | 1 | 240 | 4 | ST-3 | PP18 | PP18 | PP25 | PP25 | [7 empty] | 1 NET - 120 PCS
CT10-003 |  | - | P02-06 |  | 0 | CT10-003-P02-06 |  |  | ST | 1 | 240 | 4 | ST-3 | PP17-110T | PP17 | PP25 | PP26
CT10-003 |  | - | P03-06 |  | 0 | CT10-003-P03-06 |  |  | ST | 1 | 240 | 4 | ST-3 | PP16-110T | PP16 | PP20 | PP20
CT10-003 |  | - | P04-06 |  | 0 | CT10-003-P04-06 |  |  | ST | 1 | 240 | 4 | ST-3 | PP27-110T | PP27 | PP28 | PP28
CT10-003 |  | - | P05-06 |  | 0 | CT10-003-P05-06 |  |  | ST | 2 | 240 | 4 | ST-3 | SW01 | SW01 | SW09 | SW09
CT10-004 |  | - | P01-07 |  | 0 | CT10-004-P01-07 |  |  | ST | 1 | 120 | 2 | ST-3 | PP27-110T | PP27 | PP21 | [8 empty] | SAME TOOLING V CT10-004,CT10-005,CT10-007,CT10-008
CT10-004 |  | - | P02-07 |  | 0 | CT10-004-P02-07 |  |  | ST | 1 | 120 | 2 | ST-3 | PP16-110T | PP16 | PP17 | [8 empty] | SAME TOOLING V CT10-004,CT10-005,CT10-007,CT10-008
CT10-004 |  | - | P03-07 |  | 0 | CT10-004-P03-07 |  |  | ST | 0 | 120 | 2 | ST-3 | PP17-110T | PP17 | PP16 | [8 empty] | SAME TOOLING V CT10-004,CT10-005,CT10-007,CT10-008
CT10-004 |  | - | P04-07 |  | 0 | CT10-004-P04-07 |  |  | ST | 1 | 120 | 2 | ST-3 | TP03 | TP03 | TP09 | [8 empty] | SAME TOOLING V CT10-004,CT10-005,CT10-007,CT10-008
CT10-004 |  | - | P05-07 |  | 0 | CT10-004-P05-07 |  |  | ST | 0 | 120 | 2 | ST-3 | PP18-150T | PP18 | PP27 | [8 empty] | SAME TOOLING V CT10-004,CT10-005,CT10-007,CT10-008
CT10-004 |  | - |  |  | 0 |  |  |  | ST |  | 120 | 2 | ST-3 |  |  | - | [8 empty] | SAME TOOLING V CT10-004,CT10-005,CT10-007,CT10-008
CT10-004 |  | - | P06-07 |  | 0 | CT10-004-P06-07 |  |  | ST | 2 | 120 | 2 | ST-3 | SW01 | SW01 | SW01 | [7 empty] | SW01 - 1 OPT, CLEANNING - 1 OPT | SAME TOOLING V CT10-004,CT10-005,CT10-007,CT10-008
CT10-005 |  | - | P01-07 |  | 0 | CT10-005-P01-07 |  |  | ST | 1 | 120 | 2 | ST-3 | PP27-110T | PP27 | PP27 | [8 empty] | SAME TOOLING V CT10-004,CT10-007,CT10-008
CT10-005 |  | - | P02-07 |  | 0 | CT10-005-P02-07 |  |  | ST | 1 | 120 | 2 | ST-3 | PP16-110T | PP16 | PP21 | [8 empty] | SAME TOOLING V CT10-004,CT10-007,CT10-008
CT10-005 |  | - | P03-07 |  | 0 | CT10-005-P03-07 |  |  | ST | 1 | 120 | 2 | ST-3 | PP17-110T | PP17 | PP17 | [8 empty] | SAME TOOLING V CT10-004,CT10-007,CT10-008
CT10-005 |  | - | P04-07 |  | 0 | CT10-005-P04-07 |  |  | ST | 1 | 120 | 2 | ST-3 | TP03 | TP03 | TP09 | [8 empty] | SAME TOOLING V CT10-004,CT10-007,CT10-008
CT10-005 |  | - | P05-07 |  | 0 | CT10-005-P05-07 |  |  | ST | 1 | 120 | 2 | ST-3 | PP18-150T | PP18 | PP15 | [8 empty] | SAME TOOLING V CT10-004,CT10-007,CT10-008
CT10-005 |  | - | P06-07 |  | 0 | CT10-005-P06-07 |  |  | ST |  | 120 | 2 | ST-3 | SW01 | SW01 | SW01 | [8 empty] | SAME TOOLING V CT10-004,CT10-007,CT10-008
CT10-006 |  | - | P01-08 |  | 0 | CT10-006-P01-08 |  |  | T/S | 1 | 18 | 0.3 | TR | TM03 | TM03
CT10-006 |  | - | P02-08 |  | 0 | CT10-006-P02-08 |  |  | T/S | 1 | 240 | 4 | ST-2 | PP14-080T | PP14 | PP23 | PP14
CT10-006 |  | - | P03-08 |  | 0 | CT10-006-P03-08 |  |  | T/S | 1 | 240 | 4 | ST-2 | PP14-080T | PP14 | PP23 | PP14
CT10-006 |  | - | P04-08 |  | 0 | CT10-006-P04-08 |  |  | T/S | 1 | 240 | 4 | ST-3 | PP22-060T | PP22 | PP15 | PP22
CT10-006 |  | - | P06-08 |  | 0 | CT10-006-P06-08 |  |  | T/S | 1 | 80 | 1.3333 | TR | PB04 | PB04 | PB05
CT10-006 |  | - | P07-08 |  | 0 | CT10-006-P07-08 |  |  | T/S | 1 | 240 | 4 | TR | PB03 | PB03 | "
CT10-007 |  | - | P01-07 |  | 0 | CT10-007-P01-07 |  |  | ST | 1 | 120 | 2 | ST-3 | PP27-110T | PP27 | PP21 | [8 empty] | SAME TOOLING V CT10-004,CT10-005,CT10-008,CT10-023
CT10-007 |  | - | P02-07 |  | 0 | CT10-007-P02-07 |  |  | ST | 1 | 120 | 2 | ST-3 | PP16-110T | PP16 | PP17 | [8 empty] | SAME TOOLING V CT10-004,CT10-005,CT10-008,CT10-023
CT10-007 |  | - | P03-07 |  | 0 | CT10-007-P03-07 |  |  | ST | 0 | 120 | 2 | ST-3 | PP17-110T | PP17 | PP16 | [8 empty] | SAME TOOLING V CT10-004,CT10-005,CT10-008,CT10-023
CT10-007 |  | - | P04-07 |  | 0 | CT10-007-P04-07 |  |  | ST | 1 | 120 | 2 | ST-3 | TP03 | TP03 | TP03 | [8 empty] | SAME TOOLING V CT10-004,CT10-005,CT10-008,CT10-023
CT10-007 |  | - | P05-07 |  | 0 | CT10-007-P05-07 |  |  | ST | 0 | 120 | 2 | ST-3 | PP18-150T | PP18 | PP27 | [8 empty] | SAME TOOLING V CT10-004,CT10-005,CT10-008,CT10-023
CT10-007 |  | - | P06-07 |  | 0 | CT10-007-P06-07 |  |  | ST | 2 | 120 | 2 | ST-3 | SW01 | SW01 | SW09 | SW14 | [6 empty] | SW01 - 1 OPT, CLEANNING - 1 OPT | SAME TOOLING V CT10-004,CT10-005,CT10-008,CT10-023
CT10-008 |  | - | P01-07 | ver.02 | 0 | CT10-008-P01-07 |  |  | ST | 1 | 120 | 2 | ST-3 | PP27-110T | PP27 | [9 empty] | SAME TOOLING V CT10-004,CT10-007,CT10-005
CT10-008 | GP01-020 | - | P02-07 |  | 0 | CT10-008-P02-07 |  |  | ST | 1 | 120 | 2 | ST-3 | PP16-110T | PP16 | [9 empty] | SAME TOOLING V CT10-004,CT10-007,CT10-005
CT10-008 | GP01-020 | - | P03-07 |  | 0 | CT10-008-P03-07 |  |  | ST | 1 | 120 | 2 | ST-3 | PP17-110T | PP17 | [9 empty] | SAME TOOLING V CT10-004,CT10-007,CT10-005
CT10-008 | GP01-020 | - | P04-07 |  | 0 | CT10-008-P04-07 |  |  | ST | 1 | 120 | 2 | ST-3 | TP03 | TP03 | [9 empty] | SAME TOOLING V CT10-004,CT10-007,CT10-005
CT10-008 | GP01-020 | - | P05-07 |  | 0 | CT10-008-P05-07 |  |  | ST | 1 | 120 | 2 | ST-3 | PP18-150T | PP18 | [8 empty] | EFF-150922 | SAME TOOLING V CT10-004,CT10-007,CT10-005
CT10-008 | GP01-020 | - | P06-07 |  | 0 | CT10-008-P06-07 |  |  | ST |  | 120 | 2 | ST-3 | SW01 | SW01
CT10-009 | GP01-020 | - | P01-05 |  | 0 | CT10-009-P01-05 |  |  | ST | 1 | 60 | 1 | ST-3 | SW01 | SW01 | SW09 | SW14
CT10-009 |  | - | P02-05 |  | 0 | CT10-009-P02-05 |  |  | ST | 1 | 40 | 0.66667 | ST-3 | SW01 | SW01 | SW09 | SW14
CT10-009 |  | - | P03-05 |  | 0 | CT10-009-P03-05 |  |  | ST | 1 | 40 | 0.66667 | TR | PAINTING | PAINTING
CT10-009 |  | - | P04-05 |  | 0 | CT10-009-P04-05 |  |  | ST | 1 | 40 | 0.66667 | ST-1 | PAINTING | PAINTING
CT10-009B |  | - | P01-06 |  | 0 | CT10-009B-P01-06 |  |  | T/S | 1 | 90 | 1.5 | TR | TM03 | TM03 | [8 empty] | FOR MAT - W800-L280 NO NEED SLITING PROCESS
CT10-009B | GC02-003 | - | P02-06 |  | 0 | CT10-009B-P02-06 |  |  | T/S | 1 | 360 | 6 | ST-1 | PP31 | PP04 | PP02 | PP03 | PP31
CT10-009B | GC02-003 | - | P03-06 |  | 0 | CT10-009B-P03-06 |  |  | T/S | 1 | 360 | 6 | ST-1 | PP31 | PP04 | PP02 | PP03 | PP31
CT10-009B | GC02-003 | - | P04-06 |  | 0 | CT10-009B-P04-06 |  |  | T/S | 1 | 120 | 2 | ST-3 | TP03 | TP03 | TP08 | TP07 | TP02 | TP09
CT10-009B | GC02-003 | - | P05-06 |  | 0 | CT10-009B-P05-06 |  |  | T/S | 1 | 120 | 2 | TR | PB01 | PB01 | PB04 | [7 empty] | RUN P31,P31,TP7,PB1 ON 270622
CT10-009C | GC02-003 | - | P01-07 | ver.02 | 0 | CT10-009C-P01-07 |  |  | T/S | 1 | 36 | 0.6 | TR | TM03 | TM03 | T2-18/HR | TM06
CT10-009C |  | - | P02-07 |  | 0 | CT10-009C-P02-07 |  |  | T/S | 1 | 100 | 1.6667 | TR | PB02 | PB02 | PB03 | [7 empty] | EFF 010422 NO MORE PROCESS SM1
CT10-009C |  | - | P03-07 |  | 0 | CT10-009C-P03-07 |  |  | T/S | 1 | 100 | 1.6667 | TR | PB03 | PB03
CT10-009C |  | - | P04-07 |  | 0 | CT10-009C-P04-07 |  |  | T/S | 1 | 40 | 0.66667 | TR | PB04 | PB04 | PB02 | [7 empty] | RUN PB3/PB2,PB4,PB3,PB5,SW5 ON 250722
CT10-009C |  | - | P05-07 |  | 0 | CT10-009C-P05-07 |  |  | T/S | 1 | 50 | 0.83333 | TR | PB05 | PB05 | PB03 | [7 empty] | RUN PB2,PB3,PB4,PB5,SW5 ON 150822
CT10-009C |  | - | P06-07 |  | 0 | CT10-009C-P06-07 |  |  | T/S | 0 | 35 | 0.58333 | TR | SW09 | SW05 | SW09 | SW01 | SW13 | [5 empty] | RUN PB3,PB3,PB4,PB5,SW5 ON 240622
CT10-013A |  | - | P01-09 |  | 0 | CT10-013A-P01-09 |  |  | TR | 1 | 240 | 4 | SM | SM01 | SM01
CT10-013A |  | - | P02-09 |  | 0 | CT10-013A-P02-09 |  |  | TR | 1 | 15 | 0.25 | TR | TM03 | TM03
CT10-013A |  | - | P03-09 |  | 0 | CT10-013A-P03-09 |  |  | TR | 1 | 20 | 0.33333 | TR | PB02 | PB02
CT10-013A |  | - | P04-09 |  | 0 | CT10-013A-P04-09 |  |  | TR | 1 | 120 | 2 | TR | PB02 | PB02
CT10-013A |  | - | P05-09 |  | 0 | CT10-013A-P05-09 |  |  | TR | 1 | 80 | 1.3333 | TR | PB02 | PB02
CT10-013A |  | - | P06-09 |  | 0 | CT10-013A-P06-09 |  |  | TR | 1 | 40 | 0.66667 | TR | PB04 | PB04
CT10-013A |  | - | P07-09 |  | 0 | CT10-013A-P07-09 |  |  | TR | 1 | 200 | 3.3333 | TR | PB03 | PB03
CT10-013A |  | - | P08-09 |  | 0 | CT10-013A-P08-09 |  |  | TR | 1 | 60 | 1 | #N/A | #N/A | PB1,3,2
CT10-013A |  | - | P09-09 |  | 0 | CT10-013A-P09-09 |  |  | TR | 1 | 40 | 0.66667 | #N/A | #N/A
CT10-013 |  | - | P01-05 |  | 0 | CT10-013-P01-05 |  |  | ST | 1 | 60 | 1 | ST-3 | SW01 | SW01
CT10-013 |  | - | P02-05 |  | 0 | CT10-013-P02-05 |  |  | ST | 1 | 60 | 1 | ST-3 | SW01 | SW01
CT10-013 |  | - | P03-05 |  | 0 | CT10-013-P03-05 |  |  | ST | 1 | 60 | 1 | TR | CLEAN | CLEANING
CT10-013 |  | - | P04-05 |  | 0 | CT10-013-P04-05 |  |  | ST | 1 | 35 | 0.58333 | ST-1 | PAINTING | PAINTING
CT10-013 |  | - | P05-05 |  | 0 | CT10-013-P05-05 |  |  | ST | 1 | 35 | 0.58333 | ST-1 | PAINTING | PAINTING
CT10-014 |  | - | P01-06 |  | 0 | CT10-014-P01-06 |  |  | ST | 1 | 330 | 5.5 | ST-3 | PP09-160T | PP09 | PP24 | PP18 | PP24
CT10-014 | GP01-022 | - | P02-06 |  | 0 | CT10-014-P02-06 |  |  | ST | 1 | 330 | 5.5 | ST-3 | PP18 | PP18 | PP18 | PP21 | PP25
CT10-014 | GP01-022 | - | P03-06 |  | 0 | CT10-014-P03-06 |  |  | ST | 1 | 330 | 5.5 | ST-3 | PP17-110T | PP17 | PP17 | PP17 | PP26
CT10-014 | GP01-022 | - | P04-06 |  | 0 | CT10-014-P04-06 |  |  | ST | 1 | 330 | 5.5 | ST-3 | PP16-110T | PP16 | PP19 | PP16 | PP20
CT10-014 | GP01-022 | - | P05-06 |  | 0 | CT10-014-P05-06 |  |  | ST | 2 | 330 | 5.5 | ST-3 | PP27-110T | PP27 | PP27 | PP09 | PP28
CT10-013B | GP01-022 | - | P01-05 |  | 0 | CT10-013B-P01-05 |  |  | T/S | 1 | 90 | 1.5 | TR | TM03 | TM03
CT10-013B |  | - | P02-05 |  | 0 | CT10-013B-P02-05 |  |  | T/S | 1 | 360 | 6 | ST-1 | PP13-060T | PP13
CT10-013B |  | - | P03-05 |  | 0 | CT10-013B-P03-05 |  |  | T/S | 1 | 360 | 6 | ST-1 | PP13-060T | PP13
CT10-013B |  | - | P04-05 |  | 0 | CT10-013B-P04-05 |  |  | T/S | 1 | 120 | 2 | ST-3 | TP03 | TP03
CT10-013B |  | - | P05-05 |  | 0 | CT10-013B-P05-05 |  |  | T/S | 1 | 120 | 2 | TR | PB01 | PB01
CT10-015 |  | - | P01-05 |  | 0 | CT10-015-P01-05 |  |  | ST | 1 | 360 | 6 | ST-4 | PP24-160T | PP24 | PP10 | [7 empty] | OPF | IF PP24 MACHINE BREAK DOWN P01-04 CAN RUN PP10
CT10-015 | GP01-023 | - | P02-05 |  | 0 | CT10-015-P02-05 |  |  | ST | 1 | 360 | 6 | ST-4 | PP25-160T | PP25
CT10-015 | GP01-023 | - | P03-05 |  | 0 | CT10-015-P03-05 |  |  | ST | 1 | 360 | 6 | ST-4 | PP20-110T | PP20
CT10-015 | GP01-023 | - | P04-05 |  | 0 | CT10-015-P04-05 |  |  | ST | 1 | 360 | 6 | ST-4 | PP28-110T | PP28
CT10-016 | GP01-023 | - | P01-06 |  | 0 | CT10-016-P01-06 |  |  | ST | 1 | 5280 | 88 | SM | SM01 | SM01
CT10-016 | GP01-024 | - | P02-06 |  | 0 | CT10-016-P02-06 |  |  | ST | 1 | 360 | 6 | ST-3 | PP17-110T | PP17 | PP03 | PP21 | PP13 | PP10 | PP18
CT10-016 | GP01-024 | - | P03-06 |  | 0 | CT10-016-P03-06 |  |  | ST | 1 | 240 | 4 | ST-3 | PP16-110T | PP16 | PP13 | PP04 | PP03 | PP13 | PP17
CT10-016 | GP01-024 | - | P04-06 |  | 0 | CT10-016-P04-06 |  |  | ST | 1 | 240 | 4 | ST-3 | PP27-110T | PP27 | PP03 |  | PP04 | PP03 | PP16
CT10-016 | GP01-024 | - | P05-06 |  | 0 | CT10-016-P05-06 |  |  | ST | 1 | 300 | 5 | ST-3 | TP03 | TP03 | TP09 |  |  | TP03 | TP03
CT10-017 | GP01-024 | - | P01-03 |  | 0 | CT10-017-P01-03 |  |  | TR | 1 | 96 | 1.6 | TR | TM03 | TM03 | [8 empty] | NEED TAPPING PROCESS-TP2,100PCS/HRS | NEED RUN TM03,GOT TAPPING (M4) TM03 CAN'T RUN
CT10-017 |  | - | P02-03 |  | 0 | CT10-017-P02-03 |  |  | TR | 1 | 150 | 2.5 | #N/A | PB03 | PB02 | PB03
CT10-018 |  | - | P01-06 |  | 0 | CT10-018-P01-07 |  |  | ST | 1 | 120 | 2 | ST-3 | PP27-110T | PP27 | PP27 | PP01 | PP27
CT10-018 |  | - | P02-06 |  | 0 | CT10-018-P02-07 |  |  | ST | 1 | 120 | 2 | ST-3 | PP16-110T | PP16 | PP16 | PP21 | PP17 | [5 empty] | SHARE DIE V CT10-004,CT10-005,CT10-007,CT10-008
CT10-018 |  | - | P03-06 |  | 0 | CT10-018-P03-07 |  |  | ST | 1 | 120 | 2 | ST-3 | PP17-110T | PP17 | PP17 | PP17 | PP16 | [5 empty] | CT10-010
CT10-018 |  | - | P04-06 |  | 0 | CT10-018-P04-07 |  |  | ST | 1 | 120 | 2 | ST-3 | TP03 | TP03 | PP18 | PP16 | TP03
CT10-018 |  | - | P05-06 |  | 0 | CT10-018-P05-07 |  |  | ST | 1 | 120 | 2 | ST-3 | PP18 | PP18 | TP07 | TP03 | PP18
CT10-018 |  | - | P06-06 |  | 0 | CT10-018-P06-07 |  |  | ST | 1 | 120 | 2 | ST | SW01 | SW01 | SW01 |  | SW01
CT10-019 |  | - | P01-08 |  | 0 | CT10-019-P01-08 |  |  | ST | 1 | 240 | 4 | ST-3 | SM01 | SM01
CT10-019 |  | - | P02-08 |  | 0 | CT10-019-P02-08 |  |  | ST | 1 | 240 | 4 | ST-3 | PP09-160T | PP09
CT10-019 |  | - | P03-08 |  | 0 | CT10-019-P03-08 |  |  | ST | 1 | 240 | 4 | ST-3 | PP18-150T | PP18
CT10-019 |  | - | P04-08 |  | 0 | CT10-019-P04-08 |  |  | ST |  | 240 | 4 | ST-3 | TP03 | TP03
CT10-019 |  | - | P05-08 |  | 0 | CT10-019-P05-08 |  |  | ST | 1 | 240 | 4 | ST-3 | PP17-110T | PP17
CT10-019 |  | - | P06-08 |  | 0 | CT10-019-P06-08 |  |  | ST |  | 240 | 4 | ST-3 | PP16-110T | PP16
CT10-019 |  | - | P07-08 |  |  | CT10-019-P07-08 |  |  | ST | 1 | 240 | 4 | ST-3 | PP27-110T | PP27
CT10-020 |  | - | P01-06 |  | 0 | CT10-020-P01-06 |  |  | ST | 1 | 360 | 6 | SM | SM01 | SM01
CT10-020 |  | - | P02-06 |  | 0 | CT10-020-P02-06 |  |  | ST | 1 | 300 | 5 | ST-4 | PP24-160T | PP24 | PP25 | PP24 | [6 empty] | OPF
CT10-020 |  | - | P03-06 |  | 0 | CT10-020-P03-06 |  |  | ST | 1 | 300 | 5 | ST-4 | PP25-160T | PP25 | PP26 | PP25 | [6 empty] | MACHINE SM1-BASE ON 1905 PCS - 7 HRS
CT10-020 |  | - | P04-06 |  | 0 | CT10-020-P04-06 |  |  | ST | 1 | 300 | 5 | ST-4 | PP20-110T | PP26 | PP20 | PP20
CT10-020 |  | - | P05-06 |  | 0 | CT10-020-P05-06 |  |  | ST | 1 | 300 | 5 | ST-4 | PP28-110T | PP28 | PP28 | PP28
CT10-021 |  | - | P01-04 |  | 0 | CT10-021-P01-04 |  |  | ST | 1 | 2280 | 38 | SM | SM01 | SM01
CT10-021 |  | - | P02-04 |  | 0 | CT10-021-P02-04 |  |  | ST | 1 | 360 | 6 | ST-2 | PP15-080T | PP15 | PP16 | PP02 | PP28 | PP04 | PP21
CT10-021 |  | - | P03-04 |  | 0 | CT10-021-P03-04 |  |  | ST | 1 | 360 | 6 | ST-2 | PP15-080T | PP15 | PP27 | PP18 | PP28 | PP04 | PP15
CT10-022 |  | - | P01-02 |  | 0 | CT10-022-P01-02 |  |  | ST | 1 | 1800 | 30 | ST-1 | PP19-110T | PP19 | PP14
CT10-023 | GP01-031 | - | P01-07 |  | 0 | CT10-023-P01-07 |  | BLANKING | ST | 1 | 120 | 2 | ST-3 | PP27-110T | PP27 |  | PP21 | [6 empty] | SAME TOOLING V CT10-004,CT10-005,CT10-008,CT10-023
CT10-023 |  | - | P02-07 |  | 0 | CT10-023-P02-07 |  | BENDING 1 | ST | 1 | 120 | 2 | ST-3 | PP16-110T | PP16 |  | PP17 | [6 empty] | SAME TOOLING V CT10-004,CT10-005,CT10-008,CT10-023
CT10-023 |  | - | P03-07 |  | 0 | CT10-023-P03-07 |  | BENDING 2 | ST | 1 | 120 | 2 | ST-3 | PP17-110T | PP17 |  | PP16 | [6 empty] | SAME TOOLING V CT10-004,CT10-005,CT10-008,CT10-023
CT10-023 |  | - | P04-07 |  | 0 | CT10-023-P04-07 |  | 4-TAPPING M4X0.7 | ST | 1 | 120 | 2 | ST-3 | TP03 | TP03 | TP07 | TP03 | [6 empty] | SAME TOOLING V CT10-004,CT10-005,CT10-008,CT10-023
CT10-023 |  | - | P05-07 |  | 0 | CT10-023-P05-07 |  | BENDING 3 | ST |  | 120 | 2 | ST-3 | PP18-150T | PP18 |  | PP27 | [6 empty] | SAME TOOLING V CT10-004,CT10-005,CT10-008,CT10-023
CT10-023 |  | - | P06-07 |  | 0 | CT10-023-P06-07 |  | 3-SPOT WELD | ST | 1 | 120 | 2 | ST-3 | SW01 | SW01 | SW09 | SW01 | [6 empty] | SAME TOOLING V CT10-004,CT10-005,CT10-008,CT10-023
CT10-025 |  | - | P01-06 |  | 0 | CT10-025-P01-06 |  |  | ST | 1 | 330 | 5.5 | ST-3 | PP09-160T | PP09 | PP24 | P09
CT10-025 |  | - | P02-06 |  | 0 | CT10-025-P02-06 |  |  | ST | 1 | 330 | 5.5 | ST-3 | PP18-150T | PP18 | PP25 | PP18 | [6 empty] | SHARE DIE WITH CT10-001,CT10-014
CT10-025 |  | - | P03-06 |  | 0 | CT10-025-P03-06 |  |  | ST | 1 | 330 | 5.5 | ST-3 | PP17-110T | PP17 | PP26 | PP21
CT10-025 |  | - | P04-06 |  | 0 | CT10-025-P04-06 |  |  | ST | 1 | 330 | 5.5 | ST-3 | PP16-110T | PP16 | PP20 | PP17
CT10-025 |  | - | P05-06 |  | 0 | CT10-025-P05-06 |  |  | ST | 2 | 330 | 5.5 | ST-3 | PP27-110T | PP27 | PP28 | PP16
CU01-002 |  | - | P01-04 |  | 0 | CU01-002-P01-04 |  |  | AL | 1 | 150 | 2.5 | #N/A | CM05
CU01-002 |  | - | P02-04 |  | 0 | CU01-002-P02-04 |  |  | AL | 1 | 600 | 10 | #N/A | BDS01
CU01-002 |  | - | P03-04 |  | 0 | CU01-002-P03-04 |  |  | AL | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CU01-002 |  | - | P04-04 |  | 0 | CU01-002-P04-04 |  |  | AL | 1 | 1 DAY | 1 DAY | WH1 | WH1 | STORE
CU01-006 |  | - | P01-04 |  | 0 | CU01-006-P01-04 |  |  | AL | 1 | 84 | 1.4 | AL | CM05 | CM05
CU01-006 |  | - | P02-04 |  | 0 | CU01-006-P02-04 |  |  | AL | 1 | 600 | 10 | AL | BDS01 | BDS01
CU01-006 |  | - | P03-04 |  | 0 | CU01-006-P03-04 |  | DIESEL CLEANING | AL | 1 | 1200 | 20 | #N/A | OPT | OPT
CU01-011 |  | - | P01-06 |  | 0 | CU01-011-P01-06 |  |  | AL | 1 | 108 | 1.8 | AL | CM05 | CM5
CU01-011 |  | - | P02-06 |  | 0 | CU01-011-P02-06 |  |  | AL | 1 | 420 | 7 | AL | BL03 | BL03 | BL04
CU01-011 |  | - | P03-06 |  | 0 | CU01-011-P03-06 |  |  | AL | 1 | 240 | 4 | AL | TP02 | TP02
CU01-011 |  | - | P04-06 |  | 0 | CU01-011-P04-06 |  |  | AL | 1 | 4800 | 80 | AL | DEBURR | DEBURR
CU01-011 |  | - | P05-06 |  | 0 | CU01-011-P05-06 |  |  | AL | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CU01-015 |  | - | P01-04 |  | 0 | CU01-015-P01-04 |  |  | AL | 1 | 150 | 2.5 | AL | CM05 | CM05
CU01-015 |  | - | P02-04 |  | 0 | CU01-015-P02-04 |  |  | AL | 1 | 600 | 10 | AL | BS01 | BS01
CU01-015 |  | - | P03-04 |  | 0 | CU01-015-P03-04 |  |  | AL | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CU01-016 |  | - | P01-04 |  | 0 | CU01-016-P01-04 |  |  | AL | 1 | 150 | 2.5 | AL | CM05 | CM05
CU01-016 |  | - | P02-04 |  | 0 | CU01-016-P02-04 |  |  | AL | 1 | 600 | 10 | AL | BDS01 | BDS01
CU01-016 |  | - | P03-04 |  | 0 | CU01-016-P03-04 |  |  | AL | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CU01-018 |  | - | P01-04 |  | 0 | CU01-018-P01-04 |  |  | AL | 1 | 150 | 2.5 | AL | CM03 | CM03 | CM05
CU01-018 |  | - | P02-04 |  | 0 | CU01-018-P02-04 |  |  | AL | 1 | 600 | 10 | AL | BDS01 | BDS01
CU01-018 |  | - | P03-04 |  | 0 | CU01-018-P03-04 |  |  | AL | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CU01-031 |  | - | P01-08 |  | 0 | CU01-031-P01-08 |  |  | S/A | 1 | 120 | 2 | AL | PP02-060T | PP02
CU01-031 |  | - | P02-08 |  | 0 | CU01-031-P02-08 |  |  | S/A | 1 | 150 | 2.5 | AL | BL03 | BL03
CU01-031 |  | - | P03-08 |  | 0 | CU01-031-P03-08 |  |  | S/A | 1 | 120 | 2 | AL | BL03 | BL03
CU01-031 |  | - | P04-08 |  | 0 | CU01-031-P04-08 |  |  | S/A | 1 | 0 | 0 | AL | SUB CON
CU01-031 |  | - | P05-08 |  | 0 | CU01-031-P05-08 |  |  | S/A | 1 | 132 | 2.2 | AL | BL03 | BL03
CU01-031 |  | - | P06-08 |  | 0 | CU01-031-P06-08 |  |  | S/A | 1 | 120 | 2 | AL | TP02 | TP02 | TP04
CU01-031 |  | - | P07-08 |  | 0 | CU01-031-P07-08 |  |  | S/A | 1 | 0 | 0 | #N/A | #N/A
CU01-043 |  | - | P01-02 |  | 0 | CU01-043-P01-02 |  |  | ST | 1 | 1800 | 30 | ST-1 | PP10-080T | PP10 | PP12
CU01-046 |  | - | P01-03 |  | 0 | CU01-046-P01-03 |  |  | ST | 1 | 1800 | 30 | ST-4 | PP01-110T | PP24 |  |  | PP01 | [5 empty] | TOGETHER RUN V CU01-047
CU01-046 |  | - | P02-03 |  | 0 | CU01-046-P02-03 |  |  | ST | 1 | 240 | 4 | ST-1 | PP15-080T | PP05 | PP03 | PP15 | PP01 | [5 empty] | TOGETHER RUN V CU01-047
CU01-047 |  | - | P01-03 |  | 0 | CU01-047-P01-03 |  |  | ST | 1 | 1400 | 23.3333 | ST-4 | PP01-110T | PP24 |  |  |  | PP01 | PP01 |  |  |  | TOGETHER RUN V CU01-046
CU01-047 |  | - | P02-03 |  | 0 | CU01-047-P02-03 |  |  | ST | 1 | 240 | 4 | ST-1 | PP15-080T | PP05 | PP03 | PP24 | PP15 | PP01 | PP15 |  |  |  | TOGETHER RUN V CU01-046
CU01-048,CU01-049 |  | - | P01-03 |  | 0 | CU01-048,CU01-049-P01-03 |  |  | TR | 1 | 25920 | 432 | SM | SM01 | SM01
CU01-048,CU01-049 | GC02-031 | - | P02-03 |  | 0 | CU01-048,CU01-049-P02-03 |  |  | TR | 1 | 120 | 2 | TR | TM06 | TM06 | TM03 | TM05
CU01-048 | GC02-031 | - | P01-02 |  | 0 | CU01-048-P01-02 |  |  | TR | 1 | 180 | 3 | TR | PB04 | PB04
CU01-049 |  | - | P01-02 |  | 0 | CU01-049-P01-02 |  |  | TR | 1 | 180 | 3 | TR | PB04 | PB04
CU01-051 |  | - | P02-04 |  | 0 | CU01-051-P02-04 |  |  | ST | 1 | 480 | 8 | ST-3 | PP12-080T | PP12 | PP14
CU01-051 |  | - | P03-04 |  | 0 | CU01-051-P03-04 |  |  | ST | 1 | 360 | 6 | ST-3 | PP12-080T | PP12 | PP14 | PP05
CU03-001A |  | - | P01-01 |  | 0 | CU03-001A-P01-01 |  |  | FM | 1 | 3000 | 50 | FM | FM02 | FM02 | FM01
CU03-001 |  | - | P01-04 |  | 0 | CU03-001-P01-04 |  |  | ST | 1 | 360 | 6 | ST-2 | PP06-040T | PP06 | PP11
CU03-001 |  | - | P02-04 |  | 0 | CU03-001-P02-04 |  |  | ST | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CU03-001 |  | - | P03-04 |  | 0 | CU03-001-P03-04 |  |  | ST | 1 | 900 | 15 | #N/A | #N/A
CU03-001 |  | - | P04-04 |  | 0 | CU03-001-P04-04 |  |  | ST | 1 | 1260 | 21 | #N/A | #N/A
CU03-002/CM17-002 |  | - | P01-04 |  | 0 | CM17-002-P01-04 |  |  | F/S | 1 | 3600 | 60 | FM | FM02 | FM01 | FM02 | FM03
CU03-002/CM17-002 |  | - | P02-04 |  | 0 | CM17-002-P02-04 |  |  | F/S | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CU03-002/CM17-002 |  | - | P03-04 |  | 0 | CM17-002-P03-04 |  |  | F/S | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CU03-003/CM17-003 |  | - | P01-04 |  | 0 | CM17-003-P01-04 |  |  | ST | 1 | 1080 | 18 | ST-1 | PP02-060T | PP14 | PP02 | PP12 | PP10 | [5 empty] | PROGRESSIVE
CU03-003/CM17-003 |  | - | P02-04 |  | 0 | CM17-003-P02-04 |  |  | ST | 1 | 480 | 8 | ST-1 | PP04-060T | PP14 | PP02 | PP13 | PP15 | PP22 | PP03 | PP04 | PP05 |  | PROGRESSIVE
CU03-003/CM17-003 |  | - | P03-04 |  | 0 | CM17-003-P03-04 |  |  | ST | 1 | 240 | 4 | ST-1 | PP15-080T | P10 | PP15 | PP22
CU03-005/CM17-005 |  | - | P01-05 |  | 0 | CM17-005-P01-05 |  |  | F/S | 1 | 2400 | 40 | FM | FM02 | FM01 | FM02 | FM03 | [7 empty] | SETTING : 7 HRS
CU03-005/CM17-005 |  | - | P04-05 |  | 0 | CM17-005-P04-05 |  |  | F/S | 2 | 270 | 4.5 | AL | CHECK | CHECKING
CU03-006/CM17-006 |  | - | P01-07 |  | 0 | CM17-006-P01-07 |  |  | F/S | 1 | 3600 | 60 | FM | FM02 | FM01 | FM02
CU03-006/CM17-006 |  | - | P02-07 |  | 0 | CM17-006-P02-07 |  |  | F/S | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CU03-006/CM17-006 |  | - | P03-07 |  | 0 | CM17-006-P03-07 |  |  | F/S | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CU03-006/CM17-006 |  | - | P04-07 |  | 0 | CM17-006-P04-07 |  |  | F/S | 1 | 270 | 4.5 | FM | CHECK | CHECKING
CU03-006/CM17-006 |  | - | P05-07 |  | 0 | CM17-006-P05-07 |  |  | F/S | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CU03-006/CM17-006 |  | - | P06-07 |  | 0 | CM17-006-P06-07 |  |  | F/S | 1 | 240 | 4 | FM | CHECK | CHECKING
CU03-007 |  | - | P01-03 |  | 0 | CU03-007-P01-03 |  |  | ST | 1 | 210 | 3.5 | ST-3 | SW01 | SW01
CU03-007 |  | - | P02-03 |  | 0 | CU03-007-P02-03 |  |  | ST | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CU03-007 |  | - | P03-03 |  | 0 | CU03-007-P03-03 |  |  | ST | 1 | 1200 | 20 | AL | CHECK | CHECKING
CU03-007A |  | - | P01-01 |  | 0 | CU03-007A-P01-01 |  |  | ST | 1 | 1800 | 30 | ST-2 | PP19-110T | PP19 | [8 empty] | PROGRESSIVE
CU03-008/CM17-008 |  | - | P01-04 |  | 0 | CM17-008-P01-04 |  | PROGRESSIVE | ST | 1 | 2400 | 40 | ST-1 | PP14-080T | PP14 | PP19
CU03-008/CM17-008 |  | - | P03-04 |  | 0 | CM17-008-P03-04 |  | CHECKING | ST | 1 | 1080 | 18 | AL | CHECKING | CHECKING
CU03-011 |  | - | P01-02 |  | 0 | CU03-011-P01-02 |  |  | ST | 1 | 1800 | 30 | ST-1 | PP10-080T | PP10
CU03-011 |  | - | P02-02 |  | 0 | CU03-011-P02-02 |  |  | ST | 1 | INSUSTRIES | INSUSTRIES | #N/A | #N/A
CU03-013 |  | - | P01-03 |  | 0 | CU03-013-P01-03 |  |  | ST | 1 | 900 | 15 | #N/A | #N/A
CU03-013 |  | - | P02-03 |  | 0 | CU03-013-P02-03 |  |  | ST | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CU03-013 |  | - | P03-03 |  | 0 | CU03-013-P03-03 |  |  | ST | 1 | STORE | STORE | #N/A | #N/A
CU03-014/CM17-014 |  | - | P01-05 |  | 0 | CM17-014-P01-05 |  |  | ST | 1 | 720 | 12 | ST-1 | PP05-060T | PP05 | PP15
CU03-014/CM17-014 |  | - | P02-05 |  | 0 | CM17-014-P02-05 |  |  | ST | 1 | 180 | 3 | ST-3 | PP22-060T | PP22 | PP05
CU03-014/CM17-014 |  | - | P03-05 |  | 0 | CM17-014-P03-05 |  |  | ST | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CU03-014/CM17-014 |  | - | P04-05 |  | 0 | CM17-014-P04-05 |  |  | ST | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CU03-015/CM17-015 |  | - | P01-02 |  | 0 | CM17-015-P01-02 |  |  | ST | 1 | 1800 | 30 | ST-4 | PP30-200T | PP30 | PP33
CU03-016/CM17-016 |  | - | P01-01 |  | 0 | CM17-016-P01-02 |  |  | ST | 1 | 1200 | 20 | ST-4 | PP33 | PP33 | PP30
CU03-017/CM17-017 |  | - | P01-02 |  | 0 | CM17-017-P01-02 |  |  | ST | 1 | 1200 | 20 | ST-4 | PP30-200T | PP30
CV02-025 |  | - | P01-02 |  | 0 | CV02-025-P01-02 |  |  | ST | 1 | 2100 | 35 | ST-1 | PP14-080T | PP14
CV02-026 |  | - | P01-02 |  | 0 | CV02-026-P01-02 |  |  | ST | 1 | 1800 | 30 | ST-1 | PP12-080T | PP12
CV02-032 |  | - | P01-01 |  | 0 | CV02-032-P01-02 |  |  | ST | 1 | 1800 | 30 | ST-2 | PP19-110T | PP19 | PP14
CV02-033 |  | - | P01-02 |  | 0 | CV02-033-P01-02 |  |  | ST | 1 | 1800 | 30 | ST-2 | PP30-200T | PP01 | PP30
CV02-034 |  | - | P01-02 |  | 0 | CV02-034-P01-03 |  |  | SA | 1 | 1800 | 30 | ST-1 | PP02-060T | PP02
CV02-034 |  | - | P02-02 |  | 0 | CV02-034-P02-03 |  |  | SA | 1 | 720 | 12 | AL | TP06 | TP06
CV02-035 |  | - | P01-03 |  | 0 | CV02-035-P01-03 |  | PROGRESSIVE | SA | 1 | 2100 | 35 | ST-1 | PP10-080T | PP02 | PP10 | PP19 | PP14
CV02-035 |  | - | P02-03 |  | 0 | CV02-035-P02-03 |  | TAPPING | SA | 1 | 780 | 13 | AL | TP08 | TP06 | TP08
CV02-036 |  | - | P01-01 |  | 0 | CV02-036-P01-01 |  |  | ST | 1 | 1500 | 25 | ST-1 | PP02-060T | PP02 | PP14 | PP12
CV02-037 |  | - | P01-01 |  | 0 | CV02-037-P01-01 |  |  | ST | 1 | 1200 | 20 | ST-1 | PP12-080T | PP12 | PP02
CV02-038 |  | - | P01-02 |  | 0 | CV02-038-P01-02 |  |  | ST | 1 | 1500 | 25 | ST-1 | PP02-060T | PP02
CV02-038 |  | - | P02-02 |  | 0 | CV02-038-P02-02 |  |  | ST | 1 | 7200 | 120 | ST | DY01 | DRY1
CV02-040 |  | - | P01-01 |  | 0 | CV02-040-P01-01 |  |  | FM | 1 | 1200 | 20 | FM | FM01 | FM01
CV02-041 |  | - | P01-01 |  | 0 | CV02-041-P01-01 |  |  | FM | 1 | 1200 | 20 | FM | FM02 | FM02
CV02-042 |  | - | P01-01 |  | 0 | CV02-042-P01-01 |  |  | ST | 1 | 1200 | 20 | ST-2 | PP01-110T | PP01
CV02-050 |  | - | P01-04 |  | 0 | CV02-050-P01-04 |  |  | S/A | 1 | 300 | 5 | ST-1 | PP04-060T | PP03 | PP22 | PP03 | PP04
CV02-050 |  | - | P02-04 |  | 0 | CV02-050-P02-04 |  |  | S/A | 1 | 300 | 5 | ST-1 | PP02-060T | PP04 | PP13 | PP22 | [7 empty] | THIS PROCESS DIE NEED MACHINE ADA LUBANG PUNYA
CV02-050 |  | - | P03-04 |  | 0 | CV02-050-P03-04 |  |  | S/A | 1 | 420 | 7 | AL | TP06 | TP06 | TP02 | PP13
CV02-053 |  | - | P01-05 |  | 0 | CV02-053-P01-05 |  |  | ST | 1 | 22260 | 371 | SM | SM01 | SM01
CV02-053 |  | - | P02-05 |  | 0 | CV02-053-P02-05 |  |  | ST | 1 | 600 | 10 | ST-1 | PP10-080T | PP10 | PP03 | PP04 | [6 empty] | SHARE V CV02-056 - P02-04
CV02-053 |  | - | P03-05 |  | 0 | CV02-053-P03-05 |  |  | ST | 1 | 360 | 6 | ST-1 | PP04-060T | PP04 | PP03 | PP13 | [6 empty] | SHARE V CV02-056 - P03-04
CV02-053 |  | - | P04-05 |  | 0 | CV02-053-P04-05 |  |  | ST | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CV02-056 |  | - | P01-04 |  | 0 | CV02-056-P01-04 |  |  | ST | 1 | 240 | 4 | SM | SM01 | SM01 | [8 empty] | SIMILAR DIE WITH CV02-053
CV02-056 |  | - | P02-04 |  | 0 | CV02-056-P02-04 |  | BLANKING | ST | 1 | 750 | 12.5 | ST-1 | PP10-080T | PP10 | [8 empty] | SIMILAR DIE WITH CV02-053
CV02-056 |  | - | P03-04 |  | 0 | CV02-056-P03-04 |  |  | ST | 1 | 360 | 6 | ST-1 | PP04-060T | PP04 | [8 empty] | SIMILAR DIE WITH CV02-053
CV02-056 |  | - | P04-04 |  | 0 | CV02-056-P04-04 |  |  | ST | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON | [8 empty] | SIMILAR DIE WITH CV02-053
CV02-058 |  | - | P01-02 |  | 0 | CV02-058-P01-02 |  |  | ST | 1 | 1800 | 30 | ST-1 | PP14-080T | PP14
CV02-059 |  | - | P01-02 |  | 0 | CV02-059-P01-03 |  |  | ST | 1 | 1500 | 25 | ST-1 | PP14-080T | PP14 | PP02 | PP12 | PP22
CV02-061 |  | - | P01-04 |  | 0 | CV02-061-P01-04 |  | SLIT TO SIZE | ST | 1 | 180 | 3 | SM | SM01 | SM01
CV02-061 |  | - | P02-04 |  | 0 | CV02-061-P02-04 |  | BLANKING | ST | 1 | 360 | 6 | ST-2 | PP15-080T | PP15
CV02-061 |  | - | P03-04 |  | 0 | CV02-061-P03-04 |  | BENDING | ST | 1 | 360 | 6 | ST-3 | PP22-060T | PP22
CV02-064 |  | - | P01-02 |  | 0 | CV02-064-P01-02 |  |  | ST | 1 | 900 | 25 | ST-1 | PP01-110T | PP10 | PP01
CV04-001 |  | - | P01-01 |  | 0 | CV04-001-P01-01 |  |  | AL | 1 | 240 | 4 | AL | CM03 | CM03
CV04-008 |  | - | P01-05 |  | 0 | CV04-008-P01-05 |  |  | ST | 1 | 1800 | 30 | ST-1 | PP14-080T | PP14 | PP02 | PP19 | [6 empty] | NEED TO RUN P01,P02&P03 TOGETHER
CV04-008 |  | - | P02-05 |  | 0 | CV04-008-P02-05 |  |  | ST | 1 | 360 | 6 | ST-2 | PP06-040T | PP06 | PP12 | [7 empty] | NEED TO RUN P01,P02&P03 TOGETHER
CV04-008 |  | - | P03-05 |  | 0 | CV04-008-P03-05 |  |  | ST | 1 | 360 | 6 | ST-1 | PP11-035T | PP05 | PP11 | PP06 | PP02 | PP12 |  |  |  |  | NEED TO RUN P01,P02&P03 TOGETHER
CV04-008 |  | - | P04-05 |  | 0 | CV04-008-P04-05 |  |  | ST | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CV04-009 |  | - | P01-03 |  | 0 | CV04-009-P01-03 |  |  | ST | 1 | 2100 | 35 | ST-2 | PP06-040T | PP06
CV04-009 |  | - | P02-03 |  | 0 | CV04-009-P02-03 |  |  | ST | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CV04-009 |  | - | P03-03 |  | 0 | CV04-009-P03-03 |  |  | ST | 1 | STORE | STORE | #N/A | #N/A
CV04-010 |  | - | P01-08 |  | 0 | CV04-010-P01-08 |  |  | ST | 1 | 480 | 8 | ST-1 | PP11-035T | PP11
CV04-010 |  | - | P02-08 |  | 0 | CV04-010-P02-08 |  |  | ST | 1 | 240 | 4 | ST-1 | PP11-035T | PP11 | PP06 | PP15 | [6 empty] | SHARE DIE V CV04-013-P02 | CV04-010-P02,P03 - SAME DIE
CV04-010 |  | - | P03-08 |  | 0 | CV04-010-P03-08 |  |  | ST | 1 | 240 | 4 | ST-2 | PP06-040T | PP06 | PP05 | PP22 | [6 empty] | SHARE DIE V CV04-013-P03
CV04-010 |  | - | P04-08 |  | 0 | CV04-010-P04-08 |  |  | ST | 1 | 240 | 4 | ST-2 | PP15-080T | PP15 |  | PP06
CV04-010 |  | - | P05-08 |  | 0 | CV04-010-P05-08 |  |  | ST | 1 | 240 | 4 | #N/A | HAND BEND-JIG
CV04-010 |  | - | P06-08 |  | 0 | CV04-010-P06-08 |  |  | ST | 1 | 240 | 4 | #N/A | PLIER BENDING
CV04-010 |  | - | P07-08 |  | 0 | CV04-010-P07-08 |  |  | ST | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CV04-011 |  | - | P01-04 |  | 0 | CV04-011-P01-04 |  |  | FM | 1 | 1200 | 20 | FM | FM02 | FM02 | FM01
CV04-011 |  | - | P02-04 |  | 0 | CV04-011-P02-04 |  |  | FM | 1 | 360 | 6 | ST-1 | PP11-035T | PP11 | PP27 | PP03
CV04-012 |  | - | P01-04 |  | 0 | CV04-012-P01-04 |  |  | FM | 1 | 1200 | 20 | FM | FM01 | FM02 | FM01
CV04-012 |  | - | P02-04 |  | 0 | CV04-012-P02-04 |  |  | FM | 1 | 360 | 6 | ST-2 | PP06-040T | PP06 | PP05 | PP11
CV04-013 |  | - | P01-07 |  | 0 | CV04-013-P01-07 |  |  | ST | 1 | 360 | 6 | ST-2 | PP04-060T | PP04 | PP05 | PP13 | PP22
CV04-013 |  | - | P02-07 |  | 0 | CV04-013-P02-07 |  |  | ST | 1 | 180 | 3 | ST-1 | PP22-060T | PP04 | PP05 | PP13 | PP22 | [5 empty] | SAME DIE V CV04-010-P02
CV04-013 |  | - | P03-07 |  | 0 | CV04-013-P03-07 |  |  | ST | 1 | 240 | 4 | ST-1 | PP13-060T | PP13 | PP06 | [7 empty] | SAME DIE V CV04-010-P03
CV04-013 |  | - | P04-07 |  | 0 | CV04-013-P04-07 |  |  | ST | 1 | 180 | 3 | ST-2 | PP06-040T | PP06
CV04-013 |  | - | P05-07 |  | 0 | CV04-013-P05-07 |  |  | ST | 1 | 360 | 6 | #N/A | JIG | JIG
CV04-013 |  | - | P06-07 |  | 0 | CV04-013-P06-07 |  |  | ST | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CV04-014 |  | - | P01-04 |  | 0 | CV04-014-P01-04 |  |  | ST | 1 | 360 | 6 | ST-1 | PP05-060T | PP05
CV04-014 |  | - | P02-04 |  | 0 | CV04-014-P02-04 |  |  | ST | 1 | 360 | 6 | ST-2 | PP06-040T | PP06
CV04-015 |  | - | P01-05 |  | 0 | CV04-015-P01-05 |  |  | ST | 1 | 360 | 6 | ST-1 | PP10-080T | PP10
CV04-015 |  | - | P02-05 |  | 0 | CV04-015-P02-05 |  |  | ST | 1 | 360 | 6 | ST-1 | PP03-060T | PP03 | PP04
CV04-015 |  | - | P03-05 |  | 0 | CV04-015-P03-05 |  |  | ST | 1 | 360 | 6 | ST-1 | PP03-060T | PP03 | PP04
CV04-015 |  | - | P04-05 |  | 0 | CV04-015-P04-05 |  |  | ST | 1 | 5 DAYS | 5 DAYS | SUB CON | SUB CON | SUB CON
CV04-015 |  | - | P05-05 |  | 0 | CV04-015-P05-05 |  |  | ST | 1 | STORE | STORE | #N/A | #N/A
CV04-019 |  | - | P01-01 |  | 0 | CV04-019-P01-01 |  |  | FM | 1 | 1800 | 30 | FM | FM01 | FM04
CV06-001 |  | - | P01-03 |  | 0 | CV06-001-P01-03 |  |  | FM | 1 | 1200 | 20 | FM | FM03 | FM03
CA06-024 |  | - | P01-06 |  | 0 | CA06-024-P01-06 |  |  | ST | 1 | 240 | 4 | WN | SM01 | SM01 | [8 empty] | SAMPLE 3P620326-29/12/21
CA06-024 |  | - | P02-06 |  | 0 | CA06-024-P02-06 |  |  | ST | 1 | 720 | 12 | WN | PP02-060T | PP02
CA06-024 |  | - | P03-06 |  | 0 | CA06-024-P03-06 |  |  | AL | 1 | 600 | 10 | WN | TP06 | TP06
CA29-002 |  | - | P01-02 |  | 0 | CA29-002-P01-02 |  |  | ST | 1 | 480 | 8 | ST | PP07 | PP07
CA29-002 |  | - | P02-02 |  | 0 | CA29-002-P02-02 |  |  | ST | 1 | 120 | 2 | ST | PP21 | PP21 | [8 empty] | A,B.C - A(BENDING)
CA29-003 |  | - | P01-02 |  | 0 | CA29-003-P01-02 |  |  | ST | 1 | 480 | 8 | ST | PP07 | PP07 | [8 empty] | WIRE NET SAMPLE - 14/2/22
CA29-003 |  | - | P02-02 |  | 0 | CA29-003-P02-02 |  |  | ST | 1 | 120 | 2 | ST | PP21 | PP21
CP08-223 |  |  | P01-05 |  |  | CP08-223-P01-05 |  |  | TR | 2 | 240 | 4 | TR | SM01 | SM01
CP08-223 |  |  | P02-05 |  |  | CP08-223-P02-05 |  |  | TR | 1 | 60 | 1 | TR | TM06 | TM06 | TM03 | TM05
CP08-223 |  |  | P03-05 |  |  | CP08-223-P03-05 |  |  | TR | 1 | 150 | 2.5 | TR | PB03 | PB03
CP08-223 |  |  | P04-05 |  |  | CP08-223-P04-05 |  |  | TR | 1 | 120 | 2 | TR | PB04 | PB04
CP08-553 |  |  | P01-07 |  |  | CP08-553-P01-07 |  |  | TR | 1 | 60 | 1 | TR | SW14 | SW14 | SW09
CP08-553 |  |  | P02-07 |  |  | CP08-553-P02-07 |  |  | TR | 1 | 60 | 1 | TR | SW14 | SW14 | SW09
CP08-553 |  |  | P03-07 |  |  | CP08-553-P03-07 |  |  | TR | 1 | 60 | 1 | TR | SW14 | SW14 | SW09
CP08-553 |  |  | P04-07 |  |  | CP08-553-P04-07 |  |  | TR | 2 | 12 | 0.2 | TR | SW14 | SW14 | SW09
CP08-553 |  |  | P05-07 |  |  | CP08-553-P05-07 |  |  | TR | 2 | 12 | 0.2 | TR | PAINTING
CP08-553 |  |  | P06-07 |  |  | CP08-553-P06-07 |  |  | TR | 1 | 12 | 0.2 | TR | PACK & LABEL
CP08-552 |  |  | P01-07 |  |  | CP08-552-P01-07 |  |  | TR | 1 | 60 | 1 | TR | SW14 | SW14 | SW09 | [8 empty] | CAPACITY - PER HOUR - 7 PCS
CP08-552 |  |  | P02-07 |  |  | CP08-552-P02-07 |  |  | TR | 1 | 60 | 1 | TR | SW14 | SW14 | SW09
CP08-552 |  |  | P03-07 |  |  | CP08-552-P03-07 |  |  | TR | 1 | 60 | 1 | TR | SW14 | SW14 | SW09
CP08-552 |  |  | P04-07 |  |  | CP08-552-P04-07 |  |  | TR | 2 | 12 | 0.2 | TR | SW14 | SW14 | SW09
CP08-552 |  |  | P05-07 |  |  | CP08-552-P05-07 |  |  | TR | 2 | 12 | 0.2 | TR | PAINTING
CP08-552 |  |  | P06-07 |  |  | CP08-552-P06-07 |  |  | TR | 1 | 12 | 0.2 | TR | PACK & LABEL
CP08-553E |  |  | P01-03 |  |  | CP08-553E-P01-03 |  |  | TR | 1 | 200 | 3.3333 | TR | TM06 | TM05 | TM03 | TM06 | [6 empty] | SAME TOOLING WITH CP08-553D
CP08-553E |  |  | P02-03 |  |  | CP08-553E-P02-03 |  |  | TR | 1 | 240 | 4 | TR | PB01 | PB01 | PB04
CP08-553D |  |  | P01-03 |  |  | CP08-553D-P01-03 |  |  | TR | 1 | 100 | 1.6667 | TR | TM06 | TM03 | TM05 | TM06 | [6 empty] | SAME TOOLING WITH CP08-553E
CP08-553D |  |  | P02-03 |  |  | CP08-553D-P02-03 |  |  | TR | 1 | 240 | 4 | TR | PB01 | PB01 | PB04
CP08-552A,CP08-553A |  |  | P01-04 |  |  | CP08-552A-P01-04 |  |  | TR | 1 | 120 | 2 | TR | TM06 | TM03 | TM05 | TM06 | [6 empty] | SAME TOOLING V CP08-552D,CP08-554A
CP08-552A,CP08-553A | GC02-036 |  | P02-04 |  |  | CP08-552A-P02-04 |  |  | TR | 1 | 30 | 0.5 | TR | RL1 | RL1 | [8 empty] | PROCESS-P02-04 &P03-04 RUN ONE PIECE FLOW
CP08-552A,CP08-553A | GC02-036 |  | P03-04 |  |  | CP08-552A-P03-04 |  |  | TR | 1 | 30 | 0.5 | TR | PB02 | PB02
CP08-552B,CP08-554B | GC02-036 |  | P01-04 |  |  | CP08-552B-P01-04 |  |  | ST | 1 | 240 | 4 | ST | PP30-200T | PP30 | PP29 | PP33 | [6 empty] | MUST TOGETHER RUN V CP08-552C
CP08-552B,CP08-554B | GC02-037 |  | P02-04 |  |  | CP08-552B-P02-04 |  |  | ST | 1 | 120 | 2 | ST | PP29 | PP29 | PP30 | [7 empty] | MUST TOGETHER RUN V CP08-552C | SAME DIE WITH CP08-552B,CP08-552C,P08-554C,TOGETHER RUN
CP08-552B,CP08-554B | GC02-037 |  | P03-04 |  |  | CP08-552B-P03-04 |  |  | ST | 1 | 240 | 4 | ST | PP21 | PP27 | PP21 | PP28 | [6 empty] | MUST TOGETHER RUN V CP08-552C
CP08-552C | GC02-037 |  | P01-04 |  |  | CP08-552C-P01-04 |  |  | ST | 1 | 240 | 4 | ST | PP30-200T | PP30 | PP33 | [7 empty] | MUST TOGETHER RUN V CP08-552B | SAME DIE WITH CP08-552B,CP08-552C,P08-554C,TOGETHER RUN
CP08-552C | GC02-038 |  | P02-04 |  |  | CP08-552C-P02-04 |  |  | ST | 1 | 120 | 2 | ST | PP29 | PP29 | PP29 | PP30 | [6 empty] | MUST TOGETHER RUN V CP08-552B | TOGETHER RUN WITH CP08-552B 1 DIE ONLY
CP08-552C | GC02-038 |  | P03-04 |  |  | CP08-552C-P03-04 |  |  | ST | 1 | 240 | 4 | ST | PP21 | PP27 | PP21 | [7 empty] | MUST TOGETHER RUN V CP08-552B
CP08-552D,CP08-554D | GC02-038 |  | P01-03 |  |  | CP08-552D-P01-03 |  |  | TR | 1 | 220 | 3.6667 | TR | TM06 | TM05 | TM03 | TM06 | [6 empty] | SAME TOOLING V CP08-552A,CP08-554A
CP08-552D,CP08-554D | GC02-039 |  | P02-03 |  |  | CP08-552D-P02-03 |  |  | TR | 1 | 240 | 4 | TR | PB01 | PB01 | PB04 | PB05
CP20-002D,CD11-027D | GC02-039 |  | P01-02 |  |  | CD11-027D-P01-02 |  |  | ST | 1 | 240 | 4 | ST | PP05-060T | PP06 | PP15 | PP05 | PP02 | PP11
CP20-002A,CD11-027A |  |  | P01-02 |  |  | CD11-027A-P01-02 |  |  | FM | 1 | 1200 | 20 | FM | FM03 | FM03 | FM01 | [7 empty] | Almost same die with Cam Die with CM18-001B
CP20-002,CD11-027 |  |  | P01-06 |  |  | CD11-027-P01-06 |  |  | WN | 3 | 120 | 2 | WN | SW08 | SW08-120PCS/HRS
CP20-002,CD11-027 |  |  | P02-06 |  |  | CD11-027-P02-06 |  |  | WN | 1 | 300 | 5 | WN | PP23-060T | PP23 | PP12
CP20-002,CD11-027 |  |  | P05-06 |  |  | CD11-027-P05-06 |  |  | WN | 1 | 400 | 6.6667 | WN | TW01 | TW01 | TW02 | TW03
CM03-036 |  |  | P01-05 |  |  | CM03-036-P01-05 |  |  | TR | 1 | 132 | 2.2 | TR | TM03 | TM03 | TM05 | TM06
CM03-036 |  |  | P02-05 |  |  | CM03-036-P02-05 |  |  | TR | 1 | 66 | 1.1 | TR | OPT | OPT
CM03-036 |  |  | P03-05 |  |  | CM03-036-P03-05 |  |  | TR | 1 | 360 | 6 | TR | OPT | OPT
CM03-036 |  |  | P04-05 |  |  | CM03-036-P04-05 |  |  | TR | 1 | 200 | 3.3333 | TR | PB05 | PB04 | PB05 | PB01 | PB08
CP08-555 |  |  | P01-04 |  |  | CP08-555-P01-04 |  |  | ST | 1 | 240 | 4 | TR | PP17-110T | PP17 | PP21 | PP21 | PP16 | PP17 | PP17 | PP18
CP08-555 |  |  | P02-04 |  |  | CP08-555-P02-04 |  |  | ST | 1 | 240 | 4 | ST | PP16-110T | PP16 | PP18 | PP18 | PP17 | PP16 | PP21 | PP16
CP08-555 |  |  | P03-04 |  |  | CP08-555-P03-04 |  |  | ST | 1 | 240 | 4 | ST | PP27-110T | PP27 | PP28 | PP09 | PP18 | PP27 | PP18 | PP27
CP08-118 |  |  | P01-04 |  |  | CP08-118-P01-04 |  |  | ST | 1 | 240 | 4 | ST | SM01 | SM01
CP08-118 |  |  | P02-04 |  |  | CP08-118-P02-04 |  |  | ST | 1 | 240 | 4 | ST | PP14-080T | PP14
CP08-118 |  |  | P03-04 |  |  | CP08-118-P03-04 |  |  | ST | 1 | 240 | 4 | ST | PP14-080T | PP14
CO02-018 |  |  | P01-04 |  |  | CO02-018-P01-04 |  |  | ST | 1 | 240 | 4 | ST | SM01 | SM01
CO02-018 |  |  | P02-04 |  |  | CO02-018-P02-04 |  |  | ST | 1 | 360 | 6 | ST | PP05-060T | PP10 | PP05
Share die v CM06-007
CM06-011 |  |  | P01-04 |  |  | CM06-011-P01-04 |  |  | ST | 1 | 2100 | 35 | ST | PP02 | PP02 | PP19 | PP12 | PP14
CP08-550 |  |  | P01-02 |  |  | CP08-550-P01-02 |  |  | ST | 1 | 1200 | 20 | ST | PP30-200T | PP30
CP08-549A |  |  | P01-03 |  |  | CP08-549A-P01-03 |  |  | ST | 1 | 240 | 4 | ST | PP30-200T | PP29 | PP30
CP08-549A |  |  | P02-03 |  |  | CP08-549A-P02-03 |  |  | ST | 1 | 240 | 4 | ST | PP29 | PP30 | PP29
CP08-549 |  |  | P01-02 |  |  | CP08-549-P01-02 |  |  | ST | 1 | 120 | 2 | ST | PP21 | PP21
CP08-551 |  |  | P01-05 |  |  | CP08-551-P01-05 |  |  | ST | 1 | 360 | 6 | ST | PP24-160T | PP24 | PP25
CP08-551 |  |  | P02-05 |  |  | CP08-551-P02-05 |  |  | ST | 1 | 360 | 6 | ST | PP25-160T | PP25 | PP26
CP08-551 |  |  | P03-05 |  |  | CP08-551-P03-05 |  |  | ST | 1 | 360 | 6 | ST | PP26 | PP26 | PP20 | [7 empty] | ASSEMBLY - PER DAY WELDING ABOUT 2.5 PCS
CP08-551 |  |  | P04-05 |  |  | CP08-551-P04-05 |  |  | ST | 1 | 360 | 6 | ST | PP20-110T | PP20 | PP28
CM14-002 |  |  | P01-03 |  |  | CM14-002-P01-03 |  |  | ST | 1 | 240 | 4 | ST | SM01 | SM01
CM14-002 |  |  | P02-03 |  |  | CM14-002-P02-03 |  |  | ST | 1 | 480 | 8 | ST | PP11-035T | PP11
CU01-024 |  |  | P01-03 |  |  | CU01-024-P01-03 |  |  | ST | 1 | 240 | 4 | ST | PP06-040T | PP06 | PP11 | PP05
CU01-024 |  |  | P02-03 |  |  | CU01-024-P02-03 |  |  | SUB-CON
CP08-189A |  |  | P01-09 |  |  | CP08-189A-P01-09 |  | TURRET PUNCH | TP | 1 | 15 | 0.25 | TP | TM06 | TM03 | TM05 | TM06
CP08-189A |  |  | P02-09 |  |  | CP08-189A-P02-09 |  | BENDING | TP | 1 | 60 | 1 | TP | PB03 | PB03
CP08-189A |  |  | P03-09 |  |  | CP08-189A-P03-09 |  | BENDING | TP | 1 | 120 | 2 | TP | PB03
CP08-189A |  |  | P04-09 |  |  | CP08-189A-P04-09 |  | BENDING | TP | 1 | 108 | 1.8 | TP | PB04 | PB04 | PB01
CP08-189A |  |  | P05-09 |  | 0 | CP08-189A-P05-09 |  | BENDING | TP | 1 | 108 | 1.8 | TP | PB03 | PB04 | PB01
CP08-189A |  |  | P06-09 |  | 0 | CP08-189A-P06-09 |  | BENDING | TP | 1 | 108 | 1.8 | TP | PB04
CP08-189A |  |  | P07-09 |  | 0 | CP08-189A-P07-09 |  | BENDING | TP | 1 | 120 | 2 | TP | SW09 | SW09 | SW01
CP08-189A |  |  | P08-09 |  | 0 | CP08-189A-P08-09 |  | SPOT WELD | TP | 1 | 12 | 0.2 | TP | SW09 | SW09 | SW01
CP08-189B |  |  | P02-05 |  | 0 | CP08-189B-P02-05 |  | TURRET PUNCH | TP | 1 | 120 | 2 | TP | TM06 | TM03 | TM05 | TM06
CP08-189B |  |  | P03-05 |  | 0 | CP08-189B-P03-05 |  | BENDING | TP | 1 | 180 | 3 | TP | PB02 | PB02 | PB03
CP08-189B |  |  | P04-05 |  | 0 | CP08-189B-P04-05 |  | BENDING | TP | 1 | 120 | 2 | TP | PB03 | PB03
CP08-189 |  |  | P01-02 |  | 0 | CP08-189-P01-02 |  | SPOT WELD | TP | 1 | 60 | 1 | TP | SW09 | SW09 | SW01
CP08-190A |  |  | P02-04 |  | 0 | CP08-190A-P02-04 |  | TURRET PUNCH | TP | 1 | 120 | 2 | TP | TM06 | TM03 | TM05 | TM06
CP08-190A |  |  | P03-04 |  | 0 | CP08-190A-P03-04 |  | BENDING | TP | 1 | 120 | 2 | TP | PB04 | PB04 | PB07
CP08-190B |  |  | P01-03 |  | 0 | CP08-190B-P01-03 |  | TURRET PUNCH | TP | 1 | 120 | 2 | TP | TM06 | TM03 | TM05 | TM06
CP08-190B |  |  | P02-03 |  | 0 | CP08-190B-P02-03 |  | BENDING | TP | 1 | 120 | 2 | TP | PB01 | PB04 | PB07 | PB05 | PB01
CP08-190C |  |  | P02-09 |  | 0 | CP08-190C-P02-09 |  | TURRET PUNCH | TP | 1 | 15 | 0.25 | TP | TM06,TM02 | TM06,TM02 | TM05 | TM03
CP08-190C |  |  | P03-09 |  | 0 | CP08-190C-P03-09 |  | BENDING | TP | 1 | 120 | 2 | TP | PB03 | PB03 | PB08
CP08-190C |  |  | P04-09 |  | 0 | CP08-190C-P04-09 |  | BENDING | TP | 1 | 120 | 2 | TP | PB03 | PB03 | PB08
CP08-190C |  |  | P05-09 |  | 0 | CP08-190C-P05-09 |  | BENDING | TP | 1 | 120 | 2 | TP | PB04 | PB04
CP08-190C |  |  | P06-09 |  | 0 | CP08-190C-P06-09 |  | BENDING | TP | 1 | 60 | 1 | TP | PB01 | PB01
CP08-190C |  |  | P07-09 |  | 0 | CP08-190C-P07-09 |  | SPOT WELD | TP | 1 | 60 | 1 | TP | SW09 | SW01 | SW09
CP08-190 |  |  | P01-02 |  | 0 | CP08-190-P01-02 |  | SPOT WELD | TP | 1 | 20 | 0.33333 | TP | SW09 | SW01 | SW09
CK13-002 |  |  | P01-04 |  | 0 | CK13-002-P01-04 |  | SLITING | ST | 1 | 240 | 4 | ST-1 | SM01 | SM01 | [8 empty] | SLIT 2 TIMES
CK13-002 |  |  | P02-04 |  | 0 | CK13-002-P02-04 |  | PIERCING | ST | 1 | 240 | 4 | ST-1 | PP10-080T | PP31 | PP10
CP08-075 |  |  | P01-04 |  | 0 | CP08-075-P01-04 |  | SLITING | ST | 1 | 240 | 4 | ST-1 | SM01 | SM01
CP08-075 |  |  | P02-04 |  | 0 | CP08-075-P02-04 |  | BLANKING | ST | 1 | 360 | 6 | ST-1 | PP18 | PP16 | PP17
CP08-194 |  |  | P01-04 |  | 0 | CP08-194-P01-04 |  | SLITING | TR | 1 | 18 | 0.3 | TR | SM01 | SM01
CP08-194 |  |  | P02-04 |  | 0 | CP08-194-P02-04 |  | TURRET PUNCH | TR | 1 | 45 | 0.75 | TR | TM05 | TM03 | TM05 | TM06
CP08-194 |  |  | P03-04 |  | 0 | CP08-194-P03-04 |  | BENDING | TR | 1 | 120 | 2 | TR | PB03 | PB07
CP08-189B |  |  | P01-05 |  | 0 | CP08-189B-P01-05 |  | SLITING | TR | 1 | 240 | 4 | TR | SM01 | SM01
CP08-190A |  |  | P01-04 |  | 0 | CP08-190A-P01-04 |  | SLITING | TR | 1 | 240 | 4 | TR | SM01 | SM01
CP08-075 |  |  | P03-04 |  | 0 | CP08-075-P03-04 |  | TAPPING | ST | 1 | 300 | 5 | ST | TP03 | TP07 | TP09
CA14-014 |  |  | P01-03 |  | 0 | CA14-014-P01-03 |  | PROGRESSIVE | ST | 1 | 1200 | 20 | ST | PP01-110T | PP01
CA14-014 |  |  | P02-03 |  | 0 | CA14-014-P02-03 |  | DEGREASING | ST | 1 | 1000 | 16.6667 | ST | VM04 | VM04 | VM01
CP08-554A |  |  | P01-04 |  | 0 | CP08-554A-P01-04 |  | TURRET PUNCH | TR | 1 | 60 | 1 | TR | TM05 | TM06 | TM05 | TM03 | [6 empty] | SAME TOOLING V CP08-552A,CP08-554A
CP08-554A |  |  | P02-04 |  | 0 | CP08-554A-P02-04 |  | ROLLING | TR | 1 | 20 | 0.33333 | TR | 1
CP08-554A |  |  | P03-04 |  | 0 | CP08-554A-P03-04 |  | BENDING | TR | 1 | 30 | 0.5 | TR | PB02 | PB02 | PB03
CP08-554C |  |  | P01-04 |  | 0 | CP08-554C-P01-04 |  | BLANKING | ST | 1 | 360 | 6 | ST | PP29 | PP29 | PP30 | PP33
CP08-554C |  |  | P02-04 |  | 0 | CP08-554C-P02-04 |  | BENDING | ST | 1 | 360 | 6 | ST | PP30-200T | PP30 | PP29 | [8 empty] | SAME DIE WITH CP08-554C,TOGETHER RUN
CP08-554C |  |  | P03-04 |  | 0 | CP08-554C-P03-04 |  | BENDING | ST | 1 | 240 | 4 | ST | PP21 | PP27 | PP21
CP08-554 |  |  | P01-06 |  | 0 | CP08-554-P01-06 |  | SPOT WELD | TR | 1 | 93 | 1.55 | TR | SW14 | SW09 | SW14
CP08-554 |  |  | P02-06 |  | 0 | CP08-554-P02-06 |  | SPOT WELD | TR | 1 | 129 | 2.15 | TR | SW14 | SW09 | SW14
CP08-554 |  |  | P03-06 |  | 0 | CP08-554-P03-06 |  | SPOT WELD | TR | 2 | 12 | 0.2 | TR | SW14 | SW09 | SW14
CP08-554 |  |  | P04-06 |  | 0 | CP08-554-P04-06 |  | PAINTING | TR | 2 | 12 | 0.2 | TR | PAINTING | PAINTING
CP08-554 |  |  | P05-06 |  | 0 | CP08-554-P05-06 |  | PACK AND LABEL | TR | 1 | 12 | 0.2 | TR | PACK & LABEL | PACK & LABEL
CA14-015 |  |  | P01-03 |  | 0 | CA14-015-P01-03 |  | FORMING | FM | 1 | 3000 | 50 | FM | FM01 | FM01 | FM02
CA14-015 |  |  | P02-03 |  | 0 | CA14-015-P02-03 |  | SUB CON | SUB-CON |  |  |  |  | SUB CON | SUB CON
CU01-014 |  |  | P01-07 |  | 0 | CU01-014-P01-07 |  | CAM | AL | 1 | 240 | 4 | CM05 | CM05 | CM03
CU01-014 |  |  | P02-07 |  | 0 | CU01-014-P02-07 |  | DEBURR | AL | 1 | 360 | 6 | BDS01 | BDS01 | BDS01
CU01-014 |  |  | P03-07 |  | 0 | CU01-014-P03-07 |  | DRILL | AL | 1 | 60 | 1 | M04 | M04
CU01-014 |  |  | P04-07 |  | 0 | CU01-014-P04-07 |  | CHAMFER | AL | 1 | 360 | 6 | TP02 | TP02
CU01-014 |  |  | P05-07 |  | 0 | CU01-014-P05-07 |  | STAMPING | ST | 1 | 240 | 4 | PP15 | PP15-080T | PP02 | PP15 | PP06
CU01-014 |  |  | P06-07 |  | 0 | CU01-014-P06-07 |  | SUB CON | SUB-CON
CA24-009 |  |  | P01-03 |  | 0 | CA24-009-P01-03 |  | BLANKING | ST | 1 | 480 | 8 | ST | PP14 | PP02 | PP01 | PP19 | PP14 | [5 empty] | SAME DIE WITH CA24-009,CA24-006-P01-03,CA24-007
CA24-009 |  |  | P02-03 |  | 0 | CA24-009-P02-03 |  | BENDING | ST | 1 | 180 | 3 | ST | PP12 | PP02 | PP01 | PP21 | PP12 | [5 empty] | SAME DIE WITH CA24-009,CA24-006-P02-03,CA24-007,CA24-008,CL02-008
CC09-002 |  |  | P01-04 |  | 0 | CC09-002-P01-04 |  | SLITING | ST | 1 | 240 | 4 | ST | SM01 | SM01
CP08-442 |  |  | P03-04 |  | 0 | CP08-442-P03-04 |  | BENDING | TR | 1 | 180 | 3 | TR | PB04 | PB04
CV02-027 |  |  | P01-02 |  | 0 | CV02-027-P01-02 |  | BLANKING | ST | 1 | 480 | 8 | ST | PP11-035T
CV02-027 |  |  | P02-02 |  | 0 | CV02-027-P02-02 |  | SUB CON - INDUSTRES | SUB-CON
CM03-039 |  |  | P01-03 |  | 0 | CM03-039-P01-03 |  | PROGRESSIVE | ST | 1 | 1800 | 30 | DT | PP19-110T | PP19 | PP32 | [7 empty] | SHARE DIE V CM03-026,CM03-027
CM03-039 |  |  | P02-03 |  | 0 | CM03-039-P02-03 |  | TUMBLING | ST | 1 | 2000 | 33.3333 | ST | VM01 | VM01 | VM04
CE03-034 |  |  | P01-04 |  | 0 | CE03-034-P01-04 |  | BLANKING | ST | 1 | 480 | 8 | ST | PP03-060T | PP03
CE03-034 |  |  | P02-04 |  | 0 | CE03-034-P02-04 |  | BENDING | ST | 1 | 240 | 4 | ST | PP05-060T | PP05
CE03-034 |  |  | P03-04 |  | 0 | CE03-034-P03-04 |  | TAPPING | AL | 1 | 108 | 1.8 | AL | TP06 | TP06
CB11-003 |  |  | P01-04 |  | 0 | CB11-003-P01-04 |  | SLITING | ST | 1 | 8640 | 144 | ST | SM01 | SM01
CB11-003 |  |  | P02-04 |  | 0 | CB11-003-P02-04 |  | BLANKING | ST | 1 | 480 | 8 | ST | PP22-060T | PP22 | PP10
CB11-003 |  |  | P03-04 |  | 0 | CB11-003-P03-04 |  | BENDING | ST | 1 | 240 | 4 | ST | PP22-060T | PP22 | PP15
CP08-563A |  |  | P01-03 |  | 0 | CP08-563A-P01-03 |  | TURRET PUNCH | TR | 1 | 60 | 1 | TR | TM05 | TM05 | TM03 | TM06
CP08-563A |  |  | P02-03 |  | 0 | CP08-563A-P02-03 |  | BENDING | PB | 1 | 90 | 1.5 | PB | PB08 | PB08 | PB04 | PB02
CP08-563 |  |  | P01-04 |  | 0 | CP08-563-P01-04 |  | SPOT WELD | PB | 1 | 120 | 2 | PB | SW09 | SW09 | SW14 | SW04
CP08-563 |  |  | P02-04 |  | 0 | CP08-563-P02-04 |  | PAINTING | PB | 1 | 36 | 0.6 | PB | OPT | OPT
CP02-003 |  |  | P01-04 |  | 0 | CP02-003-P01-04 |  | FORMING | FM | 1 | 3600 | 60 | FM02 | FM02 | FM01
CP02-003 |  |  | P02-04 |  | 0 | CP02-003-P02-04 |  | SUB CON | SC
CP02-003 |  |  | P03-04 |  | 0 | CP02-003-P03-04 |  | SUB CON | SC
CP08-562A |  |  | P01-03 |  | 0 | CP08-562A-P01-03 |  | TURRET PUNCH | TR | 1 | 40 | 0.66667 | TR | TM03 | TM03 | [8 empty] | TM03,NEED TAPPING PROCESS
CP08-562A |  |  | P02-03 |  | 0 | CP08-562A-P02-03 |  | BENDING | PB | 1 | 120 | 2 | PB | PB05 | PB05 | PB01 | PB07
CP08-562B |  |  | P01-03 |  | 0 | CP08-562B-P01-03 |  | TURRET PUNCH | TR | 1 | 60 | 1 | TR | TM03
CP08-562B |  |  | P02-03 |  | 0 | CP08-562B-P02-03 |  | BENDING | PB | 1 | 100 | 1.6667 | PB | PB04 | PB07 | PB05
CP08-562C |  |  | P01-05 |  | 0 | CP08-562C-P01-05 |  | TURRET PUNCH | TR | 1 | 44 | 0.73333 | TR | TM03 | TM03 | [8 empty] | TURRET PUNCH, NEED TAPPING PROCESS
CP08-562C |  |  | P02-05 |  | 0 | CP08-562C-P02-05 |  | BENDING 1 ~ 4 | PB | 1 | 120 | 2 | PB | PB04 | PB08 | PB02 | PB03 |  | PB08
CP08-562C |  |  | P03-05 |  | 0 | CP08-562C-P03-05 |  | BENDING 5 & 6 | PB | 1 | 90 | 1.5 | PB | PB08 | PB03 | PB04 |  |  | PB04 |  |  |  |  | 3(a),3(b) PB08, PB04/PB01
CP08-562C |  |  | P04-05 |  | 0 | CP08-562C-P04-05 |  | BENDING 7 & 8 | PB | 1 | 120 | 2 | PB | PB04 | PB04 | PB07 | PB01 | PB02 | PB04
CP08-562D |  |  | P01-03 |  | 0 | CP08-562D-P01-03 |  | TURRET PUNCH | TR | 1 | 35 | 0.58333 | TR | TM03 | [9 empty] | NEED PROCESS TAPPING: TP03
CP08-562D |  |  | P02-03 |  | 0 | CP08-562D-P02-03 |  | BENDING | PB | 1 | 100 | 1.6667 | PB | PB07 | PB01 | PB05
CP08-562 |  |  | P01-05 |  | 0 | CP08-562-P01-05 |  | SW | PB | 1 | 120 | 2 | PB | SW14 | SW14 | SW09
CP08-562 |  |  | P02-05 |  | 0 | CP08-562-P02-05 |  | SW | PB | 2 | 17 | 0.28333 | PB | SW14 | SW14 | SW09
CP08-562 |  |  | P03-05 |  | 0 | CP08-562-P03-05 |  | PAINTING | PB | 2 | 50 | 0.83333 | OPT | OPT
CP08-562 |  |  | P04-05 |  | 0 | CP08-562-P04-05 |  | OPT | PB | 1 | 60 | 1 | OPT | OPT
CP08-560 |  |  | P01-04 |  | 0 | CP08-560-P01-04 |  | BLANKING | ST | 1 | 360 | 6 | ST | PP09 | PP09 | PP24 | PP24
CP08-560 |  |  | P02-04 |  | 0 | CP08-560-P02-04 |  | BENDING | ST | 1 | 300 | 5 | ST | PP18 | PP18 | PP25 | PP26
CP08-560 |  |  | P03-04 |  | 0 | CP08-560-P03-04 |  | BENDING | ST | 1 | 300 | 5 | ST | PP27-110T | PP27 | PP26 | PP28
CP08-561 |  |  | P01-04 |  | 0 | CP08-561-P01-04 |  | PROGRESSIVE | ST | 1 | 360 | 6 | ST | PP25-160T | PP24 | PP25 | PP20
CP08-561 |  |  | P02-04 |  | 0 | CP08-561-P02-04 |  | BENDING | ST | 1 | 300 | 5 | ST | PP26 | PP26 | PP26
CP08-561 |  |  | P03-04 |  | 0 | CP08-561-P03-04 |  | BENDING | ST | 1 | 300 | 5 | ST | PP20-110T | PP28 | PP28
CA06-002/CC06-002 |  |  | P01-05 |  | 0 | CC06-002-P01-05 |  | SLITING | ST | 1 | 43560 | 726 | ST | SM01 | SM01
CA06-002/CC06-002 |  |  | P02-05 |  | 0 | CC06-002-P02-05 |  | PROGRESSIVE | ST | 1 | 480 | 8 | ST | PP11-035T | PP11 | PP02
CA06-002/CC06-002 |  |  | P03-05 |  | 0 | CC06-002-P03-05 |  | EMBOSS | ST | 1 | 300 | 5 | ST | PP22-060T | PP22 | PP05 | PP13 | PP03 | PP04
CA06-002/CC06-002 |  |  | P04-05 |  | 0 | CC06-002-P04-05 |  | TAPPING | ST | 1 | 420 | 7 | AL | TP02 | TP02
CU01-049 |  |  | P01-02 |  | 0 | CU01-049-P01-02 |  | BENDING | PB | 1 | 180 | 3 | PB | PB04 | PB04
CP08-565 |  | - | P01-04 |  | 0 | CP08-565-P01-04 |  | TURRET PUNCH | TR | 1 | 80 | 1.3333 | TR | TM05 | TM03 | TM05 | TM06 | [6 empty] | ONLY CAN RUN TM03,GOT TAPPING PROCESS
CP08-565 |  | - | P02-04 |  | 0 | CP08-565-P02-04 |  | BENDING | PB | 1 | 120 | 2 | PB | PB03 | PB03 | PB02 | PB08 | PB01 | PB02 |  |  |  |  | EFF 010422 NO MORE PROCESS SM1
CP08-565 |  |  | P03-04 |  |  | CP08-565-P03-04 |  | BENDING | PB | 1 | 90 | 1.5 | PB | PB01 | PB04 | PB05 | PB01 | PB07 | PB01
CP08-564 |  | - | P01-07 | ver.03 | 0 |  |  | TURRET PUNCH | TR | 1 | 80 | 1.3333 | TR | TM03
CP08-564 |  | - | P02-07 |  | 0 |  |  | DRAWING,Z BENDING | ST | 1 | 90 | 1.5 | ST | PB02 | PB02 | PB03 | [7 empty] | EFF-180522-NO MORE SLIT PROCESS -W1219-L1100
CP08-564 |  | - | P03-07 |  | 0 |  |  | BURRING | ST | 1 | 120 | 2 | ST | PB03 | PB03 | PB02 | [7 empty] | EFF-310522
CP08-564 |  | - | P04-07 |  | 0 |  |  | BENDING HEMMING | PB | 1 | 120 | 2 | PB | PB03 | PB03 | PB02 | [7 empty] | RUN PB2,PB3,PB1,PB4 - 190922, IF RUN PB1 NO NEED RUN PROCESS PB4
CP08-564 |  | - | P05-07 |  | 0 |  |  | 3 - BENDING | PB | 1 | 72 | 1.2 | PB | PB01 | PB01 | PB07 | PB04
CP08-564 |  | - | P06-07 |  | 0 |  |  | 2 - BENDING | PB | 1 | 90 | 1.5 | PB | PB01 | PB01 | PB07 | PB04
CP08-558 |  | - | P01-02 |  | 0 | CP08-558-P01-02 |  | PROGRESSIVE | ST | 1 | 1500 | 25 | ST | PP30-200T | PP30
CA16-011B |  | - | P01-03 |  | 0 | CA16-011B-P01-03 |  | PROGRESSIVE | ST | 1 | 3000 | 50 | ST | PP19-110T | PP19 | PP12
CA16-011B |  | - | P02-03 |  | 0 | CA16-011B-P02-03 |  | DEGREASING | ST | 1 | 1000 | 16.6667 | ST | VM01 | VM01 | VM04
CA16-011 |  | - | P01-03 |  | 0 | CA16-011-P01-03 |  | SPOT WELD | FM | 1 | 450 | 7.5 | FM | SW05 | SW05 | SW15
CA16-011 |  | - | P02-03 |  | 0 | CA16-011-P02-03 |  | CHECKING | FM | 1 | 900 | 15 | FM | OPT
CP08-559 |  | - | P01-02 |  | 0 | CP08-559-P01-02 |  | PROGRESSIVE | ST | 1 | 1680 | 28 | ST | PP32 | PP32
CP08-190C |  | - | P01-09 |  | 0 | CP08-190C-P01-09 |  | SLITING | ST | 1 | 240 | 4 | ST | SM01 | SM01
CP08-190C |  | - | P08-09 |  | 0 | CP08-190C-P08-09 |  | SPOT WELD | PB | 1 | 60 | 1 | PB | SW09 | SW09
CA16-010 |  | - | P01-03 |  | 0 | CA16-010-P01-03 |  | PROGRESSIVE | ST | 1 | 3000 | 50 | ST | PP01-110T | PP01 | PP32
CA16-010 |  | - | P02-03 |  | 0 | CA16-010-P02-03 |  | DEGREASING | ST-2 | 1 | 1000 | 16.6667 | ST-1 | VM01 | VM01 | VM04
CC11-001 |  | - | P01-02 |  | 0 | CC11-001-P01-02 |  | PROGRESSIVE | ST | 1 | 3000 | 50 | ST | PP30-200T | PP30 | PP33
CP08-499B |  | - | P01-04 |  | 0 | CP08-499B-P01-04 |  | BLANKING | ST | 1 | 180 | 3 |  | PP30-200T | PP30 | PP33 | PP29
CP08-499B |  | - | P02-04 |  | 0 | CP08-499B-P02-04 |  | BENDING | ST | 1 | 180 | 3 |  | PP21 | PP21
CP08-499B |  | - | P03-04 |  | 0 | CP08-499B-P03-04 |  | BENDING | ST | 1 | 180 | 3 |  | PP30-200T | PP30 | PP29 | PP33
CP08-499C |  | - | P01-04 |  | 0 | CP08-499C-P01-04 |  | BLANKING | ST | 1 | 180 | 3 |  | PP30-200T | PP30 | PP33 | PP29
CP08-499C |  | - | P02-04 |  | 0 | CP08-499C-P02-04 |  | BENDING | ST | 1 | 180 | 3 |  | PP21 | PP21
CP08-499C |  | - | P03-04 |  | 0 | CP08-499C-P03-04 |  | BENDING | ST | 1 | 180 | 3 |  | PP30-200T | PP30 | PP33 | PP29
CD11-029A |  | - | P01-02 |  | 0 | CD11-029A-P01-02 |  | CTS | WN | 1 | 2700 | 45 |  | WS02 | WS01 | WS02 | [7 empty] | WS01-2700PCS/HR, WS02-1,320PCS/HR
CD11-029B |  | - | P01-02 |  | 0 | CD11-029B-P01-02 |  | CTS | WN | 1 | 2700 | 45 |  | WS02 | WS01 | WS02 | [7 empty] | WS01-2700PCS/HR, WS02-1,020PCS/HR
CD11-029C |  | - | P01-02 |  | 0 | CD11-029C-P01-02 |  | CTS | WN | 1 | 2700 | 45 |  | WS02 | WS01 | WS02 | [7 empty] | WS01-2700PCS/HR, WS02-1,320PCS/HR
CD11-029 |  | - | P01-06 |  | 0 | CD11-029-P01-06 |  | SPOT WELD | WN | 2 | 34.8 | 0.58 |  | SW08 | SW08
CD11-029 |  | - | P02-06 |  | 0 | CD11-029-P02-06 |  | STRAIGHTERNING | WN | 1 | 420 | 7 |  | LV01 | LV01
CD11-029 |  | - | P03-06 |  | 0 | CD11-029-P03-06 |  | CUT TO SIZE | ST | 1 | 180 | 3 |  | PP05-060T | PP05 | PP31
CD11-029 |  | - | P04-06 |  | 0 | CD11-029-P04-06 |  | CHECKING | WN | 1 | 120 | 2 |  | OPT | OPT | [8 empty] | NO NEED CHECKING,DIRECT SEND TO SUB CON FOR COATING
CD11-029 |  | - | P05-06 |  | 0 | CD11-029-P05-06 |  | COATING | SUB-CON | 1
CM10-016 |  | - | P01-03 |  | 0 | CM10-016-P01-03 |  | SLIT TO SIZE | ST | 1 | 300 | 5 |  | SM01 | SM01
CM10-016 |  | - | P02-03 |  | 0 | CM10-016-P02-03 |  | BLANKING | ST | 1 | 480 | 8 |  | PP10 | PP10
CP16-073 |  | - | P01-09 |  | 0 | CP16-073-P01-09 |  | TP | TP | 1 | 14 | 0.23333 |  | TM03 | TM03
CP16-073 |  | - | P02-09 |  | 0 | CP16-073-P02-09 |  | BENDING | PB | 1 | 90 | 1.5 |  | PB02 | PB02
CP16-073 |  | - | P03-09 |  | 0 | CP16-073-P03-09 |  | BENDING | PB | 1 | 90 | 1.5 |  | PB02 | PB02
CP16-073 |  | - | P04-09 |  | 0 | CP16-073-P04-09 |  | BENDING | PB | 1 | 90 | 1.5 |  | PB08 | PB08
CP16-073 |  | - | P05-09 |  | 0 | CP16-073-P05-09 |  | BENDING | PB | 1 | 60 | 1 |  | PB02 | PB02
CP16-073 |  | - | P06-09 |  | 0 | CP16-073-P06-09 |  | BENDING | PB | 1 | 60 | 1 |  | PB08 | PB08
CP16-073 |  | - | P07-09 |  | 0 | CP16-073-P07-09 |  | BENDING | PB | 1 | 60 | 1 |  | PB02 | PB02
CP16-073 |  | - | P08-09 |  | 0 | CP16-073-P08-09 |  | BENDING | PB | 1 | 60 | 1 |  | PB02 | PB02
CP16-074 |  | - | P01-09 |  | 0 | CP16-074-P01-09 |  | TP | TP | 1 | 14 | 0.23333 |  | TM03 | TM03
CP16-074 |  | - | P02-09 |  | 0 | CP16-074-P02-09 |  | BENDING | PB | 1 | 90 | 1.5 |  | PB02 | PB02
CP16-074 |  | - | P03-09 |  | 0 | CP16-074-P03-09 |  | BENDING | PB | 1 | 90 | 1.5 |  | PB02 | PB02
CP16-074 |  | - | P04-09 |  | 0 | CP16-074-P04-09 |  | BENDING | PB | 1 | 90 | 1.5 |  | PB08 | PB08
CP16-074 |  | - | P05-09 |  | 0 | CP16-074-P05-09 |  | BENDING | PB | 1 | 60 | 1 |  | PB02 | PB02
CP16-074 |  | - | P06-09 |  | 0 | CP16-074-P06-09 |  | BENDING | PB | 1 | 60 | 1 |  | PB08 | PB08
CP16-074 |  | - | P07-09 |  | 0 | CP16-074-P07-09 |  | BENDING | PB | 1 | 60 | 1 |  | PB02 | PB02
CP16-074 |  | - | P08-09 |  | 0 | CP16-074-P08-09 |  | BENDING | PB | 1 | 60 | 1 |  | PB02 | PB02
CV02-069 |  | - | P01-04 |  | 0 | CV02-069-P01-04 |  | TURRET PUNCH | TP | 1 | 48 | 0.8 | TP | TM03 | TM03
CV02-069 |  | - | P02-04 |  | 0 | CV02-069-P02-04 |  | BENDING 1,2 | PB | 1 | 120 | 2 | PB | PB07 | PB07 | PB05
CV02-070 |  | - | P01-04 |  | 0 | CV02-070-P01-04 |  | TURRET PUNCH | TP | 1 | 80 | 1.3333 | TP | TM03 | TM03 | TM05 | TM06
CV02-070 |  | - | P02-04 |  | 0 | CV02-070-P02-04 |  | BENDING 1,2,3,4 | PB | 1 | 120 | 2 | PB | PB07 | PB07 | PB04 | PB01
CV02-071 |  | - | P01-04 |  | 0 | CV02-071-P01-04 |  | TURRET PUNCH | TP | 1 | 40 | 0.66667 | TP | TM03 | TM03 | TM05 | TM06 | [6 empty] | SAME TOOLING WITH CV02-074,CV02-075
CV02-071 |  | - | P02-04 |  | 0 | CV02-071-P02-04 |  | BENDING 1,2,3 | PB | 1 | 90 | 1.5 | PB | PB01 | PB01 | PB07 | PB05 | [6 empty] | SAME TOOLING WITH CV02-074,CV02-075
CV02-072 |  | - | P01-04 |  | 0 | CV02-072-P01-04 |  | TURRET PUNCH | TP | 1 | 48 | 0.8 | TP | TM03 | TM03 | TM05 | TM06
CV02-072 |  | - | P02-04 |  | 0 | CV02-072-P02-04 |  | BENDING 1,2,3,4 | PB | 1 | 120 | 2 | PB | PB07 | PB07 | PB04 | PB01
CV02-073 |  | - | P01-05 |  | 0 | CV02-073-P01-05 |  | TURRET PUNCH | TP | 1 | 48 | 0.8 | TP | TM03 | TM03 | TM05 | TM06
CV02-073 |  | - | P02-05 |  | 0 | CV02-073-P02-05 |  | BENDING 1,2 | PB | 1 | 120 | 2 | PB | PB03 | PB03 | PB08 | PB01 | PB02 | PB07 | PB02
CV02-073 |  | - | P03-05 |  | 0 | CV02-073-P03-05 |  | BENDING 3 | PB | 1 | 180 | 3 | PB | PB03 | PB03 | PB01 | PB08 | PB04 | PB07 | PB02
CV02-074 |  | - | P01-04 |  | 0 | CV02-074-P01-04 |  | TURRET PUNCH | TP | 1 | 45 | 0.75 | TP | TM03 | TM03 | TM05 | TM06 | [6 empty] | SAME TOOLING WITH CV02-071,CV02-075
CV02-074 |  | - | P02-04 |  | 0 | CV02-074-P02-04 |  | BENDING 1,2,3 | PB | 1 | 90 | 1.5 | PB | PB01 | PB01 | PB07 | PB05 | [6 empty] | SAME TOOLING WITH CV02-071,CV02-075
CV02-075 |  | - | P01-04 |  | 0 | CV02-075-P01-04 |  | TURRET PUNCH | TP | 1 | 45 | 0.75 | TP | TM03 | TM03 | TM05 | TM06 | [6 empty] | SAME TOOLING WITH CV02-071,CV02-074
CV02-075 |  | - | P02-04 |  | 0 | CV02-075-P02-04 |  | BENDING 1,2,3 | PB | 1 | 90 | 1.5 | PB | PB07 | PB07 | PB01 | PB05 | [6 empty] | SAME TOOLING WITH CV02-071,CV02-074
CV02-076 |  | - | P01-04 |  | 0 | CV02-076-P01-04 |  | TURRET PUNCH | TP | 1 | 48 | 0.8 | TP | TM03 | TM03 | TM05 | TM06
CV02-076 |  | - | P02-04 |  | 0 | CV02-076-P02-04 |  | BENDING 1,2,3,4 | PB | 1 | 120 | 2 | PB | PB01 | PB01 | PB04 | PB07
CV02-067 |  | - | P02-04 |  | 0 | CV02-067-P02-04 |  | SEMI PROGRESSIVE | ST | 1 | 480 | 8 | ST | PP04 | PP04 | PP05 | PP13 | PP22
CV02-067 |  | - | P03-04 |  | 0 | CV02-067-P03-04 |  | BENDING | ST | 1 | 360 | 6 | ST | PP05 | PP04 | PP05 | PP13 | PP22
CV02-066 |  | - | P02-04 |  | 0 | CV02-066-P02-04 |  | SEMI PROGRESSIVE | ST | 1 | 480 | 8 | ST | PP13 | PP13 | PP05 |  | PP22 | PP04
CV02-066 |  | - | P03-04 |  | 0 | CV02-066-P03-04 |  | BENDING | ST | 1 | 360 | 6 | ST | PP04 | PP04 | PP05 |  | PP22 | PP13
CV02-068 |  | - | P01-05 |  | 0 | CV02-068-P01-05 |  | SEMI PROGRESSIVE | ST | 1 | 480 | 8 | ST | PP02 | PP04 | PP05 | PP13 | PP22 | PP10 | PP04 |  |  |  | P01 & P02 SHARE DIE
CV02-068 |  | - | P02-05 |  | 0 | CV02-068-P02-05 |  | BENDING | ST | 1 | 360 | 6 | ST | PP02 | PP04 | PP05 | PP13 | PP22 | PP12 | PP02
CV02-068 |  | - | P03-05 |  | 0 | CV02-068-P03-05 |  | TAPPING M4X0.7 | ST | 1 | 300 | 5 | ST | TP02 | TP03 | TP09 | TP02
CV02-068 |  | - | P04-05 |  | 0 | CV02-068-P04-05 |  | DEGREASING | ST | 1 | 480 | 8 | ST
CE03-040A |  | - | P02-04 |  | 0 | CE03-040A-P02-04 |  | TRIMMING | ST | 1 | 360 | 6 | ST | PP12 | PP12 | PP14 | PP10
CE03-040A |  | - | P03-04 |  | 0 | CE03-040A-P03-04 |  | PIERCING | ST | 1 | 480 | 8 | ST | PP13 | PP13
CP08-120 |  | - | P03-04 |  | 0 | CP08-120-P03-04 |  | BENDING | ST | 1 | 240 | 4 | ST | PP04 | PP04 | PP14 | PP10
CP08-120 |  | - | P02-04 |  | 0 | CP08-120-P02-04 |  | TRIMMING | ST | 1 | 240 | 4 | ST | PP04 | PP04
CD11-003I |  | - | P01-04 |  | 0 | CD11-003I-P01-04 |  | SLITTING | ST | 1 | 24120 | 402 | ST | SM01 | SM01
CD11-003I |  | - | P02-05 |  | 0 | CD11-003I-P02-04 |  | BLANKING | ST | 1 | 480 | 8 | ST | PP04 | PP04 | PP11
CD11-003I |  | - | P03-04 |  | 0 | CD11-003I-P03-04 |  | BENDING | ST | 1 | 360 | 6 | ST | PP04 | PP04
CD11-003I |  | - | P01-01 |  | 0 | CD11-003I-P01-01 |  | SPOT WELD | ST | 1 | 300 | 5 | ST | SW09 | SW09
CP15-004A |  | - | P01-03 |  | 0 | CP15-004A-P01-03 |  | CUT TO SIZE | ST | 1 | 300 | 5 | ST | PP07 | PP07
CP15-004A |  | -0 | P02-03 |  | 0 | CP15-004A-P02-03 |  | HAND GRINDING | ST | 1 | 510 | 8.5 | ST | OPT | OPT
CP15-004B |  | - | P04-05 |  | 0 | CP15-004B-P04-05 |  | STAMPING | ST | 1 | 240 | 4 | ST | PP02 | PP02
CP08-120 |  | - | P01-04 |  | 0 | CP08-120-P01-04 |  | SLITTING | ST | 1 | 240 | 4 | ST | SM01 | SM01
CD11-002A |  | - | P01-02 |  | 0 | CD11-002A-P01-02 |  | CUT TO SIZE | AWN | 1 | 3000 | 50 | WN | WS01 | WS01 | WS02 | [7 empty] | IF RUN M/C : WS02 : 31/MIN
CD11-002B |  | - | P01-02 |  | 0 | CD11-002B-P01-02 |  | CUT TO SIZE | AWN | 1 | 3000 | 50 | WN | WS01 | WS01 | WS02 | [7 empty] | IF RUN M/C : WS02 : 1,920 PCS/HRS
CD11-002C |  | - | P01-02 |  | 0 | CD11-002C-P01-02 |  | CUT TO SIZE | AWN | 1 | 3000 | 50 | WN | WS01 | WS01 | WS02
CD11-002 |  | - | P05-06 |  | 0 | CD11-002-P05-06 |  | SUB CON
CP08-564 |  | - | P01-05 |  | 0 | CP08-564-P01-05 |  | BLANKING | ST | 1 | 360 | 6 | ST | PP09 | PP09 | PP18 | PP21 | PP21 | [5 empty] | CHANGE TO STAMPING EFFECTIVE FROM SEPT 23??
CP08-564 |  | - | P02-05 |  | 0 | CP08-564-P02-05 |  | BENDING | ST | 1 | 360 | 6 | ST | PP18 | PP18 | PP17 | PP17 | PP17 | [5 empty] | CHANGE TO STAMPING EFFECTIVE FROM SEPT 23??
CP08-564 |  | - | P03-05 |  | 0 | CP08-564-P03-05 |  | BENDING | ST | 1 | 360 | 6 | ST | PP17 | PP17 | PP16 | PP18 | PP16 | [5 empty] | CHANGE TO STAMPING EFFECTIVE FROM SEPT 23??
CP08-564 |  | - | P04-05 |  | 0 | CP08-564-P04-05 |  | BENDING | ST | 1 | 360 | 6 | ST | PP16 | PP16 | PP27 | PP16 | PP27 | [5 empty] | CHANGE TO STAMPING EFFECTIVE FROM SEPT 23??
CP21-001A |  | - | P01-04 |  | 0 | CP21-001A-P01-04 |  | BLANKING | ST | 1 | 300 | 5 | ST | PP13 | PP13 | PP14
CP21-001A |  | - | P02-04 |  | 0 | CP21-001A-P02-04 |  | PIERCING 1 | ST | 1 | 300 | 5 | ST | PP05 | PP05 | PP05
CP21-001A |  | - | P03-04 |  | 0 | CP21-001A-P03-04 |  | PIERCING 2 | ST | 1 | 300 | 5 | ST | PP04 | PP04 | PP22
CP21-001B |  | - | P01-04 |  | 0 | CP21-001B-P01-04 |  | SLITTING | ST | 1 | 120 | 2 | ST | SM01 | SM01
CP21-001B |  | - | P02-04 |  | 0 | CP21-001B-P02-04 |  | BLANKING | ST | 1 | 300 | 5 | ST | PP04 | PP04
CP21-001B |  | - | P03-04 |  | 0 | CP21-001B-P03-04 |  | PIERCING | ST | 1 | 300 | 5 | ST | PP03 | PP03
CP21-001 |  | - | P01-02 |  | 0 | CP21-001-P01-02 |  | ASSEMBLY | ST | 1 | 120 | 2 | ST | OPT | OPT
CA14-016 |  | - | P01-04 |  | 0 | CA14-016-P01-04 |  | FORMING | FM | 1 | 4800 | 80 | FM | FM01 | FM01
CV02-065 |  | - | P01-03 |  | 0 | CV02-065-P01-03 |  | BLANKING | ST | 1 | 480 | 8 | ST | PP11 | PP11 | PP02
CV02-065 |  | - | P02-03 |  | 0 | CV02-065-P02-03 |  | BENDING | TP | 1 | 60 | 1 | ST | PB04 | PB04
CU01-054A |  | - | P01-03 |  | 0 | CU01-054A-P01-03 |  | TURRET PUNCH | TP | 1 | 15 | 0.25 | TP | TM03 | TM05 | TM06
CU01-054A |  | - | P02-03 |  | 0 | CU01-054A-P02-03 |  | BENDING | PB | 1 | 45 | 0.75 | PB | PB07 | PB07
CU01-054B |  | - | P01-03 |  | 0 | CU01-054B-P01-03 |  | TURRET PUNCH | TP | 1 | 120 | 2 | TP | TM03
CU01-054B |  | - | P02-03 |  | 0 | CU01-054B-P02-03 |  | BENDING | PB | 1 | 180 | 3 | PB | PB02 | PB02 | PB03 | PB04 | PB08 | PB01
CU01-054C |  | - | P01-03 |  | 0 | CU01-054C-P01-03 |  | TURRET PUNCH | TP | 1 | 120 | 2 | TP | TM03 | TM05 | TM06
CU01-054C |  | - | P02-03 |  | 0 | CU01-054C-P02-03 |  | BENDING | PB | 1 | 180 | 3 | PB | PB02 | PB02 | PB03 | PB04 | PB08
CU01-054D |  | - | P01-03 |  | 0 | CU01-054D-P01-03 |  | TURRET PUNCH | TP | 1 | 120 | 2 | TP | TM03 | TM05 | TM06
CU01-054D |  | - | P02-03 |  | 0 | CU01-054D-P02-03 |  | BENDING | PB | 1 | 180 | 3 | PB | PB02 | PB02 | PB03 | PB04 | PB08
CU01-054E |  | - | P01-02 |  | 0 | CU01-054E-P01-02 |  | SPOT WELD | PB | 2 | 60 | 1 | PB | SW09 | SW09
CU01-054 |  | - | P01-04 |  | 0 | CU01-054-P01-04 |  | SPOT WELD | PB | 2 | 60 | 1 | PB | SW09 | SW09
CU01-054 |  | - | P02-04 |  | 0 | CU01-054-P02-04 |  | MIG | PB | 1 | 15 | 0.25 | PB | MG01 | MG01
CU01-055A |  | - | P01-03 |  | 0 | CU01-055A-P01-03 |  | TURRET PUNCH | TP | 1 | 18 | 0.3 | TP | TM03 | TM03 | TM05 | TM06
CU01-055A |  | - | P02-03 |  | 0 | CU01-055A-P02-03 |  | BENDING | PB | 1 | 45 | 0.75 | PB | PB07 | PB07
CU01-055 |  | - | P01-04 |  | 0 | CU01-055-P01-04 |  | PB | PB | 1 | 60 | 1 | PB | SW09 | SW09
CU01-055 |  | - | P02-04 |  | 0 | CU01-055-P02-04 |  | MIG | PB | 1 | 15 | 0.25 | PB | MG01 | MG01
CU01-054F |  | - | P01-02 |  | 0 | CU01-054F-P01-02 |  | PB | PB | 2 | 60 | 1 | PB | SW09 | SW09
CA32-005 |  | - |  |  | 0
CA32-005 |  | - | P01-02 |  | 0 | CA32-005-P01-02 |  | PROGRESSIVE | ST | 1 | 1800 | 30 | ST | PP19 | PP19 | PP12
CE03-015 |  | - | P01-03 |  | 0 | CE03-015-P01-03 |  | STAMPING | ST | 1 | 480 | 8 | ST | PP06 | PP06 | PP11 | PP14 - KENA TAMBAH BANYAK
CE03-016 |  | - | P01-03 |  | 0 | CE03-016-P01-03 |  | STAMPING | ST | 1 | 480 | 8 | ST | PP06 | PP06 | PP11 | PP14 - KENA TAMBAH BANYAK
CU01-048 |  | - | P01-04 |  | 0 | CU01-048-P01-04 |  | SLITTING | ST | 2 | 5760 | 96 | ST | SM01 | SM01
CU01-048 |  | - | P02-04 |  | 0 | CU01-048-P02-04 |  | BLANKING | ST | 1 | 360 | 6 | ST | PP03 | PP03 | [8 empty] | ONE TIME RUN WITH CU01-049
CU01-048 |  | - | P03-04 |  | 0 | CU01-048-P03-04 |  | BENDING | ST | 1 | 240 | 4 | ST | PP04 | PP04 | [8 empty] | ONE TIME RUN WITH CU01-049
CU01-049 |  | - | P01-04 |  | 0 | CU01-049-P01-04 |  | SLITTING | ST | 2 | 5760 | 96 | ST | SM01 | SM01 | [8 empty] | ONE TIME RUN WITH CU01-048
CU01-049 |  | - | P02-04 |  | 0 | CU01-049-P02-04 |  | BLANKING | ST | 1 | 360 | 6 | ST | PP04 | PP04 | PP03 | [7 empty] | ONE TIME RUN WITH CU01-048
CU01-049 |  | - | P03-04 |  | 0 | CU01-049-P03-04 |  | BENDING | ST | 1 | 240 | 4 | ST | PP03 | PP03 | PP04
CP08-407 |  | - | P01-07 |  | 0 | CP08-407-P01-07 |  | TRIM | ST | 1 | 120 | 2 | ST | PP29 | PP29 | PP33
CP08-407 |  | - | P02-07 |  | 0 | CP08-407-P02-07 |  | BENDING | ST | 1 | 120 | 2 | ST | PP33 | PP33 | PP29
CP08-407 |  | - | P03-07 |  | 0 | CP08-407-P03-07 |  | TAPPING | ST | 1 | 60 | 1 | ST | TP03 | TP03 | TP07
CP08-407 |  | - | P04-07 |  | 0 | CP08-407-P04-07 |  | TAPPING | ST | 1 | 120 | 2 | ST | TP09 | TP09 | TP09
CP08-407 |  | - | P05-07 |  | 0 | CP08-407-P05-07 |  | BENDING | ST | 1 | 120 | 2 | ST | PP33 | PP33
CP08-407 |  | - | P06-07 |  | 0 | CP08-407-P06-07 |  | SPOT WELD | ST | 1 | 80 | 1.3333 | ST | SW01 | SW01 | SW09
CD11-005 |  | - | P01-05 |  | 0 | CD11-005-P01-05 |  | SLITTING | TR | 1 | 240 | 4 | TR | SM01 | SM01
CU01-055 |  | - | P03-04 |  | 0 | CU01-055-P03-04 |  | CLEANING | TR | 1 | 20 | 0.33333 | TR | OPT | OPT
CU01-054 |  | - | P03-04 |  | 0 | CU01-054-P03-04 |  | CLEANING | TR | 1 | 14 | 0.23333 | TR | OPT | OPT
CP16-009 |  | - | P01-02 |  | 0 | CP16-009-P01-02 |  | FORMING | FM | 1 | 2400 | 40 | FM | FM03 | FM03
CA24-008 |  | - | P01-03 |  | 0 | CA24-008-P01-03 |  |  | ST | 1 | 480 | 8 | ST | PP10 | PP10 |  | PP01 | PP02 | PP14 | [5 empty] | SAME DIE V CA24-006,CA24-007
CA24-008 |  | - | P02-03 |  | 0 | CA24-008-P02-03 |  |  | ST | 1 | 180 | 3 | ST | PP21 | PP21 | PP15 | PP21 | PP31 | [6 empty] | SAME DIE V CA24-006,CA24-007,CA24-009,CL02-008
CP08-151 |  | - | P01-05 |  | 0 | CP08-151-P01-05 |  | TP | TR | 1 | 103 | 1.7167 | TR | TM03 | TM03 | TM05 | TM06
CP08-151 |  | - | P02-05 |  | 0 | CP08-151-P02-05 |  | STAMPING | ST | 1 | 300 | 5 | ST | PP17 | PP17
CP08-151 |  | - | P03-05 |  | 0 | CP08-151-P03-05 |  | STAMPING | ST | 1 | 300 | 5 | ST | PP16 | PP16
CP08-151 |  | - | P04-05 |  | 0 | CP08-151-P04-05 |  | STAMPING | ST | 1 | 300 | 5 | ST | PP27 | PP27
CA24-002 |  | - | P03-04 |  | 0 | CA24-002-P03-04 |  | DEGREASING | ST | 1 | 1000 | 16.6667 | ST-2 | VM01 | VM01 | VM04
CV02-067 |  | - | P01-04 |  | 0 | CV02-067-P01-04 |  | SLITTING | ST | 2 | 41760 | 696 | ST | SM01 | SM01
CU01-051 |  | - | P01-04 |  | 0 | CU01-051-P01-04 |  | SLITTING | ST | 1 | 10620 | 177 | ST | SM01 | SM01
CP08-569 |  | - | P02-05 |  | 0 | CP08-569-P02-05 |  | TP | TR | 1 | 38 | 0.63333 | TR | TM05 | TM05 | TM03 | TM06
CP08-569 |  | - | P03-05 |  | 0 | CP08-569-P03-05 |  | BENDING | PB | 1 | 75 | 1.25 | PB | PB03 | PB03 | PB01
CP08-569 |  | - | P04-05 |  | 0 | CP08-569-P04-05 |  | BENDING | PB | 1 | 75 | 1.25 | PB | PB03 | PB03 | PB01
CP08-570 |  | - | P02-04 |  | 0 | CP08-570-P02-04 |  | TP | TR | 1 | 130 | 2.1667 | TR | TM05 | TM05
CP08-570 |  | - | P03-04 |  | 0 | CP08-570-P03-04 |  | BENDING | PB | 1 | 90 | 1.5 | PB | PB07 | PB07 | PB04
CU01-056 |  | - | P01-03 |  | 0 | CU01-056-P01-03 |  | SLITTING | ST | 2 | 180 | 3 | ST | SM01 | SM01
CU01-056 |  | - | P02-03 |  | 0 | CU01-056-P02-03 |  | CUT TO SIZE | ST | 1 | 480 | 8 | ST | PP05 | PP05 | PP13 | [7 empty] | SHARE V CL02-002-P01-05,CL02-003-P01-05
CV02-066 |  | - | P01-04 |  | 0 | CV02-066-P01-04 |  | SLITTING | ST | 1 | 41760 | 696 | ST | SM01 | SM01
CP08-571 |  | - | P01-05 |  | 0 | CP08-571-P01-05 |  | SLITTING | TR | 2 | 360 | 6 | TR | SM01 | SM01
CP08-571 |  | - | P02-05 |  | 0 | CP08-571-P02-05 |  | TURRET PUNCH | TR | 1 | 72 | 1.2 | TR | TM03 | TM03 | TM05 | TM06
CP08-571 |  | - | P03-05 |  | 0 | CP08-571-P03-05 |  | BENDING | PB | 1 | 120 | 2 | PB | PB08 | PB08 | PB03 | PB02
CP08-571 |  | - | P04-05 |  | 0 | CP08-571-P04-05 |  | BENDING | PB | 1 | 90 | 1.5 | PB | PB04 | PB04 | PB07 | PB01
CP16-075 |  | - | P01-03 |  | 0 | CP16-075-P01-03 |  | FORMING | FM | 1 |  |  | FM | FM03 | FM03 | FM02
CP08-231B | GC02-009B | - | P05-06 |  | 0 | CP08-231B-P05-06 |  | CUT TO SIZE | WN | 1 | 240 | 4 | WN | PP23 | PP23
CP08-576 |  | - | P02-04 |  | 0 | CP08-576-P02-04 |  | PROGRESSIVE | ST | 1 | 140 | 2.3333 | ST | PP10 | PP10 | PP30 | PP01 | PP15 | PP12
CP08-576 |  | - | P03-04 |  | 0 | CP08-576-P03-04 |  | TAPPING | ST | 1 | 720 | 12 | ST | TP04 | TP04
CP09-001 |  | - | P01-04 |  | 0 | CP09-001-P01-04 |  | BLANKING | ST | 1 | 600 | 10 | ST | PP03 | PP03 | PP02 | PP14
CP09-001 |  | - | P02-04 |  | 0 | CP09-001-P02-04 |  | BENDING | ST | 1 | 240 | 4 | ST | PP04 | PP04 | PP12
CP09-001 |  | - | P03-04 |  | 0 | CP09-001-P03-04 |  | SUB CON | SC
CV02-072 |  | - | P03-04 |  | 0 | CV02-072-P03-04 |  | CLEANING | TP | 1 | 180 | 3 | TP | OPT | OPT
CV02-069 |  | - | P03-04 |  | 0 | CV02-069-P03-04 |  | CLEANING | TP | 1 | 180 | 3 | TP | OPT | OPT
CV02-070 |  | - | P03-04 |  | 0 | CV02-070-P03-04 |  | CLEANING | TP | 1 | 180 | 3 | TP | OPT | OPT
CV02-073 |  | - | P04-05 |  | 0 | CV02-073-P04-05 |  | CLEANING | TP | 1 | 180 | 3 | TP | OPT | OPT
CV02-074 |  | - | P03-04 |  | 0 | CV02-074-P03-04 |  | CLEANING | TP | 1 | 180 | 3 | TP | OPT | OPT
CV02-075 |  | - | P03-04 |  | 0 | CV02-075-P03-04 |  | CLEANING | TP | 1 | 180 | 3 | TP | OPT | OPT | [8 empty] | SAME TOOLING WITH CV02-071,CV02-074
CV02-071 |  | - | P03-04 |  | 0 | CV02-071-P03-04 |  | CLEANING | TP | 1 | 180 | 3 | TP | OPT | OPT
CV02-076 |  | - | P03-04 |  | 0 | CV02-076-P03-04 |  | CLEANING | TP | 1 | 180 | 3 | TP | OPT | OPT
CP08-573 |  | - | P01-10 |  | 0 | CP08-573-P01-10 |  | 10 SPOT WELD-1 | WN | 1 | 30 | 0.5 | WN | SW04 | SW04 | SW13
CP08-573 |  | - | P02-10 |  | 0 | CP08-573-P02-10 |  | TRIMMING | WN | 1 | 180 | 3 | WN | TW01 | TW01
CP08-573 |  | - | P03-10 |  | 0 | CP08-573-P03-10 |  | CUT TO SIZE | WN | 1 | 180 | 3 | WN | PP23 | PP23
CP08-573 |  | - | P04-10 |  | 0 | CP08-573-P04-10 |  | 9 SPOT WELD-2 | WN | 1 | 30 | 0.5 | WN | SW06 | SW06 | SW13 | SW04
CP08-573 |  | - | P06-10 |  | 0 | CP08-573-P06-10 |  | BENDING | PB | 2 | 78 | 1.3 | WN | PB07 | PB08 |  | PB07
CP08-573 |  | - | P07-10 |  | 0 | CP08-573-P07-10 |  | BENDING | PB | 2 | 180 | 3 | PB | PB08 | PB02 | PB03 | PB08
CP08-575 |  | - | P01-03 |  | 0 | CP08-575-P01-03 |  | SLITTING | ST | 1 | 6240 | 104 | ST | SM01 | SM01
CP08-575 |  | - | P02-03 |  | 0 | CP08-575-P02-03 |  | PROGRESSIVE | ST | 1 | 240 | 4 | ST | PP30 | PP30 | PP01 | PP09 | [6 empty] | SHARE DIE CP08-079
CN08-001 |  | - | P01-04 |  | 0 | CN08-001-P01-04 |  | BLANKING | ST | 1 | 1200 | 20 | ST | PP14 | PP14
CN08-001 |  | - | P02-04 |  | 0 | CN08-001-P02-04 |  | TAPPING | ST | 1 | 480 | 8 | ST | TP09 | TP09
CP08-567 |  | - | P01-06 |  | 0 | CP08-567-P01-06 |  | DRAW | ST | 1 | 180 | 3 | ST | PP33 | PP33 | [8 empty] | OPF-PP33,PP29
CP08-567 |  | - | P02-06 |  | 0 | CP08-567-P02-06 |  | BLANKING | ST | 1 | 180 | 3 | ST | PP29 | PP29 | [8 empty] | OPF-PP33,PP29
CP08-567 |  | - | P03-06 |  | 0 | CP08-567-P03-06 |  | BENDING | ST | 1 | 180 | 3 | ST | PP29 | PP33 | PP29 | [7 empty] | OPF - PP29,PP30,PP33
CP08-567 |  | - | P04-06 |  | 0 | CP08-567-P04-06 |  | BENDING | ST | 1 | 180 | 3 | ST | PP30 | PP29 | PP30 | [7 empty] | OPF - PP29,PP30,PP33
CP08-567 |  | - | P05-06 |  | 0 | CP08-567-P05-06 |  | BENDING | ST | 1 | 180 | 3 | ST | PP33 | PP33 | PP33 | [7 empty] | OPF - PP29,PP30,PP33
CP08-569 |  | - | P01-05 |  | 0 | CP08-569-P01-05 |  | SLITTING | TP | 1 | 180 | 3 | ST | SM01 | SM01
CM03-042 |  | - | P01-06 |  | 0 | CM03-042-P01-06 |  | BLANKING | ST | 1 | 360 | 6 | ST | PP04 | PP04 |  | PP21 | PP14
CM03-042 |  | - | P02-06 |  | 0 | CM03-042-P02-06 |  | TAPPING | ST | 1 | 180 | 3 | ST | TP09 | TP09 | TP03
CN08-002A |  | - | P01-03 |  | 0 | CN08-002A-P01-03 |  | BLANKING | ST | 1 | 480 | 8 | ST | PP03 | PP03
CP08-572 |  | - | P01-03 |  | 0 | CP08-572-P01-03 |  | FORMING | FM | 1 | 1260 | 21 | FM | FM02 | FM02 | FM01
CV02-061 |  | - | P01-03 |  | 0 |  |  | BLANKING | ST | 1 | 288 | 4.8 | ST | PP22 | PP22
CV02-061 |  | - | P02-03 |  | 0 |  |  | BENDING | ST | 1 | 270 | 4.5 | ST | PP22 | PP22
CP08-577 |  | - | P01-04 |  | 0 | CP08-577-P01-04 |  | SLIT TO SIZE | ST | 1 | 240 | 4 | ST | SM01 | SM01
CP08-577 |  | - | P02-04 |  | 0 | CP08-577-P02-04 |  | BLANKING | ST | 1 | 480 | 8 | ST | PP03 | PP03 | PP10 | PP05
CP08-577 |  | - | P03-04 |  | 0 | CP08-577-P03-04 |  | BENDING | ST | 1 | 36 | 0.6 | ST | PP04 | PP04 | PP12 | PP05
CP08-578 |  | - | P01-04 |  | 0 | CP08-578-P01-04 |  | SLIT TO SIZE | ST | 1 | 240 | 4 | ST | SM01 | SM01
CP08-578 |  | - | P02-04 |  | 0 | CP08-578-P02-04 |  | BLANKING | ST | 1 | 480 | 8 | ST | PP03 | PP03 | PP12
CP08-578 |  | - | P03-04 |  | 0 | CP08-578-P03-04 |  | BENDING | ST | 1 | 36 | 0.6 | ST | PP04 | PP04 | PP12
CP08-579 |  | - | P01-04 |  | 0 | CP08-579-P01-04 |  | SLIT TO SIZE | ST | 1 | 240 | 4 | ST | SM01 | SM01
CP08-579 |  | - | P02-04 |  | 0 | CP08-579-P02-04 |  | BLANKING | ST | 1 | 480 | 8 | ST | PP03 | PP03 | PP10
CP08-579 |  | - | P03-04 |  | 0 | CP08-579-P03-04 |  | BENDING | ST | 1 | 36 | 0.6 | ST | PP04 | PP04 | PP12
CP08-566 |  | - | P01-04 |  | 0 | CP08-566-P01-04 |  | SLIT TO SIZE | ST | 1 | 10560 | 176 | ST | SM01 | SM01 | [8 empty] | SAME DIE WITH CP08-494
CP08-566 |  | - | P02-04 |  | 0 | CP08-566-P02-04 |  | TRIMMING | ST | 1 | 360 | 6 | ST | PP03 | PP03 | [8 empty] | SAME DIE WITH CP08-494
CP08-566 |  | - | P03-04 |  | 0 | CP08-566-P03-04 |  | BENDING | ST | 1 | 360 | 6 | ST | PP04 | PP04 | PP03 | [7 empty] | SAME DIE WITH CP08-494
CP08-570 |  | - | P01-04 |  | 0 | CP08-570-P01-04 |  | SLIT TO SIZE | TR | 1 | 210 | 3.5 | TP | SM01 | SM01
CA21-002 |  | - | P01-04 |  | 0 | CA21-002-P01-04 |  | FORMING | FM | 1 | 3000 | 50 | FM | FM02 | FM02 | FM01
CA21-003 |  | - | P01-04 |  | 0 | CA21-003-P01-04 |  | FORMING | FM | 1 | 4800 | 80 | FM | FM02 | FM02 | FM01
CP08-513 |  | - | P06-07 |  | 0 | CP08-513-P06-07 |  | STAMPING | ST | 1 | 420 | 7 | ST | OPT | OPT
CP08-573 |  | - | P08-10 |  | 0 | CP08-573-P08-10 |  | ED COATING BLACK | SUB CON
CP08-573 |  | - | P09-10 |  | 2 | CP08-573-P09-10 |  | CHECKING | WN | 1 | 18 | 0.3 | WN | OPT | OPT | [7 empty] | 1 JIG (2 OPERATORS RUNNING)
CP08-573C |  | - | P01-02 |  | 0 | CP08-573C-P01-02 |  | CUTTING | WN | 1 | 6000 | 100 | WN | WS01 | WS01
CP08-573D |  | - | P01-02 |  | 0 | CP08-573D-P01-02 |  | CUTTING | WN | 1 | 6000 | 100 | WN | WS01 | WS01
CP08-573E |  | - | P01-02 |  | 0 | CP08-573E-P01-02 |  | CUTTING | WN | 1 | 900 | 15 | WN | WS01 | WS01
CP08-573F |  | - | P01-02 |  | 0 | CP08-573F-P01-02 |  | CUTTING | WN | 1 | 2700 | 45 | WN | WS01 | WS01
CP08-573G |  | - | P01-03 |  | 0 | CP08-573G-P01-03 |  | CUTTING | WN | 1 | 1500 | 25 | WN | WS01 | WS01
CP08-573G |  | - | P02-03 |  | 0 | CP08-573G-P02-03 |  | JIG BENDING | WN | 1 | 300 | 5 | WN | OPT | OPT
CP08-573H |  | - | P01-04 |  | 0 | CP08-573H-P01-04 |  | CUTTING | WN | 1 | 1200 | 20 | WN | WS01 | WS01
CP08-573H |  | - | P02-04 |  | 0 | CP08-573H-P02-04 |  | JIG BENDING | WN | 1 | 180 | 3 | WN | OPT | OPT
CP08-573H |  | - | P03-04 |  | 0 | CP08-573H-P03-04 |  | BENDING | WN | 1 | 240 | 4 | WN | PP23 | PP23
CM03-042 |  | - | P03-06 |  | 0 | CM03-042-P03-06 |  | TAPPING | ST | 1 | 200 | 3.3333 | ST | TP07 | TP07 | TP03 | TP09
CN08-002A |  | - | P01-02 |  | 0 | CN08-002-P01-02 |  | CAULKING | ST | 1 | 240 | 4 | ST | PP11 | PP11
CP08-574 |  | - | P01-11 |  | 0 | CP08-574-P01-11 |  | SPOT WELD | WN | 2 | 25 | 0.41667 | WN | SW04 | SW08 | SW04
CP08-574 |  | - | P02-11 |  | 0 | CP08-574-P02-11 |  | CUT TO SIZE | WN | 1 | 180 | 3 | WN | PP23 | PP23
CP08-574 |  | - | P03-11 |  | 0 | CP08-574-P03-11 |  | TRIMMING | WN | 1 | 180 | 3 | WN | TW01 | TW01 | TW02 | TW03
CP08-574 |  | - | P04-11 |  | 0 | CP08-574-P04-11 |  | SPOT WELD | WN | 1 | 30 | 0.5 | WN | SW04 | SW04
CP08-574 |  | - | P05-11 |  | 0 | CP08-574-P05-11 |  | HAND CUTTING | WN | 1 | 180 | 3 | WN | OPT | OPT
CP08-574 |  | - | P06-11 |  | 0 | CP08-574-P06-11 |  | BENDING | WN | 1 | 80 | 1.3333 | PB | PB02 | PB02 | PB07 | PB01 | PB01 | PB07
CP08-574 |  | - | P07-11 |  | 0 | CP08-574-P07-11 |  | BENDING | WN | 2 | 80 | 1.3333 | PB | PB03 | PB03 | PB01 | PB08 | PB07 | PB08
CP08-574 |  | - | P08-11 |  | 0 | CP08-574-P08-11 |  | SUB CON | WN | [14 empty] | effective on 04.07.24 no Plating Process
CP08-574 |  | - | P09-11 |  | 0 | CP08-574-P09-11 |  | SUB CON | WN
CP08-574 |  | - | P10-11 |  | 0 | CP08-574-P10-11 |  | CHECKING | WN | 1 | 15 | 0.25 | WN | OPT | OPT
CP08-574A |  | - | P01-03 |  | 0 | CP08-574A-P01-03 |  | CUTTING | WN | 1 | 1800 | 30 | WN | WS01 | WS01
CP08-574A |  | - | P02-03 |  | 0 | CP08-574A-P02-03 |  | HAND BENDING | WN | 1 | 300 | 5 | WN | OPT | OPT
CP08-574B |  | - | P01-04 |  |  | CP08-574B-P01-04 |  | CUTTING | WN | 1 | 600 | 10 | WN | WS01 | WS01
CP08-574B |  | - | P02-04 |  | 0 | CP08-574B-P02-04 |  | HAND BENDING | WN | 1 | 180 | 3 | WN | OPT | OPT
CP08-574B |  | - | P03-04 |  | 0 | CP08-574B-P03-04 |  | BENDING | WN | 1 | 120 | 2 | WN | PP23 | PP23
CP08-574C |  | - | P01-02 |  | 0 | CP08-574C-P01-02 |  | CUTTING | WN | 1 | 2400 | 40 | WN | WS01 | WS01
CP08-574D |  | - | P01-02 |  | 0 | CP08-574D-P01-02 |  | CUTTING | WN | 1 | 660 | 11 | WN | WS01 | WS01
CP08-574E |  | - | P01-02 |  | 0 | CP08-574E-P01-02 |  | CUTTING | WN | 1 | 1800 | 30 | WN | WS01 | WS01
CP08-574F |  | - | P01-03 |  | 0 | CP08-574F-P01-03 |  | CUTTING | WN | 1 | 1800 | 30 | WN | WS01 | WS01
CP08-574F |  | - | P02-03 |  | 0 | CP08-574F-P02-03 |  | HAND BENDING | WN | 1 | 300 | 5 | WN | OPT | OPT
CP08-573 |  | - | P05-10 |  | 0 | CP08-573-P05-10 |  | HAND CUTTING | WN | 1 | 300 | 5 | WN | OPT | OPT
CT10-006 |  | - | P05-08 |  | 0 | CT10-006-P05-08 |  | TAPPING | TP | 1 | 100 | 1.6667 | TP | TP03 | TP03
CM03-042 |  | - | P04-06 |  | 0 | CM03-042-P04-06 |  | BENDING | ST | 1 | 240 | 4 | ST | PP15 | PP15 | PP21 | PP14
CL02-002 |  | - | P01-03 |  | 0 | CL02-002-P01-03 |  |  | ST | 1 | 480 | 8 | ST | PP14 | [9 empty] | EFFECTIVE MAY 2024 ONLY 1 PROCESS
CM17-018 |  | - | P01-02 |  | 0 | CM17-018-P01-02 |  | PROGRESSIVE | ST | 1 | 1500 | 25 | ST | PP14 | PP14 | PP09
CP08-576 |  | - | P01-04 |  | 0 | CP08-576-P01-04 |  | SLITING | ST | 2 | 96000 | 1600 | ST | SM01 | SM01 | [8 empty] | SHARE DIE V CP08-304,CP08-305
CV02-059 |  | - | P02-03 |  | 0 | CV02-059-P02-03 |  | DEGREASING | FM | 1 | 1000 | 16.6667 | FM | VM01 | VM01 | VM04
CE03-015 |  | - | P02-03 |  | 0 | CE03-015-P02-03 |  | DEGREASING | ST | 1 | 1000 | 16.6667 | FM | VM01 | VM01 | VM04
CE03-016 |  | - | P02-03 |  | 0 | CE03-016-P02-03 |  | DEGREASING | ST | 1 | 1000 | 16.6667 | FM | VM01 | VM01 | VM04
CP08-299 |  | - | P02-03 |  | 0 | CP08-299-P02-03 |  | DEGREASING | ST | 1 | 1000 | 16.6667 | FM | VM01 | VM01 | VM04
CP08-300 |  | - | P02-03 |  | 0 | CP08-300-P02-03 |  | DEGREASING | ST | 1 | 1000 | 16.6667 | FM | VM01 | VM01 | VM04
CP08-506 |  | - | P01-09 |  | 0 | CP08-506-P01-09 |  | SLITING | ST | 1 | 480 | 8 | ST | SM01 | SM01
CP08-508 |  | - | P01-09 |  | 0 | CP08-508-P01-09 |  | SLITING | ST | 1 | 480 | 8 | ST | SM01 | SM01
CP08-557 |  | - | P06-09 |  | 0 | CP08-557-P06-09 |  | DEBURR | WN | 1 | 90 | 1.5 | WN | OPT | OPT
CP08-568 |  | - | P01-03 |  | 0 | CP08-568-P01-03 |  | CNC SPOT WELD | WN | 1 | 6 | 0.1 | WN | SW08 | SW04 | SW06 | SW08 | [6 empty] | M/C:SW06 1 HOUR ONLY - 6 PCS
CP08-568 |  | - | P02-03 |  | 0 | CP08-568-P02-03 |  | TRIMMING | WN | 1 | 20.4 | 0.34 | WN | TW01 | TW01 | TW03 | TW02
CP08-568A |  | - | P01-02 |  | 0 | CP08-568A-P01-02 |  | CUT TO SIZE | WN | 1 | 900 | 15 | WN | WS01 | WS01
CP08-568B |  | - | P01-02 |  | 0 | CP08-568B-P01-02 |  | CUT TO SIZE | WN | 1 | 900 | 15 | WN | WS01 | WS01
CP08-568C |  | - | P01-02 |  | 0 | CP08-568C-P01-02 |  | CUT TO SIZE | WN | 1 | 900 | 15 | WN | WS01 | WS01
CP08-568D |  | - | P01-02 |  | 0 | CP08-568D-P01-02 |  | CUT TO SIZE | WN | 1 | 900 | 15 | WN | WS01 | WS01
CP08-568E |  | - | P01-03 |  | 0 | CP08-568E-P01-03 |  | CUT TO SIZE | WN | 1 | 900 | 15 | WN | WS01 | WS01
CP08-568E |  | - | P02-03 |  | 0 | CP08-568E-P02-03 |  | HAND CUTTING | WN | 1 | 300 | 5 | WN | OPT | OPT
CP08-568F |  | - | P01-03 |  | 0 | CP08-568F-P01-03 |  | CUT TO SIZE | WN | 1 | 900 | 15 | WN | WS01 | WS01
CP08-568F |  | - | P02-03 |  | 0 | CP08-568F-P02-03 |  | 2-HAND BENDING | WN | 1 | 120 | 2 | WN | OPT | OPT
CP08-568G |  | - | P01-04 |  | 0 | CP08-568G-P01-04 |  | CUT TO SIZE | WN | 1 | 600 | 10 | WN | WS01 | WS01
CP08-568G |  | - | P02-04 |  | 0 | CP08-568G-P02-04 |  | 2-HAND BENDING | WN | 1 | 120 | 2 | WN | OPT | OPT
CP08-568G |  | - | P03-04 |  | 0 | CP08-568G-P03-04 |  | 2-BENDING | WN | 1 | 240 | 4 | WN | PP23 | PP23
CB10-001 |  | - | P01-05 |  | 0 | CB10-001-P01-05 |  | SLITTING | TR | 1 | 240 | 4 | TR | SM01 | SM01
CB10-001 |  | - | P02-05 |  | 0 | CB10-001-P02-05 |  | TURRET PUNCH | TR | 1 | 48 | 0.8 | TR | TM03 | TM03 | TM05 | TM06
CB10-001 |  | - | P03-05 |  | 0 | CB10-001-P03-05 |  | BENDING | PB | 1 | 60 | 1 | PB | PB04 | PB04
CB10-001 |  | - | P04-05 |  | 0 | CB10-001-P04-05 |  | BENDING | PB | 1 | 48 | 0.8 | PB | PB04 | PB04
CE02-001 |  | - | P01-05 |  | 0 | CE02-001-P01-05 |  | CUT TO SIZE | ST | 1 | 180 | 3 | ST | PP02 | PP02
CE02-001 |  | - | P02-05 |  | 0 | CE02-001-P02-05 |  | PIERCING | ST | 1 | 480 | 8 | ST | PP04 | PP04 | PP03
CE02-001 |  | - | P03-05 |  | 0 | CE02-001-P03-05 |  | BENDING | ST | 1 | 360 | 6 | ST | PP05 | PP05 | PP03
CE02-002 |  | - | P01-05 |  | 0 | CE02-002-P01-05 |  | BLANKING | ST | 1 | 480 | 8 | ST | PP12 | PP04 | PP14 | PP12 | [6 empty] | P01 & P02 SHARE DIE
CE02-002 |  | - | P02-05 |  | 0 | CE02-002-P02-05 |  | PUNCHING | ST | 1 | 360 | 6 | ST | PP04 | PP04 | PP14 | PP12 | [6 empty] | P01 & P02 SHARE DIE
CE03-040B |  | - | P02-03 |  | 0 | CE03-040B-P02-03 |  | SC-CUTTING | SC | 1 |  | 0 |  | SUB CON
CP08-596 |  | - | P01-04 |  | 0 | CP08-596-P01-04 |  | SLIT TO SIZE | ST | 2 | 180 | 3 | ST | SM01 | SM01
CP08-596 |  | - | P02-04 |  | 0 | CP08-596-P02-04 |  | BLANKING | ST | 1 | 480 | 8 | ST | PP21 | PP21 | PP14
CP08-596 |  | - | P03-04 |  | 0 | CP08-596-P03-04 |  | BENDING | ST | 1 | 180 | 3 | ST | PP21 | PP21 | PP14
CE02-002 |  | - | P03-05 |  | 0 | CE02-002-P03-05 |  | BENDING | ST | 1 | 360 | 6 | ST | PP05 | PP05
CR02-003 |  | - | P02-06 |  | 0 | CR02-003-P02-06 |  | BLANKING | ST | 1 | 180 | 3 | ST | PP01 | PP01
CR02-003 |  | - | P03-06 |  | 0 | CR02-003-P03-06 |  | BENDING | ST | 1 | 150 | 2.5 | ST | PP30 | PP30 | PP30 | PP33
CR02-003 |  | - | P04-06 |  | 0 | CR02-003-P04-06 |  | DEBURRING | ST | 1 | 25 | 0.41667 | ST | VM04 | VM04 | VM01
CW01 |  | - | P01-05 |  | 0 | CW01 |  | TAPPING M3X0.5 | TP | 1 | 20 | 0.33333 | TR | TP02 | TP02
|  | - | P02-05 |  | 0 | CW01 |  | DEBURRING | TP | 1 | 30 | 0.5 | TR | OPT | OPT
|  | - | P03-05 |  | 0 | CW01 |  | BENDING | TP | 1 | 40 | 0.66667 | TR | PB07 | PB07
|  | - | P04-05 |  | 0 | CW01 |  | BENDING | TP | 1 | 90 | 1.5 | TR | PB07 | PB07
CP08-589 |  | - | P01-08 |  | 0 |  |  | TURRET PUNCH | TR | 1 | 25 | 0.41667 | TR | TM03 | TM03 | TM05 | TM06
CP08-589 |  |  | P02-08 |  | 0 |  |  | BURRING | ST | 1 | 120 | 2 | ST | PP02 | PP02 | PP04 | PP03
CP08-589 |  |  | P03-08 |  | 0 |  |  | BENDING | PB | 1 |  |  | PB | PB02 | PB02 | PB03
CP08-589 |  |  | P04-08 |  | 0 |  |  | BENDING | PB | 1 |  |  | PB | PB02 | PB02 | PB03
CP08-589 |  |  | P05-08 |  | 0 |  |  | BENDING | PB | 1 |  |  | PB | PB07 | PB07
CP08-589 |  |  | P06-08 |  | 0 |  |  | BENDING | PB | 1 |  |  | PB | PB07 | PB07
CP08-589 |  |  | P07-08 |  | 0 |  |  | BENDING | PB | 1 |  |  | PB | PB07 | PB07
CP08-593 |  |  | P02-04 |  | 0 | CP08-593-P02-04 |  | TURRET PUNCH | TR | 1 | 50.4 | 0.84 | TR | TM03 | TM03 | TM05 | TM06
CP08-593 |  |  | P03-04 |  | 0 | CP08-593-P03-04 |  | BENDING 1,2,3 | PB | 1 | 360 | 6 | ST | PP14 | PP14 | PP31
CP08-298 |  |  | P02-03 |  | 0 | CP08-298-P02-03 |  | DEGREASING | FM | 1 | 5040 | 84 | FM | VM01 | VM01 | VM04
CP08-598 |  |  | P01-03 |  | 0 | CP08-598-P01-03 |  | SLIT TO SIZE | ST | 1 | 240 | 4 | ST | SM01 | SM01 | [8 empty] | SHARE DIE WITH CP08-384
CP08-598 |  |  | P02-03 |  | 0 | CP08-598-P02-03 |  | BLANKING | ST | 1 | 180 | 3 | ST | PP21 | PP21 | [8 empty] | SHARE DIE WITH CP08-384
CP08-384 |  |  | P01-03 |  | 0 | CP08-384-P01-03 |  | SLIT TO SIZE | ST | 1 | 240 | 4 | ST | SM01 | SM01 | [8 empty] | SHARE DIE WITH CP08-598
CP08-384 |  |  | P02-03 |  | 0 | CP08-384-P02-03 |  | BLANKING | ST | 1 | 180 | 3 | ST | PP21 | PP21 | [8 empty] | SHARE DIE WITH CP08-598
CP08-599 |  |  | P03-04 |  | 0 | CP08-599-P03-04 |  | BENDING MULTI | ST | 1 | 180 | 3 | ST | PP24 | PP24 | PP09 | [7 empty] | SHARE DIE WITH CP08-502
CP08-600 |  |  | P01-03 |  | 0 | CP08-600-P01-03 |  | TRIMMING | ST | 1 | 120 | 2 | ST | PP29 | PP29 | PP29 | [7 empty] | SHARE DIE WITH CP08-404
CP08-600 |  |  | P02-03 |  | 0 | CP08-600-P02-03 |  | BENDING | ST | 1 | 120 | 2 | ST | PP33 | PP33 | PP29 | [7 empty] | SHARE DIE WITH CP08-404
CP08-404 |  |  | P01-03 |  | 0 | CP08-404-P01-03 |  | TRIMMING | ST | 1 | 120 | 2 | ST | PP29 | PP29 | PP29 | [7 empty] | SHARE DIE WITH CP08-600
CP08-404 |  |  | P02-03 |  | 0 | CP08-404-P02-03 |  | BENDING | ST | 1 | 120 | 2 | ST | PP33 | PP33 | PP29 | [7 empty] | SHARE DIE WITH CP08-600
CP08-601 |  |  | P01-03 |  | 0 | CP08-601-P01-03 |  | TRIMMING | ST | 1 | 120 | 2 | ST | PP29 | PP29 | [8 empty] | share die with cp08-405
CP08-601 |  |  | P02-03 |  | 0 | CP08-601-P02-03 |  | BENDING | ST | 1 | 120 | 2 | ST | PP33 | PP33 | [8 empty] | share die with cp08-405
CP08-601 |  |  | P03-03 |  | 0 | CP08-601-P03-03 |  | BENDING | ST | 1 | 120 | 2 | ST | PP29 | PP29 | [8 empty] | share die with cp08-405
CP08-405 |  |  | P01-03 |  | 0 | CP08-405-P01-03 |  | TRIMMING | ST | 1 | 120 | 2 | ST | PP29 | PP29 | [8 empty] | share die with cp08-601
CP08-405 |  |  | P02-03 |  | 0 | CP08-405-P02-03 |  | BENDING | ST | 1 | 120 | 2 | ST | PP33 | PP33 | [8 empty] | share die with cp08-601
CP08-405 |  |  | P03-03 |  | 0 | CP08-405-P03-03 |  | BENDING | ST | 1 | 120 | 2 | ST | PP29 | PP29 | [8 empty] | share die with cp08-601
CT10-027 |  |  | P01-04 |  | 0 | CT10-027-P01-04 |  | SPOT WELD 1,2,3,4 | TP | 1 | 45 | 0.75 | TP | SW09 | SW09 | SW13 | SW14
CT10-027 |  |  | P02-04 |  | 0 | CT10-027-P02-04 |  | PAINTING X 8 | TP | 1 | 30 | 0.5 | TP | OPT | OPT
CT10-027 |  |  | P03-04 |  | 0 | CT10-027-P03-04 |  | CLEANNING | TP | 1 | 60 | 1 | TP | OPT | OPT
CT10-027A |  |  | P01-04 |  | 0 | CT10-027A-P01-04 |  | TURRET PUNCH | TP | 1 | 24 | 0.4 | TP | TM03 | TM03 | TM05 | TM06
CT10-027A |  |  | P02-04 |  | 0 | CT10-027A-P02-04 |  | BENDING | TP | 1 | 180 | 3 | TP | PB02 | PB02 | PB03 | PB08
CT10-027A |  |  | P03-04 |  | 0 | CT10-027A-P03-04 |  | BENDING | TP | 1 | 30 | 0.5 | TP | PB07 | PB07 | PB05
CT10-027B |  |  | P01-03 |  | 0 | CT10-027B-P01-03 |  | TURRET PUNCH | TP | 1 | 54 | 0.9 | TP | TM03 | TM03 | TM05 | TM06
CT10-027B |  |  | P02-03 |  | 0 | CT10-027B-P02-03 |  | BENDING | TP | 1 | 60 | 1 | TP | PB01 | PB01 | PB04 | PB07 | PB05
CT10-026C |  |  | P01-03 |  | 0 | CT10-026C-P01-03 |  | TURRET PUNCH | TP | 1 | 51 | 0.85 | TP | TM03 | TM03 | TM05 | TM06 | [6 empty] | TOGETHER RUN WITH CT10-026G,CT10-026H
CT10-026C |  |  | P02-03 |  | 0 | CT10-026C-P02-03 |  | BENDING | TP | 1 | 90 | 1.5 | TP | PB01 | PB01 | PB04 | PB05 | PB07
CT10-026G |  |  | P01-03 |  | 0 | CT10-026G-P01-03 |  | BENDING | TP | 1 | 180 | 3 | TP | PB01 | PB01 | PB02 | PB03 | PB05 | PB07 | PB08
CT10-026G |  |  | P02-03 |  | 0 | CT10-026G-P02-03 |  | BENDING | TP | 1 | 180 | 3 | TP | PB01 | PB01 | PB02 | PB03 | PB05 | PB07
CT10-026H |  |  | P01-03 |  | 0 | CT10-026H-P01-03 |  | TAPPING M3X0.5 | TP | 1 | 120 | 2 | TP | TP02 | TP02 | TP09
CT10-026H |  |  | P02-03 |  | 0 | CT10-026H-P02-03 |  | BENDING | TP | 1 | 40 | 0.66667 | TP | PB07 | PB07 | PB01
CT10-026A-A |  |  | P01-07 |  | 0 | CT10-026A-A-P01-07 |  | TURRET PUNCH | TP | 1 | 48 | 0.8 | TP | TM03 | TM03 | TM05 | TM06
CT10-026A-A |  |  | P02-07 |  | 0 | CT10-026A-A-P02-07 |  | BENDING 1 | TP | 1 | 120 | 2 | TP | PB01 | PB01 | PB04 | PB07 | PB02 | [5 empty] | 8/1/25-RUN AT M/C : PB02,PB03,PB07 - 2 OPERATORS
CT10-026A-A |  |  | P03-07 |  | 0 | CT10-026A-A-P03-07 |  | BENDING 2,3 | TP | 1 | 60 | 1 | TP | PB01 | PB01 | PB04 | PB07
CT10-026A-A |  |  | P04-07 |  | 0 | CT10-026A-A-P04-07 |  | BENDING 4,5 | TP | 1 | 60 | 1 | TP | PB01 | PB01 | PB04 | PB07
CT10-026A-A |  |  | P05-07 |  | 0 | CT10-026A-A-P05-07 |  | BENDING 6,7 | TP | 1 | 60 | 1 | TP | PB01 | PB01 | PB04 | PB07
CT10-026A-A |  |  | P06-07 |  | 0 | CT10-026A-A-P06-07 |  | SPOT WELD 1,2,3,4 | TP | 1 | 90 | 1.5 | TP | SW09 | SW09 | SW13 | SW14
CT10-026D |  |  | P01-03 |  | 0 | CT10-026D-P01-03 |  | TURRET PUNCH | TP | 1 | 48 | 0.8 | TP | TM03 | TM03 | TM05 | TM06
CT10-026D |  |  | P02-03 |  | 0 | CT10-026D-P02-03 |  | BENDING 1,2,3,4,5,6 | TP | 1 | 50 | 0.83333 | TP | PB01 | PB01 | PB07
CT10-026 |  |  | P01-04 |  | 0 | CT10-026-P01-04 |  | SPOT WELD X 31 | TP | 1 | 12 | 0.2 | TP | SW09 | SW09 | SW13 | SW14
CT10-026 |  |  | P02-04 |  | 0 | CT10-026-P02-04 |  | PAINTING X 93 | TP | 1 | 6 | 0.1 | TP | OPT
CT10-026 |  |  | P03-04 |  | 0 | CT10-026-P03-04 |  | CLEANNING | TP | 1 | 30 | 0.5 | TP | OPT
CT10-026B |  |  | P01-03 |  | 0 | CT10-026B-P01-03 |  | TURRET PUNCH | TP | 1 | 80 | 1.3333 | TP | TM03 | TM03 | TM05 | TM06
CT10-026B |  |  | P02-03 |  | 0 | CT10-026B-P02-03 |  | BENDING 1,2 | TP | 1 | 90 | 1.5 | TP | PB01 | PB01 | PB04 | PB05 | PB07
CT10-026A |  |  | P01-02 |  | 0 | CT10-026A-P01-02 |  | SPOT WELD X 12 | TP | 1 | 8 | 0.13333 | TP | SW09 | SW09 | SW13 | SW14
CT10-026A-C |  |  | P01-08 |  | 0 | CT10-026A-C-P01-08 |  | TURRET PUNCH | TP | 1 | 15 | 0.25 | TP | TM03 | TM03 | TM05 | TM06
CT10-026A-C |  |  | P02-08 |  | 0 | CT10-026A-C-P02-08 |  | BENDING ,HEMMING | TP | 1 | 60 | 1 | TP | PB03 | PB03 | PB02
CT10-026A-C |  |  | P03-08 |  | 0 | CT10-026A-C-P03-08 |  | BENDING | TP | 1 | 90 | 1.5 | TP | PB07 | PB07
CT10-026A-C |  |  | P04-08 |  | 0 | CT10-026A-C-P04-08 |  | BENDING | TP | 1 | 60 | 1 | TP | PB02 | PB02 | PB03 | PB08
CT10-026A-C |  |  | P05-08 |  | 0 | CT10-026A-C-P05-08 |  | BENDING | TP | 1 | 90 | 1 | TP | PB04 | PB04 | PB03 | PB08 | PB02
CT10-026A-C |  |  | P06-08 |  | 0 | CT10-026A-C-P06-08 |  | BENDING | TP | 1 | 90 | 1.5 | TP | PB01 | PB01
CT10-026A-C |  |  | P07-08 |  | 0 | CT10-026A-C-P07-08 |  | BENDING | TP | 1 | 90 | 1.5 | TP | PB05 | PB05 | [8 empty] | RUN OPF (PB03,PB02,PB07,PB04,PB01,PB05 (4 OPTS)
CT10-026A-B |  |  | P01-03 |  | 0 | CT10-026A-B-P01-03 |  | TURRET PUNCH | TP | 1 | 72 | 1.2 | TP | TM03 | TM03 | [8 empty] | TOGETHER RUN CT10-026E,CT10-026F,CT10-026I
CT10-026A-B |  |  | P02-03 |  | 0 | CT10-026A-B-P02-03 |  | BENDING X 2 | TP | 1 | 120 | 2 | TP | PB01 | PB01 | PB04 | PB05 | PB07
CT10-026E |  |  | P01-02 |  | 0 | CT10-026E-P01-02 |  | BENDING | TP | 1 | 18 | 0.3 | TP | PB01 | PB01 | PB02 | PB03 | PB04 | PB05 | PB07 | PB08 |  |  | TOGETHER RUN CT10-026E,CT10-026F,CT10-026I
CT10-026F |  |  | P01-03 |  | 0 | CT10-026F-P01-03 |  | BENIDNG,HEMMING 1,2,3,4,5,6 | TP | 1 | 90 | 1.5 | TP | PB01: PB02; PB01: PB02; PB02: PB03; PB03: PB08
CT10-026F |  |  | P02-03 |  | 0 | CT10-026F-P02-03 |  | BENDING 1 (90) | TP | 1 | 180 | 3 | TP | PB01 | PB01 | PB02 | PB03 | PB04 | PB05 | PB07 | PB08 |  |  | TOGETHER RUN CT10-026E,CT10-026F,CT10-026I
CT10-026I |  |  | P01-02 |  | 0 | CT10-026I-P01-02 |  | BENDING 1,2 | TP | 1 | 90 | 1.5 | TP | PB01 | PB01 | PB04 | PB05 | PB07
CR02-003 |  |  | P01-06 |  | 0 | CR02-003-P01-06 |  | MATERIAL CLEANNING | ST | 1 | 1380 | 23 | ST | PB01: OPT; PB01: OPR
CS05-004 |  |  | P01-03 |  | 0 | CS05-004-P01-03 |  | PROGRESSIVE | ST | 1 | 1800 | 30 |  | PB01: PP02; PB01: PP02
CS05-004 |  |  | P02-03 |  | 0 | CS05-004-P02-03 |  | TIN PLATING | ST
CP08-599 |  |  | P01-04 |  | 0 | CP08-599-P01-04 |  | SLIT TO SIZE | ST | 1 | 240 | 4 | TP | PB01: SM01; PB01: SM01
CP08-599 |  |  | P02-04 |  | 0 | CP08-599-P02-04 |  | SLIT TO SIZE | ST | 1 | 360 | 6 | TP | PB01: SM01; PB01: SM01
CP08-563 |  |  | P03-04 |  | 0 | CP08-563-P03-04 |  | PACKING | TR | 1 | 80 | 1.3333 | TP | PB01: OPT; PB01: OT
CA14-017 |  |  | P01-02 |  | 0 | CA14-017-P01-02 |  | FORMING | FM | 1 | 3000 | 50 | FM | PB01: FM02; PB01: FM02
CU01-057 |  |  | P01-03 |  | 0 | CU01-057-P01-03 |  | TURRET PUNCH | TR | 1 | 66 | 1.1 | TR | PB01: TM03; PB01: TM03; PB02: TM05; PB03: TM06
CU01-057 |  |  | P02-03 |  | 0 | CU01-057-P02-03 |  | BENDING 1,2 | PB | 1 | 120 | 2 | PB | PB01: PB01; PB01: PB01; PB02: PB07; PB03: PB04
CU01-057 |  |  | P03-03 |  | 0 | CU01-057-P03-03 |  | SUB CON | SC
CU01-058 |  |  | P01-03 |  | 0 | CU01-058-P01-03 |  | TURRET PUNCH | TR | 1 | 66 | 1.1 | TR | PB01: TM03; PB01: TM03; PB02: TM05; PB03: TM06
CU01-058 |  |  | P02-03 |  | 0 | CU01-058-P02-03 |  | BENDING 1,2,3,4,5 | PB | 1 | 40 | 0.66667 | PB | PB01: PB01; PB01: PB01; PB02: PB07; PB03: PB04
CU01-058 |  |  | P03-03 |  | 0 | CU01-058-P03-03 |  | SUB CON | SC
CP08-587 |  |  | P01-04 |  | 0 | CP08-587-P01-04 |  | TURRET PUNCH | TR | 1 | 42 | 0.7 | TR | PB01: TM03; PB01: TM03; PB02: TM05; PB03: TM06
CP08-587 |  |  | P02-04 |  | 0 | CP08-587-P02-04 |  | PIERCING | ST | 1 | 300 | 5 | ST | PB01: PP05; PB01: PP05
CP08-587 |  |  | P03-04 |  | 0 | CP08-587-P03-04 |  | BENDING 1,2,3,4 | PB | 1 | 50 | 0.83333 | PB | PB01: PB01; PB01: PB01; PB02: PB07; PB03: PB05
CP08-591 |  |  | P01-09 |  | 0 | CP08-591-P01-09 |  | TURRET PUNCH | TR | 1 | 24 | 0.4 | TR | PB01: TM03; PB01: TM03; PB02: TM05; PB03: TM06
CP08-591 |  |  | P02-09 |  | 0 | CP08-591-P02-09 |  | BENDING 1 | PB | 1 | 90 | 1.5 | PB | PB02 | PB02 | PB03 | PB08 | PB02 | [5 empty] | PB02,PB01,PB03 - RUN FOR PROCESS - P02-007 - 02.12.24
CP08-591 |  |  | P03-09 |  | 0 | CP08-591-P03-09 |  | BENDING 2 | PB | 1 | 90 | 1.5 | PB | PB02 | PB02 | PB03 | PB08 | PB01 | [5 empty] | PB05 - RUN FOR P08 - 02.12.24
CP08-591 |  |  | P04-09 |  | 0 | CP08-591-P04-09 |  | BENDING 3 *DIAMOND | PB | 1 | 90 | 1.5 | PB | PB01: PB02; PB01: PB02; PB02: PB03; PB04: PB03 |  |  | ON 09.01.25 RUN : PB03,PB01,PB07,PB02,PB07
CP08-591 |  |  | P05-09 |  | 0 | CP08-591-P05-09 |  | BENDING 4,5 | PB | 1 | 60 | 1 | PB | PB01 | PB01 | PB04 | PB07 | PB05
CP08-591 |  |  | P06-09 |  | 0 | CP08-591-P06-09 |  | BENDING 6,7 | PB | 1 | 60 | 1 | PB | PB01: PB01; PB01: PB01; PB02: PB07
CP08-591 |  |  | P07-09 |  | 0 | CP08-591-P07-09 |  | BENDING 8 | PB | 1 | 120 | 2 | PB | PB01: PB01; PB01: PB01; PB02: PB07
CP08-591 |  |  | P08-09 |  | 0 | CP08-591-P08-09 |  | BENDING 9,10 | PB | 1 | 60 | 1 | PB | PB01: PB07
CP08-588 |  |  | P01-04 |  | 0 | CP08-588-P01-04 |  | SLITING | PB | 1 | 960 | 16 | PB | PB01: SM01; PB01: SM01
CP08-588 |  |  | P02-04 |  | 0 | CP08-588-P02-04 |  | TURRET PUNCH | TR | 1 | 42 | 0.7 | TR | PB01: TM03; PB01: TM03; PB02: TM05; PB03: TM06
CP08-588 |  |  | P03-04 |  | 0 | CP08-588-P03-04 |  | BENDING 1,2,3,4 | PB | 1 | 50.5 | 0.84167 | PB | PB01: PB07; PB01: PB07
CP08-585A |  |  | P01-03 |  | 0 | CP08-585A-P01-03 |  | TURRET PUNCH | TR | 1 | 50.4 | 0.84 | TR | PB01: TM03; PB01: TM03; PB02: TM05; PB03: TM06 |  |  | TOGETHER RUN OUT CP08-585B-P01-02
CP08-585A |  |  | P02-03 |  | 0 | CP08-585A-P02-03 |  | BENDING 1,2,3,4 | PB | 1 | 50.4 | 0.84 | PB | PB01: PB07; PB01: PB07; PB02: PB05; PB03: PB01
CP08-585 |  |  | P01-04 |  | 0 | CP08-585-P01-04 |  | SPOT WELD 1,2,3,4,5,6 | PB | 1 | 40.2 | 0.67 | PB | PB01: SW09; PB01: SW09; PB02: SW14
CP08-585 |  |  | P02-04 |  | 0 | CP08-585-P02-04 |  | PAINTING | PB | 1 | 40.2 | 0.67 | PB | PB01: OPT; PB01: OPT
CP08-585 |  |  | P03-04 |  | 0 | CP08-585-P03-04 |  | CLEANNING | PB | 1 | 50.4 | 0.84 | PB | PB01: OPT; PB01: OPT
CP08-589 |  |  | P01-08 |  | 0 | CP08-589-P01-08 |  | SLITTING | TP | 1 | 120 | 2 | TP | PB01: SM01; PB01: SM01
CP08-589 |  |  | P02-08 |  | 0 | CP08-589-P02-08 |  | TURRET PUNCH | TP | 1 | 27 | 0.45 | TP | PB01: TM03; PB01: TM03; PB02: TM05; PB03: TM06
CP08-589 |  |  | P03-08 |  | 0 | CP08-589-P03-08 |  | BURRING | ST | 1 | 120 | 2 | ST | PB01: PP05; PB01: PP05
CP08-589 |  |  | P04-08 |  | 0 | CP08-589-P04-08 |  | BENDING 1,2 | PB | 1 | 60 | 1 | PB | PB01: PB02; PB01: PB02; PB02: PB03; PB03: PB08 |  |  | RUN ON PB07,PB05 - 17.01.25
CP08-589 |  |  | P05-08 |  | 0 | CP08-589-P05-08 |  | BENDING 3,4,5,6,7,8 | PB | 1 | 30 | 0.5 | PB | PB01: PB07; PB01: PB07; PB02: PB05
CP08-589 |  |  | P06-08 |  | 0 | CP08-589-P06-08 |  | BENDING 9,10 | PB | 1 | 60 | 1 | PB | PB01: PB07; PB01: PB07; PB02: PB05
CP08-589 |  |  | P07-08 |  | 0 | CP08-589-P07-08 |  | BENDING 11,12 | PB | 1 | 90 | 1.5 | PB | PB01: PB07; PB01: PB07; PB02: PB05
CP08-584 |  |  | P01-04 |  | 0 | CP08-584-P01-04 |  | SPOT WELD 1,2,3 | PB | 1 | 60 | 1 | PB | PB01: SW09; PB01: SW09; PB02: SW14
CP08-584 |  |  | P02-04 |  | 0 | CP08-584-P02-04 |  | PAINTING | PB | 1 | 30 | 0.5 | PB | PB01: OPT; PB01: OPT
CP08-584 |  |  | P03-04 |  | 0 | CP08-584-P03-04 |  | CLEANNING | PB | 1 | 60 | 1 | PB | PB01: OPT; PB01: OPT
CP08-584A |  |  | P01-06 |  | 0 | CP08-584A-P01-06 |  | SLITING | TR | 1 | 120 | 2 | TR | PB01: SM01; PB01: SM01
CP08-584A |  |  | P02-06 |  | 0 | CP08-584A-P02-06 |  | TURRET PUNCH | TR | 1 | 40 | 0.66667 | TR | PB01: TM03; PB01: TM03; PB02: TM05; PB03: TM06
CP08-584A |  |  | P04-06 |  | 0 | CP08-584A-P04-06 |  | BENDING X 3 | PB | 1 | 60 | 1 | PB | PB01: PB01; PB01: PB01; PB02: PB07
CP08-584A |  |  | P05-06 |  | 0 | CP08-584A-P05-06 |  | Z BENDING | PB | 1 | 120 | 2 | PB | PB02 | PB02 | PB03 | PB08 | PB01
CP08-590 |  |  | P01-04 |  | 0 | CP08-590-P01-04 |  | SLITING | TR | 1 | 120 | 2 | TR | PB01: SM01; PB01: SM01
CP08-590 |  |  | P02-04 |  | 0 | CP08-590-P02-04 |  | TURRET PUNCH | TR | 1 | 27 | 0.45 | TR | PB01: TM03; PB01: TM03; PB02: TM05; PB03: TM06
CP08-590 |  |  | P03-04 |  | 0 | CP08-590-P03-04 |  | BENDING 1 | PB | 1 | 180 | 3 | PB | PB01 | PB01 | PB02 | PB03 | PB04 | PB05 | PB07 | PB08
CP08-592 |  |  | P01-03 |  | 0 | CP08-592-P01-03 |  | TURRET PUNCH | TR | 1 | 50.4 | 0.84 | TR | PB01: TM03; PB01: TM03; PB02: TM05; PB03: TM06
CP08-592 |  |  | P02-03 |  | 0 | CP08-592-P02-03 |  | BENDING 1,2,3 | PB | 1 | 60 | 1 | PB | PB01 | PB01 | PB04 | PB05 | PB07
CP08-603 |  |  | P01-02 |  | 0 | CP08-603-P01-02 |  | PROGRESSIVE | ST | 1 | 1800 | 30 | ST | PB01: PP32; PB01: PP32
CP08-597 |  |  | P01-05 |  | 0 | CP08-597-P01-05 |  | SLITING | ST | 1 | 360 | 6 | ST | PB01: SM01; PB01: SM01
CP08-597 |  |  | P02-05 |  | 0 | CP08-597-P02-05 |  | BLANKING | ST | 1 | 360 | 6 | ST | PB01: PP09; PB01: PP24; PB02: PP25
CP08-597 |  |  | P03-05 |  | 0 | CP08-597-P03-05 |  | BENDING | ST | 1 | 360 | 6 | ST | PB01: PP18; PB01: PP025; PB02: PP20
CP08-597 |  |  | P04-05 |  | 0 | CP08-597-P04-05 |  | BENDING | ST | 1 | 360 | 6 | ST | PB01: PP26; PB01: PP26; PB02: PP26
CP08-594 |  |  | P01-03 |  | 0 | CP08-594-P01-03 |  | TURRET PUNCH | TP | 1 | 300 | 5 | TP | PB01: TM03; PB01: TM03; PB02: TM05; PB03: YM06
CP08-594 |  |  | P02-03 |  | 0 | CP08-594-P02-03 |  | BENDING | ST | 1 | 360 | 6 | ST | PP05 | PP05 | PP04 | PP13 | PP31
CR02-003 |  |  | P05-06 |  | 0 | CR02-003-P05-06 |  | POLISHING | ST | 1 | 34 | 0.56667 | ST | PB01: VM01; PB01: VM01; PB02: VM04 |  |  | 3 HOURS - 100 PCS ONLY CAN DEBURRING - 30.12.24
CP08-593 |  |  | P01-04 |  | 0 | CP08-593-P01-04 |  | SLITTING | TP | 1 | 120 | 2 | TP | PB01: SM01; PB01: SM01
CP08-584A |  |  | P03-06 |  | 0 | CP08-584A-P03-06 |  | BENDING X 3 | PB | 1 | 60 | 1 | PB | PB01: PB01; PB01: PB01; PB02: PB07; PB03: PB03
CP08-583A |  |  | P01-05 |  | 0 | CP08-583A-P01-05 |  | TURRET PUNCH | TP | 1 | 45 | 0.75 | TP | PB01: TM03; PB01: TM03; PB02: TM05; PB03: TM06
CP08-583A |  |  | P02-05 |  | 0 | CP08-583A-P02-05 |  | Z BENDING 1 | PB | 1 | 180 | 3 | PB | PB01: PB02; PB01: PB02
CP08-583A |  |  | P03-05 |  | 0 | CP08-583A-P03-05 |  | BENDING X 4 | PB | 1 | 50.4 | 0.84 | PB | PB01: PB07; PB01: PB07
CP08-583A |  |  | P04-05 |  | 0 | CP08-583A-P04-05 |  | BENDING X 2 | PB | 1 | 90 | 1.5 | PB | PB01: PB07; PB01: PB07
CP08-583B |  |  | P01-04 |  | 0 | CP08-583B-P01-04 |  | BENDING 1,2 | PB | 1 | 90 | 1.5 | PB | PB07 | PB07 | PB01 | PB02 | PB03 | PB04 | PB05 | PB07
CP08-583B |  |  | P02-04 |  | 0 | CP08-583B-P02-04 |  | BENDING 3,4 | PB | 1 | 60 | 1 | PB | PB02 | PB02 | PB03 | PB08 |  |  |  | PB07
CP08-583B |  |  | P03-04 |  | 0 | CP08-583B-P03-04 |  | BENDING 5 | PB | 1 | 120 | 2 | PB | PB02 | PB02 | PB03 | PB08 |  |  |  | PB02
CP08-586 |  |  | P01-06 |  | 0 | CP08-586-P01-06 |  | TURRET PUNCH | TP | 1 | 24 | 0.4 | PB | PB01: TM03; PB01: TM03; PB02: TM05; PB03: TM06
CP08-586 |  |  | P02-06 |  | 0 | CP08-586-P02-06 |  | BENDING 1,2,3,4,5,6,7 | PB | 1 | 15 | 0.25 | PB | PB01: PB07; PB01: PB07; PB02: PB07 |  |  | RUN ON 31.12.24 - PB07,PB02,PB03,PB08
CP08-586 |  |  | P03-06 |  | 0 | CP08-586-P03-06 |  | BENDING 8 | TP | 2 | 60 | 1 | PB | PB01: PB02; PB01: PB02; PB02: PB02
CP08-586 |  |  | P04-06 |  | 0 | CP08-586-P04-06 |  | BENDING 9 | PB | 2 | 60 | 1 | PB | PB01: PB02; PB01: PB02; PB02: PB03
CP08-586 |  |  | P05-06 |  | 0 | CP08-586-P05-06 |  | BENDING 10 | PB | 2 | 60 | 1 | PB | PB01: PB02; PB01: PB02; PB02: PB08
CP08-583 |  |  | P01-04 |  | 0 | CP08-583-P01-04 |  | SPOT WELD | PB | 1 | 90 | 1 | PB | PB01: SW09; PB01: SW09
CP08-583 |  |  | P02-04 |  | 0 | CP08-583-P02-04 |  | PAINTING | PB | 1 | 60 | 1 | PB | PB01: OPT; PB01: OPT
CP08-583 |  |  | P03-04 |  | 0 | CP08-583-P03-04 |  | CLEANNING | PB | 1 | 60 | 1 | PB | PB01: OPT; PB01: OPT
CP08-604 |  |  | P01-03 |  | 0 | CP08-604-P01-03 |  | TURRET PUNCH | TP | 1 | 85 | 1.4167 | PB | PB01: TM03; PB01: TM03; PB02: TM05; PB03: TM06
CP08-604 |  |  | P02-03 |  | 0 | CP08-604-P02-03 |  | BENDING 1 | PB | 1 | 180 | 3 | PB | PB01 | PB01 | PB02 | PB03 | PB04 | PB05 | PB07 | PB08
CP08-605 |  |  | P01-02 |  | 0 | CP08-605-P01-03 |  | STAMPING | ST | 1 | 1800 | 30 | ST | PB01: PP01; PB01: PP01; PB02: PP10 |  |  | SHARE DIE WITH CP08-514.CP08-515,CP08-523
[10 empty] | 1 | 300 | 5 | ST | PB01: TP04
CV02-077 |  |  | P01-02 |  | 0 | CV02-077-P01-02 |  | FORMING | FM | 1 | 3000 | 50 | FM | PB01: FM01; PB01: FM01; PB02: FM03
CP08-373 |  |  | P05-06 |  | 0 | CP08-373-P05-06 |  | PIERCING | ST | 1 | 360 | 6 |  | PB01: PP26; PB01: PP26
CP08-374 |  |  |  |  | 0 | -
CP08-375 |  |  |  |  | 0 | -
CP08-376 |  |  |  |  | 0 | -
CP08-377 |  |  |  |  | 0 | -
CP08-378 |  |  |  |  | 0 | -
CP08-379 |  |  |  |  | 0 | -
CP08-595 |  |  | P01-04 |  | 0 | CP08-595-P01-04 |  | SLITING | TR | 1 | 14400 | 240 | TR | PB01: SM01; PB01: SM01
CP08-595 |  |  | P02-04 |  | 0 | CP08-595-P02-04 |  | TURRENT PUNCH | TR | 1 | 120 | 2 | TR | PB01: TM03; PB01: TM03; PB02: TM05; PB03: TM06
CP08-595 |  |  | P03-04 |  | 0 | CP08-595-P03-04 |  | BENDING 1 | TR | 1 | 120 | 2 | PB | PB01: PB03; PB01: PB03; PB02: PB08; PB03: PB02
CP08-580 |  |  | P01-07 |  | 0 | CP08-580-P01-07 |  | SLITING | TR | 1 | 4800 | 80 | TR | PB01: SM01; PB01: SM01
CP08-580 |  |  | P02-07 |  | 0 | CP08-580-P02-07 |  | TURRENT PUNCH | TR | 1 | 60 | 1 | TR | PB01: TM03; PB01: TM03; PB02: TM05; PB03: TM06
CP08-580 |  |  | P03-07 |  | 0 | CP08-580-P03-07 |  | BENDING 1 | ST | 1 | 360 | 6 | ST | PB01: PP02; PB01: PP02
CP08-580 |  |  | P04-07 |  | 0 | CP08-580-P04-07 |  | BENDING 2 | PB | 1 | 180 | 3 | PB | PB01: PB02; PB01: PB02; PB02: PB03; PB03: PB08 |  |  | RUN PB05,PB08 ON 02.01.25
CP08-580 |  |  | P05-07 |  | 0 | CP08-580-P05-07 |  | BENDING 3 | PB | 1 | 180 | 3 | PB | PB01: PB02; PB01: PB02; PB02: PB03; PB03: PB08
CP08-580 |  |  | P06-07 |  | 0 | CP08-580-P06-07 |  | BENDING 4 | PB | 1 | 180 | 3 | PB | PB01: PB02; PB01: PB02; PB02: PB03; PB03: PB08
CP08-581 |  |  | P01-07 |  | 0 | CP08-581-P01-07 |  | SLITING | TR | 1 | 3360 | 56 | TR | PB01: SM01; PB01: SM01
CP08-581 |  |  | P02-07 |  | 0 | CP08-581-P02-07 |  | TURRENT PUNCH | TR | 1 | 60 | 1 | TR | PB01: TM03; PB01: TM03; PB02: TM05; PB03: TM06
CP08-581 |  |  | P03-07 |  | 0 | CP08-581-P03-07 |  | BENDING,HEMMING 1,2 | ST | 1 | 180 | 3 | ST | PB01: PP02; PB01: PP02; PB02: PP31
CP08-581 |  |  | P04-07 |  | 0 | CP08-581-P04-07 |  | BENDING 3 | ST | 1 | 360 | 6 | ST | PB01: PP31; PB01: PP31; PB02: PP14; PB03: PP02
CP08-581 |  |  | P05-07 |  | 0 | CP08-581-P05-07 |  | BENDING 4 | ST | 1 | 360 | 6 | ST | PB01: PP31; PB01: PP31; PB02: PP14
CP08-581 |  |  | P06-07 |  | 0 | CP08-581-P06-07 |  | BENDING 5 | PB | 1 | 180 | 3 | PB | PB01 | PB01 | PB02 | PB03 | PB04 | PB05 | PB07 | PB08
CP08-582 |  |  | P01-07 |  | 0 | CP08-582-P01-07 |  | SLITING | TR | 1 | 4200 | 70 | TR | PP31 PB01: SM01; PP31 PB01: SM01
CP08-582 |  |  | P02-07 |  | 0 | CP08-582-P02-07 |  | TURRENT PUNCH | TR | 1 | 48 | 0.8 | TR | PP31 PB01: TM03; PP31 PB01: TM03; PP14 PB02: TM05; PP14 PB03: TM06
CP08-582 |  |  | P03-07 |  | 0 | CP08-582-P03-07 |  | BENDING,HEMMING 1,2 | ST | 1 | 180 | 3 | ST | PP31 PB01: PP02; PP31 PB01: PP02
CP08-582 |  |  | P04-07 |  | 0 | CP08-582-P04-07 |  | BENDING 3 | ST | 1 | 360 | 6 | ST | PP31 PB01: PP31; PP31 PB01: PP31
CP08-582 |  |  | P05-07 |  | 0 | CP08-582-P05-07 |  | BENDING 4 | ST | 1 | 360 | 6 | ST | PP31 PB01: PP31; PP31 PB01: PP31
CP08-582 |  |  | P06-07 |  | 0 | CP08-582-P06-07 |  | BENDING 5 | PB | 1 | 180 | 3 | PB | PB01 | PB01 | PB02 | PB03 | PB04 | PB05 | PB07 | PB08
CC02-007 |  |  | P01-04 |  | 0 | CC02-007-P01-04 |  | FORMING | FM | 1 | 3000 | 50 | FM | PP31 PB01: FM02; PP31 PB01: FM02
CC02-007 |  |  | P02-04 |  | 0 | CC02-007-P02-04 |  | HEAT TREATMENT
CC02-007 |  |  | P03-04 |  | 0 | CC02-007-P03-04 |  | PLATING
CP08-606 |  |  | P01-02 |  | 0 | CP08-606-P01-02 |  | PROGRESSIVE | ST | 1 | 1800 | 30 | ST | PP31 PB01: PP19; PP31 PB01: PP19
CP08-602 |  |  | P01-04 |  | 0 | CP08-602-P01-04 |  | TRIMMING | ST | 1 | 120 | 2 | ST | PP31 PB01: PP33; PP31 PB01: PP33
CP08-602 |  |  | P02-04 |  | 0 | CP08-602-P02-04 |  | BENDING | ST | 1 | 120 | 2 | ST | PP31 PB01: PP33; PP31 PB01: PP33
CP08-602 |  |  | P03-04 |  | 0 | CP08-602-P03-04 |  | BENDING | ST | 1 | 120 | 2 | ST | PP31 PB01: PP33; PP31 PB01: PP33
CP08-610 |  |  | P01-07 |  | 0 | CP08-610-P01-07 |  | TURRENT PUNCH | TR | 1 | 30 | 0.5 | TR | PP31 PB01: TM03; PP31 PB01: TM03; PP31 PB02: TM05; PP31 PB03: TM06
CP08-610 |  |  | P02-07 |  | 0 | CP08-610-P02-07 |  | BENDING | PB | 1 | 180 | 3 | PB | PP31 PB01: PB02; PP31 PB01: PB02; PP31 PB02: PB03
CP08-610 |  |  | P03-07 |  | 0 | CP08-610-P03-07 |  | BENDING | PB | 1 | 180 | 3 | PB | PP31 PB01: PB03; PP31 PB01: PB03; PP31 PB02: PB02
CP08-610 |  |  | P04-07 |  | 0 | CP08-610-P04-07 |  | BENDING | PB | 1 | 180 | 3 | PB | PP31 PB01: PB08; PP31 PB01: PB08; PP31 PB02: PB02
CP08-610 |  |  | P05-07 |  | 0 | CP08-610-P05-07 |  | BENDING | PB | 1 | 180 | 3 | PB | PP31 PB01: PB04; PP31 PB01: PB04; PP31 PB02: PB01
CP08-610 |  |  | P06-07 |  | 0 | CP08-610-P06-07 |  | BENDING | PB | 1 | 40 | 0.66667 | PB | PP31 PB01: PB07; PP31 PB01: PB07
CP08-609 |  |  | P01-05 |  | 0 | CP08-609-P01-05 |  | TURRENT PUNCH | TR | 1 | 30 | 0.5 | TR | PP31 PB01: TM03; PP31 PB01: TM03; PP31 PB02: TM05; PP31 PB03: TM06
CP08-609 |  |  | P02-05 |  | 0 | CP08-609-P02-05 |  | DRAWING-ST | ST | 1 | 120 | 2 | ST | PP31 PB01: PP31; PP31 PB01: PP31; PP31 PB02: PP12; PP31 PB03: PP14
CP08-609 |  |  | P03-05 |  | 0 | CP08-609-P03-05 |  | BENDING-ST | ST | 1 | 120 | 2 | ST | PP31 PB01: PP31; PP31 PB01: PP31; PP31 PB02: PP12; PP31 PB03: PP14
CP08-609 |  |  | P04-05 |  | 0 | CP08-609-P04-05 |  | BENDING (OPF) | PB | 1 | 60 | 1 | PB | PP31 PB01: PB07; PP31 PB01: PB02; PP31 PB02: PB03 |  |  | RUN OPF (PB07,PB02/PB03- RUN 2 OPTS)
CP08-608A |  |  | P01-03 |  | 0 | CP08-608A-P01-03 |  | TURRENT PUNCH | TP | 1 | 60 | 1 | TR | PP31 PB01: TM03; PP31 PB01: TM03; PP31 PB02: TM05; PP31 PB03: TM06
CP08-608A |  |  | P02-03 |  | 0 | CP08-608A-P02-03 |  | BENDING1,2,3,4,5,6 | PB | 1 | 50.4 | 0.84 | PB | PP31 PB01: PB07; PP31 PB01: PB07; PP31 PB02: PB01
CD11-003D |  |  | P01-03 |  | 0 | CD11-003D-P01-03 |  | TURRENT PUNCH | TR | 1 | 90 | 1.5 | TR | PP31 PB01: TM05; PP31 PB01: TM05; PP31 PB02: TM03; PP31 PB03: TM06
CD11-003D |  |  | P02-03 |  | 0 | CD11-003D-P02-03 |  | BENDING | ST | 1 | 120 | 2 | ST | PP31 PB01: PP31; PP31 PB01: PP31
CD11-003E |  |  | P01-03 |  | 0 | CD11-003E-P01-03 |  | TURRENT PUNCH | TR | 1 | 90 | 1.5 | TR | PP31 PB01: TM05; PP31 PB01: TM05; PP31 PB02: TM03; PP31 PB03: TM06
CD11-003E |  |  | P02-03 |  | 0 | CD11-003E-P02-03 |  | BENDING | ST | 1 | 120 | 2 | ST | PP31 PB01: PP31; PP31 PB01: PP31
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
[5 empty] | 0 | -
CP08-498 |  |  | P03-04 |  | 0 | CP08-498-P03-04 |  |  | TR | 1 | 240 | 4 |  | PP31 PB01: PB08; PP31 PB01: PB08
|  |  | P03-04 |  |  | CP08-498-P03-04 |  |  | TR | 1 | 240 | 4 | TR | PP31 PB01: PB08; PP31 PB01: PB01; PP31 PB02: PB04
Note on I14: PLS DON’T DELETE THIS FORMULA
Note on G1805: Serene Soo: